## Sheet1
Batch | DUID2 | Ring ID | Site ID | Site Name | Subcon | Plan Survey | Actual Survey | Plan MOS | Actual MOS | Plan Installation | Actual Installation | Plan Power Up | Actual Power Up | Plan Integration | Actual Integration | Plan Migration | Actual Migration | Break Ring Status
2014 Q2 | xD_DWDM_BRKRing_E105_8139B-MAC001 CBC_0004582309010R_00045824006624 | E105 | 8139B | 8139B-MAC001 CBC | FO&T | March | March | May Plan | June | June | July | July | July | July | July | August | August | In progress
2024 Q2 | xD_DWDM_BRKRing_E111_8317A-MAC-001 Kampung Pak Wong_0004582309010R_00045824006624 | E111 | 8317A | 8317A-MAC-001 Kampung Pak Wong | FO&T | March | March | May Plan | June | June | July | July | July | July | July | August | August | In progress
2016 Q2 | xD_DWDM_BRKRing_E111_8367A-MAG001 B.Kechil_0004582309010R_00045824006624 | E111 | 8367A | 8367A-MAG001 B.Kechil | FO&T | March | March | May Plan | June | June | July | July | July | July | July | August | August | In progress
2024 Q2 | xD_DWDM_BRKRing_E111_8439A-MAC001 A.Lintang_0004582309010R_00045824006624 | E111 | 8439A | 8439A-MAC001 A.Lintang | FO&T | March | March | May Plan | June | June | June | June | June | June | June | August | August | In progress
2018 Q2 | xD_DWDM_BRKRing_EAR01_8000A-MCR001 KTN_0004582309010R_00045824006624 | EAR01 | 8000A | 8000A-MCR001 KTN | Fo&T | March | March | May Plan | June | June | June | June | June | June | June | July | July | Completed
2024 Q2 | xD_DWDM_BRKRing_EAR01_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | EAR01 | 8224A | 8224A-MAG-001 Pasir Puteh | Fo&T | March | March | May Plan | June | June | June | June | June | June | June | July | July | Completed
2020 Q2 | xD_DWDM_BRKRing_EAR06_8000A-MSC Kuantan_0004582309010R_00045824006624 | EAR06 | 8000A | 8000A-MSC Kuantan | Fo&T | April | April | May Plan | June | June | June | June | June | June | June | July | July | Completed
2024 Q2 | xD_DWDM_BRKRing_EAR06_8513A-MAG002 Senggora_0004582309010R_00045824006624 | EAR06 | 8513A | 8513A-MAG002 Senggora | Fo&T | April | April | May Plan | June | June | June | June | June | June | June | July | July | Completed
2022 Q2 | xD_DWDM_BRKRing_EAR06_8667A-MAG 001 Kg Jerangsang_0004582309010R_00045824006624 | EAR06 | 8667A | 8667A-MAG 001 Kg Jerangsang | Fo&T | April | April | May Plan | June | June | June | June | June | June | June | July | July | Completed
2024 Q2 | xD_DWDM_BRKRing_NAR01_i_4966A_Kulim Hitech_0004582401260T_45824026527 | NAR01_i | 4966A | 4966A-MAG001 Kulim Hitech | FO&T | April | April | May Plan | June | June | July | July | July | July | July | August | August | In progress
2024 Q2 | xD_DWDM_BRKRing_NAR01_i_4946A_Bukit Selambau_0004582401260T_45824026527 | NAR01_i | 4946A | 4946A-MAG-001 Bukit Selambau | FO&T | April | April | May Plan | May | June | June | June | June | June | June | July | August | In progress
2024 Q2 | xD_DWDM_BRKRing_NAR01_i_4000A_Prai_0004582401260T_45824026527 | NAR01_i | 4000A | 4000A-MSCPrai | FO&T | April | April | May Plan | May | June | June | June | June | June | June | July | August | In progress
2024 Q2 | xD_DWDM_BRKRing_NAR01_i_4521A_Msc Ipoh_0004582401260T_45824026527 | NAR01_i | 4521A | 4521A-MSC Menglembu | FO&T | April | April | May Plan | May | June | July | July | July | July | July | August | August | In progress
2024 Q2 | xD_DWDM_BRKRing_E209_8368A Serating_0004582401310P_00045824026721 | E209 | 8368A | 8368A-MAC-001 Serating | FO&T | April | April | May Plan | June | June | July | July | July | July | July | July | August | In progress
2024 Q2 | xD_DWDM_BRKRing_E209_8429B BPayung2_0004582401310P_00045824026721 | E209 | 8429B | 8429B-MAG(M14)-001 Bpayung 2 | FO&T | April | April | May Plan | May | June | June | June | June | June | June | July | August | In progress
2024 Q2 | xD_DWDM_BRKRing_E301_8712A Kg Jawa Pekan_0004582401310P_00045824026721 | E301 | 8712A | 8712A-MAC-001 Kg. Jawa Pekan | FO&T | April | May | May Plan | May | June | June | June | June | June | June | July | July | Completed
2024 Q2 | xD_DWDM_BRKRing_E301_8088A Sg Beto_0004582401310P_00045824026721 | E301 | 8088A | 8088A-MAG-001 Sg. Beto | FO&T | April | May | May Plan | May | June | June | June | June | June | June | July | July | Completed
2024 Q2 | xD_DWDM_BRKRing_E301_8000A KTNE1_0004582401310P_00045824026721 | E301 | 8000A | 8000A-MCR-002 KTN E1 | FO&T | April | May | May Plan | June | June | July | July | July | July | July | July | July | Completed
2024 Q2 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8000A MSC KTN_0004582401310P_00045824026721 | EAR01_1 & EAR01_3 | 8000A | 8000A MSC Kuantan | FO&T | April | May | May Plan | May | June | July | July | July | July | July | August | August | In progress
2024 Q2 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8263A Pasir Mas Town_0004582401310P_00045824026721 | EAR01_1 & EAR01_3 | 8263A | 8263A-MAG(M14)-001 Pasir Mas Town | FO&T | April | May | May Plan | June | June | June | June | June | June | June | July | August | In progress
2024 Q2 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8211A WCY_0004582401310P_00045824026721 | EAR01_1 & EAR01_3 | 8211A | 8211A-MAG(M8)-001 WCY | FO&T | April | May | May Plan | May | June | June | June | June | June | June | July | August | In progress
2024 Q2 | xD_DWDM_BRKRing_NAR01_ii_4938A_Tmn Orkid_0004582401280Y_00045824026722 | NAR01_ii | 4938A | 4938A-MAG001 Taman Orkid | FO&T | April | May | May Plan | June | June | June | June | June | June | June | July | August | Pending
2024 Q2 | xD_DWDM_BRKRing_NAR01_ii_4660A KTM Alor Star_0004582401280Y_00045824026722 | NAR01_ii | 4660A | 4660A-MAG-001 KTM Alor Setar | FO&T | April | May | May Plan | May | June | June | June | June | June | June | July | August | Pending
2024 Q2 | xD_DWDM_BRKRing_NAR01_ii_4998A Air Itam Kedah_0004582401280Y_00045824026722 | NAR01_ii | 4998A | 4998A-MAG-001 Air Itam Kedah | FO&T | April | May | May Plan | May | June | June | June | June | June | June | July | August | Pending
2024 Q2 | xD_DWDM_BRKRing_NAR01_ii_4606A Padang Besar_0004582401280Y_00045824026722 | NAR01_ii | 4606A | 4606A-MAG(M8)- 001 Padang Besar | FO&T | April | May | May Plan | May | June | July | July | July | July | July | August | August | Pending
2024 Q2 | xD_DWDM_BRKRing_N401_4952B Selama_0004582401280Y_00045824026722 | N401 | 4952B | 4952B-MAG 001 Selama | FO&T | April | May | May Plan | May | June | July | July | July | July | July | August | August | In progress