## Pivot
|  | 6 | 26 | 26
Break Ring Status | (blank)
Site ID | (All) | [5 empty] | Integrated Site - Completed |  |  |  | Installation Plan
SOW | (All) | [12 empty] | Integration Plan | [18 empty] | Ipran_Chk | (Multiple Items)
Material On Site | (blank) | [9 empty] | Row Labels | Count of Site ID | Count of Site ID2 | [19 empty] | WorkWeek_Integration | (All)
2024
[5 empty] | Values | [5 empty] | Jan | 5 | 5 |  |  |  |  | Values | [14 empty] | Count of Site ID |  |  | Project_Category
Plan MOS2 | Plan MOS | Batch | Ring ID | Priority Rollout | Count of Integration | Count of Site ID |  |  |  |  | Feb | 5 | 10 | Years2 | Integrated Date (30days + install) | Integration | WorkWeek_Integration | Count of Site ID | Accu of Site ID2 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov |  | Years2 | Integrated Date (30days + install) | Integration | IP BREAK RING | PE-MCR | Ring Expansion (MAG-PE) | Grand Total
Planned |  |  |  |  | 120 | 120 |  |  |  |  | Mar | 23 | 33 | 2024 | May |  |  | 38 | 38 | Baseline | 24 | 36 | 69 | 28 | 59 | 99 | 81 | 82 | 70 | 47 |  |  | 2024 | May |  | 10 | 11 | 4 | 25
2024-07-30 | 2024-07-30 | 2023_2024 | NT09P | P1 | 1 | 1 | Count of Site ID |  |  |  | Apr | 26 | 59 |  | Jun |  |  | 86 | 124 | Acc_Baseline | 24 | 60 | 129 | 157 | 216 | 315 | 396 | 478 | 548 | 595 |  |  |  | Jun |  | 44 | 3 | 12 | 59
|  | 2024 Q1 | C0204 | P2 | 4 | 4 | Batch | Plan Survey Date | Survey Date | Total | May | 81 | 140 |  | Jul |  |  | 68 | 192 | Integrated | Jan: 81; Feb: 36; Mar: 14; Apr: 17; May: 38; Jun: 0 | 186 |  | Jul |  | 33 | 9 | 3 | 45
|  |  | C0407P | P1 | 1 | 1 | 2024 Q2 | N/A | N/A | 14 | Jun | 86 | 226 |  | Aug |  |  | 40 | 232 | Plan_Integrated | May: 7; Jun: 86; Jul: 68; Aug: 40 | 201 |  | Aug |  | 20 |  | 7 | 27
|  |  | E105 | P3 | 1 | 1 |  | 2024-04-01 | (blank) | 1 | Jul | 63 | 289 | Grand Total |  |  |  | 232 |  | Forecasted Q3&Q4 | Jul: 20; Aug: 47; Sep: 75; Oct: 66 | 208 | Grand Total |  |  | 107 | 23 | 26 | 156
|  |  | S309 | P3 | 1 | 1 |  | 2024-04-03 | (blank) | 4 | Grand Total | 289 | [7 empty] | Total | 81 | 36 | 14 | 17 | 45 | 86 | 88 | 87 | 75 | 66
|  |  | ST21P | P2 | 1 | 1 |  | 2024-04-04 | (blank) | 6 | [9 empty] | Acc_Total | 81 | 117 | 131 | 148 | 193 | 279 | 367 | 454 | 529 | 595 |  | 595
|  | 2024 Q2 | CT04 | #N/A | 3 | 3 |  | 2024-04-05 | (blank) | 4
|  |  | MAC RING 6/C09+ | #N/A | 2 | 2 |  | 2024-04-06 | (blank) | 3
|  |  | NAR01_i | #N/A | 1 | 1 |  | 2024-04-15 | (blank) | 5
|  |  | SAR03_i&SAR03iii | #N/A | 1 | 1 |  | 2024-04-16 | (blank) | 4
|  |  | C0147P | #N/A | 2 | 2 |  | 2024-04-17 | (blank) | 2
|  | 2024 Q2_2 | 1063B/AREA 154/C0211+/C0515+ | P1_Z_Jul | 2 | 2 |  | 2024-04-18 | (blank) | 1
|  |  | AREA 154/MAC Ring 15/ C21+ | P1_Z_Jul | 2 | 2 |  | 2024-04-19 | (blank) | 2
|  |  | C0211+ | #N/A | 1 | 1 |  | 2024-04-22 | (blank) | 4
|  |  | C0515+ | #N/A | 5 | 5 |  | 2024-04-25 | (blank) | 13
|  |  | CAR02-ii+ | #N/A | 1 | 1 |  | (blank) | (blank) | 20
|  |  | MAC Ring 15/C21+ | #N/A | 2 | 2 | 2024 Q2_2 | N/A | (blank) | 4
|  |  | N104+ | #N/A | 1 | 1 |  | 2024-04-15 | (blank) | 1
|  |  | N107+ | P1_Z_Oct | 3 | 3 |  | 2024-04-16 | (blank) | 20
|  |  | N405+/N408+/N411+ | #N/A | 2 | 2 |  | 2024-04-17 | (blank) | 12
|  |  | N408+ | #N/A | 2 | 2 |  | 2024-04-18 | (blank) | 17
|  |  | N411+ | #N/A | 2 | 2 |  | (blank) | (blank) | 5
|  | Pending Po | N401 | #N/A |  | 6 | Grand Total |  |  | 142
|  |  | Nar01i | #N/A |  | 5
|  |  | Nar01ii | #N/A |  | 4
30/07/2024 Total |  |  |  |  | 41 | 56
Grand Total |  |  |  |  | 161 | 176
[20 empty] | CME Type | Jan: (Multiple Items)
[14 empty] | Count of Site ID | [5 empty] | Count of Site ID
[14 empty] | Integration | Integrated Date (30days + install) | Plan Power Up | Power Up | Total |  | Years | Jan: Integrated Date (30days + install); Feb: Total
[14 empty] | N/A | Jan | (blank) | N/A | 8 |  | 2024 | Jan: May; Feb: 33
[17 empty] | (blank) | 7 |  |  | Jan: Jun; Feb: 35
[15 empty] | Apr | (blank) | N/A | 1 |  |  | Jan: Jul; Feb: 28
[15 empty] | Jul | (blank) | N/A | 2 |  |  | Jan: Aug; Feb: 10
[16 empty] | Completed | Y | 2 |  | Grand Total | Feb: 106
[15 empty] | Aug | (blank) | N/A | 7
[17 empty] | (blank) | 1
[15 empty] | Oct | (blank) | N/A | 13
[15 empty] | Nov | (blank) | N/A | 8
[15 empty] | Dec | (blank) | N/A | 9
[14 empty] | TBC_InPlan | Jun |  |  | 51
[15 empty] | Jul | (blank) | (blank) | 1
[14 empty] | TBC_MOS | May |  |  | 38
[15 empty] | Jun |  |  | 16
[14 empty] | Y |  |  |  | 196
[14 empty] | (blank) | Jan | (blank) | (blank) | 15
[14 empty] | TBC_Jul_Plan | Jul | #N/A | #N/A | 1
[16 empty] | (blank) | N/A | 1
[17 empty] | (blank) | 58
[16 empty] | 2024-06-07 | (blank) | 3
[16 empty] | 2024-06-14 | (blank) | 1
[16 empty] | 2024-07-05 | (blank) | 2
[16 empty] | 2024-05-23 | (blank) | 1
[14 empty] | TBC_Aug_plan | Aug | (blank) | (blank) | 36
[16 empty] | 2024-06-07 | (blank) | 3
[16 empty] | 2024-06-21 | (blank) | 1
[14 empty] | TBC_Jun_Plan | Jun |  |  | 19
[14 empty] | Break Ring Status | (Multiple Items) | 0 | 0 | 0
[14 empty] | Site ID | (All)
[14 empty] | Ring ID | (All)
[14 empty] | Plan MOS | (Multiple Items)
Values
[14 empty] | Batch | Count of Integration | Count of Site ID
[14 empty] | 2023 | 61 | 61
[14 empty] | 2024 Q1 | 75 | 75
[14 empty] | 2024 Q2 | 42 | 42
[14 empty] | 2024 Q2_2 | 22 | 22
[14 empty] | Grand Total | 200 | 200

## Pivot_May_plan
41 | 40 | 40 | 40 | 40
Break Ring Status | (blank)
Values
Ring ID | Site ID | Plan MOS2 | Plan MOS | Material On Site | SOW | Batch | Count of Integration | Count of Site ID
C0103 (C0126) | 1207A | 2024-05-17 | 2024-05-17 | 2024-05-17 | 1800 1 rack 1subrack | 2024 Q1 | 1 | 1
| 1359A | 2024-05-16 | 2024-05-16 | 2024-05-16 | 1800 1 rack 1subrack | 2024 Q1 | 1 | 1
[5 empty] | Board expansion | 2024 Q2 | 1 | 1
C0103 (C0126) Total | [6 empty] | 3 | 3
C0105P | 1049B | 2024-05-15 | 2024-05-15 | 2024-05-15 | 1800VPRO 1 rack 4subrack | 2024 Q1 | 1 | 1
C0105P Total | [6 empty] | 1 | 1
C0417P | 1006A | Group1 | 2024-05-20 | (blank) | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
| 1203A | Group1 | 2024-05-21 | (blank) | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
C0417P Total | [6 empty] | 2 | 2
CAR02-i+/CAR02-ii+ | 1049B | 2024-05-09 | 2024-05-09 | 2024-05-14 | Board expansion | 2024 Q2_2 | 1 | 1
| 2021B | 2024-05-09 | 2024-05-09 | 2024-05-15 | Board expansion | 2024 Q2_2 | 1 | 1
CAR02-i+/CAR02-ii+ Total | [6 empty] | 2 | 2
CAR04 | 1049B | 2024-05-15 | 2024-05-15 | 2024-05-15 | 98001 rack 1 subrack | 2024 Q1 | 1 | 1
CAR04 Total | [6 empty] | 1 | 1
CAR05 | 1037A | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
| 1039A | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
| 1110A | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
| 1120A | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
| 1122A | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
| 1128A | 2024-05-08 | 2024-05-08 | 2024-05-10 | Board expansion | 2024 Q2 | 1 | 1
| 1475A | 2024-05-08 | 2024-05-08 | 2024-05-13 | Board expansion | 2024 Q2 | 1 | 1
| 2021B | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
| 2048B | 2024-05-08 | 2024-05-08 | 2024-05-06 | Board expansion | 2024 Q2 | 1 | 1
CAR05 Total | [6 empty] | 9 | 9
CT0120 | 2632A | Group1 | 2024-05-21 | 2024-03-27 | 1800 Rack and subrack | 2023 | 1 | 1
CT0120 Total | [6 empty] | 1 | 1
CT0241P | 1197A | 2024-05-15 | 2024-05-15 | 2024-05-15 | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
| 1211A | 2024-05-17 | 2024-05-17 | 2024-05-17 | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
| 1918A | 2024-05-23 | 2024-05-23 | 2024-05-23 | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
CT0241P Total | [6 empty] | 3 | 3
E111 | 8367A | 2024-05-08 | 2024-05-08 | 2024-05-09 | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
| 8439A | 2024-05-08 | 2024-05-08 | 2024-05-08 | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
E111 Total | [6 empty] | 2 | 2
E209 | 8368A | 2024-05-15 | 2024-05-15 | 2024-05-16 | Board expansion | 2024 Q2 | 1 | 1
| 8429B | 2024-05-15 | 2024-05-15 | 2024-05-15 | Board expansion | 2024 Q2 | 1 | 1
E209 Total | [6 empty] | 2 | 2
EAR01 | 8000A | 2024-05-08 | 2024-05-08 | 2024-05-08 | Board expansion | 2024 Q1 | 1 | 1
| 8224A | 2024-05-09 | 2024-05-09 | 2024-05-09 | 9800 M24 1 rack 1 subrack | 2024 Q1 | 1 | 1
EAR01 Total | [6 empty] | 2 | 2
EAR01_1 & EAR01_3 | 8000A | 2024-05-14 | 2024-05-14 | 2024-05-14 | Board expansion | 2024 Q2 | 1 | 1
EAR01_1 & EAR01_3 Total | [6 empty] | 1 | 1
EAR06 | 8000A | 2024-05-08 | 2024-05-08 | 2024-05-08 | 9800 1subrack | 2024 Q1 | 1 | 1
| 8513A | 2024-05-08 | 2024-05-08 | 2024-05-07 | 9800 1subrack | 2024 Q1 | 1 | 1
| 8667A | 2024-05-09 | 2024-05-09 | 2024-05-09 | 9800 1subrack | 2024 Q1 | 1 | 1
EAR06 Total | [6 empty] | 3 | 3
N103 | 4863B | 2024-05-08 | 2024-05-08 | 2024-05-08 | 1800 Rack and subrack | 2023 | 1 | 1
N103 Total | [6 empty] | 1 | 1
N106+ | 4683A | 2024-05-07 | 2024-05-07 | 2024-05-07 | 1800VPRO 1 rack 1 subrack | 2024 Q1 | 1 | 1
| 4966A | 2024-05-07 | 2024-05-07 | 2024-05-09 | 1800V PRO 1 rack 2 subrack | 2024 Q1 | 1 | 1
N106+ Total | [6 empty] | 2 | 2
NAR01_i | 4000A | 2024-05-14 | 2024-05-14 | 2024-05-14 | Board expansion | 2024 Q2 | 1 | 1
| 4521A | 2024-05-14 | 2024-05-14 | 2024-05-14 | Board expansion | 2024 Q2 | 1 | 1
NAR01_i Total | [6 empty] | 2 | 2
NAR02_ii+ | 4000A | 2024-05-14 | 2024-05-14 | 2024-05-14 | Board expansion | 2024 Q2_2 | 1 | 1
NAR02_ii+ Total | [6 empty] | 1 | 1
NAR04_ii+ | 4521A | 2024-05-14 | 2024-05-14 | 2024-05-14 | Board expansion | 2024 Q2_2 | 1 | 1
NAR04_ii+ Total | [6 empty] | 1 | 1
PFSRING101/C0607P | 1899A | 2024-05-09 | 2024-05-09 | 2024-05-09 | 1800 Rack and subrack | 2023 | 1 | 1
PFSRING101/C0607P Total | [6 empty] | 1 | 1
Ring58/C1103 | 1015A | 2024-05-09 | 2024-05-09 | 2024-05-09 | 1800 subrack | 2023 | 1 | 1
Ring58/C1103 Total | [6 empty] | 1 | 1
Grand Total | [6 empty] | 41 | 41

## Apr May BR Plan
94 | 178 | 180 | 180 | 197 | 180 | 180 | 180 | 121 | 227 | 0 | 0
Break Ring Status | (blank)
[8 empty] | Values | [5 empty] | QCTE Plan End Date
Ring ID | Site ID | DUID2 | SOW | CME Request | Plan MOS | Material On Site | Batch | Count of Integration | Count of Site ID |  |  | Chk |  | #N/A
Area139 | 4000A | xD_DWDM-BRKRing_Area139_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | Single | 2024-03-22 | 2024-03-22 | 2023 | 1 | 1 |  |  |  |  | 2024-06-30
| 4946A | xD_DWDM-BRKRing_Area139_4946A Bukit Selambau_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | Single | 2023-11-22 | 2023-11-22 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
Area139 Total | [7 empty] | 2 | 2 |  |  | 0 | P0 | #N/A
C0103 (C0126) | 1049B | xD_DWDM-BRKRing_C0103_1049B MCR KPG_0004582400320X_00045824009023 | Board expansion | Single | 2024-05-24 | 2024-05-24 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1207A | xD_DWDM-BRKRing_C0103_1207A Sg Buloh New Village_0004582400320X_00045824009023 | 1800 1 rack 1subrack | #N/A | 2024-05-17 | 2024-05-17 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1359A | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | 1800 1 rack 1subrack | Single | 2024-05-16 | 2024-05-16 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1364B | xD_DWDM-BRKRing_C0103_1364B Bestari(Maxis)_0004582400320X_00045824009023 | 1800 1 rack 1subrack | #N/A | 2024-05-28 | 2024-05-28 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
C0103 (C0126) Total | [8 empty] | 4 |  |  | 0 |  | #N/A
C0105P | 1049B | xD_DWDM_BRKRing_C0105P_1049B MCR KPG_0004582309050Y_00045824006623 | 1800VPRO 1 rack 4subrack | Single | 2024-05-15 | 2024-05-15 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
C0105P Total | [8 empty] | 1 |  |  | 0 | P1 | #N/A
C0204 | 1253A | xD_DWDM_BRKRing_C0204_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | Single | 2024-07-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1261A | xD_DWDM_BRKRing_C0204_1261A KWSP_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | #N/A | 2024-07-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1851A | xD_DWDM_BRKRing_C0204_18451A KL Plaza2_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-07-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1869A | xD_DWDM_BRKRing_C0204_1869A Daya Bumi_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-07-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
C0204 Total | [8 empty] | 4 |  |  | 0 |  | #N/A
C0210P | 1253A | xD_DWDM_BRKRing_C0210P_1253A Plaza Pengkalan_0004582309010S_00045824006622 | 1800 1rack 2 subrack | Single | 2024-04-23 | 2024-04-23 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1859A | xD_DWDM_BRKRing_C0210P_1859A Midvalleycas_0004582309010S_00045824006622 | 1800 1rack 3 subrack | Single | 2024-04-24 | 2024-04-24 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 2878A | xD_DWDM_BRKRing_C0210P_2878A Mont Kiara_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Single | 2024-04-25 | 2024-04-25 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
C0210P Total | [8 empty] | 3 |  |  | 0 |  | #N/A
C0407P | 1266A | xD_DWDM_BRKRing_C0407P_1266A Sucasa_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | Single | 2024-05-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1304A | xD_DWDM_BRKRing_C0407P_1304A MMA_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | #N/A | 2024-03-26 | 2024-03-26 | 2024 Q1 |  | 1 |  |  |  |  | 2024-06-30
| 1737A | xD_DWDM_BRKRing_C0407P_1737A Bernama_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | Multiple | 2024-04-24 | 2024-04-24 | 2024 Q1 |  | 1 |  |  |  |  | 2024-04-30
| 1745A | xD_DWDM_BRKRing_C0407P_1745A Baitumal_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | #N/A | 2024-07-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
C0407P Total | [8 empty] | 4 |  |  | 0 | P1 | #N/A
C0417P | 1006A | xD_DWDM_BRKRing_C0417P_1006A JBA Gombak_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-20 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1203A | xD_DWDM_BRKRing_C0417P_1203A JBA Sri Damansara_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-21 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
C0417P Total | [8 empty] | 2 |  |  | 0 |  | #N/A
C0702P | 1096A | xD_DWDM-BRKRing_C0702P_1096A MAG KlangPerdana_0004582304330Y_00045823098821 | 1800 Rack and subrack | #N/A | 2023-11-22 | 2023-11-23 | 2023 |  | 1 |  |  |  |  | 2023-11-30
| 1153A | xD_DWDM-BRKRing_C0702P_1153A MAC PermatangKSelangor_0004582304330Y_00045823098821 | 1800 Rack and subrack | Single | 2023-11-24 | 2023-11-24 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
| 1154A | xD_DWDM-BRKRing_C0702P_1154A MAGSekinchan_0004582304330Y_00045823098821 | 1800 Rack and subrack | Single | 2023-11-23 | 2023-11-23 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
| 1156A | xD_DWDM-BRKRing_C0702P_1156A MAC BtgBerjuntai_0004582304330Y_00045823098821 | 1800 Rack and subrack | Single | 2023-11-24 | 2023-11-24 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
| 1169A | xD_DWDM-BRKRing_C0702P_1169A MAC TgKrngTrunkRd_0004582304330Y_00045823098821 | 1800 Rack and subrack | Multiple | 2023-11-24 | 2023-11-24 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
C0702P Total | [7 empty] | 4 | 5 |  |  | 0 | P1 | #N/A
C0713P | 1071A | xD_DWDM-BRKRing_C0713P_1071A_Chi Liung Plaza_0004582304330V_00045823098821 | 9800 Rack with subrack | #N/A | 2023-11-20 | 2023-11-20 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
| 1096A | xD_DWDM-BRKRing_C0713P_1096A_KlangPerdana_0004582304330V_00045823098821 | 9800 Board Expansion | #N/A | 2023-11-23 | 2023-11-23 | 2023 | 1 | 1 |  |  |  |  | 2023-11-30
| 1342A | xD_DWDM-BRKRing_C0713P_1342A_MBSA_00045823098821 | Services only | #N/A | (blank) | N/A | 2023 | 1 | 1 |  |  |  |  | 0
| 2021B | xD_DWDM-BRKRing_C0713P_2021B_SBHT_0004582304330V_00045823098821 | 9800 Board Expansion | Multiple | 2023-12-12 | 2023-12-12 | 2023 | 1 | 1 |  |  |  |  | 2023-12-22
C0713P Total | [7 empty] | 4 | 4 |  |  | 0 | P0 | #N/A
CAR01 | 1085 | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 | Board expansion | #N/A | 2024-03-20 | 2024-03-22 | 2024 Q1 | 1 | 1 |  |  |  |  | #N/A
| 1049B | xD_DWDM-BRKRing_CAR01_1049B MCR KPG_0004582400460T_00045824009529 | Board expansion | Single | 2024-03-22 | 2024-03-22 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-03-31
| 1085A | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 | Board expansion | #N/A | 2024-03-22 | 2024-03-22 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-03-31
| 1409A | xD_DWDM-BRKRing_CAR01_1409A Kota Damansara_0004582400460T_00045824009529 | Board expansion | Single | 2024-03-20 | 2024-03-21 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-03-31
| 2021B | xD_DWDM-BRKRing_CAR01_2021B SBHT_0004582400460T_00045824009529 | Board expansion | Multiple | 2024-03-20 | 2024-03-22 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-03-31
| 2777C | xD_DWDM-BRKRing_CAR01_2777C JBA Bukit Lipat_0004582400460T_00045824009529 | Board expansion | #N/A | 2024-03-21 | 2024-03-25 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-03-31
CAR01 Total | [7 empty] | 6 | 6 |  |  | 0 | P0 | #N/A
CAR04 | 1006A | xD_DWDM_BRKRing_CAR04_1006A JBA Gombak_0004582309050Y_00045824006623 | 98001 rack 1 subrack | Single | 2024-04-25 | 2024-04-25 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-05-31
| 1049B | xD_DWDM_BRKRing_CAR04_1049B KPG_0004582309050Y_00045824006623 | 98001 rack 1 subrack | Single | 2024-05-15 | 2024-05-15 | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1253A | xD_DWDM-BRKRing_CAR04_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | Services only | Single | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1261A | xD_DWDM-BRKRing_CAR04_1261A KWSP_0004582309050Y_00045824006623 | Services only | #N/A | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1266A | xD_DWDM-BRKRing_CAR04_1266A Sucasa_0004582309050Y_00045824006623 | Services only | Single | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1271A | xD_DWDM-BRKRing_CAR04_1271A Risda_0004582309050Y_00045824006623 | Services only | Single | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1304A | xD_DWDM_BRKRing_CAR04_1304A MMA_0004582309050Y_00045824006623 | 98001 rack 1 subrack | #N/A | 2024-03-26 | 2024-03-26 | 2024 Q1 |  | 1 |  |  |  |  | 2024-04-30
| 1458A | xD_DWDM_BRKRing_CAR04_1458A Endah Parade_0004582309050Y_00045824006623 | 98001 rack 1 subrack | Single | 2024-04-23 | 2024-04-23 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-05-31
| 1461A | xD_DWDM-BRKRing_CAR04_1461A Shaw Parade_0004582309050Y_00045824006623 | Services only | #N/A | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1475A | xD_DWDM_BRKRing_CAR04_1475A SKB_0004582309050Y_00045824006623 | 98001 rack 1 subrack | Single | 2024-06-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1737A | xD_DWDM-BRKRing_CAR04_1737A Bernama_0004582309050Y_00045824006623 | Services only | Multiple | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1745A | xD_DWDM_BRKRing_CAR04_1745A Baitumal_0004582309050Y_00045824006623 | 98001 rack 1 subrack | #N/A | 2024-06-30 | (blank) | 2024 Q1 |  | 1 |  |  |  |  | 2024-05-31
| 1851A | xD_DWDM-BRKRing_CAR04_1851A KL Plaza_0004582309050Y_00045824006623 | Services only | Multiple | N/A | N/A | 2024 Q1 |  | 1 |  |  |  |  | #N/A
| 1855B | xD_DWDM-BRKRing_CAR04_1855B TPM_0004582309050Y_00045824006623 | Services only | Multiple | N/A | N/A | 2024 Q1 | 1 | 1 |  |  |  |  | #N/A
CAR04 Total | [7 empty] | 3 | 14 |  |  | 0 |  | #N/A
CAR11 | 1049B | xD_DWDM-BRKRing_CAR11_1049B MCR Kepong_0004582400700P_00045824009527 | Board expansion | Single | 2024-04-22 | 2024-04-22 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-04-30
| 2070B | xD_DWDM-BRKRing_CAR11_2070B Gombak_0004582400700P_00045824009527 | Board expansion | Single | 2024-04-22 | 2024-04-22 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-04-30
| 8709A | xD_DWDM-BRKRing_CAR11_8709A Bentong_0004582400700P_00045824009527 | Board expansion | Single | 2024-04-18 | 2024-04-18 | 2024 Q1 | 1 | 1 |  |  |  |  | 2024-04-30
CAR11 Total | [7 empty] | 3 | 3 |  |  | 0 | P0 | #N/A
CT0120 | 1099A | xD-DWDM-BRKRing_CT0120_1099A HongFatt_0004582304160F_0004582308742 | 1800 Rack and subrack | Single | 2023-12-06 | 2023-12-06 | 2023 |  | 1 |  |  |  |  | 2023-12-22
| 1409A | xD-DWDM-BRKRing_CT0120_1409A Damansara_0004582304160F_0004582308742 | 1800 Rack and subrack | Single | 2023-12-07 | 2023-12-07 | 2023 |  | 1 |  |  |  |  | 2023-12-22
| 2632A | xD_DWDM-BRKRing_CT0120_2632A Ecopark_0004582304160F_0004582308742 | 1800 Rack and subrack | Single | 2024-05-21 | 2024-03-27 | 2023 | 1 | 1
CT0120 Total | [7 empty] | 1 | 3 |  |  | 0
CT0241P | 1197A | xD_DWDM_BRKRing_CT0241P_1197A JBA Effingham_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-15 | 2024-05-15 | 2024 Q1 |  | 1
| 1211A | xD_DWDM_BRKRing_CT0241P_1211A KDU_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-05-17 | 2024-05-17 | 2024 Q1 |  | 1
| 1918A | xD_DWDM_BRKRing_CT0241P_1918A Damansara Intan_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-23 | 2024-05-23 | 2024 Q1 |  | 1
CT0241P Total | [8 empty] | 3 |  |  | 0 | P1
CT04 | 1049B | xD-DWDM-BRKRing_1049B-002 MSC KEPONG_00045823053925 | 1800 Rack and subrack | Single | (blank) | 2023-09-26 | 2023 | 1 | 1
| 1412A | xD-DWDM-BRKRing_1412A BKT TADUN_00045823053925 | 1800 Rack and subrack | #N/A | (blank) | 2023-10-10 | 2023 | 1 | 1
| 1413A | xD-DWDM-BRKRing_1413A KTM RAWANG_00045823053925 | 1800 Rack and subrack | Single | 2024-06-11 | (blank) | 2023 |  | 1
CT04 Total | [7 empty] | 2 | 3 |  |  | 0 | P1
E104 | 8263A | xD_DWDM_BRKRing_E104_8263AMAG(M14)- 001 Pmas_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | Single | 2024-04-23 | 2024-04-23 | 2024 Q1 |  | 1
| 8269B | xD_DWDM_BRKRing_E104_8269B-MAC001 Chetok_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-06-04 | (blank) | 2024 Q1 |  | 1
| 8288B | xD_DWDM_BRKRing_E104_8288B-MAG001 Panau_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-04-22 | 2024-04-23 | 2024 Q1 |  | 1
| 8294A | xD_DWDM_BRKRing_E104_8294A-MAC001 Kangkong_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-06-05 | (blank) | 2024 Q1 |  | 1
E104 Total | [8 empty] | 4 |  |  | 0 | P2
E105 | 8139B | xD_DWDM_BRKRing_E105_8139B-MAC001 CBC_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-06-25 | (blank) | 2024 Q1 |  | 1
| 8211A | xD_DWDM_BRKRing_E105_8211A-MAG(M8)- 001 WCY_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | #N/A | 2024-06-25 | (blank) | 2024 Q1 |  | 1
| 8212A | xD_DWDM_BRKRing_E105_8212A-MAC001 Wbharu_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-04-24 | 2024-04-25 | 2024 Q1 |  | 1
| 8229A | xD_DWDM_BRKRing_E105_8229A-MAC001 Tumpat_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-04-24 | 2024-04-24 | 2024 Q1 |  | 1
E105 Total | [8 empty] | 4 |  |  | 0 | P3
E109 | 8222A | xD_DWDM_BRKRing_E109_8222A-MAC001 Peringat_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-04-24 | 2024-04-24 | 2024 Q1 |  | 1
| 8224A | xD_DWDM_BRKRing_E109_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | Multiple | 2024-06-06 | (blank) | 2024 Q1 |  | 1
| 8242B | xD_DWDM_BRKRing_E109_8242B-MAC001 JKKrai_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-04-25 | 2024-04-25 | 2024 Q1 |  | 1
E109 Total | [8 empty] | 3 |  |  | 0 | P3
E111 | 8317A | xD_DWDM_BRKRing_E111_8317A-MAC-001 Kampung Pak Wong_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-06-26 | (blank) | 2024 Q1 |  | 1
| 8322B | xD_DWDM_BRKRing_E111_8322B-MAC001 Padang Luas_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-04-25 | 2024-04-25 | 2024 Q1 |  | 1
| 8367A | xD_DWDM_BRKRing_E111_8367A-MAG001 B.Kechil_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-08 | 2024-05-09 | 2024 Q1 |  | 1
| 8407A | xD_DWDM_BRKRing_E111_8407A-MAC001 Jerteh_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-06-26 | (blank) | 2024 Q1 |  | 1
| 8439A | xD_DWDM_BRKRing_E111_8439A-MAC001 A.Lintang_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-08 | 2024-05-08 | 2024 Q1 |  | 1
E111 Total | [8 empty] | 5 |  |  | 0 | P0
EAR01 | 4000A | xD_DWDM_BRKRing_EAR01_4000A-MCR-001 PRI_0004582309010R_00045824006624 | Board expansion | Single | 2024-03-18 | 2024-03-19 | 2024 Q1 | 1 | 1
| 8000A | xD_DWDM_BRKRing_EAR01_8000A-MCR001 KTN_0004582309010R_00045824006624 | Board expansion | #N/A | 2024-05-08 | 2024-05-08 | 2024 Q1 | 1 | 1
| 8224A | xD_DWDM_BRKRing_EAR01_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 9800 M24 1 rack 1 subrack | Multiple | 2024-05-09 | 2024-05-09 | 2024 Q1 |  | 1
EAR01 Total | [7 empty] | 2 | 3 |  |  | 0 | P1
EAR02 | 4000A | xD-DWDM-BRKRing_EAR02_2_4000A Prai_0004582304160E_00045823087420 | 9800 Rack with subrack | Single | #N/A | #N/A | 2023 | 1 | 1
| 8000A | xD-DWDM-BRKRing_EAR02_2_8000A Kuantan_0004582304160E_00045823087420 | 9800 Rack with subrack | #N/A | (blank) | 2023-11-14 | 2023 | 1 | 1
| 8429B | xD-DWDM-BRKRing_EAR02_2_8429B BktPayung_0004582304160E_00045823087420 | 9800 Rack with subrack | Single | #N/A | #N/A | 2023 | 1 | 1
EAR02 Total | [7 empty] | 3 | 3 |  |  | 0 | P0
EAR06 | 1475A | xD_DWDM_BRKRing_EAR06_1475A-MSC MSK_0004582309010R_00045824006624 | Board expansion | Single | 2024-03-18 | 2024-03-19 | 2024 Q1 | 1 | 1
| 8000A | xD_DWDM_BRKRing_EAR06_8000A-MSC Kuantan_0004582309010R_00045824006624 | 9800 1subrack | #N/A | 2024-05-08 | 2024-05-08 | 2024 Q1 |  | 1
| 8105A | xD_DWDM_BRKRing_EAR06_8105A-MAG 001 South Of Raub_0004582309010R_00045824006624 | 9800 1subrack | #N/A | 2024-06-06 | (blank) | 2024 Q1 |  | 1
| 8112A | xD_DWDM_BRKRing_EAR06_8112A-MAG 001 Bukit Istana_0004582309010R_00045824006624 | 9800 1subrack | #N/A | 2024-04-24 | 2024-04-25 | 2024 Q1 |  | 1
| 8145Z | xD_DWDM_BRKRing_EAR06_8145Z-MAG 001 T3E 0160 Kg Paya Luas_0004582309010R_00045824006624 | 9800 1subrack | #N/A | 2024-04-25 | 2024-04-24 | 2024 Q1 |  | 1
| 8173A | xD_DWDM_BRKRing_EAR06_8173A-MAG 001 Bandar Pusat Jengka_0004582309010R_00045824006624 | 9800 1subrack | #N/A | 2024-04-25 | 2024-04-25 | 2024 Q1 |  | 1
| 8513A | xD_DWDM_BRKRing_EAR06_8513A-MAG002 Senggora_0004582309010R_00045824006624 | 9800 1subrack | Single | 2024-05-08 | 2024-05-07 | 2024 Q1 |  | 1
| 8667A | xD_DWDM_BRKRing_EAR06_8667A-MAG 001 Kg Jerangsang_0004582309010R_00045824006624 | 9800 1subrack | Single | 2024-05-09 | 2024-05-09 | 2024 Q1 |  | 1
| 8709A | xD_DWDM_BRKRing_EAR06_8709A-MAG002 Bentong_0004582309010R_00045824006624 | 9800 1 subrack | Single | 2024-06-06 | (blank) | 2024 Q1 |  | 1
EAR06 Total | [7 empty] | 1 | 9 |  |  | 0 | P3
MAC RING 9/C13 | 1295A | xD_DWDM_BRKRing_MR9/C13_1295A Com Bkt Maluri_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-05-28 | 2024-05-28 | 2024 Q1 |  | 1
MAC RING 9/C13 Total | [8 empty] | 1 |  |  | 0 | P1
MCR18/C24 | 1172A | xD_DWDM-BRKRing_MCR18/C24_1172A Glomac_0004582306610C_00045823162822 | 1800 Rack and subrack | #N/A | (blank) | N/A | 2023 | 1 | 1
| 1360A | xD_DWDM-BRKRing_MCR18/C24_1360B Hicom Glenmarie_0004582306610C_00045823162822 | 1800 Rack and subrack | Multiple | (blank) | 2024-05-11 | 2023 |  | 1
| 1362B | xD_DWDM-BRKRing_MCR18/C24_1362B Kelana Business_0004582306610C_00045823162822 | 1800 Rack and subrack | Multiple | 2023-11-22 | 2023-11-22 | 2023 |  | 1
| 1378B | xD_DWDM-BRKRing_MCR18/C24_1378B PJS 10_0004582304330Y_00045823098821 | 1800 Rack and subrack | Single | 2023-11-22 | 2023-11-23 | 2023 |  | 1
| 2021B | xD_DWDM-BRKRing_MCR18/C24_2021B SBHT_0004582306610C_00045823162822 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-07 | 2023 | 1 | 1
MCR18/C24 Total | [7 empty] | 2 | 5 |  |  | 0 | P2
MR20/C26 | 1081A | xD-DWDM-BRKRing_MR20/C26_1081A BktLipat_0004582304160F_0004582308742 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-24 | 2023 | 1 | 1
| 1085A | xD-DWDM-BRKRing_MR20/C26_1085A PekanMeru_0004582304160F_0004582308742 | 1800 Rack and subrack | #N/A | (blank) | 2023-10-06 | 2023 | 1 | 1
| 1093A | xD-DWDM-BRKRing_MR20/C26_1093A KianHoeHuat_0004582304160F_0004582308742 | 1800 Rack and subrack | Single | (blank) | 2023-11-24 | 2023 | 1 | 1
| 1104A | xD-DWDM-BRKRing_MR20/C26_1104A SurauAlAmin_0004582304160F_0004582308742 | 1800 Rack and subrack | #N/A | (blank) | 2023-10-06 | 2023 | 1 | 1
| 1627B | xD-DWDM-BRKRing_MR20/C26_1627B IndahHighway_0004582304160F_0004582308742 | 1800 Rack and subrack | Single | (blank) | 2023-10-10 | 2023 | 1 | 1
MR20/C26 Total | [7 empty] | 5 | 5 |  |  | 0 | P1
N103 | 4660A | xD_DWDM-BRKRing_N103_4660A KTM Alorstar_0004582306610C_00045823162822 | 1800 Rack and subrack | #N/A | (blank) | 2023-11-24 | 2023 | 1 | 1
| 4669A | xD_DWDM-BRKRing_N103_4669A Alor Janggus_0004582306610C_00045823162822 | 1800 Rack and subrack | Single | (blank) | 2023-11-23 | 2023 | 1 | 1
| 4863B | xD_DWDM-BRKRing_N103_4863B Wisma PKNK_0004582306610C_00045823162822 | 1800 Rack and subrack | Multiple | 2024-05-08 | 2024-05-08 | 2023 | 1 | 1
| 4998A | xD_DWDM-BRKRing_N103_4998A Air Itam Kedah_0004582306610C_00045823162822 | 1800 Rack and subrack | Single | (blank) | 2023-11-23 | 2023 | 1 | 1
N103 Total | [7 empty] | 4 | 4 |  |  | 0 | P1
N106(ii) | 4085D | xD-DWDM-BRKRing_N106_4085D Kulim Hitech 2 | Services only | Single | (blank) | N/A | 2023 | 1 | 1
| 4683A | xD-DWDM-BRKRing_N106_4683A Bkt Tok Alang | 1800 Rack and subrack | Single | (blank) | N/A | 2023 | 1 | 1
N106(ii) Total | [7 empty] | 2 | 2 |  |  | 0 | P1
N106+ | 4683A | xD_DWDM_BRKRing_N106+_4683A Bkt Tok Alang_0004582309010S_00045824006622 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-07 | 2024-05-07 | 2024 Q1 | 1 | 1
| 4966A | xD_DWDM_BRKRing_N106+_4966A Kulim Hitech_0004582309010S_00045824006622 | 1800V PRO 1 rack 2 subrack | #N/A | 2024-05-07 | 2024-05-09 | 2024 Q1 |  | 1
N106+ Total | [7 empty] | 1 | 2 |  |  | 0 | P1
N113(ii) | 4663A | xD_DWDM_BRKRing_N113_4663A Derga Jaya_0004582306610C_00045823162822 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-02-22 | 2024-02-23 | 2023 | 1 | 1
| 4973B | xD_DWDM_BRKRing_N113_4973B Tajar_0004582306610C_00045823162822 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-02-22 | 2024-02-22 | 2023 | 1 | 1
N113(ii) Total | [7 empty] | 2 | 2 |  |  | 0 | P1
N201 | 4000A | xD_DWDM-BRKRing_N201_4000A MSC Prai_000458237400E_00045823174223 | 1800 Rack and subrack | Single | (blank) | 2023-11-20 | 2023 | 1 | 1
| 4685B | xD_DWDM-BRKRing_N201_4685B Kg Sungai Karangan_000458237400E_00045823174223 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-30 | 2023 | 1 | 1
| 4950B | xD_DWDM-BRKRing_N201_4950B Pulai_000458237400E_00045823174223 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-23 | 2023 | 1 | 1
| 4956B | xD_DWDM-BRKRing_N201_4956B Kuala Pegang_000458237400E_00045823174223 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-23 | 2023 | 1 | 1
| 4968A | xD_DWDM-BRKRing_N201_4968A Inokom Kulim_000458237400E_00045823174223 | 1800 Rack and subrack | Single | (blank) | 2023-11-24 | 2023 | 1 | 1
| 4985A | xD_DWDM-BRKRing_N201_4985A Baling Town_000458237400E_00045823174223 | 1800 Rack and subrack | Single | (blank) | 2023-11-23 | 2023 | 1 | 1
| 4986A | xD_DWDM-BRKRing_N201_4986A Binjul_000458237400E_00045823174223 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-24 | 2023 | 1 | 1
| 4988A | xD_DWDM-BRKRing_N201_4988A Kupang_000458237400E_00045823174223 | 1800 Rack and subrack | Single | (blank) | 2023-11-23 | 2023 | 1 | 1
N201 Total | [7 empty] | 8 | 8 |  |  | 0 | P??
NAR03 | 4000A | xD_DWDM-BRKRing_NAR03_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | Single | (blank) | 2023-11-20 | 2023 | 1 | 1
| 4331A | xD_DWDM-BRKRing_NAR03_4331A Bagan Serai_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | #N/A | (blank) | 2023-11-22 | 2023 | 1 | 1
NAR03 Total | [7 empty] | 2 | 2 |  |  | 0 | P0
New Ring5/S406 | 6000A | xD_DWDM-BRKRing_New Ring_5/S406_6000A MSC JB_0004582306610B_00045823162821 | 1800 Rack and subrack | Single | (blank) | 2023-12-05 | 2023 | 1 | 1
| 6026A | xD_DWDM-BRKRing_New Ring_5/S406_6026A Grand Cont Hotel_0004582306610B_00045823162821 | 1800 Rack and subrack | Single | (blank) | 2023-12-07 | 2023 | 1 | 1
| 6043A | xD_DWDM-BRKRing_New Ring_5/S406_6043A KK Kam_0004582306610B_00045823162821 | 1800 Rack and subrack | #N/A | (blank) | 2023-12-07 | 2023 | 1 | 1
| 6283A | xD_DWDM-BRKRing_New Ring_5/S406_6283A Larkin Indst_0004582306610B_00045823162821 | 1800 Rack and subrack | Multiple | (blank) | 2023-12-08 | 2023 | 1 | 1
| 6502A | xD_DWDM-BRKRing_New Ring_5/S406_6502A Nusa Perintis_0004582306610B_00045823162821 | 1800 Rack and subrack | Multiple | (blank) | 2023-12-08 | 2023 | 1 | 1
| 6836A | xD_DWDM-BRKRing_New Ring_5/S406_6836A Menara Ansar_0004582306610B_0004582316282 | 1800 Rack and subrack | Single | 2024-04-24 | 2024-04-24 | 2023 | 1 | 1
New Ring5/S406 Total | [7 empty] | 6 | 6 |  |  | 0 | P0
NT09P | 4640A | xD_DWDM_BRKRing_NT09P_4640A Sp Plaza_0004582309010S_00045824006622 | 1800VPRO 1 rack 1 subrack | Single | 2024-07-30 | (blank) | 2023_2024 |  | 1
NT09P Total | [8 empty] | 1 |  |  | 0 | P0
PFSRING101/C0607P | 1063B | xD_DWDM_BRKRing_PFSRING101/C0607_1063B_Berjya Times Square Rooftop_0004582306610C_00045823162822 | 1800 Rack and subrack | Single | 2024-05-24 | 2024-05-24 | 2023 |  | 1
| 1246A | xD_DWDM-BRKRing_PFSRING101/C0607P_1246A Kompleks Nagaria_0004582306610C_00045823162822 | 1800 Rack and subrack | Single | (blank) | 2023-12-08 | 2023 | 1 | 1
| 1475A | xD_DWDM-BRKRing_PFSRING101/C0607P_1475A Sri Kembangan_0004582306610C_00045823162822 | 1800 Rack and subrack | Single | (blank) | 2023-12-04 | 2023 | 1 | 1
| 1851A | xD_DWDM-BRKRing_PFSRING101/C0607P_1851A KL Plaza2_0004582306610C_00045823162822 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-24 | 2023 | 1 | 1
| 1899A | xD_DWDM-BRKRing_PFSRING101/C0607P_1899A Berjaya Times Square CAS_0004582306610C_00045823162822 | 1800 Rack and subrack | Single | 2024-05-09 | 2024-05-09 | 2023 |  | 1
PFSRING101/C0607P Total | [7 empty] | 3 | 5 |  |  | 0 | P1
Ring58/C1103 | 1015A | xD_DWDM-BRKRing_Ring58/C1103_1015A Awana Golf_0004582307100Y_00045823168326 | 1800 subrack | #N/A | 2024-05-09 | 2024-05-09 | 2023 |  | 1
| 1016A | xD_DWDM-BRKRing_Ring58/C1103_1016A Genting Ria_0004582307100Y_00045823168326 | 1800 subrack | #N/A | 2024-06-05 | (blank) | 2023 |  | 1
| 1770B | xD_DWDM-BRKRing_Ring58/C1103_1770B Genting Sempah_0004582307100Y_00045823168326 | 1800 Rack and subrack | Single | (blank) | 2023-12-15 | 2023 | 1 | 1
| 2070B | xD_DWDM-BRKRing_Ring58/C1103_2070B Gombak_0004582307100Y_00045823168326 | 1800 Rack and subrack | Single | (blank) | 2023-10-25 | 2023 | 1 | 1
| 2833A | xD_DWDM-BRKRing_Ring58/C1103_2833A First World Hotel_0004582307100Y_00045823168326 | 1800 subrack (outdoor rack) | Single | 2024-06-06 | (blank) | 2023 |  | 1
| 8709A | xD_DWDM-BRKRing_Ring58/C1103_8709A Bentong_0004582307100Y_00045823168326 | 1800 subrack | Single | (blank) | 2023-10-25 | 2023 | 1 | 1
Ring58/C1103 Total | [7 empty] | 3 | 6 |  |  | 0 | P2
S201 | 1621A | xD-DWDM-BRKRing_S201_1621A Senawang_0004582304070S_00045823086826 | 1800 Rack and subrack | #N/A | (blank) | 2023-12-12 | 2023 | 1 | 1
| 1760A | xD-DWDM-BRKRing_S201_1760A Mambau1_0004582304070S_00045823086826 | 1800 Rack and subrack | Single | (blank) | 2023-11-15 | 2023 | 1 | 1
|  | xD-DWDM-BRKRing_S201_1760A Mambau2_0004582304070S_00045823086826 | 1800 Rack and subrack | Single | (blank) | 2023-11-15 | 2023 | 1 | 1
| 3433C | xD-DWDM-BRKRing_S201_3433C Bkt Pelandok_0004582304070S_00045823086826 | 1800 Rack and subrack | #N/A | (blank) | 2023-11-22 | 2023 | 1 | 1
S201 Total | [7 empty] | 4 | 4 |  |  | 0 | P0
S301 | 1554A | xD_DWDM_BRKRing_S301_1554AMAG(M14)-001 Rumbia_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-05-29 | 2024-05-29 | 2024 Q1 |  | 1
| 1560A | xD_DWDM_BRKRing_S301_1560A-MAC001 Bkt Tiga_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-27 | 2024-05-27 | 2024 Q1 |  | 1
| 1563A | xD_DWDM_BRKRing_S301_1563A-MAC001 Bkt Iman_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-28 | 2024-05-28 | 2024 Q1 |  | 1
| 1621A | xD_DWDM_BRKRing_S301_1621A-MCR001 SNW_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | #N/A | 2024-06-30 | (blank) | 2024 Q1 |  | 1
S301 Total | [8 empty] | 4 |  |  | 0 | P1
S309 | 1553A | xD_DWDM_BRKRing_S309_1553AMAG(M14)-001 Umbai_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-06-30 | (blank) | 2024 Q1 |  | 1
|  | xD-DWDM-BRKRing_S309_1553A Umbai_0004582304160F_0004582308742 | 1800 Rack and subrack | Multiple | 2024-06-30 | (blank) | 2023 |  | 1
| 1556A | xD_DWDM_BRKRing_S309_1556A-MAC001 Merlimau_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-06-12 | (blank) | 2024 Q1 |  | 1
| 1599A | xD_DWDM_BRKRing_S309_1599A-MAC001 Bkt Gambir Town_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-06-30 | (blank) | 2024 Q1 |  | 1
| 2402B | xD_DWDM_BRKRing_S309_2402B-MAG001 Pagoh Highway_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Multiple | 2024-04-23 | 2024-04-23 | 2024 Q1 |  | 1
S309 Total | [8 empty] | 5 |  |  | 0 | P3
S313P_2_2 | 1525A | xD_DWDM-BRKRing_S313P_2_2_1525A Graha Maju_0004582304160F_00045823087420 | 1800 Rack and subrack | Multiple | (blank) | 2023-11-24 | 2023 | 1 | 1
| 1533A | xD-DWDM-BRKRing_S313P_2_2_DUYONG_0004582304160F_00045823087420 | 1800 Rack and subrack | Multiple | (blank) | 2023-10-10 | 2023 | 1 | 1
| 1553A | xD-DWDM-BRKRing_S313P_2_2_UMBAI_0004582304160F_00045823087420 | 1800 Rack and subrack | Multiple | 2024-06-30 | (blank) | 2023 |  | 1
| 1554A | xD-DWDM-BRKRing_S313P_2_2_RUMBIA_0004582304160F_00045823087420 | 1800 Rack and subrack | Multiple | (blank) | 2023-10-10 | 2023 | 1 | 1
S313P_2_2 Total | [7 empty] | 3 | 4 |  |  | 0 | P3
S406 | 6442A | xD_DWDM-BRKRing_S406_6442A Senai Airport_0004582306610B_00045823162821 | 1800 Rack and subrack | Single | (blank) | 2023-12-06 | 2023 | 1 | 1
| 6576A | xD_DWDM-BRKRing_S406_6576A Jln Seelong_0004582306610B_00045823162821 | 1800 Rack and subrack | Multiple | (blank) | 2024-02-16 | 2023 | 1 | 1
S406 Total | [7 empty] | 2 | 2 |  |  | 0 | P0
S501 | 1591A | xD-DWDM-BRKRing_S501_1_1591A Parit Bakar_0004582304160F_0004582308742 | 1800 Rack and subrack | Single | (blank) | 2023-11-22 | 2023 | 1 | 1
| 2227B | xD-DWDM-BRKRing_S501_1_1591A Sri Jeram_0004582304160F_0004582308742 | 1800 Rack and subrack | Multiple | (blank) | 2023-10-12 | 2023 | 1 | 1
| 2388B | xD-DWDM-BRKRing_S501_1_2388B Desa Muar_0004582304160F_0004582308742 | 1800 Rack and subrack | Multiple | (blank) | 2023-10-12 | 2023 | 1 | 1
S501 Total | [7 empty] | 3 | 3 |  |  | 0 | P0
SAR01 | 1552A | xD_DWDM_BRKRing_SAR01_1552A-MAG(M8)-001 Tanjung Bidara_0004582309010R_00045824006624 | Board expansion | #N/A | 2024-03-21 | 2024-04-05 | 2024 Q1 | 1 | 1
| 1621A | xD_DWDM_BRKRing_SAR01_1621A-MCR Senawang_0004582309010R_00045824006624 | Board expansion | #N/A | 2024-03-22 | 2024-04-05 | 2024 Q1 | 1 | 1
| 1640A | xD_DWDM_BRKRing_SAR01_1640A-MAG(M8)-001 Politeknik Port Dickson_0004582309010R_00045824006624 | Board expansion | #N/A | 2024-03-22 | 2024-04-05 | 2024 Q1 | 1 | 1
| 2021B | xD_DWDM_BRKRing_SAR01_2021B-Subang Hi-Tech_0004582309010R_00045824006624 | Board expansion | Multiple | 2024-03-21 | 2023-12-21 | 2024 Q1 | 1 | 1
SAR01 Total | [7 empty] | 4 | 4 |  |  | 0 | P0
SAR04 | 1659A | xD_DWDM-BRKRing_SAR04_1659A Bahau Tower_0004582400710C_00045824009526 | Board expansion | #N/A | 2024-04-18 | 2024-04-18 | 2024 Q1 | 1 | 1
| 6442A | xD_DWDM-BRKRing_SAR04_6442A Senai Airport_0004582400710C_00045824009526 | Board expansion | Single | 2024-04-23 | 2024-04-23 | 2024 Q1 | 1 | 1
| 6911C | xD_DWDM-BRKRing_SAR04_6911C KTM Labis_0004582400710C_00045824009526 | Board expansion | #N/A | 2024-04-24 | 2024-04-24 | 2024 Q1 | 1 | 1
SAR04 Total | [7 empty] | 3 | 3 |  |  | 0 | P0
ST21P | 6000A | xD_DWDM_BRKRing_ST21P_6000A-MCR002 JBR_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | Single | 2024-06-07 | (blank) | 2024 Q1 |  | 1
| 6312A | xD_DWDM_BRKRing_ST21P_6312A-MAC-001 Jln Cenderai_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-06-06 | (blank) | 2024 Q1 |  | 1
| 6369A | xD_DWDM_BRKRing_ST21P_6369A-MAG001 Sri Saujana_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | Multiple | 2024-04-26 | 2024-04-26 | 2024 Q1 |  | 1
| 6400A | xD_DWDM_BRKRing_ST21P_6400A-MAC-001 Jln Perak_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-06-30 | (blank) | 2024 Q1 |  | 1
ST21P Total | [8 empty] | 4 |  |  | 0 | P1
ST21P_1 | 6063A | xD_DWDM_BRKRing_ST21P_1_6063A-MAC-001 KTM Plentong_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-04-25 | 2024-04-25 | 2024 Q1 | 1 | 1
| 6382A | xD_DWDM_BRKRing_ST21P_1_6382A-MAC-001 KTM Pasir Gudang_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-06-04 | (blank) | 2024 Q1 |  | 1
ST21P_1 Total | [7 empty] | 1 | 2 |  |  | 0 | P1
ST27P | 1607A | xD_DWDM_BRKRing_ST27P_1607A-MAG001 KM Plaza_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-27 | 2024-05-27 | 2024 Q1 |  | 1
| 1608A | xD_DWDM_BRKRing_ST27P_1608A KTM Seremban_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | #N/A | 2024-05-28 | 2024-05-28 | 2024 Q1 |  | 1
| 1610A | xD_DWDM_BRKRing_ST27P_1610A Gun Hill_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Single | 2024-05-29 | 2024-05-29 | 2024 Q1 |  | 1
ST27P Total | [8 empty] | 3 |  |  | 0 | P3
Grand Total | [7 empty] | 89 | 179
Area139
C0713P
CAR01
CAR11
EAR02
MR20/C26
N103
N106(ii)
N113(ii)
N201
NAR03
New Ring5/S406
S201
S406
S501
SAR01
SAR04

## Apr May BR Plan (2)
Break Ring Status | (blank) | 267 | 267 | 268 | 268 | 268 | 268 | 268 | 268 | 101 | 35600% | [6 empty] | 3
CME Request | (All)
Actual Utilisation | (All)
Utilisation2 | (All) | [17 empty] | QCTE Plan End Date
Site ID | (All) | [10 empty] | Ring_Ready_Chk |  | Ring | ID | Count of Site ID | Chk |  | #N/A
#N/A
[10 empty] | Values | [8 empty] | #N/A
Priority Rollout | Ring ID | DUID2 | SOW | Status | Plan MOS | Material On Site | Batch | Integration | Integrated Date (30days + install) | Count of Integration | Count of Site ID |  | P0 | Area139 |  | 2 | 0 | P0 | #N/A
P?? | N201 | xD_DWDM-BRKRing_N201_4000A MSC Prai_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-20 | 2023 | Y | 2023-11-19 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4685B Kg Sungai Karangan_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-30 | 2023 | Y | 2024-02-01 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4950B Pulai_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-23 | 2023 | Y | 2024-02-06 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4956B Kuala Pegang_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-23 | 2023 | Y | 2024-02-05 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4968A Inokom Kulim_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-24 | 2023 | Y | 2024-01-30 | 1 | 1 |  | P2 | C0103 | (C0126) | 4 | 4 | P2 | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4985A Baling Town_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-23 | 2023 | Y | 2024-02-07 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4986A Binjul_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-24 | 2023 | Y | 2024-02-02 | 1 | 1 |  | P1 | C0105P |  | 1 | 1 | P1 | 2023-11-30
|  | xD_DWDM-BRKRing_N201_4988A Kupang_000458237400E_00045823174223 | 1800 Rack and subrack | Completed | (blank) | 2023-11-23 | 2023 | Y | 2024-02-05 | 1 | 1 | [7 empty] | 2023-11-30
| N201 Total | [8 empty] | 8 | 8 | -8 | [6 empty] | #N/A
P?? Total | [9 empty] | 8 | 8 | [7 empty] | #N/A
P0 | Area139 | xD_DWDM-BRKRing_Area139_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | Completed | 2024-03-22 | 2024-03-22 | 2023 | N/A | 2024-04-05 | 1 | 1 | [7 empty] | 2024-06-30
|  | xD_DWDM-BRKRing_Area139_4946A Bukit Selambau_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | Drop | 2023-11-22 | 2023-11-22 | 2023 | N/A | 2024-01-31 | 1 | 1 |  | P2 | C0204 |  | 4 | 4 | P2 | 2023-11-30
| Area139 Total | [8 empty] | 2 | 2 | -2 | [6 empty] | #N/A
| C0713P | xD_DWDM-BRKRing_C0713P_1071A_Chi Liung Plaza_0004582304330V_00045823098821 | 9800 Rack with subrack | (blank) | 2023-11-20 | 2023-11-20 | 2023 | Y | 2024-01-10 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_C0713P_1096A_KlangPerdana_0004582304330V_00045823098821 | 9800 Board Expansion | (blank) | 2023-11-23 | 2023-11-23 | 2023 | Y | 2023-11-23 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_C0713P_2021B_SBHT_0004582304330V_00045823098821 | 9800 Board Expansion | PRPO | 2023-12-12 | 2023-12-12 | 2023 | Y | 2023-12-12 | 1 | 1 |  | P3 | C0210P |  | 3 | 3 | P3 | 2023-12-22
| C0713P Total | [8 empty] | 3 | 3 | -3 | [6 empty] | #N/A
| EAR02 | xD-DWDM-BRKRing_EAR02_2_4000A Prai_0004582304160E_00045823087420 | 9800 Rack with subrack | Completed | #N/A | #N/A | 2023 | Y | 2024-01-17 | 1 | 1 | [7 empty] | 2023-11-17
|  | xD-DWDM-BRKRing_EAR02_2_8000A Kuantan_0004582304160E_00045823087420 | 9800 Rack with subrack | (blank) | (blank) | 2023-11-14 | 2023 | Y | 2024-01-17 | 1 | 1 | [7 empty] | 2023-11-17
|  | xD-DWDM-BRKRing_EAR02_2_8429B BktPayung_0004582304160E_00045823087420 | 9800 Rack with subrack | Drop | #N/A | #N/A | 2023 | Y | 2024-01-17 | 1 | 1 | [7 empty] | 2023-11-17
| EAR02 Total | [8 empty] | 3 | 3 | -3 | P1 | C0407P |  | 4 | 4 | P1 | #N/A
| NAR03 | xD_DWDM-BRKRing_NAR03_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | Completed | (blank) | 2023-11-20 | 2023 | Y | 2024-01-12 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_NAR03_4331A Bagan Serai_0004582306610A_0004582306610D_00045823162822 | 9800 SFP only | (blank) | (blank) | 2023-11-22 | 2023 | Y | 2024-01-12 | 1 | 1 | [7 empty] | 2023-11-30
| NAR03 Total | [8 empty] | 2 | 2 | -2 | P2 | C0417P |  | 2 | 2 | P2 | #N/A
| S201 | xD-DWDM-BRKRing_S201_1621A Senawang_0004582304070S_00045823086826 | 1800 Rack and subrack | (blank) | (blank) | 2023-12-12 | 2023 | Y | 2024-01-16 | 1 | 1 | [7 empty] | 2023-12-22
|  | xD-DWDM-BRKRing_S201_1760A Mambau1_0004582304070S_00045823086826 | 1800 Rack and subrack | Completed | (blank) | 2023-11-15 | 2023 | Y | 2023-11-20 | 1 | 1 | [7 empty] | 2023-11-24
|  | xD-DWDM-BRKRing_S201_1760A Mambau2_0004582304070S_00045823086826 | 1800 Rack and subrack | Completed | (blank) | 2023-11-15 | 2023 | Y | 2023-11-20 | 1 | 1 | [7 empty] | 2023-11-24
|  | xD-DWDM-BRKRing_S201_3433C Bkt Pelandok_0004582304070S_00045823086826 | 1800 Rack and subrack | (blank) | (blank) | 2023-11-22 | 2023 | Y | 2023-11-22 | 1 | 1 | [7 empty] | 2023-11-30
| S201 Total | [8 empty] | 4 | 4 | -4 | [6 empty] | #N/A
| S406 | xD_DWDM-BRKRing_S406_6442A Senai Airport_0004582306610B_00045823162821 | 1800 Rack and subrack | Completed | (blank) | 2023-12-06 | 2023 | Y | 2024-02-15 | 1 | 1 |  | P1 | C0702P |  | 5 | 1 | P1 | 2023-12-22
|  | xD_DWDM-BRKRing_S406_6576A Jln Seelong_0004582306610B_00045823162821 | 1800 Rack and subrack | Completed | (blank) | 2024-02-16 | 2023 | Y | 2024-02-20 | 1 | 1 | [7 empty] | 2024-02-29
| S406 Total | [8 empty] | 2 | 2 | -2 | [6 empty] | #N/A
| S501 | xD-DWDM-BRKRing_S501_1_1591A Parit Bakar_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | (blank) | 2023-11-22 | 2023 | Y | 2023-11-22 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD-DWDM-BRKRing_S501_1_1591A Sri Jeram_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | (blank) | 2023-10-12 | 2023 | Y | 2024-02-02 | 1 | 1 | [7 empty] | 2023-10-20
|  | xD-DWDM-BRKRing_S501_1_2388B Desa Muar_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | (blank) | 2023-10-12 | 2023 | Y | 2024-02-02 | 1 | 1 |  | P0 | C0713P |  | 4 | 0 | P0 | 2023-10-20
| S501 Total | [8 empty] | 3 | 3 | -3 | [6 empty] | #N/A
| SAR04 | xD_DWDM_BRKRing_SAR04_1621A MSC SNW_0004582401310P_00045824026721 | 9800M24 1subrack | (blank) | 2024-06-06 | (blank) | 2024 Q2 | (blank) | 2024-06-20 |  | 1 | [7 empty] | 2024-05-31
| SAR04 Total | [9 empty] | 1 | -1 | [6 empty] | #N/A
P0 Total | [9 empty] | 19 | 20 | [7 empty] | #N/A
P1 | C0105P | xD_DWDM_BRKRing_C0105P_1049B MCR KPG_0004582309050Y_00045824006623 | 1800VPRO 1 rack 4subrack | PRPO | 2024-05-15 | 2024-05-15 | 2024 Q1 | (blank) | 2024-05-22 |  | 1 | [7 empty] | 2024-05-31
| C0105P Total | [9 empty] | 1 | -1 | [6 empty] | #N/A
| C0407P | xD_DWDM_BRKRing_C0407P_1266A Sucasa_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | PRPO | 2024-05-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1 |  | P0 | CAR01 |  | 6 | 0 | P0 | 2024-05-31
|  | xD_DWDM_BRKRing_C0407P_1304A MMA_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | (blank) | 2024-03-26 | 2024-03-26 | 2024 Q1 | (blank) | 2024-05-09 |  | 1 | [7 empty] | 2024-06-30
|  | xD_DWDM_BRKRing_C0407P_1737A Bernama_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | PRPO | 2024-04-24 | 2024-04-24 | 2024 Q1 | (blank) | 2024-05-09 |  | 1 | [7 empty] | 2024-04-30
|  | xD_DWDM_BRKRing_C0407P_1745A Baitumal_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | (blank) | 2024-07-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1 | [7 empty] | 2024-05-31
| C0407P Total | [9 empty] | 4 | -4 | [6 empty] | #N/A
| C0702P | xD_DWDM-BRKRing_C0702P_1096A MAG KlangPerdana_0004582304330Y_00045823098821 | 1800 Rack and subrack | (blank) | 2023-11-22 | 2023-11-23 | 2023 | (blank) | 2024-05-09 |  | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_C0702P_1153A MAC PermatangKSelangor_0004582304330Y_00045823098821 | 1800 Rack and subrack | Completed | 2023-11-24 | 2023-11-24 | 2023 | Y | 2023-11-24 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_C0702P_1154A MAGSekinchan_0004582304330Y_00045823098821 | 1800 Rack and subrack | Drop | 2023-11-23 | 2023-11-23 | 2023 | Y | 2023-11-23 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_C0702P_1156A MAC BtgBerjuntai_0004582304330Y_00045823098821 | 1800 Rack and subrack | Drop | 2023-11-24 | 2023-11-24 | 2023 | Y | 2023-11-24 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD_DWDM-BRKRing_C0702P_1169A MAC TgKrngTrunkRd_0004582304330Y_00045823098821 | 1800 Rack and subrack | Completed | 2023-11-24 | 2023-11-24 | 2023 | Y | 2024-01-23 | 1 | 1 | [7 empty] | 2023-11-30
| C0702P Total | [8 empty] | 4 | 5 | -5 | [6 empty] | #N/A
| CT0241P | xD_DWDM_BRKRing_CT0241P_1197A JBA Effingham_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-15 | 2024-05-15 | 2024 Q1 | (blank) | 2024-05-22 |  | 1 | [7 empty] | 2024-05-31
|  | xD_DWDM_BRKRing_CT0241P_1211A KDU_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-05-17 | 2024-05-17 | 2024 Q1 | (blank) | 2024-05-22 |  | 1 | [7 empty] | 2024-05-31
|  | xD_DWDM_BRKRing_CT0241P_1918A Damansara Intan_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-23 | 2024-05-23 | 2024 Q1 | (blank) | 2024-05-22 |  | 1 | [7 empty] | 2024-05-31
| CT0241P Total | [9 empty] | 3 | -3 | [6 empty] | #N/A
| CT04 | xD-DWDM-BRKRing_1049B-002 MSC KEPONG_00045823053925 | 1800 Rack and subrack | PRPO | (blank) | 2023-09-26 | 2023 | Y | 2024-01-29 | 1 | 1 |  | P3 | CAR04 |  | 14 | 14 | P3 | 2023-10-13
|  | xD-DWDM-BRKRing_1412A BKT TADUN_00045823053925 | 1800 Rack and subrack | (blank) | (blank) | 2023-10-10 | 2023 | Y | 2024-01-15 | 1 | 1 | [7 empty] | 2023-10-13
|  | xD-DWDM-BRKRing_1413A KTM RAWANG_00045823053925 | 1800 Rack and subrack | Completed | 2024-06-11 | (blank) | 2023 | (blank) | 2024-07-18 |  | 1 | [7 empty] | 2024-04-30
| CT04 Total | [8 empty] | 2 | 3 | -3 | [6 empty] | #N/A
| MAC RING 9/C13 | xD_DWDM_BRKRing_MR9/C13_1295A Com Bkt Maluri_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-05-28 | 2024-05-28 | 2024 Q1 | (blank) | 2024-06-11 |  | 1 |  | P0 | CAR11 |  | 3 | 0 | P0 | 2024-07-31
| MAC RING 9/C13 Total | [9 empty] | 1 | -1 | [6 empty] | #N/A
| MR20/C26 | xD-DWDM-BRKRing_MR20/C26_1081A BktLipat_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | (blank) | 2023-11-24 | 2023 | Y | 2024-01-23 | 1 | 1 | [7 empty] | 2023-11-30
|  | xD-DWDM-BRKRing_MR20/C26_1085A PekanMeru_0004582304160F_0004582308742 | 1800 Rack and subrack | (blank) | (blank) | 2023-10-06 | 2023 | Y | 2023-12-08 | 1 | 1
|  | xD-DWDM-BRKRing_MR20/C26_1093A KianHoeHuat_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | (blank) | 2023-11-24 | 2023 | Y | 2024-02-01 | 1 | 1 |  | P2 | C |  | 3 | 2 | P2
|  | xD-DWDM-BRKRing_MR20/C26_1104A SurauAlAmin_0004582304160F_0004582308742 | 1800 Rack and subrack | (blank) | (blank) | 2023-10-06 | 2023 | Y | 2024-01-18 | 1 | 1
|  | xD-DWDM-BRKRing_MR20/C26_1627B IndahHighway_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | (blank) | 2023-10-10 | 2023 | Y | 2024-01-18 | 1 | 1
| MR20/C26 Total | [8 empty] | 5 | 5 | -5
| N103 | xD_DWDM-BRKRing_N103_4660A KTM Alorstar_0004582306610C_00045823162822 | 1800 Rack and subrack | (blank) | (blank) | 2023-11-24 | 2023 | Y | 2024-01-18 | 1 | 1 |  | P1 | C |  | 3 | 3 | P1
|  | xD_DWDM-BRKRing_N103_4669A Alor Janggus_0004582306610C_00045823162822 | 1800 Rack and subrack | Completed | (blank) | 2023-11-23 | 2023 | Y | 2024-03-12 | 1 | 1
|  | xD_DWDM-BRKRing_N103_4863B Wisma PKNK_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | 2024-05-08 | 2024-05-08 | 2023 | Y | 2024-05-09 | 1 | 1
|  | xD_DWDM-BRKRing_N103_4998A Air Itam Kedah_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | (blank) | 2023-11-23 | 2023 | Y | 2024-01-17 | 1 | 1
| N103 Total | [8 empty] | 4 | 4 | -4 | P1 | C |  | 3 | 1 | P1
| N106(ii) | xD-DWDM-BRKRing_N106_4683A Bkt Tok Alang | 1800 Rack and subrack | PRPO | (blank) | N/A | 2023 | N/A | 0 | 1 | 1
| N106(ii) Total | [8 empty] | 1 | 1 | -1
| N106+ | xD_DWDM_BRKRing_N106+_4683A Bkt Tok Alang_0004582309010S_00045824006622 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-07 | 2024-05-07 | 2024 Q1 | Y | 2024-05-07 | 1 | 1
|  | xD_DWDM_BRKRing_N106+_4966A Kulim Hitech_0004582309010S_00045824006622 | 1800V PRO 1 rack 2 subrack | (blank) | 2024-05-07 | 2024-05-09 | 2024 Q1 | (blank) | 2024-05-16 |  | 1
| N106+ Total | [8 empty] | 1 | 2 | -2 | P2 | E104 |  | 4 | 4 | P2
| N113(ii) | xD_DWDM_BRKRing_N113_4663A Derga Jaya_0004582306610C_00045823162822 | 1800VPRO 1 rack 1 subrack | Completed | 2024-02-22 | 2024-02-23 | 2023 | Y | 2024-03-13 | 1 | 1
|  | xD_DWDM_BRKRing_N113_4973B Tajar_0004582306610C_00045823162822 | 1800VPRO 1 rack 1 subrack | Completed | 2024-02-22 | 2024-02-22 | 2023 | Y | 2024-04-24 | 1 | 1
| N113(ii) Total | [8 empty] | 2 | 2 | -2
| New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6000A MSC JB_0004582306610B_00045823162821 | 1800 Rack and subrack | Completed | (blank) | 2023-12-05 | 2023 | Y | 2024-02-15 | 1 | 1
|  | xD_DWDM-BRKRing_New Ring_5/S406_6026A Grand Cont Hotel_0004582306610B_00045823162821 | 1800 Rack and subrack | Completed | (blank) | 2023-12-07 | 2023 | Y | 2024-02-19 | 1 | 1 |  | P3 | E105 |  | 4 | 4 | P3
|  | xD_DWDM-BRKRing_New Ring_5/S406_6043A KK Kam_0004582306610B_00045823162821 | 1800 Rack and subrack | (blank) | (blank) | 2023-12-07 | 2023 | Y | 2024-01-11 | 1 | 1
|  | xD_DWDM-BRKRing_New Ring_5/S406_6283A Larkin Indst_0004582306610B_00045823162821 | 1800 Rack and subrack | Completed | (blank) | 2023-12-08 | 2023 | Y | 2024-05-07 | 1 | 1
|  | xD_DWDM-BRKRing_New Ring_5/S406_6502A Nusa Perintis_0004582306610B_00045823162821 | 1800 Rack and subrack | Completed | (blank) | 2023-12-08 | 2023 | Y | 2024-01-10 | 1 | 1
|  | xD_DWDM-BRKRing_New Ring_5/S406_6836A Menara Ansar_0004582306610B_0004582316282 | 1800 Rack and subrack | Completed | 2024-04-24 | 2024-04-24 | 2023 | Y | 2024-05-09 | 1 | 1 |  | P3 | E109 |  | 3 | 3 | P3
| New Ring5/S406 Total | [8 empty] | 6 | 6 | -6
| NT09P | xD_DWDM_BRKRing_NT09P_4640A Sp Plaza_0004582309010S_00045824006622 | 1800VPRO 1 rack 1 subrack | Completed | 2024-07-30 | (blank) | 2023_2024 | (blank) | 2024-07-11 |  | 1
| NT09P Total | [9 empty] | 1 | -1
| PFSRING101/C0607P | xD_DWDM_BRKRing_PFSRING101/C0607_1063B_Berjya Times Square Rooftop_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | 2024-05-24 | 2024-05-24 | 2023 | (blank) | 2024-06-07 |  | 1
|  | xD_DWDM-BRKRing_PFSRING101/C0607P_1246A Kompleks Nagaria_0004582306610C_00045823162822 | 1800 Rack and subrack | Completed | (blank) | 2023-12-08 | 2023 | Y | 2024-01-09 | 1 | 1
|  | xD_DWDM-BRKRing_PFSRING101/C0607P_1475A Sri Kembangan_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | (blank) | 2023-12-04 | 2023 | Y | 2024-01-24 | 1 | 1 |  | P0 | E111 |  | 5 | 5 | P0
|  | xD_DWDM-BRKRing_PFSRING101/C0607P_1851A KL Plaza2_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | (blank) | 2023-11-24 | 2023 | Y | 2024-02-20 | 1 | 1
|  | xD_DWDM-BRKRing_PFSRING101/C0607P_1899A Berjaya Times Square CAS_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | 2024-05-09 | 2024-05-09 | 2023 | (blank) | 2024-05-16 |  | 1
| PFSRING101/C0607P Total | [8 empty] | 3 | 5 | -5
P1 Total | [9 empty] | 28 | 43 |  | P1 | EAR01 |  | 3 | 1 | P1
P1_IP_BR-Q1 | C0210P | xD_DWDM_BRKRing_C0210P_1253A Plaza Pengkalan_0004582309010S_00045824006622 | 1800 1rack 2 subrack | PRPO | 2024-04-23 | 2024-04-23 | 2024 Q1 | (blank) | 2024-05-09 |  | 1
|  | xD_DWDM_BRKRing_C0210P_1859A Midvalleycas_0004582309010S_00045824006622 | 1800 1rack 3 subrack | PRPO | 2024-04-24 | 2024-04-24 | 2024 Q1 | (blank) | 2024-05-09 |  | 1
|  | xD_DWDM_BRKRing_C0210P_2878A Mont Kiara_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-25 | 2024-04-25 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
| C0210P Total | [9 empty] | 3 | -3 | P0 | EAR02 |  | 3 | 0 | P0
| CT0120 | xD_DWDM-BRKRing_CT0120_2632A Ecopark_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | 2024-05-21 | 2024-03-27 | 2023 | Y | 2024-04-25 | 1 | 1
|  | xD-DWDM-BRKRing_CT0120_1099A HongFatt_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | 2023-12-06 | 2023-12-06 | 2023 | (blank) | 2024-05-09 |  | 1
|  | xD-DWDM-BRKRing_CT0120_1409A Damansara_0004582304160F_0004582308742 | 1800 Rack and subrack | Completed | 2023-12-07 | 2023-12-07 | 2023 | (blank) | 2024-06-21 |  | 1
| CT0120 Total | [8 empty] | 1 | 3 | -3
| E104 | xD_DWDM_BRKRing_E104_8263AMAG(M14)- 001 Pmas_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | PRPO | 2024-04-23 | 2024-04-23 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
|  | xD_DWDM_BRKRing_E104_8269B-MAC001 Chetok_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-04 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_E104_8288B-MAG001 Panau_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-22 | 2024-04-23 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
|  | xD_DWDM_BRKRing_E104_8294A-MAC001 Kangkong_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-05 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
| E104 Total | [9 empty] | 4 | -4
| E105 | xD_DWDM_BRKRing_E105_8139B-MAC001 CBC_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-25 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1 |  | P3 | EAR06 |  | 9 | 8 | P3
|  | xD_DWDM_BRKRing_E105_8211A-MAG(M8)- 001 WCY_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | (blank) | 2024-06-25 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_E105_8212A-MAC001 Wbharu_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-04-24 | 2024-04-25 | 2024 Q1 | (blank) | 2024-05-09 |  | 1 |  | P1 | MAC | RING | 1 | 1 | P1
|  | xD_DWDM_BRKRing_E105_8229A-MAC001 Tumpat_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-24 | 2024-04-24 | 2024 Q1 | (blank) | 2024-06-28 |  | 1
| E105 Total | [9 empty] | 4 | -4
| E109 | xD_DWDM_BRKRing_E109_8222A-MAC001 Peringat_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-24 | 2024-04-24 | 2024 Q1 | (blank) | 2024-06-28 |  | 1
|  | xD_DWDM_BRKRing_E109_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | PRPO | 2024-06-06 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_E109_8242B-MAC001 JKKrai_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-25 | 2024-04-25 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
| E109 Total | [9 empty] | 3 | -3 | P2 | MCR18/C24 |  | 5 | 3 | P2
| E111 | xD_DWDM_BRKRing_E111_8317A-MAC-001 Kampung Pak Wong_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_E111_8322B-MAC001 Padang Luas_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-25 | 2024-04-25 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
|  | xD_DWDM_BRKRing_E111_8367A-MAG001 B.Kechil_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-08 | 2024-05-09 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
|  | xD_DWDM_BRKRing_E111_8407A-MAC001 Jerteh_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_E111_8439A-MAC001 A.Lintang_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-08 | 2024-05-08 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
| E111 Total | [9 empty] | 5 | -5 | P1 | MR20/C26 |  | 5 | 0 | P1
| EAR01 | xD_DWDM_BRKRing_EAR01_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 9800 M24 1 rack 1 subrack | PRPO | 2024-05-09 | 2024-05-09 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
| EAR01 Total | [9 empty] | 1 | -1
| N407 | xD_DWDM-BRKRing_N407_4432A KTM Sg Siput_0004582401300R_00045824026922 | 1800 Vpro 1 subrack | (blank) | 2024-05-31 | (blank) | 2024 Q2 | (blank) | 2024-06-14 |  | 1
|  | xD_DWDM-BRKRing_N407_4493A KTM Ipoh_0004582401300R_00045824026922 | 1800 Vpro 1 subrack | (blank) | 2024-06-27 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM-BRKRing_N407_4498A Lap Tambun1 N 2_0004582401300R_00045824026922 | 1800 Vpro 1 subrack | (blank) | 2024-05-12 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1 |  | P1 | N103 |  | 4 | 0 | P1
|  | xD_DWDM-BRKRing_N407_4515A Tg Rambutan_0004582401300R_00045824026922 | 1800 Vpro 1 subrack | (blank) | 2024-06-28 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM-BRKRing_N407_4541A Bercham Industry_0004582401300R_00045824026922 | 1800 Vpro 1 subrack | (blank) | 2024-05-12 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
| N407 Total | [9 empty] | 5 | -5 | P1 | N106(ii) |  | 2 | 0 | P1
| S301 | xD_DWDM_BRKRing_S301_1554AMAG(M14)-001 Rumbia_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-29 | 2024-05-29 | 2024 Q1 | (blank) | 2024-06-12 |  | 1
|  | xD_DWDM_BRKRing_S301_1560A-MAC001 Bkt Tiga_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-27 | 2024-05-27 | 2024 Q1 | (blank) | 2024-06-10 |  | 1
|  | xD_DWDM_BRKRing_S301_1563A-MAC001 Bkt Iman_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-28 | 2024-05-28 | 2024 Q1 | (blank) | 2024-06-11 |  | 1 |  | P1 | N106+ |  | 2 | 1 | P1
|  | xD_DWDM_BRKRing_S301_1621A-MCR001 SNW_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
| S301 Total | [9 empty] | 4 | -4
| ST21P | xD_DWDM_BRKRing_ST21P_6000A-MCR002 JBR_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | Completed | 2024-06-07 | (blank) | 2024 Q1 | (blank) | 2024-07-11 |  | 1 |  | P1 | N113(ii) |  | 2 | 0 | P1
|  | xD_DWDM_BRKRing_ST21P_6312A-MAC-001 Jln Cenderai_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-06 | (blank) | 2024 Q1 | (blank) | 2024-07-11 |  | 1
|  | xD_DWDM_BRKRing_ST21P_6369A-MAG001 Sri Saujana_0004582309010R_00045824006624 | 1800VPRO 1 rack 2 subrack | PRPO | 2024-04-26 | 2024-04-26 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
|  | xD_DWDM_BRKRing_ST21P_6400A-MAC-001 Jln Perak_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q1 | (blank) | 2024-07-11 |  | 1
| ST21P Total | [9 empty] | 4 | -4
| ST21P_1 | xD_DWDM_BRKRing_ST21P_1_6063A-MAC-001 KTM Plentong_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-04-25 | 2024-04-25 | 2024 Q1 | Y | 2024-05-08 | 1 | 1
|  | xD_DWDM_BRKRing_ST21P_1_6382A-MAC-001 KTM Pasir Gudang_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-04 | (blank) | 2024 Q1 | (blank) | 2024-07-11 |  | 1
| ST21P_1 Total | [8 empty] | 1 | 2 | -2
| ST27P | xD_DWDM_BRKRing_ST27P_1607A-MAG001 KM Plaza_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-27 | 2024-05-27 | 2024 Q1 | (blank) | 2024-06-10 |  | 1
|  | xD_DWDM_BRKRing_ST27P_1608A KTM Seremban_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-05-28 | 2024-05-28 | 2024 Q1 | (blank) | 2024-06-11 |  | 1 |  | P?? | N201 |  | 8 | 0 | P??
|  | xD_DWDM_BRKRing_ST27P_1610A Gun Hill_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-29 | 2024-05-29 | 2024 Q1 | (blank) | 2024-06-12 |  | 1
| ST27P Total | [9 empty] | 3 | -3
P1_IP_BR-Q1 Total | [9 empty] | 2 | 41 |  | P0 | NAR03 |  | 2 | 0 | P0
P1_IP_BR-Q2 | C0211+ | xD_DWDM-BRKRing_C0211+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 1800VPRO 1 subrack | PRPO | 2024-05-30 | 2024-05-30 | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_C0211+_2888A Plaza Central_0004582401310N_00045824027823 | 9800M12 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
| C0211+ Total | [9 empty] | 2 | -2
| C0515+ | xD_DWDM-BRKRing_C0515+_1039A Cheras Jaya_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_C0515+_1902B Bdr Sg Long3_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_C0515+_2024A Bdr Makhota Cheras_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_C0515+_2424A PUAS Tmn Tun Perak_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1 |  | P0 | New | Ring5/S406 | 6 | 0 | P0
|  | xD_DWDM-BRKRing_C0515+_2448A Asmah Tower_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
| C0515+ Total | [9 empty] | 5 | -5 | P0 | N |  | 1 | 1 | P0
| N104+ | xD_DWDM-BRKRing_N104+_4665A Jitra_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | PRPO | 2024-05-30 | 2024-05-30 | 2024 Q2_2 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM-BRKRing_N104+_4672A Changloon_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | PRPO | 2024-05-29 | 2024-05-29 | 2024 Q2_2 | (blank) | 2024-06-12 |  | 1
|  | xD_DWDM-BRKRing_N104+_4991A UUM_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | PRPO | 2024-05-29 | 2024-05-29 | 2024 Q2_2 | (blank) | 2024-06-12 |  | 1
|  | xD_DWDM-BRKRing_N104+_4992A Pendang_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | Completed | 2024-05-30 | 2024-05-30 | 2024 Q2_2 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM-BRKRing_N104+_4995A UUMHW_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-25 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
| N104+ Total | [9 empty] | 5 | -5 | P1 | PFSRING101/C0607P |  | 5 | 2 | P1
| N408+ | xD_DWDM-BRKRing_N408+_4493A KTM Ipoh_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-27 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N408+_4506A Perak Taipu_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-27 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N408+_4515A Tg Rambutan_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-28 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N408+_4546A KWSP Ipoh_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-28 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
| N408+ Total | [9 empty] | 4 | -4
| N411+ | xD_DWDM-BRKRing_N411+_4373A KTM K Kangsar_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-25 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N411+_4377B Karai_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-25 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1 |  | P2 | Ring58/C1103 |  | 6 | 3 | P2
|  | xD_DWDM-BRKRing_N411+_4433A LAP Sg Siput_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
| N411+ Total | [9 empty] | 3 | -3
P1_IP_BR-Q2 Total | [10 empty] | 19
P1_IP_BR-Q3 | E301 | xD_DWDM_BRKRing_E301_8712A Kg Jawa Pekan_0004582401310P_00045824026721 | 9800M24 1 rack 2subrack | Completed | 2024-06-06 | (blank) | 2024 Q2 | (blank) | 2024-06-20 |  | 1
| E301 Total | [9 empty] | 1 | -1 | P0 | S201 |  | 4 | 0 | P0
| S305 | xD_DWDM_BRKRing_S305_2402B Pagoh Highway_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S305_6088A ABI_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S305_6093A Sri Medan_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S305_6104A Bkt Kelicap_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S305_6701A Parit Subang_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1 |  | P1 | S301 |  | 4 | 4 | P1
| S305 Total | [9 empty] | 5 | -5
| S504M | xD_DWDM_BRKRing_S504M_6126A KTM Kluang_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S504M_6134A Kluang Indst(Profina)_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S504M_6138A Kahang Maxis_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | Completed | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S504M_6151A Mersing_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S504M_6160A Bkt Tinggi Maxis_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1 |  | P3 | S309 |  | 5 | 5 | P3
|  | xD_DWDM_BRKRing_S504M_6166A Felda Nitar2_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S504M_6369A Sri Saujana_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_S504M_6616A Sri Permai_0004582401310P_00045824026721 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
| S504M Total | [9 empty] | 8 | -8
P1_IP_BR-Q3 Total | [10 empty] | 14 |  | P3 | S313P_2_2 |  | 4 | 1 | P3
P1_IP_R_EXP-Q1 | EAR06 | xD_DWDM_BRKRing_EAR06_8000A-MSC Kuantan_0004582309010R_00045824006624 | 9800 1subrack | (blank) | 2024-05-08 | 2024-05-08 | 2024 Q1 | (blank) | 2024-05-16 |  | 1
|  | xD_DWDM_BRKRing_EAR06_8105A-MAG 001 South Of Raub_0004582309010R_00045824006624 | 9800 1subrack | (blank) | 2024-06-06 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_EAR06_8112A-MAG 001 Bukit Istana_0004582309010R_00045824006624 | 9800 1subrack | (blank) | 2024-04-24 | 2024-04-25 | 2024 Q1 | (blank) | 2024-05-16 |  | 1 |  | P0 | S406 |  | 2 | 0 | P0
|  | xD_DWDM_BRKRing_EAR06_8145Z-MAG 001 T3E 0160 Kg Paya Luas_0004582309010R_00045824006624 | 9800 1subrack | (blank) | 2024-04-25 | 2024-04-24 | 2024 Q1 | (blank) | 2024-05-09 |  | 1
|  | xD_DWDM_BRKRing_EAR06_8173A-MAG 001 Bandar Pusat Jengka_0004582309010R_00045824006624 | 9800 1subrack | (blank) | 2024-04-25 | 2024-04-25 | 2024 Q1 | (blank) | 2024-05-16 |  | 1
|  | xD_DWDM_BRKRing_EAR06_8513A-MAG002 Senggora_0004582309010R_00045824006624 | 9800 1subrack | PRPO | 2024-05-08 | 2024-05-07 | 2024 Q1 | (blank) | 2024-06-21 |  | 1
|  | xD_DWDM_BRKRing_EAR06_8667A-MAG 001 Kg Jerangsang_0004582309010R_00045824006624 | 9800 1subrack | PRPO | 2024-05-09 | 2024-05-09 | 2024 Q1 | (blank) | 2024-06-21 |  | 1 |  | P0 | S501 |  | 3 | 0 | P0
|  | xD_DWDM_BRKRing_EAR06_8709A-MAG002 Bentong_0004582309010R_00045824006624 | 9800 1 subrack | Completed | 2024-06-06 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
| EAR06 Total | [9 empty] | 8 | -8
P1_IP_R_EXP-Q1 Total | [10 empty] | 8
P1_IP_R_EXP-Q2 | CAR02-ii+ | xD_DWDM-BRKRing_CAR02-ii+_1172A Glomac_0004582401310N_00045824027823 | 9800M12 1 subrack | Completed | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_CAR02-ii+_1918A Damansara Intan_0004582401310N_00045824027823 | 9800M12 1 subrack | PRPO | 2024-06-06 | (blank) | 2024 Q2_2 | (blank) | 2024-06-20 |  | 1 |  | P0 | SAR01 |  | 4 | 0 | P0
| CAR02-ii+ Total | [9 empty] | 2 | -2
| NAR01_iii+ | xD_DWDM-BRKRing_NAR01_iii+_4000A MSC Prai_0004582401310N_00045824027823 | 9800M12 1rack 1 subrack | Completed | 2024-05-12 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_NAR01_iii+_4493A KTM Ipoh_0004582401310N_00045824027823 | 9800M12 1 subrack | (blank) | 2024-06-27 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_NAR01_iii+_4606A Padang Besar_0004582401310N_00045824027823 | 9800M12 1 subrack | (blank) | 2024-06-28 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1 |  | P0 | SAR04 |  | 3 | 0 | P0
|  | xD_DWDM-BRKRing_NAR01_iii+_4992A Pendang_0004582401310N_00045824027823 | 9800M12 1 subrack | Completed | 2024-06-11 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_NAR01_iii+_4995A UUM HW_0004582401310N_00045824027823 | 9800M12 1rack 1 subrack | (blank) | 2024-06-11 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
| NAR01_iii+ Total | [9 empty] | 5 | -5
| NAR04_ii+ | xD_DWDM-BRKRing_NAR04_ii+_4432A KTM Sungai Siput_0004582401310N_00045824027823 | 9800M12 1rack 1 subrack | (blank) | 2024-06-11 | (blank) | 2024 Q2_2 | (blank) | 2024-06-25 |  | 1
|  | xD_DWDM-BRKRing_NAR04_ii+_4455A KTM Taiping_0004582401310N_00045824027823 | 9800M12 1 subrack | (blank) | 2024-06-11 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1 |  | P1 | S |  | 4 | 4 | P1
| NAR04_ii+ Total | [9 empty] | 2 | -2
P1_IP_R_EXP-Q2 Total | [10 empty] | 9
P1_IP_R_EXP-Q3 | EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_4000A Msc Prai_0004582401310P_00045824026721 | 9800M12 1subrack | Completed | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1 |  | P1 | S |  | 2 | 1 | P1
|  | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8224A Pasir Puteh_0004582401310P_00045824026721 | 9800M12 1rack 1subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8282B Pergau_0004582401310P_00045824026721 | 9800M12 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8285A Bukit Bunga_0004582401310P_00045824026721 | 9800M12 1rack 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8288B Panau_0004582401310P_00045824026721 | 9800M12 1rack 1subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1 |  | P3 | S |  | 3 | 3 | P3
|  | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8367A B.Kechil_0004582401310P_00045824026721 | 9800M12 1rack 1subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1 |  |  | Grand |  | 179
| EAR01_1 & EAR01_3 Total | [9 empty] | 6 | -6
P1_IP_R_EXP-Q3 Total | [10 empty] | 6
P1_Z_Aug | Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_1015A Awana Golf_0004582307100Y_00045823168326 | 1800 subrack | (blank) | 2024-05-09 | 2024-05-09 | 2023 | (blank) | 2024-05-16 |  | 1
|  | xD_DWDM-BRKRing_Ring58/C1103_1016A Genting Ria_0004582307100Y_00045823168326 | 1800 subrack | (blank) | 2024-06-05 | (blank) | 2023 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM-BRKRing_Ring58/C1103_1770B Genting Sempah_0004582307100Y_00045823168326 | 1800 Rack and subrack | Completed | (blank) | 2023-12-15 | 2023 | Y | 2024-01-17 | 1 | 1
|  | xD_DWDM-BRKRing_Ring58/C1103_2070B Gombak_0004582307100Y_00045823168326 | 1800 Rack and subrack | Completed | (blank) | 2023-10-25 | 2023 | Y | 2023-11-06 | 1 | 1
|  | xD_DWDM-BRKRing_Ring58/C1103_2833A First World Hotel_0004582307100Y_00045823168326 | 1800 subrack (outdoor rack) | Completed | 2024-06-06 | (blank) | 2023 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM-BRKRing_Ring58/C1103_8709A Bentong_0004582307100Y_00045823168326 | 1800 subrack | Completed | (blank) | 2023-10-25 | 2023 | Y | 2024-01-09 | 1 | 1
| Ring58/C1103 Total | [8 empty] | 3 | 6 | -6
P1_Z_Aug Total | [9 empty] | 3 | 6
P1_Z_Jul | 1063B/AREA 154/C0211+/C0515+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1475A SKB_0004582401310N_00045824027823 | 1800vPro 1rack 2 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1851A KL Plaza2_0004582401310N_00045824027823 | 1800VPRO 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
| 1063B/AREA 154/C0211+/C0515+ Total | [9 empty] | 2 | -2
| AREA 154/MAC Ring 15/ C21+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1855B TPM_0004582401310N_00045824027823 | 1800vPro 1rack 2 subrack | Completed | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_AREA 154/MAC Ring 15/ C21+_1458A Endah Parade_0004582401310N_00045824027823 | 1800vPro 1rack 2 subrack | Completed | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
| AREA 154/MAC Ring 15/ C21+ Total | [9 empty] | 2 | -2
P1_Z_Jul Total | [10 empty] | 4
P1_Z_June | CAR04 | xD_DWDM_BRKRing_CAR04_1006A JBA Gombak_0004582309050Y_00045824006623 | 98001 rack 1 subrack | Completed | 2024-04-25 | 2024-04-25 | 2024 Q1 | Y | 2024-05-09 | 1 | 1
|  | xD_DWDM_BRKRing_CAR04_1049B KPG_0004582309050Y_00045824006623 | 98001 rack 1 subrack | PRPO | 2024-05-15 | 2024-05-15 | 2024 Q1 | (blank) | 2024-05-22 |  | 1
|  | xD_DWDM_BRKRing_CAR04_1304A MMA_0004582309050Y_00045824006623 | 98001 rack 1 subrack | (blank) | 2024-03-26 | 2024-03-26 | 2024 Q1 | (blank) | 2024-05-09 |  | 1
|  | xD_DWDM_BRKRing_CAR04_1458A Endah Parade_0004582309050Y_00045824006623 | 98001 rack 1 subrack | Completed | 2024-04-23 | 2024-04-23 | 2024 Q1 | Y | 2024-05-07 | 1 | 1
|  | xD_DWDM_BRKRing_CAR04_1475A SKB_0004582309050Y_00045824006623 | 98001 rack 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_CAR04_1745A Baitumal_0004582309050Y_00045824006623 | 98001 rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
| CAR04 Total | [8 empty] | 2 | 6 | -6
P1_Z_June Total | [9 empty] | 2 | 6
P1_Z_Oct | N107+ | xD_DWDM-BRKRing_N107+_4601A Federal Kangsar_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-27 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N107+_4604A Kuala Perlis_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N107+_4606A Padang Besar_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-28 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N107+_4612A Jln Kaki Bkt_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-27 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N107+_4613A Taman Bestari Perlis_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N107+_4998A Air Itam Kedah_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | PRPO | 2024-05-28 | 2024-05-28 | 2024 Q2_2 | (blank) | 2024-06-11 |  | 1
| N107+ Total | [9 empty] | 6 | -6
P1_Z_Oct Total | [10 empty] | 6
P2 | C0103 | xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922 | 1800 Vpro 1 subrack | PRPO | 2024-05-24 | 2024-05-24 | 2024 Q2_2 | (blank) | 2024-06-07 |  | 1
| C0103 Total | [9 empty] | 1 | -1
| C0103 (C0126) | xD_DWDM-BRKRing_C0103_1207A Sg Buloh New Village_0004582400320X_00045824009023 | 1800 1 rack 1subrack | (blank) | 2024-05-17 | 2024-05-17 | 2024 Q1 | (blank) | 2024-05-22 |  | 1
|  | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | 1800 1 rack 1subrack | PRPO | 2024-05-16 | 2024-05-16 | 2024 Q1 | (blank) | 2024-05-22 |  | 1
|  | xD_DWDM-BRKRing_C0103_1364B Bestari(Maxis)_0004582400320X_00045824009023 | 1800 1 rack 1subrack | (blank) | 2024-05-28 | 2024-05-28 | 2024 Q1 | (blank) | 2024-06-11 |  | 1
| C0103 (C0126) Total | [9 empty] | 3 | -3
| C0204 | xD_DWDM_BRKRing_C0204_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | PRPO | 2024-07-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_C0204_1261A KWSP_0004582309050Y_00045824006623 | 9800M12 1 rack 1 subrack | (blank) | 2024-07-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_C0204_18451A KL Plaza2_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-07-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_C0204_1869A Daya Bumi_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | (blank) | 2024-07-30 | (blank) | 2024 Q1 | (blank) | 2024-06-13 |  | 1
| C0204 Total | [9 empty] | 4 | -4
| C0417P | xD_DWDM_BRKRing_C0417P_1006A JBA Gombak_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | Completed | 2024-05-20 | (blank) | 2024 Q1 | (blank) | 2024-06-03 |  | 1
|  | xD_DWDM_BRKRing_C0417P_1203A JBA Sri Damansara_0004582309050Y_00045824006623 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-05-21 | (blank) | 2024 Q1 | (blank) | 2024-06-04 |  | 1
| C0417P Total | [9 empty] | 2 | -2
| MCR18/C24 | xD_DWDM-BRKRing_MCR18/C24_1172A Glomac_0004582306610C_00045823162822 | 1800 Rack and subrack | (blank) | (blank) | N/A | 2023 | N/A | 2023-11-14 | 1 | 1
|  | xD_DWDM-BRKRing_MCR18/C24_1360B Hicom Glenmarie_0004582306610C_00045823162822 | 1800 Rack and subrack | Completed | (blank) | 2024-05-11 | 2023 | (blank) | 2024-06-15 |  | 1
|  | xD_DWDM-BRKRing_MCR18/C24_1362B Kelana Business_0004582306610C_00045823162822 | 1800 Rack and subrack | Completed | 2023-11-22 | 2023-11-22 | 2023 | (blank) | 2024-05-09 |  | 1
|  | xD_DWDM-BRKRing_MCR18/C24_1378B PJS 10_0004582304330Y_00045823098821 | 1800 Rack and subrack | Completed | 2023-11-22 | 2023-11-23 | 2023 | (blank) | 2024-05-09 |  | 1
|  | xD_DWDM-BRKRing_MCR18/C24_2021B SBHT_0004582306610C_00045823162822 | 1800 Rack and subrack | PRPO | (blank) | 2023-11-07 | 2023 | Y | 2023-12-12 | 1 | 1
| MCR18/C24 Total | [8 empty] | 2 | 5
P2 Total | [9 empty] | 2 | 15
P3 | S309 | xD_DWDM_BRKRing_S309_1553AMAG(M14)-001 Umbai_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_S309_1556A-MAC001 Merlimau_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-06-12 | (blank) | 2024 Q1 | (blank) | 2024-06-20 |  | 1
|  | xD_DWDM_BRKRing_S309_1599A-MAC001 Bkt Gambir Town_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | Completed | 2024-06-30 | (blank) | 2024 Q1 | (blank) | 2024-07-11 |  | 1
|  | xD_DWDM_BRKRing_S309_2402B-MAG001 Pagoh Highway_0004582309010R_00045824006624 | 1800VPRO 1 rack 1 subrack | PRPO | 2024-04-23 | 2024-04-23 | 2024 Q1 | (blank) | 2024-06-18 |  | 1
|  | xD-DWDM-BRKRing_S309_1553A Umbai_0004582304160F_0004582308742 | 1800 Rack and subrack | PRPO | 2024-06-30 | (blank) | 2023 | (blank) | 2024-07-18 |  | 1
| S309 Total | [9 empty] | 5
| S313P_2_2 | xD_DWDM-BRKRing_S313P_2_2_1525A Graha Maju_0004582304160F_00045823087420 | 1800 Rack and subrack | Completed | (blank) | 2023-11-24 | 2023 | Y | 2024-02-07 | 1 | 1
|  | xD-DWDM-BRKRing_S313P_2_2_DUYONG_0004582304160F_00045823087420 | 1800 Rack and subrack | Completed | (blank) | 2023-10-10 | 2023 | Y | 2024-02-07 | 1 | 1
|  | xD-DWDM-BRKRing_S313P_2_2_RUMBIA_0004582304160F_00045823087420 | 1800 Rack and subrack | PRPO | (blank) | 2023-10-10 | 2023 | Y | 2024-01-15 | 1 | 1
|  | xD-DWDM-BRKRing_S313P_2_2_UMBAI_0004582304160F_00045823087420 | 1800 Rack and subrack | PRPO | 2024-06-30 | (blank) | 2023 | (blank) | 2024-07-18 |  | 1
| S313P_2_2 Total | [8 empty] | 3 | 4
P3 Total | [9 empty] | 3 | 9
#N/A | CAR02-i+/CAR02-ii+ | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1253A Plaza Pengkalan_0004582401310N_00045824027823 | 9800M12 1 subrack | PRPO | 2024-06-04 | (blank) | 2024 Q2_2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1851A KL Plaza2_0004582401310N_00045824027823 | 9800M12 1 subrack | PRPO | 2024-06-05 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 9800M12 1 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
| CAR02-i+/CAR02-ii+ Total | [9 empty] | 3
| CT04 | xD_DWDM_BRKRing_CT04_1049B KPG_0004582401280Y_00045824026722 | 1800vPro 2 subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_CT04_1412 Bkt Tadun_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_CT04_1413A KTM Rawang_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | Completed | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
| CT04 Total | [9 empty] | 3
| MAC Ring 15/C21+ | xD_DWDM-BRKRing_MAC Ring 15/C21+_1745A Baitumal_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-08 |  | 1
|  | xD_DWDM-BRKRing_MAC Ring 15/C21+_1974A Jln Sg Besi_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-07-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_MAC Ring 15/C21+_2502A Bdar Tun Razak_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-07-30 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
| MAC Ring 15/C21+ Total | [9 empty] | 3
| MAC RING 6/C09+ | xD_DWDM_BRKRing_MAC RING 6/C09+_1192A Subang New Village_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_MAC RING 6/C09+_1230A P Indus Sg Buloh_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_MAC RING 6/C09+_2021B SBHT_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
| MAC RING 6/C09+ Total | [9 empty] | 3
| N401 | MAC | 1800VPRO 1 rack 1 subrack | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 2
|  | MAC001 Machang Bubuk 2 | 1800VPRO 1 rack 1 subrack | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | MAC001 Tmn Desa Impian | 1800VPRO 1 rack 1 subrack | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | MAG001 Selama | 1800VPRO 1 subrack | (blank) | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | MCR002 PRI | 1800VPRO 1 rack 1 subrack | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM_BRKRing_N401_4000A MSC Prai_0004582401280Y_00045824026722 | 1800vPro 1subrack | Completed | 2024-05-12 | (blank) | 2024 Q2 | (blank) | 2024-07-25 |  | 1
|  | xD_DWDM_BRKRing_N401_4118A Machang Bubuk2_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | Completed | 2024-05-30 | 2024-05-30 | 2024 Q2 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_N401_4684B Terap_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | Completed | 2024-05-28 | 2024-05-28 | 2024 Q2 | (blank) | 2024-06-11 |  | 1
|  | xD_DWDM_BRKRing_N401_4689A Tmn Desa Impian_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | Completed | 2024-05-29 | 2024-05-29 | 2024 Q2 | (blank) | 2024-06-12 |  | 1
|  | xD_DWDM_BRKRing_N401_4952B Selama_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | (blank) | 2024-05-28 | 2024-05-28 | 2024 Q2 | (blank) | 2024-06-11 |  | 1
|  | xD_DWDM_BRKRing_N401_4965A Politeknik Kulim_0004582401280Y_00045824026722 | 1800vPro 1rack 1subrack | Completed | 2024-05-29 | 2024-05-29 | 2024 Q2 | (blank) | 2024-06-12 |  | 1
| N401 Total | [9 empty] | 12
| N405+/N408+/N411+ | xD_DWDM-BRKRing_N405+/N408+/N411+_4374A LAP Talang_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-25 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N405+/N408+/N411+_4378A Jerlun Tower_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N405+/N408+/N411+_4379A Bkt Mercu_0004582401310N_00045824027823 | 1800vPro 1rack 1 subrack | (blank) | 2024-06-26 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
|  | xD_DWDM-BRKRing_N405+/N408+/N411+_4432A KTM Sg Siput_0004582401310N_00045824027823 | 1800vPro 1rack 2 subrack | (blank) | 2024-05-31 | (blank) | 2024 Q2_2 | (blank) | 2024-06-14 |  | 1
|  | xD_DWDM-BRKRing_N405+/N408+/N411+_4455A KTM Taiping_0004582401310N_00045824027823 | 1800vPro 1rack 2 subrack | (blank) | 2024-06-25 | (blank) | 2024 Q2_2 | (blank) | 2024-08-15 |  | 1
| N405+/N408+/N411+ Total | [9 empty] | 5
| NAR01_i | xD_DWDM_BRKRing_NAR01_i_4946A_Bukit Selambau_0004582401260T_45824026527 | 9800M12 1 subrack | Drop | 2024-05-12 | (blank) | 2024 Q2 | (blank) | 2024-05-26 |  | 1
|  | xD_DWDM_BRKRing_NAR01_i_4966A_Kulim Hitech_0004582401260T_45824026527 | 9800M12 1 subrack | (blank) | 2024-06-05 | (blank) | 2024 Q2 | (blank) | 2024-06-19 |  | 1
|  | xD_DWDM_BRKRing_NAR01_i_4992A_Pendang_0004582401260T_45824026527 | 9800M12 1 subrack | Completed | 2024-06-25 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
| NAR01_i Total | [9 empty] | 3
| Nar01i | xD_DWDM-BRKRing_Nar01i_4000A Msc Prai | 9800 Board Expansion | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM-BRKRing_Nar01i_4521A Msc Ipoh | 9800 Board Expansion | (blank) | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM-BRKRing_Nar01i_4946A Bkt Selambau | 9800 Board Expansion | Drop | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM-BRKRing_Nar01i_4966A Kulim Hitech | 9800 Board Expansion | (blank) | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM-BRKRing_Nar01i_4992A Pendang | 9800 Board Expansion | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
| Nar01i Total | [9 empty] | 5
| Nar01ii | xD_DWDM-BRKRing_Nar01ii_4606A Padang Besar | 9800 Board Expansion | (blank) | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM-BRKRing_Nar01ii_4638A Tmn Orkid | 9800 Board Expansion | Completed | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | 9800 Board Expansion | PRPO | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
|  |  |  | (blank) | 2024-07-30 | (blank) | Pending Po | (blank) | 0 |  | 1
| Nar01ii Total | [9 empty] | 4
| SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1553A Umbai_0004582401310P_00045824026721 | 9800M12 1subrack | PRPO | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1554A Rumbia_0004582401310P_00045824026721 | 9800M12 1subrack | PRPO | 2024-05-29 | 2024-05-29 | 2024 Q2 | (blank) | 2024-06-12 |  | 1
|  | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1621A SNW_0004582401310P_00045824026721 | 9800M12 1rack 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6000A MSC JBR_0004582401310P_00045824026721 | 9800M12 1subrack | Completed | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6104A Bkt Kelicap_0004582401310P_00045824026721 | 9800M12 1rack 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6405A Sri Bunian_0004582401310P_00045824026721 | 9800M12 1subrack | (blank) | 2024-06-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6502A Nusa Perintis_0004582401310P_00045824026721 | 9800M12 1subrack | Completed | 2024-07-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
| SAR03_i&SAR03iii Total | [9 empty] | 7
| C0147P | xD_DWDM_BRKRing_C0147P_1197A JBA Effingham_0004582401280Z_45824026526 | 1800vPro 1rack 1Subrack | PRPO | 2024-05-30 | 2024-05-30 | 2024 Q2 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_C0147P_1211A KDU_0004582401280Z_45824026526 | 1800vPro 1rack 1Subrack | (blank) | 2024-05-30 | (blank) | 2024 Q2 | (blank) | 2024-06-13 |  | 1
|  | xD_DWDM_BRKRing_C0147P_1336A Balai Islam TTDI_0004582401280Z_45824026526 | 1800vPro 1rack 1Subrack | (blank) | 2024-07-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
|  | xD_DWDM_BRKRing_C0147P_1918A Damansara Intan_0004582401280Z_45824026526 | 1800vPro 1rack 1Subrack | PRPO | 2024-05-29 | 2024-05-29 | 2024 Q2 | (blank) | 2024-06-12 |  | 1
|  | xD_DWDM_BRKRing_C0147P_2021B_SBHT_0004582401280Z_45824026526 | 1800VPRO 1 subrack | PRPO | 2024-05-28 | 2024-05-28 | 2024 Q2 | (blank) | 2024-06-11 |  | 1
|  | xD_DWDM_BRKRing_C0147P_2831A One Utama Ph2_0004582401280Z_45824026526 | 1800vPro 1rack 1Subrack | (blank) | 2024-07-30 | (blank) | 2024 Q2 | (blank) | 2024-07-18 |  | 1
| C0147P Total | [9 empty] | 6
#N/A Total | [10 empty] | 54
Grand Total | [9 empty] | 67 | 268

## Master Data
111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 111 | 53 | 35 | 18 | 111 | 111 | 58 | 58 | 58 | 58 | 111 | 58 | 58 | 62 | 111 | 111 | 111 | 110 | 111 | 45 | 20 | 9 | 53 | 36 | 1 | 13 | 49 | 0 | 111 | 0 | 111 | 111 | 111 |  | 7 | 0 | 2 | 2 | 2 | 14 | 3 | 36 | 36
Ring ID | Actual Utilisation | Forecaseted Utilisation | Batch | Site ID | DUID2 | Utilisation2 | Site Name | SOW | Subcon | Plan Survey Date | Survey Date | TSSR Date | CME Tracker Zul | CME Request | Request Yr | Request Month | DWDM | Project/ Ring (yang besar) | DWDM | Site ID | Status | CME Type | Proposed Cabinet type | TSSR Status 17/5/2024 | TSSR Status 28/5/2024 | Plan MOS | WorkWeek_Install | Material On Site (MOS) | Issue Remarks - Rodney | Issue Remarks (Stella) | Remarks (Ummu) | Plan Power Up | Power Up | Plan Integration | Plan Integration (Yaohan) | Integration | Integrated Date (30days + install) | WorkWeek_Integration | Priority Rollout (colour) | Ipran_Chk | Project_Category | chk | Follow-up (Stella) | Remarks (Stella) | Column2 | Migration | Break Ring Status | Break Ring Date | Remarks | NFS | Plan RFS | Filter | chk_Ipran_Urgent | Ring
N401 | 55.59% | #N/A | Pending Po | 4686B | MAC | #N/A |  | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4686B_Completed_DC BREAKER: 63 A X 4 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4686B | 4686B | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | #N/A |  | 0 |  | #N/A | N401 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N401 | 55.59% | #N/A | Pending Po | 4965A | MAC | #N/A |  | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4965A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4965A | 4965A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | #N/A |  | 0 |  | #N/A | N401 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N401 | 55.59% | #N/A | Pending Po | 4118A | MAC001 Machang Bubuk 2 | #N/A | Machang Bubuk 2 | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Single_2023_December_DWDM_(blank)_4118A_Completed_DCPDB = 1 | Single | 2023 | December | DWDM | (blank) | DWDM-4118A | 4118A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | #N/A |  | 0 |  | #N/A | N401 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N401 | 55.59% | #N/A | Pending Po | 4689A | MAC001 Tmn Desa Impian | #N/A | Tmn Desa Impian | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4689A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4689A | 4689A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | #N/A |  | 0 |  | #N/A | N401 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N401 | 55.59% | #N/A | Pending Po | 4952B | MAG001 Selama | #N/A | Selama | 1800VPRO 1 subrack | Fo&T |  |  | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | #N/A |  | 0 |  | #N/A | N401 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N401 | 55.59% | #N/A | Pending Po | 4000A | MCR002 PRI | #N/A | MSC Prai | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | N/A | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | #N/A |  | 0 |  | #N/A | N401 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 1362B | xD_DWDM-BRKRing_MCR18/C24_1362B Kelana Business_0004582306610C_00045823162822 | #N/A | 1362B Kelana Business | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1362B_Completed_DCPDB = 1 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1362B | 1362B | Completed | DCPDB = 1 | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-22 | Pending PFS Swap | Pending PFS Swap | 0527: Access issue IPRAN 0517: Pending PFS swap. F/u w/ Nazwan |  |  | 2024-02-12 | 2024-02-12 |  | 2024-05-09 |  | P2 | MCR18/C24 | IP BREAK RING | #N/A | 2024-02-15 09:54 |  |  |  |  | 00/01/1900 |  |  |  | #N/A | #N/A | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1253A | xD_DWDM_BRKRing_C0204_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 73.65% | 1253A Plaza Pengkalan | 9800M12 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | Indoor Rack | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-07-30 | Wk31 |  | Technical Request On HOLD |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-13 |  | P2 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1261A | xD_DWDM_BRKRing_C0204_1261A KWSP_0004582309050Y_00045824006623 | 73.65% | 1261A KWSP | 9800M12 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-07-30 | Wk31 |  | Technical Request On HOLD | [5 empty] | Pending ES PO |  | 2024-06-13 |  | P2 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1851A | xD_DWDM_BRKRing_C0204_18451A KL Plaza2_0004582309050Y_00045824006623 | 73.65% | 1851A-MAG(M14)-001 KL Plaza 2 | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-07-30 | Wk31 |  | Technical Request On HOLD |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-13 |  | P2 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1869A | xD_DWDM_BRKRing_C0204_1869A Daya Bumi_0004582309050Y_00045824006623 | 73.65% | 1869A Dayabumi | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.6 Pending CME approval | 1.7 TSSR Approved | 2024-07-30 | Wk31 |  | Technical Request On HOLD | [5 empty] | Pending ES PO |  | 2024-06-13 |  | P2 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | #N/A
C0702P | 91.22% | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_C0702P_1096A MAG KlangPerdana_0004582304330Y_00045823098821 | #N/A | 1096A MAG KlangPerdana | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-23 | Pending PFS Swap | postpone pending solution from customer |  |  |  | 2024-02-15 | TBC |  | 2024-05-09 |  | P1 | C0702P | IP BREAK RING | #N/A | [5 empty] | 0 | 0702 shortage |  |  | #N/A | #N/A | IP BREAK RING
MCR18/C24 | #N/A | #N/A | 2023 | 1378B | xD_DWDM-BRKRing_MCR18/C24_1378B PJS 10_0004582304330Y_00045823098821 | #N/A | 1378B PJS 10 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1378B_Completed_DC BREAKER: 63A X 2 | Single | 2023 | October | DWDM | (blank) | DWDM-1378B | 1378B | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-23 | CRQ approved, apply BM Access, Plan 7th May | 29/1: Key issue | 0521: CD give permision to drill the padlock 0517: Key issue. Need to f/u with Zul |  |  | 2024-02-12 | 2024-02-12 |  | 2024-05-09 |  | P2 | MCR18/C24 | IP BREAK RING | #N/A | 2024-02-15 09:54 |  | No key | [6 empty] | #N/A | #N/A | #N/A
CT0120 | 79.05% | #N/A | 2023 | 1099A | xD-DWDM-BRKRing_CT0120_1099A HongFatt_0004582304160F_0004582308742 | #N/A | 1099A HongFatt | 1800 Rack and subrack | Advance |  |  |  | Single_2023_October_DWDM_(blank)_1099A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =3 | Single | 2023 | October | DWDM | (blank) | DWDM-1099A | 1099A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A | 2023-12-06 | Wk49 | 2023-12-06 | CME RFS - 19/3/2024 (Haji) |  |  |  |  | 2024-04-23 | TBC |  | 2024-05-09 |  | P1_IP_BR-Q1 | CT0120 | IP BREAK RING | P1_IP_BR-Q1 | 2024-02-19 11:09 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
C0407P | 41.97% | 73.2% | 2024 Q1 | 1266A | xD_DWDM_BRKRing_C0407P_1266A Sucasa_0004582309050Y_00045824006623 | 73.2% | 1266A Sucasa | 9800M12 1 rack 1 subrack | BBand |  | 2023-12-01 | 2024-02-15 | Single_2024_May_DWDM_C0407P_1266A_PRPO_1.Add module = 1 2.Add battery bank = 1 | Single | 2024 | May | DWDM | C0407P | DWDM-1266A | 1266A | PRPO | 1.Add module = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 |  |  | 2024-06-06 | 0530: Access issue. Need to replan 0524: Waiting outbound MOS freezed. Pending confirmation availability of material. | 2024-06-04 |  |  | Pending ES PO |  | 2024-06-13 |  | P1 | #N/A | MAG Swap - BR | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | MAG Swap - BR
CT0120 | 79.05% | #N/A | 2023 | 1409A | xD-DWDM-BRKRing_CT0120_1409A Damansara_0004582304160F_0004582308742 | #N/A | 1409A Damansara | 1800 Rack and subrack | Advance |  |  |  | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A | 2023-12-07 | Wk49 | 2023-12-07 | CME RFS - 19/3/2024 (Haji) |  |  | 2024-06-07 |  | 2024-04-24 | TBC |  | 2024-06-21 |  | P1_IP_BR-Q1 | CT0120 | IP BREAK RING | P1_IP_BR-Q1 | 2024-02-19 11:09 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
C0407P | 41.97% | 73.2% | 2024 Q1 | 1304A | xD_DWDM_BRKRing_C0407P_1304A MMA_0004582309050Y_00045824006623 | 73.2% | 1304A MMA | 9800M12 1 rack 1 subrack | BBand |  | 2023-12-07 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-03-26 | Wk13 | 2024-03-26 | [6 empty] | Pending ES PO |  | 2024-05-09 |  | P1 | #N/A | MAG Swap - BR | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | MAG Swap - BR
C0407P | 41.97% | 73.2% | 2024 Q1 | 1745A | xD_DWDM_BRKRing_C0407P_1745A Baitumal_0004582309050Y_00045824006623 | 73.2% | 1745A Baitamal | 9800M12 1 rack 1 subrack | BBand |  | 2023-11-30 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | swap emerson rectifier c/w 6 bank battery | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-07-30 | Wk31 |  |  |  | 0527: 0517: Remove unused rack by CME MOS freezed. Pending confirmation availability of material. | 2024-06-21 |  |  | Pending ES PO |  | 2024-06-13 |  | P1 | #N/A | MAG Swap - BR | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | MAG Swap - BR
C0417P | 30.12% | 98.46% | 2024 Q1 | 1006A | xD_DWDM_BRKRing_C0417P_1006A JBA Gombak_0004582309050Y_00045824006623 | 98.46% | 1006A JBA Gombak | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | Single_2023_December_DWDM_(blank)_1006A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-1006A | 1006A | Completed | RECTIFIER + DCPDB = 1 | Indoor | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | 2024-05-20 | Wk21 |  |  | Spillover to June | 0523: RN created. Need to replan 0520: Key issue. Need to return and reschedule 0516: Waiting outbound |  |  |  | Pending ES PO |  | 2024-06-03 |  | P2 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-21 | #N/A | #N/A | #N/A
C0417P | 30.12% | 98.46% | 2024 Q1 | 1203A | xD_DWDM_BRKRing_C0417P_1203A JBA Sri Damansara_0004582309050Y_00045824006623 | 98.46% | 1203A JBA Sri Damansara | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_May_DWDM_C0417P_1203A_PRPO_1. Add Battery Bank = 4 2. Swap breaker DC BREAKER: 63A X 4 | Single | 2024 | May | DWDM | C0417P | DWDM-1203A | 1203A | PRPO | 1. Add Battery Bank = 4 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-21 | Wk21 |  |  |  | 0523: Need to rearrange with crane 0521: Access issue. Slippery and need crane to unload @ survey again to check access for material 0516: Waiting outbound | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-04 |  | P2 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-21 | #N/A | #N/A | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1006A | xD_DWDM_BRKRing_CAR04_1006A JBA Gombak_0004582309050Y_00045824006623 | 85.39% | 1006A JBA Gombak | 98001 rack 1 subrack | BBand |  | 2023-12-07 | 21/1/2/2023 | Single_2023_December_DWDM_(blank)_1006A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-1006A | 1006A | Completed | RECTIFIER + DCPDB = 1 | Indoor Rack | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 |  |  | 0517: Done int |  |  |  |  | Y | 2024-05-09 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1304A | xD_DWDM_BRKRing_CAR04_1304A MMA_0004582309050Y_00045824006623 | 85.39% | 1304A MMA | 98001 rack 1 subrack | BBand |  | 2024-12-07 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-03-26 | Wk13 | 2024-03-26 |  |  | 0528: TI done | [5 empty] | 2024-05-09 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
C0210P | #N/A | 149.5% | 2024 Q1 | 1253A | xD_DWDM_BRKRing_C0210P_1253A Plaza Pengkalan_0004582309010S_00045824006622 | 149.5% | 1253A Plaza Pengkalan | 1800 1rack 2 subrack | Advance |  | 2024-01-27 |  | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | #N/A | #N/A | #N/A | 2024-04-23 | Wk17 | 2024-04-23 | [6 empty] | Pending ES PO |  | 2024-05-09 |  | P1_IP_BR-Q1 | C0210P | IP BREAK RING | P1_IP_BR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-31 | #N/A | C0210P | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1458A | xD_DWDM_BRKRing_CAR04_1458A Endah Parade_0004582309050Y_00045824006623 | 85.39% | 1458A Endah Parade | 98001 rack 1 subrack | BBand |  | 2024-12-07 | 2023-12-21 | Single_2024_January_DWDM_(blank)_1458A_Completed_BATTERY BANK = 1 | Single | 2024 | January | DWDM | (blank) | DWDM-1458A | 1458A | Completed | BATTERY BANK = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-23 | Wk17 | 2024-04-23 |  |  | 0517: Done int |  |  |  |  | Y | 2024-05-07 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1475A | xD_DWDM_BRKRing_CAR04_1475A SKB_0004582309050Y_00045824006623 | 85.39% | 1475A SKB | 98001 rack 1 subrack | BBand |  | 2024-02-13 | 2024-02-15 | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | 1.ODF Rack (Glass Door) | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-30 | Wk26 |  |  |  | 0517: Pending re-survey. Plan WK21 | [5 empty] | 2024-06-13 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1745A | xD_DWDM_BRKRing_CAR04_1745A Baitumal_0004582309050Y_00045824006623 | 85.39% | 1745A Baitumal | 98001 rack 1 subrack | BBand |  | 2023-11-30 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-30 | Wk26 |  |  |  | 0517: Remove unused rack by CME MOS freezed. Pending confirmation availability of material. | 2024-06-21 |  |  |  |  | 2024-06-13 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
E104 | 27.23% | 51.85% | 2024 Q1 | 8263A | xD_DWDM_BRKRing_E104_8263AMAG(M14)- 001 Pmas_0004582309010R_00045824006624 | 51.85% | 8263AMAG(M14)- 001 Pmas | 1800VPRO 1 rack 2 subrack | Advance |  | 2024-01-30 |  | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | Single | 2024 | April | DWDM | E104;EAR01 N EAR03 | DWDM-8263A | 8263A | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-23 | Wk17 | 2024-04-23 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | E104 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-03-26 | #N/A | E104 | IP BREAK RING
E104 | 27.23% | 51.85% | 2024 Q1 | 8288B | xD_DWDM_BRKRing_E104_8288B-MAG001 Panau_0004582309010R_00045824006624 | 51.85% | 8288B-MAG001 Panau | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_May_DWDM_E104;EAR01 N EAR03_8288B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 7 | Single | 2024 | May | DWDM | E104;EAR01 N EAR03 | DWDM-8288B | 8288B | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-22 | Wk17 | 2024-04-23 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | E104 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-14 | #N/A | E104 | IP BREAK RING
S309 | 38.82% | 53.25% | 2024 Q1 | 2402B | xD_DWDM_BRKRing_S309_2402B-MAG001 Pagoh Highway_0004582309010R_00045824006624 | 53.25% | 2402B-MAG001 Pagoh Highway | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-01-23 |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | Subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-23 | Wk17 | 2024-04-23 |  |  |  | 2024-06-04 |  |  | Pending ES PO |  | 2024-06-18 |  | P3 | S309 | IP BREAK RING | #N/A | [7 empty] | Y | 2024-06-13 | #N/A | #N/A | IP BREAK RING
C0210P | #N/A | 149.5% | 2024 Q1 | 1859A | xD_DWDM_BRKRing_C0210P_1859A Midvalleycas_0004582309010S_00045824006622 | 149.5% | 1859A Midvalleycas | 1800 1rack 3 subrack | Advance |  | 2024-01-26 | 2024-02-07 | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4 | Single | 2024 | May | DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | DWDM-1859A | 1859A | PRPO | 1.Add modules = 2 | #N/A | #N/A | #N/A | 2024-04-24 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  | 2024-05-09 |  | P1_IP_BR-Q1 | C0210P | IP BREAK RING | P1_IP_BR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-31 | #N/A | C0210P | PFS Swap
E104 | 27.23% | 51.85% | 2024 Q1 | 8269B | xD_DWDM_BRKRing_E104_8269B-MAC001 Chetok_0004582309010R_00045824006624 | 51.85% | 8269B-MAC001 Chetok | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-04 | Wk23 |  | Outdoor |  | 0520: RAD changed to 4/6 0517: Need to change RAD // 0516: Waiting outbound. Not freeze in KHE due to no DUID |  |  |  | Pending ES PO |  | 2024-06-13 |  | P1_IP_BR-Q1 | E104 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-14 | #N/A | E104 | IP BREAK RING
C0407P | 41.97% | 73.2% | 2024 Q1 | 1737A | xD_DWDM_BRKRing_C0407P_1737A Bernama_0004582309050Y_00045824006623 | 73.2% | 1737A Bernama | 9800M12 1 rack 1 subrack | BBand |  | 2023-12-07 | 2023-12-21 | Multiple_2024_April_DWDM_C0407P_1737A_PRPO_1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | Multiple | 2024 | April | DWDM | C0407P | DWDM-1737A | 1737A | PRPO | 1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 |  |  |  | 2024-06-04 |  |  | Pending ES PO |  | 2024-05-09 |  | P1 | #N/A | MAG Swap - BR | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A | #N/A | MAG Swap - BR
E104 | 27.23% | 51.85% | 2024 Q1 | 8294A | xD_DWDM_BRKRing_E104_8294A-MAC001 Kangkong_0004582309010R_00045824006624 | 51.85% | 8294A-MAC001 Kangkong | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_May_DWDM_E104_8294A_PRPO_1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 4 | Single | 2024 | May | DWDM | E104 | DWDM-8294A | 8294A | PRPO | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) | Outdoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-05 | Wk23 |  | outdoor |  | 0517: Need to change RAD // 0516: Waiting outbound (not freeze in KHE. Only in KM2) 0515: Pending DN | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-13 |  | P1_IP_BR-Q1 | E104 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-14 | #N/A | E104 | IP BREAK RING
E105 | 91.65% | 112.8% | 2024 Q1 | 8139B | xD_DWDM_BRKRing_E105_8139B-MAC001 CBC_0004582309010R_00045824006624 | 112.8% | 8139B-MAC001 CBC | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | Single_2024_May_DWDM_E105_8139B_PRPO_1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.Add battery bank = 4 | Single | 2024 | May | DWDM | E105 | DWDM-8139B | 8139B | PRPO | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) | Outdoor | 1.6 Pending FF approval | 1.33 FF reject/Pending resubmission from partner | 2024-06-25 | Wk26 |  | CME -Plinth |  | 0521: F/u w/ CME | 2024-06-14 |  |  | Pending ES PO |  | 2024-06-20 |  | P1_IP_BR-Q1 | E105 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-24 | #N/A | E105 | IP BREAK RING
E105 | 91.65% | 112.8% | 2024 Q1 | 8211A | xD_DWDM_BRKRing_E105_8211A-MAG(M8)- 001 WCY_0004582309010R_00045824006624 | 112.8% | 8211A-MAG(M8)- 001 WCY | 1800VPRO 1 rack 2 subrack | FO&T |  | 2023-12-19 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-25 | Wk26 | [7 empty] | Pending ES PO |  | 2024-06-20 |  | P1_IP_BR-Q1 | E105 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-24 | #N/A | E105 | IP BREAK RING
E105 | 91.65% | 112.8% | 2024 Q1 | 8229A | xD_DWDM_BRKRing_E105_8229A-MAC001 Tumpat_0004582309010R_00045824006624 | 112.8% | 8229A-MAC001 Tumpat | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | Single_2024_April_DWDM_E105_8229A_PRPO_1. Add Battery Bank = 3 2 .Add Aircond = 1 (Action THOR) 3.Floor mounted DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | April | DWDM | E105 | DWDM-8229A | 8229A | PRPO | 1. Add Battery Bank = 3 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 |  |  |  | 2024-06-14 |  |  | Pending ES PO |  | 2024-06-28 |  | P1_IP_BR-Q1 | E105 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-24 | #N/A | E105 | IP BREAK RING
E109 | 60.29% | 71.65% | 2024 Q1 | 8222A | xD_DWDM_BRKRing_E109_8222A-MAC001 Peringat_0004582309010R_00045824006624 | 71.65% | 8222A-MAC001 Peringat | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_April_DWDM_E109_8222A_PRPO_1. Add Battery Bank = 4 2. Add Aircond = 1 (Action THOR) 3. DCPDB (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | April | DWDM | E109 | DWDM-8222A | 8222A | PRPO | 1. Add Battery Bank = 4 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 |  |  |  | 2024-06-14 |  |  | Pending ES PO |  | 2024-06-28 |  | P1_IP_BR-Q1 | E109 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-04-26 | #N/A | E109 | IP BREAK RING
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8145Z | xD_DWDM_BRKRing_EAR06_8145Z-MAG 001 T3E 0160 Kg Paya Luas_0004582309010R_00045824006624 | 91.72% | 8145Z-MAG 001 T3E 0160 Kg Paya Luas | 9800 1subrack | Fo&T |  | 2024-02-06 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-04-25 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  | 2024-05-09 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
E109 | 60.29% | 71.65% | 2024 Q1 | 8224A | xD_DWDM_BRKRing_E109_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 71.65% | 8224A-MAG-001 Pasir Puteh | 1800VPRO 1 rack 2 subrack | Advance |  |  |  | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Indoor | 1.6 Pending FF approval | 1.7 TSSR Approved | 2024-06-06 | Wk23 |  |  |  | 0520: RAD changed to 6/6 0517: Need to change RAD // 0516: Waiting outbound | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-20 |  | P1_IP_BR-Q1 | E109 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-03-26 | #N/A | E109 | IP BREAK RING
C0210P | #N/A | 149.5% | 2024 Q1 | 2878A | xD_DWDM_BRKRing_C0210P_2878A Mont Kiara_0004582309050Y_00045824006623 | 149.5% | 2878A Mont Kiara | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-26 | 2024-02-07 | Single_2024_April_DWDM_C0210P_2878A_PRPO_1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) 2. Add Modules = 4 3. Battery Bank = 6 | Single | 2024 | April | DWDM | C0210P | DWDM-2878A | 2878A | PRPO | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | C0210P | IP BREAK RING | P1_IP_BR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-31 | #N/A | C0210P | PFS Swap
E111 | 70.34% | 121.3% | 2024 Q1 | 8317A | xD_DWDM_BRKRing_E111_8317A-MAC-001 Kampung Pak Wong_0004582309010R_00045824006624 | 121.3% | 8317A-MAC-001 Kampung Pak Wong | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.6 Pending CME approval | 1.6 Pending CME approval | 2024-06-26 | Wk26 |  | CME- Dismantle cage | [5 empty] | Pending ES PO |  | 2024-06-20 |  | P1_IP_BR-Q1 | E111 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | May | #N/A | E111 | IP BREAK RING
E105 | 91.65% | 112.8% | 2024 Q1 | 8212A | xD_DWDM_BRKRing_E105_8212A-MAC001 Wbharu_0004582309010R_00045824006624 | 112.8% | 8212A-MAC001 Wbharu | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-04-24 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  | 2024-05-09 |  | P1_IP_BR-Q1 | E105 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-24 | #N/A | E105 | IP BREAK RING
E109 | 60.29% | 71.65% | 2024 Q1 | 8242B | xD_DWDM_BRKRing_E109_8242B-MAC001 JKKrai_0004582309010R_00045824006624 | 71.65% | 8242B-MAC001 JKKrai | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_April_DWDM_E109_8242B_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | April | DWDM | E109 | DWDM-8242B | 8242B | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | E109 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-04-26 | #N/A | E109 | IP BREAK RING
E111 | 70.34% | 121.3% | 2024 Q1 | 8407A | xD_DWDM_BRKRing_E111_8407A-MAC001 Jerteh_0004582309010R_00045824006624 | 121.3% | 8407A-MAC001 Jerteh | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.112 CD TSSR reject/Pending resubmission from partner | 1.112 CD TSSR reject/Pending resubmission from partner | 2024-06-26 | Wk26 | [7 empty] | Pending ES PO |  | 2024-06-20 |  | P1_IP_BR-Q1 | E111 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | May | #N/A | E111 | IP BREAK RING
E111 | 70.34% | 121.3% | 2024 Q1 | 8322B | xD_DWDM_BRKRing_E111_8322B-MAC001 Padang Luas_0004582309010R_00045824006624 | 121.3% | 8322B-MAC001 Padang Luas | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | Single_2024_May_DWDM_E111_8322B_PRPO_1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1 | Single | 2024 | May | DWDM | E111 | DWDM-8322B | 8322B | PRPO | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1 | Outdoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | E111 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | May | #N/A | E111 | IP BREAK RING
EAR01 | #N/A | #N/A | 2024 Q1 | 4000A | xD_DWDM_BRKRing_EAR01_4000A-MCR-001 PRI_0004582309010R_00045824006624 | #N/A | 4000A-MCR-001 PRI | Board expansion | Fo&T |  | N/A | N/A | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-18 | Wk12 | 2024-03-19 | [6 empty] | Pending ES PO | Y | 2024-03-19 | Wk12 | P1_IP_BR-Q1 | EAR01 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-04-19 | #N/A | EAR01 | IP BREAK RING
EAR01 | #N/A | #N/A | 2024 Q1 | 8000A | xD_DWDM_BRKRing_EAR01_8000A-MCR001 KTN_0004582309010R_00045824006624 | #N/A | 8000A-MCR001 KTN | Board expansion | Fo&T |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-08 | [6 empty] | Pending ES PO | N/A | 0 |  | P1_IP_BR-Q1 | EAR01 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-04-19 | #N/A | EAR01 | IP BREAK RING
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8112A | xD_DWDM_BRKRing_EAR06_8112A-MAG 001 Bukit Istana_0004582309010R_00045824006624 | 91.72% | 8112A-MAG 001 Bukit Istana | 9800 1subrack | Fo&T |  | 2024-02-06 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-04-24 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  | 2024-05-16 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
EAR06 | 53.85% | 91.72% | 2024 Q1 | 1475A | xD_DWDM_BRKRing_EAR06_1475A-MSC MSK_0004582309010R_00045824006624 | 91.72% | 1475A-MSC MSK | Board expansion | Fo&T |  | N/A | N/A | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-18 | Wk12 | 2024-03-19 | [6 empty] | Pending ES PO | Y | 2024-03-19 | Wk12 | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8173A | xD_DWDM_BRKRing_EAR06_8173A-MAG 001 Bandar Pusat Jengka_0004582309010R_00045824006624 | 91.72% | 8173A-MAG 001 Bandar Pusat Jengka | 9800 1subrack | Fo&T |  | 2024-02-06 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  | 2024-05-16 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8105A | xD_DWDM_BRKRing_EAR06_8105A-MAG 001 South Of Raub_0004582309010R_00045824006624 | 91.72% | 8105A-MAG 001 South Of Raub | 9800 1subrack | Fo&T |  | 2024-03-13 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.4 Pending FF and CME Planner approval | 1.6 Pending FF approval | 2024-06-06 | Wk23 |  |  |  | 0524: Freezed. Pending DN 0521: Need to freeze |  |  |  | Pending ES PO |  | 2024-06-20 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
ST21P | 73.72% | 110.6% | 2024 Q1 | 6369A | xD_DWDM_BRKRing_ST21P_6369A-MAG001 Sri Saujana_0004582309010R_00045824006624 | 110.6% | 6369A-MAG001 Sri Saujana | 1800VPRO 1 rack 2 subrack | BBand |  | 2023-12-30 |  | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | Multiple | 2024 | May | DWDM | ST21P;S504M | DWDM-6369A | 6369A | PRPO | 1. Add Battery Bank = 6 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-04-26 | Wk17 | 2024-04-26 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | ST21P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | ST21P | IP BREAK RING
CAR05 | 80.84% | #N/A | 2024 Q2 | 2021B | xD_DWDM_BRKRing_CAR05_2021B SBHT_0004582401290A_00045824026525 | #N/A | 2021B Subang Hitech | Board expansion | BBand | N/A | N/A |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
CAR05 | 80.84% | #N/A | 2024 Q2 | 1110A | xD_DWDM_BRKRing_CAR05_1110A Berjaya Indst Park_0004582401290A_00045824026525 | #N/A | 1110A Berjaya industrial Park | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
CAR05 | 80.84% | #N/A | 2024 Q2 | 1037A | xD_DWDM_BRKRing_CAR05_1037A_JBA Bangi_0004582401290A_00045824026525 | #N/A | 1037A JBA Bangi | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
CAR05 | 80.84% | #N/A | 2024 Q2 | 1039A | xD_DWDM_BRKRing_CAR05_1039A JBA Cheras Jaya_0004582401290A_00045824026525 | #N/A | 1039A JBA Cheras Jaya | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8709A | xD_DWDM_BRKRing_EAR06_8709A-MAG002 Bentong_0004582309010R_00045824006624 | 91.72% | 8709A-MAG002 Bentong | 9800 1 subrack | Fo&T |  | N/A | N/A | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | RECTIFIER + DCPDB = 1 | Subrack only | 1.4 Pending FF and CME Planner approval | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-06 | Wk23 |  |  |  | 0524: Freezed. Pending DN 0521: Need to freeze |  |  |  | Pending ES PO |  | 2024-06-20 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
MAC RING 9/C13 | 23.36% | 70.55% | 2024 Q1 | 1295A | xD_DWDM_BRKRing_MR9/C13_1295A Com Bkt Maluri_0004582309050Y_00045824006623 | 70.55% | 1295A-MAC-001 | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0524: Waiting outbound 0523: Freezed. Pending DN |  |  |  | Pending ES PO |  | 2024-06-11 |  | P1 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-14 | #N/A | #N/A | #N/A
N106+ | #N/A | #N/A | 2024 Q1 | 4683A | xD_DWDM_BRKRing_N106+_4683A Bkt Tok Alang_0004582309010S_00045824006622 | #N/A | 4683A Bkt Tok Alang | 1800VPRO 1 rack 1 subrack | FO&T | Week 12 March | 2024-03-20 |  | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3 | Single | 2024 | May | DWDM | N106+ | DWDM-4683A | 4683A | PRPO | 1. Add Battery Bank = 3 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-07 | Wk19 | 2024-05-07 |  |  |  | 2024-06-07 |  |  |  | Y | 2024-05-07 | Wk19 | P1 | #N/A | #N/A | #N/A | 0 | [6 empty] | Y | May | #N/A | #N/A | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1120A | xD_DWDM_BRKRing_CAR05_1120A Kota Kemuning_0004582401290A_00045824026525 | #N/A | 1120A Kota Kemuning | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
N113(ii) | #N/A | #N/A | 2023 | 4663A | xD_DWDM_BRKRing_N113_4663A Derga Jaya_0004582306610C_00045823162822 | #N/A | 4663A Derga Jaya | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4663A_Completed_DC BREAKER : 100A X 2 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4663A | 4663A | Completed | DC BREAKER : 100A X 2 | #N/A | #N/A | #N/A | 2024-02-22 | Wk8 | 2024-02-23 | CME | OUTDOOR |  |  |  | 2024-03-13 | #N/A | Y | 2024-03-13 | Wk11 | P1 | N113 | IP BREAK RING | #N/A | 2024-03-13 09:41 |  |  |  |  | #N/A |  |  |  | #N/A | #N/A | #N/A
N113(ii) | #N/A | #N/A | 2023 | 4973B | xD_DWDM_BRKRing_N113_4973B Tajar_0004582306610C_00045823162822 | #N/A | 4973B Tajar | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4973B_Completed_MGB = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4973B | 4973B | Completed | MGB = 1 | #N/A | #N/A | #N/A | 2024-02-22 | Wk8 | 2024-02-22 | CME |  |  |  |  | Plan | #N/A | Y | 2024-04-24 | Wk17 | P1 | N113 | IP BREAK RING | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N115 | 23.69% | #N/A | 2023_2024 | 4770A | xD_DWDM_BRKRing_N115_4770A Tok Lin_0004582309010S_00045824006622 | #N/A | 4770A Tok Lin | 1800VPRO 1 rack 1 subrack |  |  |  |  | Single_2023_October_DWDM_(blank)_4770A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4770A | 4770A | Completed | RECTTIFIER MODULE = 2 | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-11 |  | #N/A | #N/A | MAC Swap - BR | #N/A | 0 |  |  |  | Completed | 2023-12-21 | Mitigation | Y |  | #N/A | #N/A | MAC Swap - BR
NT09P | 0.801% | #N/A | 2023_2024 | 4640A | xD_DWDM_BRKRing_NT09P_4640A Sp Plaza_0004582309010S_00045824006622 | #N/A | 4640A Sp Plaza | 1800VPRO 1 rack 1 subrack |  |  |  |  | Single_2023_November_DWDM_(blank)_4640A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4640A | 4640A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 | [9 empty] | 2024-07-11 |  | P1 | #N/A | #N/A | #N/A | 0 | [6 empty] | Y |  | #N/A | #N/A | #N/A
S301 | 63.36% | #N/A | 2024 Q1 | 1554A | xD_DWDM_BRKRing_S301_1554AMAG(M14)-001 Rumbia_0004582309010R_00045824006624 | #N/A | 1554AMAG(M14)-001 Rumbia | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-01-24 |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | Subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-12 |  | P1_IP_BR-Q1 | S301 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-13 | #N/A | S301 | IP BREAK RING
S301 | 63.36% | #N/A | 2024 Q1 | 1560A | xD_DWDM_BRKRing_S301_1560A-MAC001 Bkt Tiga_0004582309010R_00045824006624 | #N/A | 1560A-MAC001 Bkt Tiga | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-02 | 2024-02-15 | Single_2024_May_DWDM_S301_1560A_PRPO_1.Add module = 1 2.Add battery bank = 2 3.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | May | DWDM | S301 | DWDM-1560A | 1560A | PRPO | 1.Add module = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-27 | Wk22 | 2024-05-27 |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-04 |  |  | Pending ES PO |  | 2024-06-10 |  | P1_IP_BR-Q1 | S301 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-13 | #N/A | S301 | IP BREAK RING
S301 | 63.36% | #N/A | 2024 Q1 | 1563A | xD_DWDM_BRKRing_S301_1563A-MAC001 Bkt Iman_0004582309010R_00045824006624 | #N/A | 1563A-MAC001 Bkt Iman | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-02 | 2024-02-15 | Single_2024_May_DWDM_S301_1563A_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | May | DWDM | S301 | DWDM-1563A | 1563A | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0523: Pending DN 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-04 |  |  | Pending ES PO |  | 2024-06-11 |  | P1_IP_BR-Q1 | S301 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-13 | #N/A | S301 | IP BREAK RING
S301 | 63.36% | #N/A | 2024 Q1 | 1621A | xD_DWDM_BRKRing_S301_1621A-MCR001 SNW_0004582309010R_00045824006624 | #N/A | 1621A-MCR001 SNW | 1800VPRO 1 rack 2 subrack | BBand |  | 2024-01-23 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.6 Pending CME approval | 1.6 Pending CME approval | 2024-06-30 | Wk26 |  |  |  | 0517: F/u w/ Zul for TSSR |  |  |  | Pending ES PO |  | 2024-06-20 |  | P1_IP_BR-Q1 | S301 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-06-13 | #N/A | S301 | IP BREAK RING
S309 | 38.82% | 53.25% | 2024 Q1 | 1553A | xD_DWDM_BRKRing_S309_1553AMAG(M14)-001 Umbai_0004582309010R_00045824006624 | 53.25% | 1553AMAG(M14)-001 Umbai | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-05 | 2024-02-08 | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-30 | Wk26 |  |  |  | 0523: CME Plinth | 2024-07-05 |  |  | Pending ES PO |  | 2024-06-20 |  | P3 | S309 | IP BREAK RING | #N/A | [7 empty] | Y | 2024-06-13 | #N/A | #N/A | IP BREAK RING
S309 | 38.82% | 53.25% | 2024 Q1 | 1556A | xD_DWDM_BRKRing_S309_1556A-MAC001 Merlimau_0004582309010R_00045824006624 | 53.25% | 1556A-MAC001 Merlimau | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-03-05 |  | Multiple_2024_May_DWDM_S309_1556A_PRPO_BATTERY BANK = 3 Remove battery = 1 | Multiple | 2024 | May | DWDM | S309 | DWDM-1556A | 1556A | PRPO | BATTERY BANK = 3 | Subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-12 | Wk24 |  |  |  | 0524: Waiting outbound. Need to reconfirm with faizal 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-20 |  | P3 | S309 | IP BREAK RING | #N/A | [7 empty] | Y | 2024-06-13 | #N/A | #N/A | IP BREAK RING
S309 | 38.82% | 53.25% | 2024 Q1 | 1599A | xD_DWDM_BRKRing_S309_1599A-MAC001 Bkt Gambir Town_0004582309010R_00045824006624 | 53.25% | 1599A-MAC001 Bkt Gambir Town | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-01 |  | Multiple_2023_September_DWDM_(blank)_1599A_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-1599A | 1599A | Completed | BATTERY BANK = 3 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [7 empty] | Pending ES PO |  | 2024-07-11 |  | P3 | S309 | IP BREAK RING | #N/A | [7 empty] | Y | 2024-06-13 | #N/A | #N/A | IP BREAK RING
CAR05 | 80.84% | #N/A | 2024 Q2 | 1122A | xD_DWDM_BRKRing_CAR05_1122A Jenjarum_0004582401290A_00045824026525 | #N/A | 1122A Jenjarum | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
SAR01 | 43.19% | 78.56% | 2024 Q1 | 1552A | xD_DWDM_BRKRing_SAR01_1552A-MAG(M8)-001 Tanjung Bidara_0004582309010R_00045824006624 | 78.56% | 1552A-MAG(M8)-001 Tanjung Bidara | Board expansion | Bband |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-21 | Wk12 | 2024-04-05 |  |  | 0517: PO for remob to install SFP and patching |  |  |  | Pending ES PO | Y | 2024-04-05 | Wk14 | P0 | SAR01 | PE-MCR | #N/A | [7 empty] | Y | 2024-04-26 | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2024 Q1 | 1621A | xD_DWDM_BRKRing_SAR01_1621A-MCR Senawang_0004582309010R_00045824006624 | 78.56% | 1621A-MCR Senawang | Board expansion | Bband |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-22 | Wk12 | 2024-04-05 | [6 empty] | Pending ES PO | Y | 2024-04-05 | Wk14 | P0 | SAR01 | PE-MCR | #N/A | [7 empty] | Y | 2024-04-26 | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2024 Q1 | 1640A | xD_DWDM_BRKRing_SAR01_1640A-MAG(M8)-001 Politeknik Port Dickson_0004582309010R_00045824006624 | 78.56% | 1640A-MAG(M8)-001 Politeknik Port Dickson | Board expansion | Bband |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-22 | Wk12 | 2024-04-05 |  |  | 0517: PO for remob to install SFP and patching |  |  |  | Pending ES PO | Y | 2024-04-05 | Wk14 | P0 | SAR01 | PE-MCR | #N/A | [7 empty] | Y | 2024-04-26 | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2024 Q1 | 2021B | xD_DWDM_BRKRing_SAR01_2021B-Subang Hi-Tech_0004582309010R_00045824006624 | 78.56% | 2021B-Subang Hi-Tech | Board expansion | Bband |  | N/A | N/A | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | 0 | 0. No Survey required | 0. No Survey required | 2024-03-21 | Wk12 | 2023-12-21 | [6 empty] | Pending ES PO | Y | 2023-12-21 | Wk51 | P0 | SAR01 | PE-MCR | #N/A | [7 empty] | Y | 2024-04-26 | #N/A | SAR01 | IP BREAK RING
Spare | #N/A | #N/A | 2023 | 2021B | xD_DWDM_BRKRing_Spare_2021B SBHT_0004582307400B_0004582307400C_00045823174223 | #N/A | 2021B SBHT | Board expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A | 2023-12-12 | Wk50 | 2023-12-12 |  |  |  |  | N/A | N/A | Completed | Y | 2023-12-12 | Wk50 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | N/A | 0 |  |  |  | #N/A | #N/A | #N/A
ST21P_1 | 51.9% | #N/A | 2024 Q1 | 6063A | xD_DWDM_BRKRing_ST21P_1_6063A-MAC-001 KTM Plentong_0004582309010R_00045824006624 | #N/A | 6063A-MAC-001 KTM Plentong | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-27 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending CME approval | 1.6 Pending CME approval | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO | Y | 2024-05-08 | Wk19 | P1_IP_BR-Q1 | ST21P_1 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | ST21P_1 | IP BREAK RING
ST21P_1 | 51.9% | #N/A | 2024 Q1 | 6382A | xD_DWDM_BRKRing_ST21P_1_6382A-MAC-001 KTM Pasir Gudang_0004582309010R_00045824006624 | #N/A | 6382A-MAC-001 KTM Pasir Gudang | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-28 | 2024-02-15 | Single_2024_May_DWDM_ST21P_6382A_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) 2.Add top Fixing cable ladder = 1 | Single | 2024 | May | DWDM | ST21P | DWDM-6382A | 6382A | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-04 | Wk23 |  |  |  | 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-14 |  |  | Pending ES PO |  | 2024-07-11 |  | P1_IP_BR-Q1 | ST21P_1 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | ST21P_1 | IP BREAK RING
ST21P | 73.72% | 110.6% | 2024 Q1 | 6000A | xD_DWDM_BRKRing_ST21P_6000A-MCR002 JBR_0004582309010R_00045824006624 | 110.6% | 6000A-MCR002 JBR | 1800VPRO 1 rack 2 subrack | BBand |  | 2024-01-23 |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | Subrack only | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | 2024-06-07 | Wk23 |  |  |  | 0524: Freezed. Pending DN |  |  |  | Pending ES PO |  | 2024-07-11 |  | P1_IP_BR-Q1 | ST21P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | ST21P | IP BREAK RING
ST21P | 73.72% | 110.6% | 2024 Q1 | 6312A | xD_DWDM_BRKRing_ST21P_6312A-MAC-001 Jln Cenderai_0004582309010R_00045824006624 | 110.6% | 6312A-MAC-001 Jln Cenderai | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-30 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-06 | Wk23 |  |  |  | 0524: Pending DN 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  | 2024-07-11 |  | P1_IP_BR-Q1 | ST21P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | ST21P | IP BREAK RING
CAR05 | 80.84% | #N/A | 2024 Q2 | 2048B | xD_DWDM_BRKRing_CAR05_2048B Sg Merab_0004582401290A_00045824026525 | #N/A | 2048B Sg Merab | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
ST21P | 73.72% | 110.6% | 2024 Q1 | 6400A | xD_DWDM_BRKRing_ST21P_6400A-MAC-001 Jln Perak_0004582309010R_00045824006624 | 110.6% | 6400A-MAC-001 Jln Perak | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-30 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.4 Pending FF and CME Planner approval | 1.4 Pending FF and CME Planner approval | 2024-06-30 | Wk26 |  |  |  | 0523: plinth issue (outdoor cabinet) |  |  |  | Pending ES PO |  | 2024-07-11 |  | P1_IP_BR-Q1 | ST21P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | ST21P | IP BREAK RING
ST27P | #N/A | 102.8% | 2024 Q1 | 1607A | xD_DWDM_BRKRing_ST27P_1607A-MAG001 KM Plaza_0004582309010R_00045824006624 | 102.8% | 1607A-MAG001 KM Plaza | 1800VPRO 1 rack 1 subrack | Bband |  | 2023-12-21 | 2024-02-15 | Single_2024_May_DWDM_ST27P_1607A_PRPO_1. Decomm Cabinet | Single | 2024 | May | DWDM | ST27P | DWDM-1607A | 1607A | PRPO | 1. Decomm Cabinet | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-27 | Wk22 | 2024-05-27 |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-10 |  | P1_IP_BR-Q1 | ST27P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-17 | #N/A | ST27P | IP BREAK RING
ST27P | #N/A | 102.8% | 2024 Q1 | 1608A | xD_DWDM_BRKRing_ST27P_1608A KTM Seremban_0004582309010R_00045824006624 | 102.8% | 1608A KTM Seremban | 1800VPRO 1 rack 1 subrack | Bband |  | 2023-12-21 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  | 2024-06-11 |  | P1_IP_BR-Q1 | ST27P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-17 | #N/A | ST27P | IP BREAK RING
ST27P | #N/A | 102.8% | 2024 Q1 | 1610A | xD_DWDM_BRKRing_ST27P_1610A Gun Hill_0004582309010R_00045824006624 | 102.8% | 1610A Gun Hill | 1800VPRO 1 rack 1 subrack | Bband |  | 2023-12-21 | 2024-02-15 | Single_2024_May_DWDM_ST27P_1610A_PRPO_1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 4.Relocate unuse battery to make space for Rectifier and DWDM rack | Single | 2024 | May | DWDM | ST27P | DWDM-1610A | 1610A | PRPO | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-12 |  | P1_IP_BR-Q1 | ST27P | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-05-17 | #N/A | ST27P | IP BREAK RING
Area139 | #N/A | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_Area139_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4000A MSC Prai | 9800 SFP only | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | #N/A | #N/A | #N/A | 2024-03-22 | Wk12 | 2024-03-22 | Plan Outbound | Invalid |  |  | N/A |  | Completed | N/A | 2024-04-05 | Wk14 | P0 | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | [6 empty] | #N/A | #N/A | #N/A
Area139 | #N/A | #N/A | 2023 | 4946A | xD_DWDM-BRKRing_Area139_4946A Bukit Selambau_0004582306610A_0004582306610D_00045823162822 | #N/A | 4946A Bukit Selambau | 9800 SFP only | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | No CME | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-22 |  |  |  |  | N/A |  | Completed | N/A | 2024-01-31 | Wk5 | P0 | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1049B | xD_DWDM-BRKRing_C0103_1049B MCR KPG_0004582400320X_00045824009023 | #N/A | 1049B-MCR001 KPG | Board expansion | Advance |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-24 | Wk21 | 2024-05-24 |  |  | 0523: Waiting outbound 0516: Pending DN. Freezed to lock material. Need to reconfirm from Amir | 2024-05-23 |  |  |  |  | 2024-06-07 |  | P2 | #N/A | #N/A | #N/A | 0 | [7 empty] | 2024-05-28 | #N/A | #N/A | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8513A | xD_DWDM_BRKRing_EAR06_8513A-MAG002 Senggora_0004582309010R_00045824006624 | 91.72% | 8513A-MAG002 Senggora | 9800 1subrack | Fo&T |  | 2024-02-02 |  | Single_2024_May_DWDM_EAR06_8513A_PRPO_1.Add battery bank = 2 | Single | 2024 | May | DWDM | EAR06 | DWDM-8513A | 8513A | PRPO | 1.Add battery bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-08 | Wk19 | 2024-05-07 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
E111 | 70.34% | 121.3% | 2024 Q1 | 8439A | xD_DWDM_BRKRing_E111_8439A-MAC001 A.Lintang_0004582309010R_00045824006624 | 121.3% | 8439A-MAC001 A.Lintang | 1800VPRO 1 rack 1 subrack | FO&T |  | 2024-02-07 |  | Single_2024_May_DWDM_E111_8439A_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | E111 | DWDM-8439A | 8439A | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.6 Pending FF approval | 1.7 TSSR Approved | 2024-05-08 | Wk19 | 2024-05-08 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | E111 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | May | #N/A | E111 | IP BREAK RING
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1364B | xD_DWDM-BRKRing_C0103_1364B Bestari(Maxis)_0004582400320X_00045824009023 | #N/A | 1364B-MAC-001 Bestari (Maxis) | 1800 1 rack 1subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0524: Pending DN. If 30/5 is failed, change date to 3 june / 7 june | [5 empty] | 2024-06-11 |  | P2 | #N/A | #N/A | #N/A | 0 | [7 empty] | 2024-05-28 | #N/A | #N/A | #N/A
C0607P | 55.22% | #N/A | 2023 | 1196A | xD_DWDM-BRKRing_C0607P_1196A JBA Puchong_0004582306610C_00045823162822 | #N/A | 1196A JBA Puchong | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1196A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | November | DWDM | (blank) | DWDM-1196A | 1196A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-22 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-23 | Wk47 | P1_Z_Oct | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-05-07 | 2024-05-07 |  |  | #N/A | #N/A | IP BREAK RING
C0607P | 55.22% | #N/A | 2023 | 1402A | xD_DWDM-BRKRing_C0607P_1402A Jalan Industry Puchong_0004582306610C_00045823162822 | #N/A | 1402A Jalan Industry Puchong | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1402A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | November | DWDM | (blank) | DWDM-1402A | 1402A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-22 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-23 | Wk47 | P1_Z_Oct | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-05-07 | 2024-05-07 |  |  | #N/A | #N/A | IP BREAK RING
C0607P | 55.22% | #N/A | 2023 | 1408A | xD_DWDM-BRKRing_C0607P_1408A Puchong Jaya_0004582306610C_00045823162822 | #N/A | 1408A Puchong Jaya | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1408A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1408A | 1408A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A | 2023-11-22 | Wk47 | 2023-11-22 | Pending EB CRQ |  |  |  |  | Replan | 2024-02-16 | Y | 2024-02-22 | Wk8 | P1_Z_Oct | #N/A | IP BREAK RING | #N/A | 2024-02-19 11:12 |  |  | Y | Completed | 2024-05-07 | 2024-05-07 |  |  | #N/A | #N/A | IP BREAK RING
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8000A | xD_DWDM_BRKRing_EAR06_8000A-MSC Kuantan_0004582309010R_00045824006624 | 91.72% | 8000A-MSC Kuantan | 9800 1subrack | Fo&T |  | 2024-02-02 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack | 1.4 Pending FF and CME Planner approval | 1.4 Pending FF and CME Planner approval | 2024-05-08 | Wk19 | 2024-05-08 | [6 empty] | Pending ES PO |  | 2024-05-16 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
C0702P | 91.22% | #N/A | 2023 | 1153A | xD_DWDM-BRKRing_C0702P_1153A MAC PermatangKSelangor_0004582304330Y_00045823098821 | #N/A | 1153A MAC PermatangKSelangor | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1153A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-1153A | 1153A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | 2023-11-24 | Wk47 | 2023-11-24 |  |  |  | Completed | Y |  | 2024-01-18 | Y | 2023-11-24 | Wk47 | P1 | C0702P | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
C0702P | 91.22% | #N/A | 2023 | 1154A | xD_DWDM-BRKRing_C0702P_1154A MAGSekinchan_0004582304330Y_00045823098821 | #N/A | 1154A MAGSekinchan | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1154A_Drop_ODF CABINET = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1154A | 1154A | Drop | ODF CABINET = 1 | #N/A | #N/A | #N/A | 2023-11-23 | Wk47 | 2023-11-23 |  |  |  | Completed | Y |  | 2024-01-18 | Y | 2023-11-23 | Wk47 | P1 | C0702P | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
C0702P | 91.22% | #N/A | 2023 | 1156A | xD_DWDM-BRKRing_C0702P_1156A MAC BtgBerjuntai_0004582304330Y_00045823098821 | #N/A | 1156A MAC BtgBerjuntai | 1800 Rack and subrack | BBand |  |  |  | Single_2023_December_DWDM_(blank)_1156A_Drop_ODF CABINET = 1 | Single | 2023 | December | DWDM | (blank) | DWDM-1156A | 1156A | Drop | ODF CABINET = 1 | #N/A | #N/A | #N/A | 2023-11-24 | Wk47 | 2023-11-24 |  |  |  | Completed | Y |  | 2024-01-18 | Y | 2023-11-24 | Wk47 | P1 | C0702P | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
C0702P | 91.22% | #N/A | 2023 | 1169A | xD_DWDM-BRKRing_C0702P_1169A MAC TgKrngTrunkRd_0004582304330Y_00045823098821 | #N/A | 1169A MAC TgKrngTrunkRd | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1169A_Completed_DCPDB = 1 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1169A | 1169A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A | 2023-11-24 | Wk47 | 2023-11-24 |  | Plan 23/1 |  | Completed | Y | 2024-01-22 | 2024-01-18 | Y | 2024-01-23 | Wk4 | P1 | C0702P | IP BREAK RING | #N/A | 2024-01-23 10:40 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
C0704P | 29.33% | #N/A | 2023 | 1073A | xD_DWDM-BRKRing_C0704P_1073A KTM PadangJawa_0004582306610C_00045823162822 | #N/A | 1073A KTM PadangJawa | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1073A_Drop_NOT REQUIRED | Single | 2023 | October | DWDM | (blank) | DWDM-1073A | 1073A | Drop | NOT REQUIRED | #N/A | #N/A | #N/A | 2023-11-23 | Wk47 | 2023-11-23 |  | Pending Fiberail Access |  |  |  | 2024-01-26 | TBC | Y | 2024-01-29 | Wk5 | #N/A | #N/A | #N/A | #N/A | 2024-01-29 09:52 |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A | #N/A | #N/A
C0704P | 29.33% | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_C0704P_1096A Klang Perdana_0004582306610C_00045823162822 | #N/A | 1096A Klang Perdana | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2023-11-23 | Wk47 | 2023-11-23 | Pending PFS Swap | postpone pending solution from customer |  |  |  | 2024-02-15 | TBC |  | 2024-07-11 |  | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A | #N/A | #N/A
C0704P | 29.33% | #N/A | 2023 | 1342A | xD_DWDM-BRKRing_C0704P_1342A MBSA_0004582306610C_00045823162822 | #N/A | 1342A MBSA | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-02-20 | Wk8 | 2024-02-20 | Access | Access |  |  |  |  | TBC | Y | 2024-02-20 | Wk8 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A | #N/A | #N/A
C0704P | 29.33% | #N/A | 2023 | 1367A | xD_DWDM-BRKRing_C0704P_1367A Worldwide Biz_0004582306610C_00045823162822 | #N/A | 1367A Worldwide Biz | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1367A_Drop_NOT REQUIRED | Single | 2023 | October | DWDM | (blank) | DWDM-1367A | 1367A | Drop | NOT REQUIRED | #N/A | #N/A | #N/A | 2023-11-24 | Wk47 | 2023-11-24 | [5 empty] | 2024-01-05 | Completed | Y | 2024-01-16 | Wk3 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-10-23 | Completed |  |  | #N/A | #N/A | #N/A
C0704P | 29.33% | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_C0704P_2021B SBHT_0004582306610C_00045823162822 | #N/A | 2021B SBHT | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A | 2023-12-04 | Wk49 | 2023-12-04 | [5 empty] | 2024-01-09 | Completed | Y | 2023-12-12 | Wk50 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A | #N/A | #N/A
C0713P | 61.78% | #N/A | 2023 | 1071A | xD_DWDM-BRKRing_C0713P_1071A_Chi Liung Plaza_0004582304330V_00045823098821 | #N/A | Chi Liung Plaza | 9800 Rack with subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2023-11-20 | Wk47 | 2023-11-20 |  |  |  | Completed | Y | 4//1/2024 | 2024-01-08 | Y | 2024-01-10 | Wk2 | P0 | #N/A | #N/A | #N/A |  |  | CME completed12/Jan |  |  |  | Schedule for migration |  |  | #N/A | #N/A | #N/A
C0713P | 61.78% | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_C0713P_1096A_KlangPerdana_0004582304330V_00045823098821 | #N/A | KlangPerdana | 9800 Board Expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2023-11-23 | Wk47 | 2023-11-23 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-23 | Wk47 | P0 | #N/A | #N/A | #N/A | [6 empty] | Schedule for migration |  |  | #N/A | #N/A | #N/A
C0713P | 61.78% | #N/A | 2023 | 1342A | xD_DWDM-BRKRing_C0713P_1342A_MBSA_00045823098821 | #N/A | MBSA | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | N/A | Services only | Services only |  |  | N/A |  | 2024-01-08 | N/A | 2024-01-08 | Wk2 | P0 | #N/A | #N/A | #N/A | [6 empty] | Schedule for migration |  |  | #N/A | #N/A | #N/A
C0713P | 61.78% | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_C0713P_2021B_SBHT_0004582304330V_00045823098821 | #N/A | SBHT | 9800 Board Expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A | 2023-12-12 | Wk50 | 2023-12-12 |  |  |  | Completed | Y |  | Completed | Y | 2023-12-12 | Wk50 | P0 | #N/A | #N/A | #N/A | [6 empty] | Schedule for migration |  |  | #N/A | #N/A | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 1049B | xD_DWDM-BRKRing_CAR01_1049B MCR KPG_0004582400460T_00045824009529 | #N/A | 1049B MCR KPG | Board expansion | BBand |  | N/A | N/A | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A | 2024-03-22 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A | 0 | [7 empty] | 2024-04-19 | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 1049B | xD_DWDM-BRKRing_CAR01_1049B_KPG_0004582304330V_00045823098821 | #N/A | KPG | 9800 Board Expansion | BBand |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A | 2023-11-06 | Wk45 | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 1058A | xD_DWDM-BRKRing_CAR01_1058A_Pekan Meru_00045823098821 | #N/A | Pekan Meru | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 1071A | xD_DWDM-BRKRing_CAR01_1071A_Chi Liung Plaza_00045823098821 | #N/A | Chi Liung Plaza | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2024 Q1 | 1085A | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 | #N/A | 1085A Pekan Meru | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-22 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A | 0 | [7 empty] | 2024-04-19 | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_CAR01_1096A_KlangPerdana_00045823098821 | #N/A | KlangPerdana | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 1359A | xD_DWDM-BRKRing_CAR01_1359A_Mutiara Subang_00045823098821 | #N/A | Mutiara Subang | Services only | BBand |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2024 Q1 | 1409A | xD_DWDM-BRKRing_CAR01_1409A Kota Damansara_0004582400460T_00045824009529 | #N/A | 1409A Kota Damansara | Board expansion | BBand |  | N/A | N/A | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-20 | Wk12 | 2024-03-21 | [7 empty] | Y | 2024-03-21 | Wk12 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A | 0 | [7 empty] | 2024-04-19 | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 1409A | xD_DWDM-BRKRing_CAR01_1409A_Kota Damansara_00045823098821 | #N/A | Kota Damansara | Services only | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2024 Q1 | 2021B | xD_DWDM-BRKRing_CAR01_2021B SBHT_0004582400460T_00045824009529 | #N/A | 2021B SBHT | Board expansion | BBand |  | N/A | N/A | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-20 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A | 0 | [7 empty] | 2024-04-19 | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_CAR01_2021B_SBHT_0004582304330V_00045823098821 | #N/A | SBHT | 9800 Board Expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 2631A | xD_DWDM-BRKRing_CAR01_2631A_Samarinda_00045823098821 | #N/A | Samarinda | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2024 Q1 | 2777C | xD_DWDM-BRKRing_CAR01_2777C JBA Bukit Lipat_0004582400460T_00045824009529 | #N/A | 2777C JBA Bukit Lipat | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-21 | Wk12 | 2024-03-25 | [7 empty] | Y | 2024-03-25 | Wk13 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A | 0 | [7 empty] | 2024-04-19 | #N/A | #N/A | PE-MCR
CAR01 | #N/A | #N/A | 2023 | 2777C | xD_DWDM-BRKRing_CAR01_2777C_JBABkitLipat_0004582304330V_00045823098821 | #N/A | JBABkitLipat | 9800 Board Expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A | #N/A | PE-MCR
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1253A | xD_DWDM-BRKRing_CAR04_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 85.39% | Plaza Pengkalan 1253A | Services only | BBand |  | N/A | N/A | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-11 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1261A | xD_DWDM-BRKRing_CAR04_1261A KWSP_0004582309050Y_00045824006623 | 85.39% | KWSP 1261A | Services only | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-11 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1266A | xD_DWDM-BRKRing_CAR04_1266A Sucasa_0004582309050Y_00045824006623 | 85.39% | Sucasa 1266A | Services only | BBand |  | N/A | N/A | Single_2024_May_DWDM_C0407P_1266A_PRPO_1.Add module = 1 2.Add battery bank = 1 | Single | 2024 | May | DWDM | C0407P | DWDM-1266A | 1266A | PRPO | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-11 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1271A | xD_DWDM-BRKRing_CAR04_1271A Risda_0004582309050Y_00045824006623 | 85.39% | Risda 1271A | Services only | BBand |  | N/A | N/A | Single_2024_May_DWDM_DWDM-120Ch_1271A_PRPO_1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.battery bank = 6 | Single | 2024 | May | DWDM | DWDM-120Ch | DWDM-1271A | 1271A | PRPO | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-11 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1461A | xD_DWDM-BRKRing_CAR04_1461A Shaw Parade_0004582309050Y_00045824006623 | 85.39% | Shaw parade 1461A | Services only | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-11 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1737A | xD_DWDM-BRKRing_CAR04_1737A Bernama_0004582309050Y_00045824006623 | 85.39% | Bernama 1737A | Services only | BBand |  | N/A | N/A | Multiple_2024_April_DWDM_C0407P_1737A_PRPO_1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | Multiple | 2024 | April | DWDM | C0407P | DWDM-1737A | 1737A | PRPO | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-18 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1851A | xD_DWDM-BRKRing_CAR04_1851A KL Plaza_0004582309050Y_00045824006623 | 85.39% | KL Plaze 1851A | Services only | BBand |  | N/A | N/A | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [8 empty] | 2024-07-18 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1855B | xD_DWDM-BRKRing_CAR04_1855B TPM_0004582309050Y_00045824006623 | 85.39% | TPM 1855B | Services only | BBand |  | N/A | N/A | Multiple_2023_December_DWDM_(blank)_1855B_Completed_DCPDB = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-1855B | 1855B | Completed | No CME | #N/A | #N/A | #N/A | N/A | WK0 | N/A | [7 empty] | Y | 0 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | 0 | [6 empty] | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CAR11 | 52.48% | #N/A | 2024 Q1 | 1049B | xD_DWDM-BRKRing_CAR11_1049B MCR Kepong_0004582400700P_00045824009527 | #N/A | 1049B-MCR-002 KPG | Board expansion | BBand |  | N/A | N/A | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-22 | Wk17 | 2024-04-22 | [7 empty] | Y | 2024-04-22 | Wk17 | P0 | CAR11 | PE-MCR | #N/A | 0 | [7 empty] | 2024-04-18 | #N/A | #N/A | PE-MCR
CAR11 | 52.48% | #N/A | 2024 Q1 | 2070B | xD_DWDM-BRKRing_CAR11_2070B Gombak_0004582400700P_00045824009527 | #N/A | 2070B-MAG-001 Gombak Tx | Board expansion | BBand |  | N/A | N/A | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2070B | 2070B | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-22 | Wk17 | 2024-04-22 | [7 empty] | Y | 2024-04-22 | Wk17 | P0 | CAR11 | PE-MCR | #N/A | 0 | [7 empty] | 2024-04-18 | #N/A | #N/A | PE-MCR
CAR11 | 52.48% | #N/A | 2024 Q1 | 8709A | xD_DWDM-BRKRing_CAR11_8709A Bentong_0004582400700P_00045824009527 | #N/A | 8709A-MAG-003 Bentong | Board expansion | BBand |  | N/A | N/A | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-18 | Wk16 | 2024-04-18 | [7 empty] | Y | 2024-04-29 | Wk18 | P0 | CAR11 | PE-MCR | #N/A | 0 | [7 empty] | 2024-04-18 | #N/A | #N/A | PE-MCR
CT0120 | 79.05% | #N/A | 2023 | 2632A | xD_DWDM-BRKRing_CT0120_2632A Ecopark_0004582304160F_0004582308742 | #N/A | 2632A Ecopark | 1800 Rack and subrack | Advance |  |  |  | Single_2023_October_DWDM_(blank)_2632A_Completed_AC BREAKER : 32 X 3 | Single | 2023 | October | DWDM | (blank) | DWDM-2632A | 2632A | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A | 2024-05-21 | Wk21 | 2024-03-27 | replace outdoor (syabas) | Entrance issue (gate) | 0523: Replaced old outdoor rack |  |  | 2024-04-23 | TBC | Y | 2024-04-25 | Wk17 | P1_IP_BR-Q1 | CT0120 | IP BREAK RING | P1_IP_BR-Q1 | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8923B | xD_DWDM-BRKRing_E212_8923B Tmn Semarak_0004582304160F_00045823087420 | 107.7% | 8923B Tmn Semarak | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_January_DWDM_(blank)_8923B_Drop_ADD 100A X 2 BREAKER ADD GROUNDING X 1 ADD PLINTH X 1 ADD ODF PANEL X 1 | Single | 2024 | January | DWDM | (blank) | DWDM-8923B | 8923B | Drop | ADD 100A X 2 BREAKER | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Site Dropped | Resurvey AC |  |  |  |  | TBC | N/A | 0 |  | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
EAR04 | #N/A | #N/A | 2023 | 1049B | xD_DWDM-BRKRing_EAR04_1049B_KPG_00045823098821 | #N/A | KPG | Services only | FO&T |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A | #N/A | IP BREAK RING
EAR04 | #N/A | #N/A | 2023 | 1475A | xD_DWDM-BRKRing_EAR04_1475A_MSC MSK_00045823098821 | #N/A | MSC MSK | Services only | FO&T |  |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A | #N/A | IP BREAK RING
EAR04 | #N/A | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_EAR04_2021B_SBHT_00045823098821 | #N/A | SBHT | Services only | FO&T |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A | #N/A | IP BREAK RING
EAR04 | #N/A | #N/A | 2023 | 8000A | xD_DWDM-BRKRing_EAR04_8000A_MSC KTN_00045823098821 | #N/A | MSC KTN | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A | #N/A | IP BREAK RING
EAR04 | #N/A | #N/A | 2023 | 8703A | xD_DWDM-BRKRing_EAR04_8703A_KG Awah_00045823098821 | #N/A | KG Awah | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A | #N/A | IP BREAK RING
MCR144 | #N/A | #N/A | 2023 | 1007A | xD_DWDM-BRKRing_MCR144_1007A MAC Mimaland_0004582304330Y_00045823098821 | #N/A | 1007A MAC Mimaland | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1007A_Completed_DCPDB = 1 UNIT MGB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1007A | 1007A | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-10 | Wk41 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | #N/A
MCR144 | #N/A | #N/A | 2023 | 1770B | xD_DWDM-BRKRing_MCR144_1770B MAC GentingSempah_0004582304330Y_00045823098821 | #N/A | 1770B MAC GentingSempah | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1770B_Completed_AC BREAKER : 32 X 3 | Single | 2023 | October | DWDM | (blank) | DWDM-1770B | 1770B | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-17 | Wk42 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | #N/A
MCR144 | #N/A | #N/A | 2023 | 1787B | xD_DWDM-BRKRing_MCR144_1787B MAC KarakHW_0004582304330Y_00045823098821 | #N/A | 1787B MAC KarakHW | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1787B_Completed_DC BREAKER: 63A X 2 | Single | 2023 | October | DWDM | (blank) | DWDM-1787B | 1787B | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-17 | Wk42 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | #N/A
MCR144 | #N/A | #N/A | 2023 | 2070B | xD_DWDM-BRKRing_MCR144_2070B MAC Gombak_0004582304330Y_00045823098821 | #N/A | 2070B MAC Gombak | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2070B | 2070B | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-19 | Wk42 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | #N/A
MCR144 | #N/A | #N/A | 2023 | 2086A | xD_DWDM-BRKRing_MCR144_2086A Balai Polis Bkt Tinggi_0004582304330Y_00045823098821 | #N/A | 2086A Balai Polis Bkt Tinggi | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_2086A_Completed_DC BREAKER: 63A X 2 | Single | 2023 | October | DWDM | (blank) | DWDM-2086A | 2086A | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-18 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-18 | Wk42 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | #N/A
MCR144 | #N/A | #N/A | 2023 | 8709A | xD_DWDM-BRKRing_MCR144_8709A MAG Bentong_0004582304330Y_00045823098821 | #N/A | 8709A MAG Bentong | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-16 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-16 | Wk42 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 1172A | xD_DWDM-BRKRing_MCR18/C24_1172A Glomac_0004582306610C_00045823162822 | #N/A | 1172A Glomac | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | N/A |  |  |  |  | N/A |  | 2024-02-12 | N/A | 2023-11-14 | Wk46 | P2 | MCR18/C24 | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
E111 | 70.34% | 121.3% | 2024 Q1 | 8367A | xD_DWDM_BRKRing_E111_8367A-MAG001 B.Kechil_0004582309010R_00045824006624 | 121.3% | 8367A-MAG001 B.Kechil | 1800VPRO 1 rack 1 subrack | FO&T |  | 2024-02-07 |  | Single_2024_May_DWDM_E111;EAR01 N EAR03_8367A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | Single | 2024 | May | DWDM | E111;EAR01 N EAR03 | DWDM-8367A | 8367A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-08 | Wk19 | 2024-05-09 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | E111 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | May | #N/A | E111 | IP BREAK RING
EAR01 | #N/A | #N/A | 2024 Q1 | 8224A | xD_DWDM_BRKRing_EAR01_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | #N/A | 8224A-MAG-001 Pasir Puteh | 9800 M24 1 rack 1 subrack | Fo&T |  | 2023-12-21 | 2024-02-16 | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Indoor | 1.6 Pending FF approval | 1.7 TSSR Approved | 2024-05-09 | Wk19 | 2024-05-09 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_BR-Q1 | EAR01 | IP BREAK RING | P1_IP_BR-Q1 | [7 empty] | Y | 2024-04-19 | #N/A | EAR01 | IP BREAK RING
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8667A | xD_DWDM_BRKRing_EAR06_8667A-MAG 001 Kg Jerangsang_0004582309010R_00045824006624 | 91.72% | 8667A-MAG 001 Kg Jerangsang | 9800 1subrack | Fo&T |  | 2024-02-07 |  | Single_2024_May_DWDM_EAR06_8667A_PRPO_1.Add modules = 2 2.Add battery bank = 6 | Single | 2024 | May | DWDM | EAR06 | DWDM-8667A | 8667A | PRPO | 1.Add modules = 2 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-09 | Wk19 | 2024-05-09 |  |  |  | 2024-06-07 |  |  | Pending ES PO |  | 2024-06-21 |  | P1_IP_R_EXP-Q1 | EAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q1 | [7 empty] | Y | 2024-05-15 | #N/A | EAR06 | Ring Expansion (MAG-PE)
MCR18/C24 | #N/A | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_MCR18/C24_2021B SBHT_0004582306610C_00045823162822 | #N/A | 2021B SBHT | 1800 Rack and subrack | Bband |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-07 |  |  |  | Completed | Y | 2024-01-09 | 2024-02-12 | Y | 2023-12-12 | Wk50 | P2 | MCR18/C24 | IP BREAK RING | #N/A |  | Integrated but plan next date | completed | [6 empty] | #N/A | #N/A | #N/A
N103 | 57.39% | #N/A | 2023 | 4660A | xD_DWDM-BRKRing_N103_4660A KTM Alorstar_0004582306610C_00045823162822 | #N/A | 4660A KTM Alorstar | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  | Request DCPDB, subrack can move to existing rack 12/1: Pending odf panel 16/1: bring ODF panel & travel |  |  |  | 2024-01-12 | 2024-02-07 | Y | 2024-01-18 | Wk3 | P1 | N103 | IP BREAK RING | #N/A | 2024-01-17 09:48 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
N103 | 57.39% | #N/A | 2023 | 4669A | xD_DWDM-BRKRing_N103_4669A Alor Janggus_0004582306610C_00045823162822 | #N/A | 4669A Alor Janggus | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4669A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4669A | 4669A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 | CME | 12/1: Pending odf panel 16/1: bring ODF panel & travel 23/1: Pending CME 30/1: Pending DCPDB 7/2: Pending DCPDB |  | Completed | Y | 2024-03-15 | 2024-02-07 | Y | 2024-03-12 | Wk11 | P1 | N103 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
N103 | 57.39% | #N/A | 2023 | 4863B | xD_DWDM-BRKRing_N103_4863B Wisma PKNK_0004582306610C_00045823162822 | #N/A | 4863B Wisma PKNK | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2024_April_DWDM_N103_4863B_PRPO_1. Add Battery Bank = 1 | Multiple | 2024 | April | DWDM | N103 | DWDM-4863B | 4863B | PRPO | 1. Add Battery Bank = 1 | #N/A | #N/A | #N/A | 2024-05-08 | Wk19 | 2024-05-08 |  | OUTDOOR |  | 2024-05-25 |  | Replan | 2024-02-07 | Y | 2024-05-09 | Wk19 | P1 | N103 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
N103 | 57.39% | #N/A | 2023 | 4998A | xD_DWDM-BRKRing_N103_4998A Air Itam Kedah_0004582306610C_00045823162822 | #N/A | 4998A Air Itam Kedah | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | 1. Add Battery Bank = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  | 12/1: Pending odf panel 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-12 | 2024-01-16 | Y | 2024-01-17 | Wk3 | P1 | N103 | IP BREAK RING | #N/A | 2024-01-17 09:48 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
N106 | 40.89% | #N/A | 2023 | 4085D | xD_DWDM-BRKRing_N106_4085D Kulim Hitech2_0004582306610C_00045823162822 | #N/A | 4085D Kulim Hitech2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4085D_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | November | DWDM | (blank) | DWDM-4085D | 4085D | Completed | RECTTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-08 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A | #N/A | MAC Swap - BR
N106 | 40.89% | #N/A | 2023 | 4683A | xD_DWDM-BRKRing_N106_4683A Bkt Tok Alang_0004582306610C_00045823162822 | #N/A | 4683A Bkt Tok Alang | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3 | Single | 2024 | May | DWDM | N106+ | DWDM-4683A | 4683A | PRPO | 1. Add Battery Bank = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-09 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A | #N/A | MAC Swap - BR
N106 | 40.89% | #N/A | 2023 | 4946A | xD_DWDM-BRKRing_N106_4946A Bukit Selambau_0004582306610C_00045823162822 | #N/A | 4946A Bukit Selambau | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | DROP | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-09 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A | #N/A | MAC Swap - BR
N106 | 40.89% | #N/A | 2023 | 4966A | xD_DWDM-BRKRing_N106_4966A Kulim Hi Tech_0004582306610C_00045823162822 | #N/A | 4966A Kulim Hi Tech | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-08 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A | #N/A | MAC Swap - BR
N113 | 41.2% | #N/A | 2023 | 4662A | xD_DWDM-BRKRing_N113_4662A MAC BktTinggiJitra_0004582304330Y_00045823098821 | #N/A | 4662A MAC BktTinggiJitra | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4662A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4662A | 4662A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-25 |  |  |  | Completed | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A | N113 | IP BREAK RING | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N113 | 41.2% | #N/A | 2023 | 4678A | xD_DWDM-BRKRing_N113_4678A MAC JlnLanggar_0004582304330Y_00045823098821 | #N/A | 4678A MAC JlnLanggar | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4678A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4678A | 4678A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-23 |  |  |  | Completed | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A | N113 | IP BREAK RING | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N113 | 41.2% | #N/A | 2023 | 4992A | xD_DWDM-BRKRing_N113_4992A MAG Pendang_0004582304330Y_00045823098821 | #N/A | 4992A MAG Pendang | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-25 |  |  |  | Completed | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A | N113 | IP BREAK RING | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N113 | 41.2% | #N/A | 2023 | 4995A | xD_DWDM-BRKRing_N113_4995A MAG UUMHW_0004582304330Y_00045823098821 | #N/A | 4995A MAG UUMHW | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-23 |  |  |  | Completed | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A | N113 | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N114M | 10.29% | #N/A | 2023 | 4660A | xD_DWDM-BRKRing_N114M_4660A Ktm Astar_000458237400E_00045823174223 | #N/A | 4660A Ktm Astar | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  |  |  | Completed | Y | 2024-01-18 | 2024-01-18 | Y | 2024-01-18 | Wk3 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A | #N/A | #N/A
N114M | 10.29% | #N/A | 2023 | 4692A | xD_DWDM-BRKRing_N114M_4692A Gurun_0004582306610C_00045823162822 | #N/A | 4692A Gurun | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 |  | 23/1: Pending power tap |  |  |  | 2024-01-29 | 2024-02-06 | Y | 2024-01-29 | Wk5 | #N/A | #N/A | #N/A | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A | #N/A | #N/A
N114M | 10.29% | #N/A | 2023 | 4938A | xD_DWDM-BRKRing_N114M_4938A Tmn Orkid_000458237400E_00045823174223 | #N/A | 4938A Tmn Orkid | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 | CME - Special Power Cable | 16mm power cable required, 40m breaker x 4 1/2: Pending power cable 16mm2 6/2: Pending power cable 16mm2 |  |  |  | 2024-03-07 | 2024-02-06 | Y | 2024-03-07 | Wk10 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A | #N/A | #N/A
N114M | 10.29% | #N/A | 2023 | 4938A | xD_DWDM-BRKRing_N114M_4938A Tmn Orkid2_000458237400E_00045823174223 | #N/A | 4938A Tmn Orkid2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 | CME - Special Power Cable | 6/2: Pending power cable 16mm2 |  |  |  | 2024-03-07 | #N/A | Y | 2024-03-07 | Wk10 | #N/A | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A | #N/A | #N/A
N114M | 10.29% | #N/A | 2023 | 4940A | xD_DWDM-BRKRing_N114M_4940A Semeling_0004582306610C_00045823162822 | #N/A | 4940A Semeling | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4940A_Completed_BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4940A | 4940A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 | [5 empty] | 2024-01-30 | 2024-02-06 | Y | 2024-01-30 | Wk5 | #N/A | #N/A | #N/A | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A | #N/A | #N/A
N115 | 23.69% | #N/A | 2023 | 4770A | xD_DWDM-BRKRing_N115_4770A Toklin_0004582304160F_00045823087420 | #N/A | 4770A Toklin | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4770A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4770A | 4770A | Completed | RECTTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-12-21 | Completed |  |  | #N/A | #N/A | MAC Swap - BR
N201 | 63.25% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_N201_4000A MSC Prai_000458237400E_00045823174223 | #N/A | 4000A MSC Prai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-20 |  |  |  | Completed | Y | 2024-01-31 | Completed | Y | 2023-11-19 | Wk46 | P?? | N201 | IP BREAK RING | #N/A |  |  | CME completed12/Jan |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4685B | xD_DWDM-BRKRing_N201_4685B Kg Sungai Karangan_000458237400E_00045823174223 | #N/A | 4685B Kg Sungai Karangan | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4685B_Completed_DCPDB = 1 UNIT MGB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4685B | 4685B | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-30 |  |  |  | Completed | Y | 2024-02-01 | 2024-01-30 | Y | 2024-02-01 | Wk5 | P?? | N201 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4950B | xD_DWDM-BRKRing_N201_4950B Pulai_000458237400E_00045823174223 | #N/A | 4950B Pulai | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_October_DWDM_(blank)_4950B_Completed_DC BREAKER: 63 A X 4 | Multiple | 2023 | October | DWDM | (blank) | DWDM-4950B | 4950B | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 | [5 empty] | 2024-02-06 | 2024-01-30 | Y | 2024-02-06 | Wk6 | P?? | N201 | IP BREAK RING | #N/A | 2024-02-06 09:38 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4956B | xD_DWDM-BRKRing_N201_4956B Kuala Pegang_000458237400E_00045823174223 | #N/A | 4956B Kuala Pegang | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4956B_Completed_DCPDB = 1 UNIT MGB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4956B | 4956B | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 | [5 empty] | 2024-02-05 | 2024-01-30 | Y | 2024-02-05 | Wk6 | P?? | N201 | IP BREAK RING | #N/A | 2024-02-05 09:37 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4968A | xD_DWDM-BRKRing_N201_4968A Inokom Kulim_000458237400E_00045823174223 | #N/A | 4968A Inokom Kulim | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4968A_Completed_AC BREAKER : 32 X 3 | Single | 2023 | November | DWDM | (blank) | DWDM-4968A | 4968A | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  | 12/1: Pending DCPDB, odf panel 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-30 | 2024-01-30 | Y | 2024-01-30 | Wk5 | P?? | N201 | IP BREAK RING | #N/A | 2024-01-26 09:59 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4985A | xD_DWDM-BRKRing_N201_4985A Baling Town_000458237400E_00045823174223 | #N/A | 4985A Baling Town | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4985A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =2 | Single | 2023 | November | DWDM | (blank) | DWDM-4985A | 4985A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  |  |  | Completed | Y | 2024-02-07 | 2024-01-30 | Y | 2024-02-07 | Wk6 | P?? | N201 | IP BREAK RING | #N/A | 2024-02-07 09:48 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4986A | xD_DWDM-BRKRing_N201_4986A Binjul_000458237400E_00045823174223 | #N/A | 4986A Binjul | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4986A_Completed_DCPDB = 1 UNIT MGB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4986A | 4986A | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 | [5 empty] | 2024-02-02 | 2024-01-30 | Y | 2024-02-02 | Wk5 | P?? | N201 | IP BREAK RING | #N/A | 2024-02-02 11:21 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N201 | 63.25% | #N/A | 2023 | 4988A | xD_DWDM-BRKRing_N201_4988A Kupang_000458237400E_00045823174223 | #N/A | 4988A Kupang | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4988A_Completed_BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4988A | 4988A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  |  |  | Completed | Y | 2024-02-05 | 2024-01-30 | Y | 2024-02-05 | Wk6 | P?? | N201 | IP BREAK RING | #N/A | 2024-02-05 09:37 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N302 | 67.19% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_N302_4000A MSC Prai_0004582306610C_00045823162822 | #N/A | 4000A MSC Prai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-20 |  | 23/1: Pending power tap |  |  |  | 2024-01-31 | 2024-02-16 | Y | 2024-01-31 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-26 09:59 |  | CME completed12/Jan | Y | Completed | 2024-04-25 | 2024-04-25 |  |  | #N/A | #N/A | IP BREAK RING
N302 | 67.19% | #N/A | 2023 | 4188A | xD_DWDM-BRKRing_N302_4188A Nibong tebal2_0004582306610C_00045823162822 | #N/A | 4188A Nibong tebal2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4188A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-4188A | 4188A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  |  |  | Completed | Y | 2024-01-16 | 2024-01-16 | Y | 2024-01-16 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-16 10:25 |  |  | Y | Completed | 2024-04-25 | 2024-04-25 |  |  | #N/A | #N/A | IP BREAK RING
N302 | 67.19% | #N/A | 2023 | 4241A | xD_DWDM-BRKRing_N302_4241A Juru Tower_0004582306610C_00045823162822 | #N/A | 4241A Juru Tower | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-20 |  |  |  | Completed | Y | 2024-01-16 | 2024-01-16 | Y | 2024-01-17 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-17 09:48 |  |  | Y | Completed | 2024-04-25 | 2024-04-25 |  |  | #N/A | #N/A | IP BREAK RING
N404 | 33.59% | #N/A | 2023 | 4427B | xD_DWDM-BRKRing_N404_4427B MAC SimpangTaiping_0004582304330Y_00045823098821 | #N/A | 4427B MAC SimpangTaiping | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4427B_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-4427B | 4427B | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  | Completed | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-15 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N404 | 33.59% | #N/A | 2023 | 4454B | xD_DWDM-BRKRing_N404_4454B MAC KubuGajah_0004582304330Y_0004582307060Z_00045823098821 | #N/A | 4454B MAC KubuGajah | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_4454B_Completed_DC BREAKER : 100A X 2 I-BEAM = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-4454B | 4454B | Completed | DC BREAKER : 100A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-10 |  |  |  | Completed | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-15 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N404 | 33.59% | #N/A | 2023 | 4455A | xD_DWDM-BRKRing_N404_4455A MAG KTMTaiping_0004582304330Y_00045823098821 | #N/A | 4455A MAG KTMTaiping | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  | Completed | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-12 | Wk2 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N404 | 33.59% | #N/A | 2023 | 4457A | xD_DWDM-BRKRing_N404_4457A MAC KamuntingIndst_0004582304330Y_00045823098821 | #N/A | 4457A MAC KamuntingIndst | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-18 |  |  |  | Completed | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-12 | Wk2 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N404 | 33.59% | #N/A | 2023 | 4465A | xD_DWDM-BRKRing_N404_4465A MAC TmnLongJaafar_0004582304330Y_00045823098821 | #N/A | 4465A MAC TmnLongJaafar | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4465A_Completed_BATTERY BANK = 7 | Single | 2023 | November | DWDM | (blank) | DWDM-4465A | 4465A | Completed | BATTERY BANK = 7 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-18 |  | 12/1: Plan next week |  | Completed | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-15 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N404 | 33.59% | #N/A | 2023 | 4952B | xD_DWDM-BRKRing_N404_4952B MAG Selama_0004582304330Y_00045823098821 | #N/A | 4952B MAG Selama | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  | Completed | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-12 | Wk2 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N406 | 17.94% | #N/A | 2023 | 4432A | xD_DWDM-BRKRing_N406_4432A MAG KTMSgSiput_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4432A MAG KTMSgSiput | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-03-20 | Wk12 | 2024-03-22 | [5 empty] | 2024-03-14 | NO EQUIPMENT REDELPOY TO KUSZA (E212) | Y | 2024-03-22 | Wk12 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N406 | 17.94% | #N/A | 2023 | 4493A | xD_DWDM-BRKRing_N406_4493A MAG KTMIpoh_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4493A MAG KTMIpoh | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Material relocation |  |  |  |  | 2024-03-14 | NO EQUIPMENT REDELPOY TO BKT PAYUNG 2 (E212) |  | 2024-07-18 |  | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N406 | 17.94% | #N/A | 2023 | 4496A | xD_DWDM-BRKRing_N406_4496A MAC LapTasek1N2_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4496A MAC LapTasek1N2 | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-02-23 | Wk8 | 2024-02-23 | [5 empty] | 2024-03-14 |  | Y | 2024-03-13 | Wk11 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N406 | 17.94% | #N/A | 2023 | 4536A | xD_DWDM-BRKRing_N406_4536A MAC TasekIndst_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4536A MAC TasekIndst | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Material relocation |  |  |  |  | 2024-03-14 | NO EQUIPMENT REDELPOY TO TMN SEMARAK (E212) |  | 2024-07-18 |  | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N601 | 43.15% | #N/A | 2023 | 4368A | xD_DWDM-BRKRing_N601_4368A Tar College_0004582306900G_00045823168029 | #N/A | 4368A Tar College | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4368A_Completed_DC BREAKER : 63A X 4 MGB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4368A | 4368A | Completed | DC BREAKER : 63A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-21 | EB site- CRQ |  |  | Completed | Y | 2024-01-29 | 2024-02-05 | Y | 2024-01-29 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N601 | 43.15% | #N/A | 2023 | 4440B | xD_DWDM-BRKRing_N601_4440B Tapah Road_0004582306900G_00045823168029 | #N/A | 4440B Tapah Road | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4440B_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-4440B | 4440B | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 | EB site- CRQ |  |  | Completed | Y | 2024-01-17 | Completed | Y | 2024-01-16 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A |  |  | completed | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N601 | 43.15% | #N/A | 2023 | 4509A | xD_DWDM-BRKRing_N601_4509A Tamn Taufik_0004582306900G_00045823168029 | #N/A | 4509A Tamn Taufik | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4509A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4509A | 4509A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 | EB site- CRQ | 23/1: Pending DCPDB 6/2: Plan 7/2 due to site key not available |  |  |  | 2024-02-06 | 2024-02-07 | Y | 2024-02-07 | Wk6 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N601 | 43.15% | #N/A | 2023 | 4516A | xD_DWDM-BRKRing_N601_4516A Simpang Pulai_0004582306900G_00045823168029 | #N/A | 4516A Simpang Pulai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4516A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4516A | 4516A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 | EB site- CRQ | 23/1: Pending DCPDB |  |  |  | 2024-02-07 | 2024-02-07 | Y | 2024-02-06 | Wk6 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | IP BREAK RING
N601 | 43.15% | #N/A | 2023 | 4521A | xD_DWDM-BRKRing_N601_4521A MSC Ipoh_0004582306900G_00045823168029 | #N/A | 4521A MSC Ipoh | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-21 | [5 empty] | 2024-01-29 | 2024-02-07 | Y | 2024-01-30 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | IP BREAK RING
Nar01i | #N/A | #N/A | Pending PO | 4000A | xD_DWDM-BRKRing_Nar01i_4000A Msc Prai | #N/A | 4000A Msc Prai | 9800 Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4521A | xD_DWDM-BRKRing_Nar01i_4521A Msc Ipoh | #N/A | 4521A Msc Ipoh | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4946A | xD_DWDM-BRKRing_Nar01i_4946A Bkt Selambau | #N/A | 4946A Bkt Selambau | 9800 Board expansion | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01i | #N/A | #N/A | Pending Po | 4966A | xD_DWDM-BRKRing_Nar01i_4966A Kulim Hitech | #N/A | 4966A Kulim Hitech | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4992A | xD_DWDM-BRKRing_Nar01i_4992A Pendang | #N/A | 4992A Pendang | 9800 Board expansion | FO&T |  |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4606A | xD_DWDM-BRKRing_Nar01ii_4606A Padang Besar | #N/A | 4606A Padang Besar | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4938A | xD_DWDM-BRKRing_Nar01ii_4638A Tmn Orkid | #N/A | 4638A Tmn Orkid | 9800 Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4660A | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | #N/A | 4660A Ktm Astar | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4998A | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | #N/A | 4660A Ktm Astar | 9800 Board expansion | FO&T |  |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | No CME | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  | 0 |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
NAR03 | 49.46% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_NAR03_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4000A MSC Prai | 9800 SFP only | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-20 | [5 empty] | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | P0 | #N/A | PFS Swap | #N/A | 2024-01-17 09:48 | [8 empty] | #N/A | #N/A | PFS Swap
NAR03 | 49.46% | #N/A | 2023 | 4331A | xD_DWDM-BRKRing_NAR03_4331A Bagan Serai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4331A Bagan Serai | 9800 SFP only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | P0 | #N/A | PFS Swap | #N/A | 2024-01-17 09:48 | [8 empty] | #N/A | #N/A | PFS Swap
NAR06 | 22.23% | #N/A | 2023 | 1049B | xD_DWDM-BRKRing_NAR06_1049B Kpg_0004582306610A_0004582306610D_00045823162822 | #N/A | 1049B Kpg | 9800 SFP only | FO&T |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-15 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | N/A | 2024-01-24 | Wk4 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | PE-MCR
NAR06 | 22.23% | #N/A | 2023 | 1701A | xD_DWDM-BRKRing_NAR06_1801A Kerling Trnk_0004582306610A_0004582306610D_00045823162822 | #N/A | 1801A Kerling Trnk | 9800 SFP only | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_1701A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-1701A | 1701A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | N/A | Material combined to Nar06 kepong | Material combined to Nar06 kepong |  |  | N/A | 2024-01-08 | 2024-01-10 | N/A | 2024-01-24 | Wk4 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | PE-MCR
NAR06 | 22.23% | #N/A | 2023 | 4412A | xD_DWDM-BRKRing_NAR06_4412A KTM Sungkai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4412A KTM Sungkai | 9800 SFP only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | N/A | Material combined to Nar06 kepong | Material combined to Nar06 kepong |  |  | N/A | 2024-01-08 | 2024-01-10 | N/A | 2024-01-24 | Wk4 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | PE-MCR
NAR06 | 22.23% | #N/A | 2023 | 4440B | xD_DWDM-BRKRing_NAR06_4440B Tapah Road_0004582306610A_0004582306610D_00045823162822 | #N/A | 4440B Tapah Road | 9800 Board expansion | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4440B_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-4440B | 4440B | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2024-01-23 | Invalid Config | Invalid Config |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | PE-MCR
NAR06 | 22.23% | #N/A | 2023 | 4521A | xD_DWDM-BRKRing_NAR06_4521A MSC IPOH_0004582306610A_0004582306610D_00045823162822 | #N/A | 4521A MSC IPOH | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-21 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | PE-MCR
NAR06 | 22.23% | #N/A | 2023 | 4521A | xD_DWDM-BRKRing_NAR06_4521A MSC IPOH_0004582306610A_0004582306610D_00045823162822 | #N/A | 4521A MSC IPOH | 9800 SFP only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-21 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-24 | Wk4 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A | #N/A | PE-MCR
New Ring5/S406 | #N/A | #N/A | 2023 | 6000A | xD_DWDM-BRKRing_New Ring_5/S406_6000A MSC JB_0004582306610B_00045823162821 | #N/A | 6000A MSC JB | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-05 | [5 empty] | 2024-02-15 | 2024-02-14 | Y | 2024-02-15 | Wk7 | P1 | New Ring5/S406 | IP BREAK RING | #N/A | 2024-02-15 09:54 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6026A | xD_DWDM-BRKRing_New Ring_5/S406_6026A Grand Cont Hotel_0004582306610B_00045823162821 | #N/A | 6026A Grand Cont Hotel | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6026A_Completed_DC BREAKER: 63A X 3 | Single | 2023 | November | DWDM | (blank) | DWDM-6026A | 6026A | Completed | DC BREAKER: 63A X 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 | [5 empty] | 2024-02-15 | 2024-02-14 | Y | 2024-02-19 | Wk8 | P1 | New Ring5/S406 | IP BREAK RING | #N/A | 2024-02-15 09:54 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6043A | xD_DWDM-BRKRing_New Ring_5/S406_6043A KK Kam_0004582306610B_00045823162821 | #N/A | 6043A KK Kam | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  | Completed | Y | 2024-01-10 | 2024-02-14 | Y | 2024-01-11 | Wk2 | P1 | New Ring5/S406 | IP BREAK RING | #N/A | 2024-01-15 11:00 | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6283A | xD_DWDM-BRKRing_New Ring_5/S406_6283A Larkin Indst_0004582306610B_00045823162821 | #N/A | 6283A Larkin Indst | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6283A_Completed_DCPDB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6283A | 6283A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-08 | CME Done | Pending CRQ |  |  |  | 2024-03-12 | 2024-02-14 | Y | 2024-05-07 |  | P1 | New Ring5/S406 | IP BREAK RING | #N/A | 2024-03-14 09:26 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6502A | xD_DWDM-BRKRing_New Ring_5/S406_6502A Nusa Perintis_0004582306610B_00045823162821 | #N/A | 6502A Nusa Perintis | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6502A | 6502A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-08 |  |  |  | Completed | Y |  | 2024-02-14 | Y | 2024-01-10 | Wk2 | P1 | New Ring5/S406 | IP BREAK RING | #N/A |  | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6836A | xD_DWDM-BRKRing_New Ring_5/S406_6836A Menara Ansar_0004582306610B_0004582316282 | #N/A | 6836A Menara Ansar | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_(blank)_6836A_Completed_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | May | DWDM | (blank) | DWDM-6836A | 6836A | Completed | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 |  | 29/1: TSSR pending Haji approval |  |  |  |  | 2024-02-14 | Y | 2024-05-09 | Wk19 | P1 | New Ring5/S406 | IP BREAK RING | #N/A | 2024-02-02 11:13 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
NT09P | 0.801% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_NT09P_4000A MSC Prai_000458237400E_00045823174223 | #N/A | 4000A MSC Prai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  | Wk52 | Completed | Invalid Config | Invalid Config |  |  | N/A |  | 2024-02-05 | N/A | 2024-01-31 | Wk5 | P1 | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A | #N/A | #N/A
NT09P | 0.801% | #N/A | 2023 | 4621A | xD_DWDM-BRKRing_NT09P_4621A Cayman Shop Comp_000458237400E_00045823174223 | #N/A | 4621A Cayman Shop Comp | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4621A_Completed_BATTERY BANK = 3 | Single | 2023 | December | DWDM | (blank) | DWDM-4621A | 4621A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  |  |  | Completed | Y | 2024-01-30 | 2024-02-05 | Y | 2024-01-30 | Wk5 | P1 | #N/A | #N/A | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A | #N/A | #N/A
NT09P | 0.801% | #N/A | 2023 | 4625A | xD_DWDM-BRKRing_NT09P_4625A KTM Sg Petani_000458237400E_00045823174223 | #N/A | 4625A KTM Sg Petani | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4625A_Completed_BATTERY BANK = 3 | Single | 2023 | December | DWDM | (blank) | DWDM-4625A | 4625A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  |  |  | Completed | Y | 2024-01-31 | 2024-02-05 | Y | 2024-01-31 | Wk5 | P1 | #N/A | #N/A | #N/A |  |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A | #N/A | #N/A
NT09P | 0.801% | #N/A | 2023 | 4640A | xD_DWDM-BRKRing_NT09P_4640A SP Plaza_0004582304160F_00045823087420 | #N/A | 4640A SP Plaza | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4640A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4640A | 4640A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  | 12/1: Pending DCPDB, ODF panel 16/1: pending DCPDB |  |  |  | 2024-02-01 | 2024-02-05 | Y | 2024-02-01 | Wk5 | P1 | #N/A | #N/A | #N/A | 2024-01-26 09:59 |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A | #N/A | #N/A
NT09P | 0.801% | #N/A | 2023 | 4693A | xD_DWDM-BRKRing_NT09P_4693A Ktm Gurun_000458237400E_00045823174223 | #N/A | 4693A Ktm Gurun | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4693A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | November | DWDM | (blank) | DWDM-4693A | 4693A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 |  | 12/1: Pending odf panel 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-29 | 2024-02-05 | Y | 2024-01-29 | Wk5 | P1 | #N/A | #N/A | #N/A | 2024-01-29 09:59 |  | CME completed12/Jan | Y | Completed | 2024-03-19 | Completed |  |  | #N/A | #N/A | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1246A | xD_DWDM-BRKRing_PFSRING101/C0607P_1246A Kompleks Nagaria_0004582306610C_00045823162822 | #N/A | 1246A Kompleks Nagaria | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1246A_Completed_DC BREAKER: 63 A X 4 POLE RELOCATE = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1246A | 1246A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-08 | [5 empty] | 2024-02-16 | 2024-02-16 | Y | 2024-01-09 | Wk2 | P1 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1475A | xD_DWDM-BRKRing_PFSRING101/C0607P_1475A Sri Kembangan_0004582306610C_00045823162822 | #N/A | 1475A Sri Kembangan | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-04 |  | Pending power up |  | Completed | Y | 2024-01-22 | 2024-02-16 | Y | 2024-01-24 | Wk4 | P1 | #N/A | #N/A | #N/A | 2024-01-26 09:54 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1851A | xD_DWDM-BRKRing_PFSRING101/C0607P_1851A KL Plaza2_0004582306610C_00045823162822 | #N/A | 1851A KL Plaza2 | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 | [5 empty] | 2024-02-16 | 2024-02-16 | Y | 2024-02-20 | Wk8 | P1 | #N/A | #N/A | #N/A | 2024-02-19 11:08 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
N106+ | #N/A | #N/A | 2024 Q1 | 4966A | xD_DWDM_BRKRing_N106+_4966A Kulim Hitech_0004582309010S_00045824006622 | #N/A | 4966A Kulim Hitech | 1800V PRO 1 rack 2 subrack | FO&T | Week 12 March | 2024-03-20 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only, require 9800 door | 1.33 FF reject/Pending resubmission from partner | 1.33 FF reject/Pending resubmission from partner | 2024-05-07 | Wk19 | 2024-05-09 | [5 empty] | June Plan |  |  | 2024-05-16 |  | P1 | #N/A | #N/A | #N/A | 0 | [6 empty] | Y | May | #N/A | #N/A | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1899A | xD_DWDM-BRKRing_PFSRING101/C0607P_1899A Berjaya Times Square CAS_0004582306610C_00045823162822 | #N/A | 1899A Berjaya Times Square | 1800 Rack and subrack | BBand |  | 2024-03-07 |  | Single_2024_May_DWDM_PFSRING101/C0607P_1899A_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | PFSRING101/C0607P | DWDM-1899A | 1899A | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | #N/A | #N/A | 2024-05-09 | Wk19 | 2024-05-09 | Access - BM (CD acknowledged) | Access |  |  |  |  | 2024-02-16 |  | 2024-05-16 |  | P1 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 1016A | xD_DWDM-BRKRing_Ring58/C1103_1016A Genting Ria_0004582307100Y_00045823168326 | #N/A | 1016A Genting Ria | 1800 subrack | BBand | 2024-04-26 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.4 Pending FF and CME Planner approval | 1.4 Pending FF and CME Planner approval | 2024-06-05 | Wk23 |  | OUTDOOR | OUTDOOR | 0524: Freezed. Pending Dn. Not yet freeze in KHE. No DUID 0523: Need to freeze |  |  |  | 2024-02-16 |  | 2024-07-18 |  | P1_Z_Aug | C1103 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 1770B | xD_DWDM-BRKRing_Ring58/C1103_1770B Genting Sempah_0004582307100Y_00045823168326 | #N/A | 1770B Genting Sempah | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1770B_Completed_AC BREAKER : 32 X 3 | Single | 2023 | October | DWDM | (blank) | DWDM-1770B | 1770B | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-15 | [5 empty] | 2024-01-16 | 2024-02-15 | Y | 2024-01-17 | Wk3 | P1_Z_Aug | C1103 | IP BREAK RING | #N/A | 2024-01-17 09:35 | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 2070B | xD_DWDM-BRKRing_Ring58/C1103_2070B Gombak_0004582307100Y_00045823168326 | #N/A | 2070B Gombak | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2070B | 2070B | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-25 |  |  |  | Completed | Y |  | 2024-02-16 | Y | 2023-11-06 | Wk45 | P1_Z_Aug | C1103 | IP BREAK RING | #N/A |  | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 2833A | xD_DWDM-BRKRing_Ring58/C1103_2833A First World Hotel_0004582307100Y_00045823168326 | #N/A | 2833A First World Hotel | 1800 subrack (outdoor rack) | BBand |  |  |  | Single_2023_October_DWDM_(blank)_2833A_Completed_AC BREAKER : 32 X 1 I-BEAM = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2833A | 2833A | Completed | AC BREAKER : 32 X 1 | #N/A | #N/A | #N/A | 2024-06-06 | Wk23 |  | Access issue | OUTDOOR | 0523: Change RAD to 6/6 0520: Waiting outbound 0517: Need to freeze |  |  |  | TBC |  | 2024-07-18 |  | P1_Z_Aug | C1103 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 8709A | xD_DWDM-BRKRing_Ring58/C1103_8709A Bentong_0004582307100Y_00045823168326 | #N/A | 8709A Bentong | 1800 subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-25 |  |  |  | Completed | Y | 2024-02-16 | 2024-02-16 | Y | 2024-01-09 | Wk2 | P1_Z_Aug | C1103 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1525A | xD_DWDM-BRKRing_S313P_2_2_1525A Graha Maju_0004582304160F_00045823087420 | #N/A | 1525A Graha Maju | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1525A_Completed_DC BREAKER: 16A X 2 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1525A | 1525A | Completed | DC BREAKER: 16A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 | Pending PFS Swap | 7/2: Pending IPRan PFS Swap |  | Completed | Y | 2024-03-11 | 2024-01-19 | Y | 2024-02-07 | Wk6 | P3 | #N/A | #N/A | #N/A | 2024-02-15 09:54 |  | CME completed12/Jan |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
S406 | #N/A | #N/A | 2023 | 6442A | xD_DWDM-BRKRing_S406_6442A Senai Airport_0004582306610B_00045823162821 | #N/A | 6442A Senai Airport | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6442A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-6442A | 6442A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-06 | [5 empty] | 2024-02-23 | 2024-02-15 | Y | 2024-02-15 | Wk7 | P0 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
S406 | #N/A | #N/A | 2023 | 6576A | xD_DWDM-BRKRing_S406_6576A Jln Seelong_0004582306610B_00045823162821 | #N/A | 6576A Jln Seelong | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6576A_Completed_DC BREAKER: 63A X 2 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6576A | 6576A | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2024-02-16 |  | plan MOS TBC | 0517: F/u w/ FF (Alarm High temperature) |  |  | 2024-02-24 | 2024-02-15 | Y | 2024-02-20 | Wk8 | P0 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
S602M | 69.74% | 103% | 2023 | 6000A | xD_DWDM-BRKRing_S602M_6000A MSC JB_0004582306610B_00045823162821 | 103% | 6000A MSC JB | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-14 |  | 7/2: integrate together with S602M, SAR05, S406 [only S406 done power up] |  |  | 2024-02-14 | 2024-02-15 | 2024-02-15 | Y | 2024-02-19 | Wk8 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-15 09:54 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S602M | 69.74% | 103% | 2023 | 6369A | xD_DWDM-BRKRing_S602M_6369A Sri Saujana_0004582306610B_00045823162821 | 103% | 6369A Sri Saujana | Spare | BBand |  |  |  | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | Multiple | 2024 | May | DWDM | ST21P;S504M | DWDM-6369A | 6369A | PRPO | 1. Add Battery Bank = 6 | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 |  | Spare - Kuan Yen Request onhold | Kuan Yen Request onhold |  |  |  | 2024-01-09 | 2024-02-15 | Y | 2024-02-05 | Wk6 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-05 09:37 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S602M | 69.74% | 103% | 2023 | 6955A | xD_DWDM-BRKRing_S602M_6955A Putri Wangsa2_0004582306610B_00045823162821 | 103% | 6955A Putri Wangsa2 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6955A_Completed_DCPDB = 1 UNIT MGB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-6955A | 6955A | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-06 |  |  |  | Completed | Y | 2024-01-10 | 2024-01-17 | Y | 2024-01-08 | Wk2 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2023 | 1690A | xD_DWDM-BRKRing_SAR01_1690A BktPelandok_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1690A BktPelandok | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-22 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 | SAR01 | PE-MCR | #N/A |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A | SAR01 | IP BREAK RING
SAR04 | 78.07% | 74.54% | 2024 Q1 | 1659A | xD_DWDM-BRKRing_SAR04_1659A Bahau Tower_0004582400710C_00045824009526 | 74.54% | 1659A-MAG-001 Bahau Tower | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-18 | Wk16 | 2024-04-18 | [7 empty] | Y | 2024-04-18 | Wk16 | P0 | SAR04 | PE-MCR | #N/A | 0 | [7 empty] | 2024-04-25 | #N/A | #N/A | PFS Swap
SAR04 | 78.07% | 74.54% | 2024 Q1 | 6442A | xD_DWDM-BRKRing_SAR04_6442A Senai Airport_0004582400710C_00045824009526 | 74.54% | 6442A-MAG-001 Senai Airport | Board expansion | BBand |  | N/A | N/A | Single_2023_November_DWDM_(blank)_6442A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-6442A | 6442A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-23 | Wk17 | 2024-04-23 | [7 empty] | Y | 2024-04-23 | Wk17 | P0 | SAR04 | PE-MCR | #N/A | 0 | [7 empty] | 2024-04-25 | #N/A | #N/A | PFS Swap
SAR04 | 78.07% | 74.54% | 2024 Q1 | 6911C | xD_DWDM-BRKRing_SAR04_6911C KTM Labis_0004582400710C_00045824009526 | 74.54% | 6911C-MAG-001 KTM Labis | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-24 | Wk17 | 2024-04-24 | [7 empty] | Y | 2024-04-24 | Wk17 | P0 | SAR04 | PE-MCR | #N/A | 0 | [7 empty] | 2024-04-25 | #N/A | #N/A | PFS Swap
C0114 | 34.86% | #N/A | 2023 | 2021B | xD-DWDM_BRKRingC0114_2021B SUBANG HITECH_00045823086827 | #N/A | 2021B SUBANG HITECH | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  | Completed | Y |  | Completed | N/A | 2023-07-09 | Wk27 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-07-09 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0114 | 34.86% | #N/A | 2023 | 2631A | xD-DWDM_BRKRingC0114_2631A SAMARINDA_00045823086827 | #N/A | 2631A SAMARINDA | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  | Completed | Y |  | Completed | N/A | 2023-07-09 | Wk27 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-07-09 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0501P | 34.97% | #N/A | 2023 | 1110A | xD-DWDM_BRKRingC0501P_1110A BERJAYA INDUSTRIAL PARK_0045823085921 | #N/A | 1110A BERJAYA INDUSTRIAL PARK | 9800 Board expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | Completed |  |  |  | Completed | Y |  | Completed | Y | 2023-07-06 | Wk27 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-07-06 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0501P | 34.97% | #N/A | 2023 | 2021B | xD-DWDM_BRKRingC0501P_2021B SUBANG HITECH_0045823085921 | #N/A | 2021B SUBANG HITECH | 9800 Board expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | Completed |  |  |  | Completed | Y |  | Completed | Y | 2023-07-06 | Wk27 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-07-06 | Completed |  |  | #N/A | #N/A | IP BREAK RING
CT04 | #N/A | #N/A | 2023 | 1049B | xD-DWDM-BRKRing_1049B-002 MSC KEPONG_00045823053925 | #N/A | 1049B-002 MSC KEPONG | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | #N/A | #N/A | #N/A |  | Wk52 | 2023-09-26 |  | Plan power up 24/1 |  | Completed | Y | 2024-01-22 | 2024-01-09 | Y | 2024-01-29 | Wk5 | P1 | CT04 | IP BREAK RING | #N/A | 2024-01-29 09:52 | [8 empty] | #N/A | #N/A | #N/A
CT04 | #N/A | #N/A | 2023 | 1412A | xD-DWDM-BRKRing_1412A BKT TADUN_00045823053925 | #N/A | 1412A BKT TADUN | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 |  |  |  | Completed | Y | 2024-01-12 | 2024-01-12 | Y | 2024-01-15 | Wk3 | P1 | CT04 | IP BREAK RING | #N/A | 2024-01-15 11:00 | Reminder | [7 empty] | #N/A | #N/A | #N/A
CT04 | #N/A | #N/A | 2023 | 1413A | xD-DWDM-BRKRing_1413A KTM RAWANG_00045823053925 | #N/A | 1413A KTM RAWANG | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1413A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-1413A | 1413A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | 2024-06-11 | Wk24 |  | Access issue - CD Desmond | Casualty | 0521: Fiberail need 5 days to approved 0517: Pending fibrerail access approval |  | N/A |  | TBC |  | 2024-07-18 |  | P1 | CT04 | IP BREAK RING | #N/A |  |  | CME completed12/Jan | [6 empty] | #N/A | #N/A | #N/A
C0103 | 7.548% | #N/A | 2023 | 1049B | xD-DWDM-BRKRing_C0103_1049B Kepong_0004582304150Y_00045823087420 | #N/A | 1049B Kepong | 9800 Board Expansion | Advance |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-17 | Wk42 | P2 | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-10-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0103 | 7.548% | #N/A | 2023 | 1359A | xD-DWDM-BRKRing_C0103_1359A MutiaraSubang_0004582304150Y_00045823087420 | #N/A | 1359A MutiaraSubang | 9800 Rack with subrack | Advance |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | 1. Swap breaker DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-17 | Wk42 | P2 | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-10-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0103 | 7.548% | #N/A | 2023 | 1409A | xD-DWDM-BRKRing_C0103_1409A Damansara_0004582304150Y_00045823087420 | #N/A | 1409A Damansara | 9800 Board Expansion | Advance |  |  |  | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  | Completed | Y |  | Completed | Y | 2023-10-17 | Wk42 | P2 | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-10-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0803 | 39.99% | #N/A | 2023 | 1066A | xD-DWDM-BRKRing_C0803_1066A Sungai Choh_0004582304160F_0004582308742 | #N/A | 1066A Sungai Choh | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 | CRQ | Plan 17/1 |  | Completed | Y | 4//1/2024 | 2024-01-08 | Y | 2024-01-16 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-16 10:25 |  |  | Y | Completed | 2024-01-30 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0803 | 39.99% | #N/A | 2023 | 1070A | xD-DWDM-BRKRing_C0803_1070A Wsma LowKang_0004582304160F_0004582308742 | #N/A | 1070A Wsma LowKang | 1800 Rack and subrack | BBand |  |  |  | Single_2024_January_DWDM_(blank)_1070A_Drop_BATTERY BANK = 1 | Single | 2024 | January | DWDM | (blank) | DWDM-1070A | 1070A | Drop | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 | breaker swap | CME WIP |  |  |  | 4//1/2024 | 2024-01-08 | Y | 2024-01-19 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-19 11:08 |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0803 | 39.99% | #N/A | 2023 | 1145A | xD-DWDM-BRKRing_C0803_1145A BatangKali_0004582304160F_0004582308742 | #N/A | 1145A BatangKali | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1145A_Completed_DC BREAKER : 63A X 4 MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1145A | 1145A | Completed | DC BREAKER : 63A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 | Construction | Construction |  | Completed | Y | 4//1/2024 | 2024-01-08 | Y | 2024-01-04 | Wk1 | #N/A | #N/A | IP BREAK RING | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0803 | 39.99% | #N/A | 2023 | 1146A | xD-DWDM-BRKRing_C0803_1146A KubuBaru_0004582304160F_0004582308742 | #N/A | 1146A KubuBaru | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1146A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-1146A | 1146A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 |  |  |  | Completed | Y | 2024-01-05 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A | #N/A | IP BREAK RING | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0803 | 39.99% | #N/A | 2023 | 1701A | xD-DWDM-BRKRing_C0803_1701A Kerling Trnk_0004582304160F_0004582308742 | #N/A | 1701A Kerling Trnk | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1701A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-1701A | 1701A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-13 | WIP | Plan 17/1 |  |  |  | 2024-01-05 | 2024-01-08 | Y | 2024-01-17 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-17 09:35 |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A | #N/A | IP BREAK RING
C0803 | 39.99% | #N/A | 2023 | 2038A | xD-DWDM-BRKRing_C0803_2038A AntraGapi_0004582304160F_0004582308742 | #N/A | 2038A AntraGapi | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2024-01-09 |  |  |  | Completed | Y | 2024-01-09 | 2024-01-09 | Y | 2024-01-10 | Wk2 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-01-30 | Completed |  |  | #N/A | #N/A | IP BREAK RING
Ring58/C1103 | #N/A | #N/A | 2023 | 1015A | xD_DWDM-BRKRing_Ring58/C1103_1015A Awana Golf_0004582307100Y_00045823168326 | #N/A | 1015A Awana Golf | 1800 subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-05-09 | Wk19 | 2024-05-09 | Access issue | Access | Installation complete |  |  |  | TBC |  | 2024-05-16 |  | P1_Z_Aug | C1103 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1128A | xD_DWDM_BRKRing_CAR05_1128A Kg Ola Lempik_0004582401290A_00045824026525 | #N/A | 1128A Kg Ola Lempik | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-10 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
CT01P | 18.34% | #N/A | 2023 | 1049B | xD-DWDM-BRKRing_CT01P_1049B Kpg_000458237400E_00045823174223 | #N/A | 1049B Kpg | 1800 Rack and subrack | Bband |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-06 |  | Plan power up 24/1 |  | Completed | Y | 2024-01-26 | 2024-01-09 | Y | 2024-01-26 | Wk4 | #N/A | #N/A | #N/A | #N/A | 2024-01-29 09:52 |  |  | Y | Completed | 2024-01-31 | Completed |  |  | #N/A | #N/A | #N/A
CT01P | 18.34% | #N/A | 2023 | 1298A | xD-DWDM-BRKRing_CT01P_1298A Kpg Knit_000458237400E_00045823174223 | #N/A | 1298A Kpg Knit | 1800 Rack and subrack | Bband |  |  |  | Single_2023_November_DWDM_(blank)_1298A_Completed_DCPDB = 1 CABLE LADDER = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1298A | 1298A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  | Completed | Y | 2024-01-05 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-31 | Completed |  |  | #N/A | #N/A | #N/A
CT01P | 18.34% | #N/A | 2023 | 1309A | xD-DWDM-BRKRing_CT01P_1309A Ivory_000458237400E_00045823174223 | #N/A | 1309A Ivory | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2024-01-17 | WIP | WIP |  | Completed | Y | 2024-01-17 |  | Y | 2024-01-17 | Wk3 | #N/A | #N/A | #N/A | #N/A | 2024-01-17 09:35 |  |  | Y | Completed | 2024-01-31 | Completed |  |  | #N/A | #N/A | #N/A
CT11P | #N/A | #N/A | 2023 | 1050B | xD-DWDM-BRKRing_CT11P_1050B MAH_00045823086823 | #N/A | 1050B MAH | Decomm | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-11-14 | Wk46 | #N/A | #N/A | #N/A | #N/A |  |  |  | N/A | Completed | 2023-12-19 | Completed |  |  | #N/A | #N/A | #N/A
CT11P | #N/A | #N/A | 2023 | 1080A | xD-DWDM-BRKRing_CT11P_1080A WIT KLANG_00045823086823 | #N/A | 1080A WIT KLANG | Services only - Redeploy rack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1080A_Completed_DCPDB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1080A | 1080A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  | Completed | Y |  | 2023-10-31 | Y | 2023-11-14 | Wk46 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-12-21 | Completed |  |  | #N/A | #N/A | #N/A
CT11P | #N/A | #N/A | 2023 | 1087A | xD-DWDM-BRKRing_CT11P_1087A RANTAU PANJANG_00045823086823 | #N/A | 1087A RANTAU PANJANG | Services only - Redeploy rack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1087A_Completed_DCPDB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1087A | 1087A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 |  |  |  | Completed | Y |  | 2023-10-31 | Y | 2023-11-14 | Wk46 | #N/A | #N/A | #N/A | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-12-21 | Completed |  |  | #N/A | #N/A | #N/A
CT11P | #N/A | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_CT11P_8000A MSC KUANTAN_00045823086823 | #N/A | 8000A MSC KUANTAN | Decomm | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-11-14 | Wk46 | #N/A | #N/A | #N/A | #N/A |  |  |  | N/A | Completed | 2023-12-19 | Completed |  |  | #N/A | #N/A | #N/A
E107 | 22.89% | #N/A | 2023 | 8211A | xD-DWDM-BRKRing_E107_8211A WCY_0004582304150Y_00045823087420 | #N/A | 8211A WCY | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  | Completed | Y |  | Completed | Y | 2023-08-24 | Wk34 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E107 | 22.89% | #N/A | 2023 | 8263A | xD-DWDM-BRKRing_E107_8217A PASIR MAS_0004582304150Y_00045823087420 | #N/A | 8217A PASIR MAS | 9800 Board Expansion | FO&T |  |  |  | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | Single | 2024 | April | DWDM | E104;EAR01 N EAR03 | DWDM-8263A | 8263A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  | Completed | Y |  | Completed | Y | 2023-08-24 | Wk34 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E107 | 22.89% | #N/A | 2023 | 8217A | xD-DWDM-BRKRing_E107_8217A PG TEMBAK_0004582304150Y_00045823087420 | #N/A | 8217A PG TEMBAK | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  | Completed | Y |  | Completed | Y | 2023-08-24 | Wk34 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-24 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E110 | 58.21% | 57.48% | 2023 | 8211A | xD-DWDM-BRKRing_E110_8211A WCY_0004582304160F_0004582308742 | 57.48% | 8211A WCY | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-04 | [5 empty] | 2024-01-08 | 2024-01-08 | Y | 2024-01-15 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2023-07-06 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E110 | 58.21% | 57.48% | 2023 | 8224A | xD-DWDM-BRKRing_E110_8224A Pasir Puteh_0004582304160F_0004582308742 | 57.48% | 8224A Pasir Puteh | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-04 |  |  |  | Completed | Y | 2024-01-08 | 2024-01-08 | Y | 2024-01-15 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A |  | 9/1: pending break ring | CME completed12/Jan | Y | Completed | 2023-07-06 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E110 | 58.21% | 57.48% | 2023 | 8268A | xD-DWDM-BRKRing_E110_8268A Bachok_0004582304160F_0004582308742 | 57.48% | 8268A Bachok | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8268A_Completed_MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-8268A | 8268A | Completed | MGB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-05 |  |  |  | Completed | Y | 2024-01-08 | 2024-01-08 | Y | 2024-01-15 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A |  | 10/1: pending break ring | CME completed12/Jan | Y | Completed | 2023-07-06 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_E202_8000A MSC Kuantan_0004582304160F_0004582308742 | #N/A | 8000A MSC Kuantan | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-13 |  | 12/1: Plan next week 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-22 | 2024-01-26 | Y | 2024-01-22 | Wk4 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-22 11:43 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8023B | xD-DWDM-BRKRing_E202_8023B Balok Baru_0004582304160F_0004582308742 | #N/A | 8023B Balok Baru | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8023B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8023B | 8023B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  | 12/1: Plan next week 16/1: bring ODF panel & travel |  | Completed | Y | 2024-02-01 | 2024-01-26 | Y | 2024-02-01 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-26 09:59 |  | Huawei provide breaker | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8035A | xD-DWDM-BRKRing_E202_8035A Balok Kg Chengal_0004582304160F_0004582308742 | #N/A | 8035A Balok Kg Chengal | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8035A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 2 BATTERY RACK = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-8035A | 8035A | Completed | RECTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 |  |  |  | Completed | Y | 2024-02-02 | 2024-01-26 | Y | 2024-02-02 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-02 11:21 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8061A | xD-DWDM-BRKRing_E202_8061A Bkt Pelindung_0004582304160F_0004582308742 | #N/A | 8061A Bkt Pelindung | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8061A_Completed_DC BREAKER = 63A X 4 DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8061A | 8061A | Completed | DC BREAKER = 63A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-13 |  | 30/1: Pending power tap 1/2: Pending power tap |  |  |  | 2024-02-06 | 2024-01-26 | Y | 2024-02-06 | Wk6 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-06 09:38 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8408A | xD-DWDM-BRKRing_E202_8408A Cheneh_0004582304160F_0004582308742 | #N/A | 8408A Cheneh | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_8408A_Completed_BATTERY BANK = 2 | Single | 2023 | December | DWDM | (blank) | DWDM-8408A | 8408A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-24 |  | 29/1: Reschedule 30/1: plan 31/1, wrong site key given |  | Completed | Y | 2024-01-31 | 2024-01-26 | Y | 2024-01-31 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8434A | xD-DWDM-BRKRing_E202_8434A Felda Neram_0004582304160F_0004582308742 | #N/A | 8434A Felda Neram | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8434A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8434A | 8434A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 |  | Pending DCPDB 1/2: Pending power tap |  |  |  | 2024-02-07 | 2024-01-26 | Y | 2024-02-07 | Wk6 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8936A | xD-DWDM-BRKRing_E202_8936A Sg Karang_0004582304160F_0004582308742 | #N/A | 8936A Sg Karang | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8936A_Completed_DC BREAKER : 100A X 2 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8936A | 8936A | Completed | DC BREAKER : 100A X 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  | 30/1: Unable reach site owner |  | Completed | Y | 2024-02-15 | 2024-01-26 | Y | 2024-02-02 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-02 11:21 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E202 | 44.31% | #N/A | 2023 | 8953A | xD-DWDM-BRKRing_E202_8953A Balok Perdana_0004582304160F_0004582308742 | #N/A | 8953A Balok Perdana | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8953A_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK = 3 | Single | 2023 | September | DWDM | (blank) | DWDM-8953A | 8953A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  |  |  | Completed | Y | 2024-02-15 | 2024-01-26 | Y | 2024-02-01 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-26 09:59 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A | #N/A | IP BREAK RING
E205 | 75.08% | #N/A | 2023 | 8321A | xD-DWDM-BRKRing_E205_8321A Tabung Hji Kemaman_0004582304160F_0004582308742 | #N/A | 8321A Tabung Hji Kemaman | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_8321A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8321A | 8321A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Material relocation | EQ mapping removed |  |  |  |  | Relocate to N201 - MSC Prai (4000A) | Y | 2024-04-17 | Wk16 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E205 | 75.08% | #N/A | 2023 | 8330A | xD-DWDM-BRKRing_E205_8330A Kemuning_0004582304160F_0004582308742 | #N/A | 8330A Kemuning | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_8330A_Completed_BATTERY BANK = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8330A | 8330A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  | Material relocation | EQ mapping removed |  |  |  |  | TBC | Y | 2024-04-17 | Wk16 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E205 | 75.08% | #N/A | 2023 | 8403A | xD-DWDM-BRKRing_E205_8403A Bkt Mentok_0004582304160F_0004582308742 | #N/A | 8403A Bkt Mentok | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_E205_8403A_PRPO_Extend platform = 1 | Multiple | 2023 | September | DWDM | E205 | DWDM-8403A | 8403A | PRPO | Extend platform = 1 | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 |  | Extend platform - CME to check | OUTDOOR |  | 2024-06-14 |  |  | Relocate to 4770A | Y | 2024-04-17 | Wk16 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E205 | 75.08% | #N/A | 2023 | 8473A | xD-DWDM-BRKRing_E205_8473A FeldaSeberangTayur_0004582304160F_0004582308742 | #N/A | 8473A FeldaSeberangTayur | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8473A_Completed_DC BREAKER: 100A X 2 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8473A | 8473A | Completed | DC BREAKER: 100A X 2 | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 |  | Material relocation | OUTDOOR |  |  |  |  | Relocate to E212 - Tmn Semarak (8923B) | Y | 2024-04-17 | Wk16 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E205 | 75.08% | #N/A | 2023 | 8483A | xD-DWDM-BRKRing_E205_8483 Desa Solehah_0004582304160F_0004582308742 | #N/A | 8483 Desa Solehah | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8483A_Completed_MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-8483A | 8483A | Completed | MGB = 1 | #N/A | #N/A | #N/A | 2024-03-21 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-04-17 | Wk16 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8314A | xD-DWDM-BRKRing_E212_8314A Gong Terap_0004582304160F_0004582308742 | 107.7% | 8314A Gong Terap | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-23 |  | 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-15 | 2024-02-17 | Y | 2024-01-17 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-17 09:48 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8344A | xD-DWDM-BRKRing_E212_8344A Felda Belara_0004582304160F_0004582308742 | 107.7% | 8344A Felda Belara | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 |  | 16/1: bring ODF panel & travel 18/1: accessories boxes not found at site |  | Completed | Y | 2024-01-29 | 2024-02-17 | Y | 2024-01-29 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8350B | xD-DWDM-BRKRing_E212_8350B Kustem_0004582304160F_0004582308742 | 107.7% | 8350B Kustem | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8350B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8350B | 8350B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-15 |  | 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-30 | 2024-02-15 | Y | 2024-01-30 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-30 10:58 |  | Huawei provide breaker | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8353A | xD-DWDM-BRKRing_E212_8353A Kg Manir_0004582304160F_0004582308742 | 107.7% | 8353A Kg Manir | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8353A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8353A | 8353A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 |  |  |  | Completed | Y | 2024-02-01 | 2024-01-24 | Y | 2024-01-29 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A |  | next week |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8354A | xD-DWDM-BRKRing_E212_8354A Kusza_0004582304160F_0004582308742 | 107.7% | 8354A Kusza | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8354A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 4 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8354A | 8354A | Completed | RECTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 |  |  |  | Completed | Y | 2024-01-31 | 2024-01-29 | Y | 2024-01-31 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-26 09:59 | EB CRQ Approval |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8361A | xD-DWDM-BRKRing_E212_8361A Batu Rakit_0004582304160F_0004582308742 | 107.7% | 8361A Batu Rakit | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 |  | 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-15 | 2024-01-17 | Y | 2024-01-18 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-17 09:48 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E212 | 79.14% | 107.7% | 2023 | 8429B | xD-DWDM-BRKRing_E212_8429B B Payung2_0004582304160F_0004582308742 | 107.7% | 8429B B Payung2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8429B | 8429B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-10 |  | 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-15 | 2024-01-16 | Y | 2024-01-17 | Wk3 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-16 10:25 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E404 | 55.78% | 59.03% | 2023 | 8025A | xD-DWDM-BRKRing_E404_8025A Risda_0004582304160F_0004582308742 | 59.03% | 8025A Risda | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8025A_Completed_MGB = 1 CABLE LADDER= 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8025A | 8025A | Completed | MGB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 |  | 7/2: Pending ODF Rack |  |  |  | 2024-02-07 | 2024-02-07 | Y | 2024-02-14 | Wk7 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E404 | 55.78% | 59.03% | 2023 | 8059A | xD-DWDM-BRKRing_E404_8059A Bkt Sulai_0004582304160F_0004582308742 | 59.03% | 8059A Bkt Sulai | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-24 |  | 16/1: bring ODF panel & travel |  | Completed | Y | 2024-01-23 | 2024-01-23 | Y | 2024-01-23 | Wk4 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-23 10:39 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E404 | 55.78% | 59.03% | 2023 | 8128A | xD-DWDM-BRKRing_E404_8128A Kg Luit_0004582304160F_0004582308742 | 59.03% | 8128A Kg Luit | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8128A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8128A | 8128A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 |  | 7/2: Pending power tap |  |  |  | 2024-03-12 | 2024-02-07 | Y | 2024-02-12 | Wk7 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E404 | 55.78% | 59.03% | 2023 | 8191A | xD-DWDM-BRKRing_E404_8191A Sg Semuji_0004582304160F_0004582307060Z_0004582308742 | 59.03% | 8191A Sg Semuji | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_October_DWDM_(blank)_8191A_Completed_RECTTIFIER MODULE = 3 BATTERY BANK = 2 | Multiple | 2023 | October | DWDM | (blank) | DWDM-8191A | 8191A | Completed | RECTTIFIER MODULE = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  |  |  | Completed | Y | 2024-02-01 | 2024-01-23 | Y | 2024-02-01 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E404 | 55.78% | 59.03% | 2023 | 8513A | xD-DWDM-BRKRing_E404_8513A Senggora_0004582304160F_0004582308742 | 59.03% | 8513A Senggora | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_EAR06_8513A_PRPO_1.Add battery bank = 2 | Single | 2024 | May | DWDM | EAR06 | DWDM-8513A | 8513A | PRPO | 1.Add battery bank = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-24 |  | 16/1: bring ODF panel & travel |  | Completed | Y | 2024-02-07 | 2024-01-23 | Y | 2024-02-01 | Wk5 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E404 | 55.78% | 59.03% | 2023 | 8965A | xD-DWDM-BRKRing_E404_8965A Spg Lepar Hilir_0004582304160F_0004582308742 | 59.03% | 8965A Spg Lepar Hilir | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8965A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8965A | 8965A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 |  | 7/2: Pending power tap |  |  |  | 2024-03-12 | 2024-02-07 | Y | 2024-02-13 | Wk7 | #N/A | #N/A | IP BREAK RING | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 1475A | xD-DWDM-BRKRing_E407_1475A MSC SRI KEMBANGAN_00045823086828 | #N/A | 1475A MSC SRI KEMBANGAN | Services only | FO&T |  |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_E407_8000A MSC KUANTAN_00045823086828 | #N/A | 8000A MSC KUANTAN | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 |  |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8025A | xD-DWDM-BRKRing_E407_8025A RISDA_00045823086828 | #N/A | 8025A RISDA | Services only | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8025A_Completed_MGB = 1 CABLE LADDER= 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8025A | 8025A | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed | [6 empty] | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8046A | xD-DWDM-BRKRing_E407_8046A BANDAR INDERA MAHKOTA_00045823086828 | #N/A | 8046A BANDAR INDERA MAHKOTA | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8050A | xD-DWDM-BRKRing_E407_8050A PERMATANG BADAK_00045823086828 | #N/A | 8050A PERMATANG BADAK | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8059A | xD-DWDM-BRKRing_E407_8059A BUKIT SULAI_00045823086828 | #N/A | 8059A BUKIT SULAI | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8314A | xD-DWDM-BRKRing_E407_8314A GONG TERAP_00045823086828 | #N/A | 8314A GONG TERAP | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E407 | 24.73% | #N/A | 2023 | 8344A | xD-DWDM-BRKRing_E407_8344A FELDA BELARA_00045823086828 | #N/A | 8344A FELDA BELARA | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A | #N/A | IP BREAK RING
E408 | 20.5% | #N/A | 2023 | 8033A | xD-DWDM-BRKRing_E408_8033A Kg Pandan_0004582304150Y_00045823087420 | #N/A | 8033A Kg Pandan | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-07-21 | Wk29 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-07-21 | Remote ATP submission |  |  | #N/A | #N/A | IP BREAK RING
E408 | 20.5% | #N/A | 2023 | 8933A | xD-DWDM-BRKRing_E408_8933A Bt6 Jln Gambang_0004582304150Y_00045823087420 | #N/A | 8933A Bt6 Jln Gambang | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-07-21 | Wk29 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-07-21 | Remote ATP submission |  |  | #N/A | #N/A | IP BREAK RING
EAR02 | #N/A | #N/A | 2023 | 4000A | xD-DWDM-BRKRing_EAR02_2_4000A Prai_0004582304160E_00045823087420 | #N/A | 4000A Prai | 9800 Rack with subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | Y | 2024-01-09 | Completed | Y | 2024-01-17 | Wk3 | P0 | #N/A | #N/A | #N/A |  |  | CME completed12/Jan |  |  | 0 | 2024-03-27 |  |  | #N/A | #N/A | #N/A
EAR02 | #N/A | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_EAR02_2_8000A Kuantan_0004582304160E_00045823087420 | #N/A | 8000A Kuantan | 9800 Rack with subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-14 |  |  |  | Completed | Y |  | No PO - Design Change | Y | 2024-01-17 | Wk3 | P0 | #N/A | #N/A | #N/A | [6 empty] | 2024-03-27 |  |  | #N/A | #N/A | #N/A
EAR02 | #N/A | #N/A | 2023 | 8429B | xD-DWDM-BRKRing_EAR02_2_8429B BktPayung_0004582304160E_00045823087420 | #N/A | 8429B BktPayung | 9800 Rack with subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8429B | 8429B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A | #N/A | WK0 | #N/A |  |  |  |  | Y | 2024-01-09 | 2024-01-17 | Y | 2024-01-17 | Wk3 | P0 | #N/A | #N/A | #N/A | [5 empty] | 0 | 2024-03-27 |  |  | #N/A | #N/A | #N/A
MR20/C26 | #N/A | #N/A | 2023 | 1081A | xD-DWDM-BRKRing_MR20/C26_1081A BktLipat_0004582304160F_0004582308742 | #N/A | 1081A BktLipat | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_January_DWDM_(blank)_1081A_Completed_BATTERY BANK = 2 | Multiple | 2024 | January | DWDM | (blank) | DWDM-1081A | 1081A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 |  | Plan 24/1 |  |  |  | 2024-01-22 | 2024-02-23 | Y | 2024-01-23 | Wk4 | P1 | MR20/C26 | IP BREAK RING | #N/A | 2024-01-22 11:43 |  |  |  |  | 0 | 2024-05-15 |  |  | #N/A | #N/A | IP BREAK RING
MR20/C26 | #N/A | #N/A | 2023 | 1085A | xD-DWDM-BRKRing_MR20/C26_1085A PekanMeru_0004582304160F_0004582308742 | #N/A | 1085A PekanMeru | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-06 |  |  |  | Completed | Y |  | 2024-02-23 | Y | 2023-12-08 | Wk49 | P1 | MR20/C26 | IP BREAK RING | #N/A |  | Integrated but plan next date | completed |  |  | 0 | 2024-05-15 |  |  | #N/A | #N/A | IP BREAK RING
MR20/C26 | #N/A | #N/A | 2023 | 1093A | xD-DWDM-BRKRing_MR20/C26_1093A KianHoeHuat_0004582304160F_0004582308742 | #N/A | 1093A KianHoeHuat | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1093A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1093A | 1093A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 | [5 empty] | 2024-02-23 | 2024-02-23 | Y | 2024-02-01 | Wk5 | P1 | MR20/C26 | IP BREAK RING | #N/A | [5 empty] | 0 | 2024-05-15 |  |  | #N/A | #N/A | IP BREAK RING
MR20/C26 | #N/A | #N/A | 2023 | 1104A | xD-DWDM-BRKRing_MR20/C26_1104A SurauAlAmin_0004582304160F_0004582308742 | #N/A | 1104A SurauAlAmin | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-06 |  |  |  | Completed | Y | 2024-01-09 | 2024-02-23 | Y | 2024-01-18 | Wk3 | P1 | MR20/C26 | IP BREAK RING | #N/A |  | Integrated but plan next date | completed |  |  |  | 2024-05-15 |  |  | #N/A | #N/A | IP BREAK RING
MR20/C26 | #N/A | #N/A | 2023 | 1627B | xD-DWDM-BRKRing_MR20/C26_1627B IndahHighway_0004582304160F_0004582308742 | #N/A | 1627B IndahHighway | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1627B_Completed_DCPDB = 1 UNIT MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1627B | 1627B | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 | [5 empty] | 2024-01-08 | 2024-02-23 | Y | 2024-01-18 | Wk3 | P1 | MR20/C26 | IP BREAK RING | #N/A | 2024-01-17 09:35 | [5 empty] | 2024-05-15 |  |  | #N/A | #N/A | IP BREAK RING
N106(ii) | #N/A | #N/A | 2023 | 4085D | xD-DWDM-BRKRing_N106_4085D Kulim Hitech 2 | #N/A | 4085D Kulim Hitech2 | Services only | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4085D_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | November | DWDM | (blank) | DWDM-4085D | 4085D | Completed | No CME | #N/A | #N/A | #N/A |  | Wk52 | N/A | Invalid PO | Invalid PO |  |  | N/A |  | #N/A | N/A | 0 |  | P1 | #N/A | #N/A | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N106(ii) | #N/A | #N/A | 2023 | 4683A | xD-DWDM-BRKRing_N106_4683A Bkt Tok Alang | #N/A | 4683A Bkt Tok Alang | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3 | Single | 2024 | May | DWDM | N106+ | DWDM-4683A | 4683A | PRPO | 1. Add Battery Bank = 3 | #N/A | #N/A | #N/A |  | Wk52 | N/A | Invalid PO | Invalid PO |  |  | N/A |  | #N/A | N/A | 0 |  | P1 | #N/A | #N/A | #N/A | [5 empty] | #N/A |  |  |  | #N/A | #N/A | #N/A
N106 | 40.89% | #N/A | 2023 | 4946A | xD-DWDM-BRKRing_N106_4946A Bkt Selambau_000458237400E_00045823174223 | #N/A | 4946A Bkt Selambau | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | DROP | #N/A | #N/A | #N/A | #N/A | WK0 | #N/A |  |  |  |  | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-12-21 |  |  |  | #N/A | #N/A | MAC Swap - BR
N106 | 40.89% | #N/A | 2023 | 4966A | xD-DWDM-BRKRing_N106_4966A Kulim Hitech_000458237400E_00045823174223 | #N/A | 4966A Kulim Hitech | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-06 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-12-21 |  |  |  | #N/A | #N/A | MAC Swap - BR
N115 | 23.69% | #N/A | 2023 | 4688A | xD-DWDM-BRKRing_N115_4668A Lunas_0004582306610C_00045823162822 | #N/A | 4668A Lunas | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4688A_Completed_DCPDB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4688A | 4688A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-24 | [5 empty] | 2024-02-07 | Completed | Y | 2024-02-07 | Wk6 | #N/A | #N/A | MAC Swap - BR | #N/A | 2024-02-07 09:48 |  |  |  | Completed | 2023-12-21 |  |  |  | #N/A | #N/A | MAC Swap - BR
N115 | 23.69% | #N/A | 2023 | 4932A | xD-DWDM-BRKRing_N115_4932A Bkt Tok Acheh_0004582306610C_00045823162822 | #N/A | 4932A Bkt Tok Acheh | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4932A_Completed_BATTERY BANK = 2 | Single | 2023 | December | DWDM | (blank) | DWDM-4932A | 4932A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A | #N/A | MAC Swap - BR | #N/A |  |  |  | Y | Completed | 2023-12-21 | Completed |  |  | #N/A | #N/A | MAC Swap - BR
S201 | 31.14% | #N/A | 2023 | 1621A | xD-DWDM-BRKRing_S201_1621A Senawang_0004582304070S_00045823086826 | #N/A | 1621A Senawang | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-12-12 |  | Continue 16/1 |  | Completed | Y | 2024-01-12 | 2024-01-12 | Y | 2024-01-16 | Wk3 | P0 | #N/A | #N/A | #N/A | 2024-01-16 10:25 | [8 empty] | #N/A | #N/A | #N/A
S201 | 31.14% | #N/A | 2023 | 1760A | xD-DWDM-BRKRing_S201_1760A Mambau1_0004582304070S_00045823086826 | #N/A | 1760A Mambau1 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1760A_Completed_CABINET DISMANTLE = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1760A | 1760A | Completed | CABINET DISMANTLE = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-15 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-20 | Wk47 | P0 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
S201 | 31.14% | #N/A | 2023 | 1760A | xD-DWDM-BRKRing_S201_1760A Mambau2_0004582304070S_00045823086826 | #N/A | 1760A Mambau2 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1760A_Completed_CABINET DISMANTLE = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1760A | 1760A | Completed | CABINET DISMANTLE = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-15 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-20 | Wk47 | P0 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
S201 | 31.14% | #N/A | 2023 | 3433C | xD-DWDM-BRKRing_S201_3433C Bkt Pelandok_0004582304070S_00045823086826 | #N/A | 3433C Bkt Pelandok | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-22 | Wk47 | P0 | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
S307 | 64.45% | #N/A | 2023 | 6405A | xD-DWDM-BRKRing_S307_6405A Sri Bunian_0004582304160E_00045823087420 | #N/A | 6405A Sri Bunian | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-17 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-17 | Wk42 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 2023-10-17 |  |  |  | #N/A | #N/A | IP BREAK RING
S307 | 64.45% | #N/A | 2023 | 6502A | xD-DWDM-BRKRing_S307_6502A Nusa Perintis_0004582304160E_00045823087420 | #N/A | 6502A Nusa Perintis | 9800 SFP only | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6502A | 6502A | Completed | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-12 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-17 | Wk42 | #N/A | #N/A | IP BREAK RING | #N/A |  |  |  |  | Completed | 2023-10-17 |  |  |  | #N/A | #N/A | IP BREAK RING
S309 | 38.82% | 53.25% | 2023 | 1553A | xD-DWDM-BRKRing_S309_1553A Umbai_0004582304160F_0004582308742 | 53.25% | 1553A Umbai | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 |  | Space | Space | 0524: Umbai space issue | 2024-07-05 |  |  | Re-survey |  | 2024-07-18 |  | P3 | S309 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | IP BREAK RING
S309 | 38.82% | 53.25% | 2023 | 1556A | xD-DWDM-BRKRing_S309_1556A Merlimau_0004582304160F_0004582308742 | 53.25% | 1556A Merlimau | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_S309_1556A_PRPO_BATTERY BANK = 3 Remove battery = 1 | Multiple | 2024 | May | DWDM | S309 | DWDM-1556A | 1556A | PRPO | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 | [6 empty] | Completed | Y | 2023-11-07 | Wk45 | P3 | S309 | IP BREAK RING | #N/A |  |  |  |  | Completed | 2023-11-07 |  |  |  | #N/A | #N/A | IP BREAK RING
S309 | 38.82% | 53.25% | 2023 | 1599A | xD-DWDM-BRKRing_S309_1599A Gambir Town_0004582304160F_0004582308742 | 53.25% | 1599A Gambir Town | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_September_DWDM_(blank)_1599A_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-1599A | 1599A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-11 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-07 | Wk45 | P3 | S309 | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-11-07 |  |  |  | #N/A | #N/A | IP BREAK RING
S309 | 38.82% | 53.25% | 2023 | 2402B | xD-DWDM-BRKRing_S309_2402B Pagoh highway_0004582304160F_0004582308742 | 53.25% | 2402B Pagoh highway | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-13 |  |  |  | Completed | Y |  | Completed | Y | 2023-11-07 | Wk45 | P3 | S309 | IP BREAK RING | #N/A |  |  |  | N/A | Completed | 2023-11-07 |  |  |  | #N/A | #N/A | IP BREAK RING
S313P_2 | 61.69% | 127.3% | 2023 | 1512A | xD-DWDM-BRKRing_S313P_2_1512A BKTRAMBAI_00045823087420 | 127.3% | 1512A BKTRAMBAI | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | P1_IP_BR-Q3 | S313P_2 | IP BREAK RING | P1_IP_BR-Q3 |  |  |  |  | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S313P_2 | 61.69% | 127.3% | 2023 | 1553A | xD-DWDM-BRKRing_S313P_2_1553A UMBAI_00045823087420 | 127.3% | 1553A UMBAI | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | P1_IP_BR-Q3 | S313P_2 | IP BREAK RING | P1_IP_BR-Q3 |  |  |  |  | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S313P_2 | 61.69% | 127.3% | 2023 | 1554A | xD-DWDM-BRKRing_S313P_2_1554A RUMBIA_00045823087420 | 127.3% | 1554A RUMBIA | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | P1_IP_BR-Q3 | S313P_2 | IP BREAK RING | P1_IP_BR-Q3 |  |  |  |  | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S313P_2 | 61.69% | 127.3% | 2023 | 1621A | xD-DWDM-BRKRing_S313P_2_1621A MSC Senawang_00045823087420 | 127.3% | 1621A MSC Senawang | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | P1_IP_BR-Q3 | S313P_2 | IP BREAK RING | P1_IP_BR-Q3 |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S313P_2_2 | #N/A | #N/A | 2023 | 1533A | xD-DWDM-BRKRing_S313P_2_2_DUYONG_0004582304160F_00045823087420 | #N/A | DUYONG | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1533A_Completed_BATTERY RACK = 1 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1533A | 1533A | Completed | BATTERY RACK = 1 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 |  | 30/1: Plan 2/2 |  |  |  | 2024-02-07 | 2024-01-19 | Y | 2024-02-07 | Wk6 | P3 | #N/A | #N/A | #N/A | 2024-02-07 09:50 |  |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1554A | xD-DWDM-BRKRing_S313P_2_2_RUMBIA_0004582304160F_00045823087420 | #N/A | RUMBIA | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-10 |  |  |  | Completed | Y | 8/1/2024-9/1/2024 | 2024-01-19 | Y | 2024-01-15 | Wk3 | P3 | #N/A | #N/A | #N/A | 2024-01-15 11:00 | Reminder |  |  |  | 0 |  |  |  | #N/A | #N/A | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1553A | xD-DWDM-BRKRing_S313P_2_2_UMBAI_0004582304160F_00045823087420 | #N/A | UMBAI | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 |  | Space | Space | 0524: Umbai space issue | 2024-07-05 |  |  | Re-survey |  | 2024-07-18 |  | P3 | #N/A | #N/A | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
S313P_2 | 61.69% | 127.3% | 2023 | 2021B | xD-DWDM-BRKRing_S313P_2_2021B SBHT_00045823087420 | 127.3% | 2021B SBHT | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | P1_IP_BR-Q3 | S313P_2 | IP BREAK RING | P1_IP_BR-Q3 |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A | #N/A | IP BREAK RING
S501 | 21.55% | 52.03% | 2023 | 1591A | xD-DWDM-BRKRing_S501_1_1591A Parit Bakar_0004582304160F_0004582308742 | 52.03% | 1591A Parit Bakar | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1591A_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1591A | 1591A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-22 | Pending CME - Umbai |  |  | Completed | Y | 2024-01-24 | 2024-01-23 | Y | 2023-11-22 | Wk47 | P0 | S501 | IP BREAK RING | #N/A |  | Integrated but plan next date | completed |  |  | 0 | Replan migration - Umbai CME |  |  | #N/A | #N/A | #N/A
S501 | 21.55% | 52.03% | 2023 | 2227B | xD-DWDM-BRKRing_S501_1_1591A Sri Jeram_0004582304160F_0004582308742 | 52.03% | 1591A Sri Jeram | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_September_DWDM_(blank)_2227B_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-2227B | 2227B | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 | Pending CME - Umbai | 29/1: Do after network freeze (1st week of Feb) 30/1: Plan 1/2 1/2: Plan 2/2 |  |  |  | 2024-02-01 | 2024-02-15 | Y | 2024-02-02 | Wk5 | P0 | S501 | IP BREAK RING | #N/A | 2024-02-02 11:13 |  | WIP |  |  | 0 | Replan migration - Umbai CME |  |  | #N/A | #N/A | #N/A
S501 | 21.55% | 52.03% | 2023 | 2388B | xD-DWDM-BRKRing_S501_1_2388B Desa Muar_0004582304160F_0004582308742 | 52.03% | 2388B Desa Muar | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_September_DWDM_(blank)_2388B_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-2388B | 2388B | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-12 | Pending CME - Umbai |  |  |  |  | 2024-02-14 | 2024-02-15 | Y | 2024-02-02 | Wk5 | P0 | S501 | IP BREAK RING | #N/A | 2024-02-02 11:13 |  | Swap breaker issue |  |  | 0 | Replan migration - Umbai CME |  |  | #N/A | #N/A | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 1552A | xD-DWDM-BRKRing_SAR01_1552A TanjungBidara_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1552A TanjungBidara | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-21 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 | SAR01 | PE-MCR | #N/A |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2023 | 1554A | xD-DWDM-BRKRing_SAR01_1554A Rumbia_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1554A Rumbia | 9800 SFP only | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 | SAR01 | PE-MCR | #N/A |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2023 | 1621A | xD-DWDM-BRKRing_SAR01_1621A Senawang_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1621A Senawang | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 | SAR01 | PE-MCR | #N/A |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2023 | 1640A | xD-DWDM-BRKRing_SAR01_1640A Politenik PD_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1640A Politenik PD | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-22 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 | SAR01 | PE-MCR | #N/A |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A | SAR01 | IP BREAK RING
SAR01 | 43.19% | 78.56% | 2023 | 2021B | xD-DWDM-BRKRing_SAR01_2021B SBHT_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 2021B SBHT | 9800 SFP only | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  | Wk52 | 2023-10-19 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 | SAR01 | PE-MCR | #N/A |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A | SAR01 | IP BREAK RING
SAR03ii | #N/A | #N/A | 2023 | 2402B | xD-DWDM-BRKRing_SAR03ii_2402B PagohHighway_0004582304160E_00045823087420 | #N/A | 2402B PagohHighway | 9800 Rack with subrack | BBand |  |  |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-23 |  |  |  | Completed | Y |  | Completed | Y | 2023-12-08 | Wk49 | #N/A | #N/A | #N/A | #N/A |  | Integrated but plan next date | completed | Y | completed | 2024-01-23 | Completed |  |  | #N/A | #N/A | #N/A
SAR03iii | #N/A | #N/A | 2023 | 1554A | xD-DWDM-BRKRing_SAR03iii_1554A Rumbia_0004582304160E_00045823087420 | #N/A | 1554A Rumbia | 9800 Rack with subrack | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | #N/A | #N/A | #N/A | #N/A | WK0 | #N/A |  |  |  |  | Y |  | Completed | Y | 2023-12-08 | Wk49 | #N/A | #N/A | #N/A | #N/A |  |  | completed | Y | completed | 2024-01-23 | Completed |  |  | #N/A | #N/A | #N/A
SAR05 | #N/A | 99.18% | 2023 | 1621A | xD-DWDM-BRKRing_SAR05_1621A Senawang_0004582304160E_00045823087420 | 99.18% | 1621A Senawang | 9800 Rack with subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-15 |  |  |  | Completed | Y |  | Completed | Y | 2024-01-22 | Wk4 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | PE-MCR
SAR05 | #N/A | 99.18% | 2023 | 6000A | xD-DWDM-BRKRing_SAR05_6000A JB_0004582304160E_00045823087420 | 99.18% | 6000A JB | 9800 Rack with subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  | Wk52 | 2023-11-16 |  |  |  | Completed | Y |  | 2024-01-17 | Y | 2024-01-23 | Wk4 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | PE-MCR
SAR05 | #N/A | 99.18% | 2023 | 6083A | xD-DWDM-BRKRing_SAR05_6083A Soga_0004582304160E_00045823087420 | 99.18% | 6083A Soga | 9800 Rack with subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6083A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =3 | Single | 2023 | November | DWDM | (blank) | DWDM-6083A | 6083A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | #N/A |  | 2024-02-15 | 2024-02-15 | Y | 2024-02-01 | Wk5 | #N/A | #N/A | PE-MCR | #N/A |  |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A | #N/A | PE-MCR
| #N/A | 99.18% |  | 1195A | #N/A | 99.18% |  | site drop | N/A |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | #N/A | WK0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A |  |  |  | #N/A | #N/A | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 1085 | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 |  | 1085A Pekan Meru | Board expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-20 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | #N/A | Ring Expansion (MAG-PE) | #N/A | [9 empty] | #N/A | #N/A | PE-MCR
PFSRING101/C0607P | #N/A |  | 2023 | 1063B | xD_DWDM_BRKRing_PFSRING101/C0607_1063B_Berjya Times Square Rooftop_0004582306610C_00045823162822 |  | 1063B Berjaya Times Square Rooftop | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_PFSRING101/C0607P_1063B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | PFSRING101/C0607P | DWDM-1063B | 1063B | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A | 2024-05-24 | Wk21 | 2024-05-24 |  |  | 0528: TI done 0521: Pending DN 0517: Need to freeze // Return material due to lift breakdown | [5 empty] | 2024-06-07 |  | P1 | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0103 | 7.548% | #N/A | 2024 Q2 | 1049B | xD_DWDM_BRKRing_C0103_1049B-MCR 001 KPG_0004582400930A_00045824009023 | #N/A | 1049B-MCR 001 KPG | Board expansion | Advance |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-24 | Wk21 | 2024-05-24 |  |  | DN combined w/ xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922 | [5 empty] | 2024-06-07 |  | P2 | #N/A | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | IP BREAK RING
MCR18/C24 | #N/A | #N/A | 2023 | 1360A | xD_DWDM-BRKRing_MCR18/C24_1360B Hicom Glenmarie_0004582306610C_00045823162822 | #N/A | 1360B Hicom Glenmarie | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_(blank)_1360A_Completed_1. Swap Cabine | Multiple | 2024 | May | DWDM | (blank) | DWDM-1360A | 1360A | Completed | 1. Swap Cabine | #N/A | #N/A | #N/A |  | Wk52 | 2024-05-11 | CME - Decom | OUTDOOR | 0524: Plan to power up and int on 30/5 0517: Pending access | 2024-05-30 |  | Replan | 2024-02-12 |  | 2024-06-15 |  | P2 | MCR18/C24 | IP BREAK RING | #N/A | [5 empty] | 0 |  |  |  | #N/A | #N/A | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1475A | xD_DWDM_BRKRing_CAR05_1475A MSC MSK_0004582401290A_00045824026525 | #N/A | 1475A MSC MSK | Board expansion | BBand | N/A | N/A |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-13 | [8 empty] | 2024-05-16 |  | P1_Z_Oct | CAR05 | PE-MCR | #N/A | [8 empty] | 2024-05-23 | #N/A | #N/A | PE-MCR
CAR02-i+/CAR02-ii+ | #N/A |  | 2024 Q2_2 | 1049B | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1049B KPG_0004582401310N_00045824027823 | 23% | 1049B Kepong | board expansion | BBand | N/A |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-09 | Wk19 | 2024-05-14 | [8 empty] | 2024-05-22 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0105P | #N/A | 98.91% | 2024 Q1 | 1049B | xD_DWDM_BRKRing_C0105P_1049B MCR KPG_0004582309050Y_00045824006623 | 98.91% | 1049B-MCR-002-KPG | 1800VPRO 1 rack 4subrack | Advance |  | 2024-01-30 |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done | 2024-05-23 |  |  | Pending ES PO |  | 2024-05-22 |  | P1 | #N/A | PFS Swap | #N/A | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-10 | #N/A | #N/A | PFS Swap
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1049B | xD_DWDM_BRKRing_CAR04_1049B KPG_0004582309050Y_00045824006623 | 85.39% | 1049B MCR KPG | 98001 rack 1 subrack | BBand |  | 2024-02-13 | 2024-02-15 | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done | [5 empty] | 2024-05-22 |  | P1_Z_June | CAR04 | PE-MCR | P1_PE-MCR-Q1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A | CAR04 | PFS Swap
CT0241P | 466.7% | 103.4% | 2024 Q1 | 1197A | xD_DWDM_BRKRing_CT0241P_1197A JBA Effingham_0004582309050Y_00045824006623 | 103.4% | 1197A JBA Effingham | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_May_DWDM_CT0241P;C0417P_1197A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P | DWDM-1197A | 1197A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done | 2024-05-28 |  |  | Pending ES PO |  | 2024-05-22 |  | P1 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A | Plan RFS MAY2024 (ZTE) | Y | 2023-05-21 | #N/A | #N/A | #N/A
E209 | 67.37% | 70.37% | 2024 Q2 | 8429B | xD_DWDM_BRKRing_E209_8429B BPayung2_0004582401310P_00045824026721 | 70.37% | 8429B-MAG(M14)-001 Bpayung 2 | Board expansion | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8429B | 8429B | Drop | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done | [5 empty] | 2024-05-22 |  | P1_IP_BR-Q3 | E209 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
CAR02-i+/CAR02-ii+ | #N/A |  | 2024 Q2_2 | 2021B | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_2021B SBHT_0004582401310N_00045824027823 | 23% | 2021B Subang Hi-Tech | board expansion | BBand | N/A |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-09 | Wk19 | 2024-05-15 |  |  | 0520: TI done Installation not done - pending diagram | [5 empty] | 2024-05-22 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1359A | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | #N/A | 1359A-MAC-001 Mutiara Subang | 1800 1 rack 1subrack | Advance |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | 1. Swap breaker DC BREAKER: 63A X 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-16 | Wk20 | 2024-05-16 |  |  | 0520: TI done 0517: TI WIP // 0516: Waiting outbound | 2024-05-22 |  |  |  |  | 2024-05-22 |  | P2 | #N/A | #N/A | #N/A | 0 | [7 empty] | 2024-05-28 | #N/A | #N/A | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 2021B | xD_DWDM_BRKRing_C0147P_2021B_SBHT_0004582401280Z_45824026526 | 22% | 2021B SBHT | 1800vPro 1 Subrack | BBand | 2024-04-04 |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A | 2024-05-28 | Wk22 | 2024-05-28 | [8 empty] | 2024-06-11 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1918A | xD_DWDM_BRKRing_C0147P_1918A Damansara Intan_0004582401280Z_45824026526 | 22% | 1918A Damansara Intan | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P;CAR02-ii+ | DWDM-1918A | 1918A | PRPO | 1. Add Battery Bank = 2 | #N/A | #N/A | #N/A | 2024-05-29 | Wk22 | 2024-05-29 |  |  | MOS freezed. Pending confirmation availability of material. | [5 empty] | 2024-06-12 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1336A | xD_DWDM_BRKRing_C0147P_1336A Balai Islam TTDI_0004582401280Z_45824026526 | 22% | 1336A Balai Islam TTDI | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  |  |  | 0523: Pending survey | [5 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 2831A | xD_DWDM_BRKRing_C0147P_2831A One Utama Ph2_0004582401280Z_45824026526 | 22% | 2831A One Utama Phase 2 | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 |  |  |  | 0523: Pending suervey | [5 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1197A | xD_DWDM_BRKRing_C0147P_1197A JBA Effingham_0004582401280Z_45824026526 | 22% | 1197A JBA Effingham | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | Single_2024_May_DWDM_CT0241P;C0417P_1197A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P | DWDM-1197A | 1197A | PRPO | 1. Add Battery Bank = 2 | #N/A | #N/A | #N/A | 2024-05-30 | Wk22 | 2024-05-30 |  |  | MOS freezed. Pending confirmation availability of material. | [5 empty] | 2024-06-13 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1211A | xD_DWDM_BRKRing_C0147P_1211A KDU_0004582401280Z_45824026526 | 22% | 1211A KDU | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-05-30 | Wk22 |  |  | 2024-06-06 | 0528: Access issue. Need to replan 0527: Change date due to access not approved yet MOS freezed. Pending confirmation availability of material. | [5 empty] | 2024-06-13 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_i | #N/A | 22% | 2024 Q2 | 4966A | xD_DWDM_BRKRing_NAR01_i_4966A_Kulim Hitech_0004582401260T_45824026527 | 22% | 4966A-MAG001 Kulim Hitech | 9800M12 1 subrack | FO&T | 2024-04-04 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Submission using N106 | 1.33 FF reject/Pending resubmission from partner | 1.33 FF reject/Pending resubmission from partner | 2024-06-05 | Wk23 |  |  |  | 0527: Rescheduled due to material shortage other sitePending TSSR. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-19 |  | #N/A | NAR01_i | Ring Expansion (MAG-PE) | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_i | #N/A | 22% | 2024 Q2 | 4946A | xD_DWDM_BRKRing_NAR01_i_4946A_Bukit Selambau_0004582401260T_45824026527 | 22% | 4946A-MAG-001 Bukit Selambau | 9800M12 1 subrack | FO&T | 2024-04-04 |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | DROP | Subrack | 1.4 Pending FF and CME Planner approval | 1.6 Pending FF approval | 2024-05-12 | Wk19 |  |  |  | 0523: EB site. Need to install after calendar freeze 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-05-26 |  | #N/A | NAR01_i | Ring Expansion (MAG-PE) | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_i | #N/A | 22% | 2024 Q2 | 4992A | xD_DWDM_BRKRing_NAR01_i_4992A_Pendang_0004582401260T_45824026527 | 22% | 4992A-MAG-001 Pendang | 9800M12 1 subrack | FO&T | 2024-04-04 |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-25 | Wk26 | [9 empty] | 2024-07-18 |  | #N/A | NAR01_i | Ring Expansion (MAG-PE) | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_i | #N/A | #N/A | 2024 Q2 | 4000A | xD_DWDM_BRKRing_NAR01_i_4000A_Prai_0004582401260T_45824026527 | #N/A | 4000A-MSCPrai | Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A | 0 |  | #N/A | NAR01_i | Ring Expansion (MAG-PE) | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_i | #N/A | #N/A | 2024 Q2 | 4521A | xD_DWDM_BRKRing_NAR01_i_4521A_Msc Ipoh_0004582401260T_45824026527 | #N/A | 4521A-MSC Menglembu | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A | 0 |  | #N/A | NAR01_i | Ring Expansion (MAG-PE) | #N/A | [9 empty] | #N/A | #N/A | #N/A
E209 | 67.37% | 70.37% | 2024 Q2 | 8368A | xD_DWDM_BRKRing_E209_8368A Serating_0004582401310P_00045824026721 | 70.37% | 8368A-MAC-001 Serating | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-15 | Wk20 | 2024-05-16 |  |  | 0520: TI done | [5 empty] | 2024-05-22 |  | P1_IP_BR-Q3 | E209 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0103 (C0126) | #N/A | #N/A | 2024 Q2 | 1359A | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | #N/A | 1359A-MAC-001 Mutiara Subang | Board expansion | Advance |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-16 | Wk20 | 2024-05-16 |  |  | 0520: TI done 0517: TI WIP // 0516: Waiting outbound | 2024-05-22 |  |  |  |  | 2024-05-22 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
E301 | 75.11% | 85.02% | 2024 Q2 | 8712A | xD_DWDM_BRKRing_E301_8712A Kg Jawa Pekan_0004582401310P_00045824026721 | 85.02% | 8712A-MAC-001 Kg. Jawa Pekan | 9800M24 1 rack 2subrack | FO&T | 2024-04-05 |  |  | Multiple_2024_January_DWDM_(blank)_8712A_Completed_BATTERY BANK = 2 | Multiple | 2024 | January | DWDM | (blank) | DWDM-8712A | 8712A | Completed | BATTERY BANK = 2 | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 Pending TSSR. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-20 |  | P1_IP_BR-Q3 | E301 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
E301 | 75.11% | 85.02% | 2024 Q2 | 8088A | xD_DWDM_BRKRing_E301_8088A Sg Beto_0004582401310P_00045824026721 | 85.02% | 8088A-MAG-001 Sg. Beto | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-29 | Wk22 | 2024-05-29 |  |  | Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-12 |  | P1_IP_BR-Q3 | E301 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
E301 | 75.11% | 85.02% | 2024 Q2 | 8000A | xD_DWDM_BRKRing_E301_8000A KTNE1_0004582401310P_00045824026721 | 85.02% | 8000A-MCR-002 KTN E1 | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 | 2024-05-28 |  |  | Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-11 |  | P1_IP_BR-Q3 | E301 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 4000A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_4000A Msc Prai_0004582401310P_00045824026721 | 64% | 4000A MSC Prai | 9800M12 1subrack | FO&T | 2024-04-05 |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | #N/A | 2024 Q2 | 8000A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8000A MSC KTN_0004582401310P_00045824026721 | #N/A | 8000A MSC Kuantan | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A | 0 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8282B | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8282B Pergau_0004582401310P_00045824026721 | 64% | 8282B-MAG(M14)-001 Pergau | 9800M12 1subrack | FO&T | 2024-04-05 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8285A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8285A Bukit Bunga_0004582401310P_00045824026721 | 64% | 8285A-MAG(M14)-001 Bukit Bunga | 9800M12 1rack 1subrack | FO&T | 2024-04-05 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8288B | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8288B Panau_0004582401310P_00045824026721 | 64% | 8288B-MAG(M14)-001 Panau | 9800M12 1rack 1subrack | FO&T | 2024-04-06 |  |  | Single_2024_May_DWDM_E104;EAR01 N EAR03_8288B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 7 | Single | 2024 | May | DWDM | E104;EAR01 N EAR03 | DWDM-8288B | 8288B | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | #N/A | 2024 Q2 | 8263A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8263A Pasir Mas Town_0004582401310P_00045824026721 | #N/A | 8263A-MAG(M14)-001 Pasir Mas Town | Board expansion | FO&T |  |  |  | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | Single | 2024 | April | DWDM | E104;EAR01 N EAR03 | DWDM-8263A | 8263A | PRPO | No CME | #N/A | #N/A | #N/A | 2024-06-05 | Wk23 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-19 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | #N/A | 2024 Q2 | 8211A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8211A WCY_0004582401310P_00045824026721 | #N/A | 8211A-MAG(M8)-001 WCY | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-06-05 | Wk23 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-19 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8224A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8224A Pasir Puteh_0004582401310P_00045824026721 | 64% | 8224A-MAG(M14)-001 Pasir Puteh | 9800M12 1rack 1subrack | FO&T | 2024-04-06 |  |  | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8367A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8367A B.Kechil_0004582401310P_00045824026721 | 64% | 8367A-MAG(M14)-001 B. Kechil | 9800M12 1rack 1subrack | FO&T | 2024-04-06 |  |  | Single_2024_May_DWDM_E111;EAR01 N EAR03_8367A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | Single | 2024 | May | DWDM | E111;EAR01 N EAR03 | DWDM-8367A | 8367A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 |  |  | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 1621A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1621A SNW_0004582401310P_00045824026721 | 61% | MIP2013 1621A-MCR-001 SNW | 9800M12 1rack 1subrack | BBand | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 |  | Material not arrived yet | [7 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6000A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6000A MSC JBR_0004582401310P_00045824026721 | 61% | MIP2013 6000A-MCR-001 JBR | 9800M12 1subrack | BBand | 2024-04-22 |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 1554A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1554A Rumbia_0004582401310P_00045824026721 | 61% | 1554A-MAG(M14)-001 Rumbia | 9800M12 1subrack | BBand | 2024-04-04 |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | #N/A | #N/A | #N/A | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0523: Freezed. Pending DN | [5 empty] | 2024-06-12 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 1553A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1553A Umbai_0004582401310P_00045824026721 | 61% | 1553A-MAG(M14)-001 Umbai | 9800M12 1subrack | BBand | 2024-04-01 |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6104A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6104A Bkt Kelicap_0004582401310P_00045824026721 | 61% | 6104A-MAG(M8)-001 Bkt Kelicap | 9800M12 1rack 1subrack | BBand | 2024-04-22 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6405A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6405A Sri Bunian_0004582401310P_00045824026721 | 61% | MIP2016 6405A-MAG-001 Sri Bunian | 9800M12 1subrack | BBand | 2024-04-22 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-06-30 | Wk26 | [9 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6502A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6502A Nusa Perintis_0004582401310P_00045824026721 | 61% | 6502A-MAG-001 Nusa Perintis | 9800M12 1subrack | BBand | 2024-04-22 |  |  | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6502A | 6502A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A | 2024-07-30 | Wk31 | [9 empty] | 2024-07-18 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
SAR06 | 58.87% | 71.67% | 2024 Q2 | 6000A | xD_DWDM_BRKRing_SAR06_6000A MSC JB_0004582401310P_00045824026721 | 71.67% | 6000A-MCR-001 JBR | Board expansion | BBand | N/A | N/A |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0523: Freezed. Pending DN | [5 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 | SAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
SAR06 | 58.87% | 71.67% | 2024 Q2 | 8000A | xD_DWDM_BRKRing_SAR06_8000A KTN_0004582401310P_00045824026721 | 71.67% | 8000A-MCR-001 KTN | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-05 | Wk23 |  | Material shortage |  | 0527: Plan changed due to no team 0516: Waiting outbound // 0515: Freeze on 23/5. Need to recheck material availability | [5 empty] | 2024-06-19 |  | P1_IP_R_EXP-Q3 | SAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
SAR06 | 58.87% | 71.67% | 2024 Q2 | 6707A | xD_DWDM_BRKRing_SAR06_6707A Jambi_0004582401310P_00045824026721 | 71.67% | 6707A_MAG_001 Jambi | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-05 | Wk23 |  |  |  | 0524: Pending DN Freezed to lock material | [5 empty] | 2024-07-18 |  | P1_IP_R_EXP-Q3 | SAR06 | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q3 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
SAR04 | 78.07% | 74.54% | 2024 Q2 | 1621A | xD_DWDM_BRKRing_SAR04_1621A MSC SNW_0004582401310P_00045824026721 | 74.54% | MIP2013 1621A-MCR-001 SNW | 9800M24 1subrack | BBand | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | subrack only | 1.6 Pending CME approval | 1.6 Pending CME approval | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 0527: Material shortage. Plan arrived end of June // Freezed to lock material | [5 empty] | 2024-06-20 |  | P0 | SAR04 | PE-MCR | #N/A | [9 empty] | #N/A | #N/A | PFS Swap
SAR04 | 78.07% | 74.54% | 2024 Q2 | 6000A | xD_DWDM_BRKRing_SAR04_6000A MSC JB_0004582401310P_00045824026721 | 74.54% | MIP2013 6000A-MCR-001 JBR | Board expansion | BBand | N/A | N/A |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0523: Freezed. Pending DN | [5 empty] | 2024-07-25 |  | P0 | SAR04 | PE-MCR | #N/A | [9 empty] | #N/A | #N/A | PFS Swap
CAR11 | 52.48% | #N/A | 2024 Q2 | 8000A | xD_DWDM_BRKRing_CAR11_8000A MSC KTN_0004582401310P_00045824026721 | #N/A | MIP2013 8000A-MCR-002 KTN | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-04 | Wk23 |  |  |  | 0524: Pending DN Freezed to lock material | [5 empty] | 2024-07-25 |  | P0 | CAR11 | PE-MCR | #N/A | [9 empty] | #N/A | #N/A | PE-MCR
S305 | 57.52% | 120.3% | 2024 Q2 | 6701A | xD_DWDM_BRKRing_S305_6701A Parit Subang_0004582401310P_00045824026721 | 120.3% | 6701A-MAC-001 Parit Sulong | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S305 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S305 | 57.52% | 120.3% | 2024 Q2 | 6093A | xD_DWDM_BRKRing_S305_6093A Sri Medan_0004582401310P_00045824026721 | 120.3% | 6093A-MAC-001 Sri Medan | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Single_2024_May_DWDM_S305_6093A_PRPO_1. Add Battery Bank = 1 2. DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 3. New MGB = 1 | Single | 2024 | May | DWDM | S305 | DWDM-6093A | 6093A | PRPO | 1. Add Battery Bank = 1 | indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-30 | Wk26 |  |  |  |  | 2024-06-07 |  |  |  |  | 2024-07-25 |  | P1_IP_BR-Q3 | S305 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S305 | 57.52% | 120.3% | 2024 Q2 | 6088A | xD_DWDM_BRKRing_S305_6088A ABI_0004582401310P_00045824026721 | 120.3% | 6088A-MAC-001 ABI | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S305 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S305 | 57.52% | 120.3% | 2024 Q2 | 2402B | xD_DWDM_BRKRing_S305_2402B Pagoh Highway_0004582401310P_00045824026721 | 120.3% | 2402B-MAG(M14)-001 Pagoh Highway | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S305 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S305 | 57.52% | 120.3% | 2024 Q2 | 6104A | xD_DWDM_BRKRing_S305_6104A Bkt Kelicap_0004582401310P_00045824026721 | 120.3% | 6104A-MAG(M8)-001 Bkt Kelicap | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S305 | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6151A | xD_DWDM_BRKRing_S504M_6151A Mersing_0004582401310P_00045824026721 | 114.5% | 6151A-MAC-001 Mersing | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6166A | xD_DWDM_BRKRing_S504M_6166A Felda Nitar2_0004582401310P_00045824026721 | 114.5% | 6166A-MAC-001 Felda Nitar2 | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6160A | xD_DWDM_BRKRing_S504M_6160A Bkt Tinggi Maxis_0004582401310P_00045824026721 | 114.5% | 6160A-MAC-001 Bkt Tinggi(Maxis) | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6138A | xD_DWDM_BRKRing_S504M_6138A Kahang Maxis_0004582401310P_00045824026721 | 114.5% | 6138A-MAC-001 Kahang Maxis | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Multiple_2024_January_DWDM_(blank)_6138A_Completed_DISMANTLE CABINET = 1 | Multiple | 2024 | January | DWDM | (blank) | DWDM-6138A | 6138A | Completed | DISMANTLE CABINET = 1 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6134A | xD_DWDM_BRKRing_S504M_6134A Kluang Indst(Profina)_0004582401310P_00045824026721 | 114.5% | 6134A-MAC-001 Kluang Industry (Profina) | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6616A | xD_DWDM_BRKRing_S504M_6616A Sri Permai_0004582401310P_00045824026721 | 114.5% | 6616A-MAC-001 Sri Permai | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6369A | xD_DWDM_BRKRing_S504M_6369A Sri Saujana_0004582401310P_00045824026721 | 114.5% | 6369A-MAG-002 Sri Saujana | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | Multiple | 2024 | May | DWDM | ST21P;S504M | DWDM-6369A | 6369A | PRPO | 1. Add Battery Bank = 6 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-30 | Wk26 |  |  |  |  | 2024-06-07 |  |  |  |  | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
S504M | 55.81% | 114.5% | 2024 Q2 | 6126A | xD_DWDM_BRKRing_S504M_6126A KTM Kluang_0004582401310P_00045824026721 | 114.5% | 6126A-MAG(M8)-001 KTM Kluang | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q3 | S504M | IP BREAK RING | P1_IP_BR-Q3 | [9 empty] | #N/A | #N/A | IP BREAK RING
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4938A | xD_DWDM_BRKRing_NAR01_ii_4938A_Tmn Orkid_0004582401280Y_00045824026722 | #N/A | 4938A-MAG001 Taman Orkid | Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-20 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4660A | xD_DWDM_BRKRing_NAR01_ii_4660A KTM Alor Star_0004582401280Y_00045824026722 | #N/A | 4660A-MAG-001 KTM Alor Setar | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-20 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4998A | xD_DWDM_BRKRing_NAR01_ii_4998A Air Itam Kedah_0004582401280Y_00045824026722 | #N/A | 4998A-MAG-001 Air Itam Kedah | Board expansion | FO&T |  |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-20 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4606A | xD_DWDM_BRKRing_NAR01_ii_4606A Padang Besar_0004582401280Y_00045824026722 | #N/A | 4606A-MAG(M8)- 001 Padang Besar | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-20 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
CT04 | #N/A | #N/A | 2024 Q2 | 1049B | xD_DWDM_BRKRing_CT04_1049B KPG_0004582401280Y_00045824026722 | #N/A | 1049B-MCR 001 KPG | 1800vPro 2 subrack | BBand | 2024-04-17 |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-30 | Wk26 |  | Material on hold - Sean |  |  | 2024-05-23 |  |  |  |  | 2024-07-25 |  | #N/A | CT04 | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
CT04 | #N/A | #N/A | 2024 Q2 | 1413A | xD_DWDM_BRKRing_CT04_1413A KTM Rawang_0004582401280Y_00045824026722 | #N/A | 1413A-MAC-001 KTM Rawang | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | Single_2023_October_DWDM_(blank)_1413A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-1413A | 1413A | Completed | DC BREAKER: 63 A X 4 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  | Material on hold - Sean | [7 empty] | 2024-07-25 |  | #N/A | CT04 | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
CT04 | #N/A | #N/A | 2024 Q2 | 1412A | xD_DWDM_BRKRing_CT04_1412 Bkt Tadun_0004582401280Y_00045824026722 | #N/A | 1412A-MAC-001 Bkt Tadun | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  | Material on hold - Sean | [7 empty] | 2024-07-25 |  | #N/A | CT04 | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
MAC RING 6/C09+ | #N/A | 29% | 2024 Q2 | 2021B | xD_DWDM_BRKRing_MAC RING 6/C09+_2021B SBHT_0004582401280Y_00045824026722 | 29% | 2021B-MCR 001 SHT | 1800vPro 1rack 1subrack | BBand | 2024-04-04 |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-30 | Wk26 | [9 empty] | 2024-07-25 |  | #N/A | MAC RING 6/C09+ | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
MAC RING 6/C09+ | #N/A | 29% | 2024 Q2 | 1192A | xD_DWDM_BRKRing_MAC RING 6/C09+_1192A Subang New Village_0004582401280Y_00045824026722 | 29% | 1192A-MAC 001 Subang New Village | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor (delivery require Crane) | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-30 | Wk26 |  |  |  | 0524: Sharing rack with Advance. Need to f/u w/ Advance (need to recheck) Not freeze in KHE | [5 empty] | 2024-07-25 |  | #N/A | MAC RING 6/C09+ | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
MAC RING 6/C09+ | #N/A | 29% | 2024 Q2 | 1230A | xD_DWDM_BRKRing_MAC RING 6/C09+_1230A P Indus Sg Buloh_0004582401280Y_00045824026722 | 29% | 1230A-MAC 001 P indus Sg Buloh | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | Single_2024_May_DWDM_MAC RING 6/C09+_1230A_PRPO_1. Add Battery Bank = 2 2. Swap breaker DC BREAKER: 63A X 4 | Single | 2024 | May | DWDM | MAC RING 6/C09+ | DWDM-1230A | 1230A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-30 | Wk26 |  |  |  | 0523: CME need to decom rack MOS freezed. Pending confirmation availability of material. | 2024-06-07 |  |  |  |  | 2024-07-25 |  | #N/A | MAC RING 6/C09+ | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4952B | xD_DWDM_BRKRing_N401_4952B Selama_0004582401280Y_00045824026722 | 52% | 4952B-MAG 001 Selama | 1800vPro 1rack 1subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-28 | Wk22 | 2024-05-28 |  |  | MOS freezed. Pending confirmation availability of material. | [5 empty] | 2024-06-11 |  | #N/A | N401 | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4000A | xD_DWDM_BRKRing_N401_4000A MSC Prai_0004582401280Y_00045824026722 | 52% | 4000A-MCR 002 PRI | 1800vPro 1subrack | FO&T | 2024-04-17 |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | subrack only | 1.11 HW TSSR reject/Pending resubmission from partner | 1.6 Pending FF approval | 2024-05-12 | Wk19 | [9 empty] | 2024-07-25 |  | #N/A | N401 | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4686B | xD_DWDM_BRKRing_N401_4684B Terap_0004582401280Y_00045824026722 | 52% | 4686B-MAC-001 Terap | 1800vPro 1rack 1subrack | FO&T |  |  |  | Multiple_2023_December_DWDM_(blank)_4686B_Completed_DC BREAKER: 63 A X 4 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4686B | 4686B | Completed | DC BREAKER: 63 A X 4 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN // 0515: Need 4WD |  |  | 2024-06-11 |  |  | 2024-06-11 |  | #N/A | N401 | IP BREAK RING | #N/A | [9 empty] | YES | #N/A | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4965A | xD_DWDM_BRKRing_N401_4965A Politeknik Kulim_0004582401280Y_00045824026722 | 52% | 4965A-MAC-001 Politeknik Kulim | 1800vPro 1rack 1subrack | FO&T |  |  |  | Multiple_2023_December_DWDM_(blank)_4965A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4965A | 4965A | Completed | BATTERY BANK = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN // 0515: Need 4WD |  |  | 2024-06-12 |  |  | 2024-06-12 |  | #N/A | N401 | IP BREAK RING | #N/A | [9 empty] | YES | #N/A | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4689A | xD_DWDM_BRKRing_N401_4689A Tmn Desa Impian_0004582401280Y_00045824026722 | 52% | 4689A-MAC 001 Tmn Desa Impian | 1800vPro 1rack 1subrack | FO&T |  |  |  | Multiple_2023_December_DWDM_(blank)_4689A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4689A | 4689A | Completed | BATTERY BANK = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok |  |  | 2024-06-12 |  |  | 2024-06-12 |  | #N/A | N401 | IP BREAK RING | #N/A | [9 empty] | YES | #N/A | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4118A | xD_DWDM_BRKRing_N401_4118A Machang Bubuk2_0004582401280Y_00045824026722 | 52% | 4118A-MAC 001 Machang Bubuk 2 | 1800vPro 1rack 1subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4118A_Completed_DCPDB = 1 | Single | 2023 | December | DWDM | (blank) | DWDM-4118A | 4118A | Completed | DCPDB = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 | 2024-05-30 |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok |  |  | 2024-06-13 |  |  | 2024-06-13 |  | #N/A | N401 | IP BREAK RING | #N/A | [9 empty] | YES | #N/A | #N/A
CT0241P | 466.7% | 103.4% | 2024 Q1 | 1211A | xD_DWDM_BRKRing_CT0241P_1211A KDU_0004582309050Y_00045824006623 | 103.4% | 1211A KDU | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-17 | Wk20 | 2024-05-17 |  |  | 0520: TI done 0517: TI WIP // 0516: Waiting outbound |  |  |  | Pending ES PO |  | 2024-05-22 |  | P1 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A | Plan RFS MAY2024 (ZTE) | Y | 2023-05-21 | #N/A | #N/A | #N/A
N407 | 51.3% | 53% | 2024 Q2 | 4493A | xD_DWDM-BRKRing_N407_4493A KTM Ipoh_0004582401300R_00045824026922 | 53% | 4493A KTM Ipoh | 1800 Vpro 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending CME approval | 2024-06-27 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q1 | N407 | IP BREAK RING | P1_IP_BR-Q1 | [9 empty] | #N/A | #N/A | IP BREAK RING
N407 | 51.3% | 53% | 2024 Q2 | 4432A | xD_DWDM-BRKRing_N407_4432A KTM Sg Siput_0004582401300R_00045824026922 | 53% | 4432A KTM SG SIPUT | 1800 Vpro 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-31 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-14 |  | P1_IP_BR-Q1 | N407 | IP BREAK RING | P1_IP_BR-Q1 | [9 empty] | #N/A | #N/A | IP BREAK RING
N407 | 51.3% | 53% | 2024 Q2 | 4515A | xD_DWDM-BRKRing_N407_4515A Tg Rambutan_0004582401300R_00045824026922 | 53% | 4515A TG RAMBUTAN | 1800 Vpro 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-28 | Wk26 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q1 | N407 | IP BREAK RING | P1_IP_BR-Q1 | [9 empty] | #N/A | #N/A | IP BREAK RING
N407 | 51.3% | 53% | 2024 Q2 | 4498A | xD_DWDM-BRKRing_N407_4498A Lap Tambun1 N 2_0004582401300R_00045824026922 | 53% | 4498A LAP Tambun 1&2 | 1800 Vpro 1 subrack | FO&T | 2024-04-19 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-05-12 | Wk19 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q1 | N407 | IP BREAK RING | P1_IP_BR-Q1 | [9 empty] | #N/A | #N/A | IP BREAK RING
N407 | 51.3% | 53% | 2024 Q2 | 4541A | xD_DWDM-BRKRing_N407_4541A Bercham Industry_0004582401300R_00045824026922 | 53% | 4541A Bercham Industry | 1800 Vpro 1 subrack | FO&T | 2024-04-19 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-05-12 | Wk19 | [9 empty] | 2024-07-25 |  | P1_IP_BR-Q1 | N407 | IP BREAK RING | P1_IP_BR-Q1 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0103 | 7.548% | 23% | 2024 Q2_2 | 1049B | xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922 | 23% | 1049B-MCR 001 KPG | 1800 Vpro 1 subrack | Advance | 2024-04-15 |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-24 | Wk21 | 2024-05-24 |  |  | 0523: Partial DN. Need to raise 2nd to outbound SFP | 2024-05-23 |  |  |  |  | 2024-06-07 |  | P2 | #N/A | IP BREAK RING | #N/A | [9 empty] | #N/A | #N/A | IP BREAK RING
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 4000A | xD_DWDM-BRKRing_NAR02_ii+_4000A MSC Prai_0004582401310N_00045824027823 |  | 4000A MSC Prai | board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A | 0 |  | P1_IP_R_EXP-Q2 | NAR02_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 8000A | xD_DWDM-BRKRing_NAR02_ii+_8000A MSC KTN_0004582401310N_00045824027823 |  | 8000A MSC Kuantan | board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-11 | Wk24 |  |  |  | 0527: Material shortage. Taregt inbound 30/5 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-06-25 |  | P1_IP_R_EXP-Q2 | NAR02_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 4985A | xD_DWDM-BRKRing_NAR02_ii+_4985A Baling Town_0004582401310N_00045824027823 |  | 4985A-MAG-001 Baling Town | board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4985A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =2 | Single | 2023 | November | DWDM | (blank) | DWDM-4985A | 4985A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0524: Waiting outbound 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | [5 empty] | 2024-06-11 |  | P1_IP_R_EXP-Q2 | NAR02_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 8282B | xD_DWDM-BRKRing_NAR02_ii+_8282B Pergau_0004582401310N_00045824027823 |  | 8282B-MAG(M14)-001 Pergau | board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-26 | Wk26 |  |  |  | 0527: Material shortage. Taregt inbound 30/5 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [5 empty] | 2024-07-10 |  | P1_IP_R_EXP-Q2 | NAR02_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1207A | xD_DWDM-BRKRing_C0103_1207A Sg Buloh New Village_0004582400320X_00045824009023 | #N/A | 1207A-MAC-001 Sg Buloh New Village | 1800 1 rack 1subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.6 Pending CME approval | 1.7 TSSR Approved | 2024-05-17 | Wk20 | 2024-05-17 |  |  | 0520: TI done 0517: Waiting outbound // 0516: Pending TSSR approval. DN issued (Waiting outbound) | [5 empty] | 2024-05-22 |  | P2 | #N/A | #N/A | #N/A | 0 | [7 empty] | 2024-05-28 | #N/A | #N/A | #N/A
CT0241P | 466.7% | 103.4% | 2024 Q1 | 1918A | xD_DWDM_BRKRing_CT0241P_1918A Damansara Intan_0004582309050Y_00045824006623 | 103.4% | 1918A - Damansara Intan | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P;CAR02-ii+ | DWDM-1918A | 1918A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-23 | Wk21 | 2024-05-23 |  |  | 0528: TI done 0521: RAD change to 23/5 due to system issue . Rescheduled 0520: RAD changed to 21/5 0517: Need to change RAD to 21/5 0516: Waiting outbound | 2024-05-28 |  |  | Pending ES PO |  | 2024-05-22 |  | P1 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A | Plan RFS MAY2024 (ZTE) | Y | 2023-05-21 | #N/A | #N/A | #N/A
CAR02-i+/CAR02-ii+ | #N/A | 34% | 2024 Q2_2 | 1253A | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1253A Plaza Pengkalan_0004582401310N_00045824027823 | 34% | 1253A-MAG(M14)-001 Plaza Pengkalan | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | 0 | 1.4 Pending FF and CME Planner approval | 1.6 Pending FF approval | 2024-06-04 | Wk23 |  |  |  | 0524: Pending DN | [5 empty] | 2024-07-25 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
CAR02-i+/CAR02-ii+ | #N/A | 34% | 2024 Q2_2 | 1851A | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1851A KL Plaza2_0004582401310N_00045824027823 | 34% | 1851A-MAG(M14)-001 KL Plaza 2 | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-05 | Wk23 |  |  |  | 0523: Freezed. Pending DN | 2024-06-07 |  |  |  |  | 2024-08-08 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
CAR02-i+/CAR02-ii+ | #N/A | 34% | 2024 Q2_2 | 1859A | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 34% | 1859A-MAG(M14)-001 Midvalleycas | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4 | Single | 2024 | May | DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | DWDM-1859A | 1859A | PRPO | 1.Add modules = 2 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-30 | Wk26 |  |  |  | 0528: Material shortage. Target inbound end of june 0524: Pending Advance integrate to add subrack. Freezed. Pending DN. (Need to recheck CME readiness) | [5 empty] | 2024-08-08 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
CAR02-ii+ | #N/A | 22% | 2024 Q2_2 | 1918A | xD_DWDM-BRKRing_CAR02-ii+_1918A Damansara Intan_0004582401310N_00045824027823 | 22% | 1918A-MAG(M14)-001 Damansara Intan | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P;CAR02-ii+ | DWDM-1918A | 1918A | PRPO | 1. Add Battery Bank = 2 | Existing | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-06 | Wk23 |  |  |  | 0527: Material shortage. Target inbound 5/6 MOS freezed. Pending confirmation availability of material. | 2024-05-28 |  |  |  |  | 2024-06-20 |  | P1_IP_R_EXP-Q2 | CAR02-ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
CAR02-ii+ | #N/A | 22% | 2024 Q2_2 | 1172A | xD_DWDM-BRKRing_CAR02-ii+_1172A Glomac_0004582401310N_00045824027823 | 22% | 1172A-MAG(M14)-001 Glomac | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2023_October_DWDM_(blank)_1172A_Completed_DC BREAKER : 63A X 4 MGB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1172A | 1172A | Completed | DC BREAKER : 63A X 4 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | CAR02-ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4000A | xD_DWDM-BRKRing_NAR01_iii+_4000A MSC Prai_0004582401310N_00045824027823 | 76% | 4000A MSC Prai | 9800M12 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | 0 | 1.11 HW TSSR reject/Pending resubmission from partner | 1.6 Pending FF approval | 2024-05-12 | Wk19 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | NAR01_iii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4493A | xD_DWDM-BRKRing_NAR01_iii+_4493A KTM Ipoh_0004582401310N_00045824027823 | 76% | 4493A KTM IPOH | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending CME approval | 2024-06-27 | Wk26 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | NAR01_iii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4606A | xD_DWDM-BRKRing_NAR01_iii+_4606A Padang Besar_0004582401310N_00045824027823 | 76% | 4606A-MAG(M8)-001 Padang Besar | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.11 HW TSSR reject/Pending resubmission from partner | 1.6 Pending FF approval | 2024-06-28 | Wk26 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | NAR01_iii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4995A | xD_DWDM-BRKRing_NAR01_iii+_4995A UUM HW_0004582401310N_00045824027823 | 76% | 4995A-MAG(M14)-001 UUM Highway | 9800M12 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-11 | Wk24 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | NAR01_iii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4992A | xD_DWDM-BRKRing_NAR01_iii+_4992A Pendang_0004582401310N_00045824027823 | 76% | 4992A-MAG(M14)-001 Pendang | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-11 | Wk24 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | NAR01_iii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR04_ii+ | #N/A |  | 2024 Q2_2 | 4521A | xD_DWDM-BRKRing_NAR04_ii+_4521A Ipoh_0004582401310N_00045824027823 |  | 4521A - IPOH | board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A | 0 |  | P1_IP_R_EXP-Q2 | NAR04_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR04_ii+ | #N/A | 52% | 2024 Q2_2 | 4455A | xD_DWDM-BRKRing_NAR04_ii+_4455A KTM Taiping_0004582401310N_00045824027823 | 52% | 4455A-MAG(M14)-001 KTM Taiping | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-06-11 | Wk24 | [9 empty] | 2024-08-08 |  | P1_IP_R_EXP-Q2 | NAR04_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
NAR04_ii+ | #N/A | 52% | 2024 Q2_2 | 4432A | xD_DWDM-BRKRing_NAR04_ii+_4432A KTM Sungai Siput_0004582401310N_00045824027823 | 52% | 4432A-MAG(M14)-001 KTM Sungai Siput | 9800M12 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-11 | Wk24 |  |  |  | 0527: Material shortage. Target inbound 5/6 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN | [5 empty] | 2024-06-25 |  | P1_IP_R_EXP-Q2 | NAR04_ii+ | Ring Expansion (MAG-PE) | P1_IP_R_EXP-Q2 | [9 empty] | #N/A | #N/A | Ring Expansion (MAG-PE)
C0211+ | #N/A | 30% | 2024 Q2_2 | 2888A | xD_DWDM-BRKRing_C0211+_2888A Plaza Central_0004582401310N_00045824027823 | 30% | 2888A-MAC-001 Plaza Central | 9800M12 1 subrack | BBand | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  |  |  | 0517: Pending survey. Access issue to survey | [5 empty] | 2024-08-08 |  | P1_IP_BR-Q2 | C0211+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
1063B/AREA 154/C0211+/C0515+ | #N/A | 65% | 2024 Q2_2 | 1475A | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1475A SKB_0004582401310N_00045824027823 | 65% | 1475A SKB | 1800vPro 1rack 2 subrack | BBand | 2024-04-17 |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | 1.ODF Rack (Glass Door) | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-30 | Wk26 | [9 empty] | 2024-08-08 |  | P1_Z_Jul | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A | 65% | 2024 Q2_2 | 1851A | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1851A KL Plaza2_0004582401310N_00045824027823 | 65% | 1851A-MAG(M14)-001 KL Plaza 2 | 1800vPro 1 subrack | BBand | 2024-04-16 |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-30 | Wk26 |  |  |  |  | 2024-06-07 |  |  |  |  | 2024-08-08 |  | P1_Z_Jul | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A |  | 2024 Q2_2 | 1246A | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1246A Berjaya Plaza_0004582401310N_00045824027823 |  | BERJAYA PLAZA 1246A | board expansion | BBand | N/A |  |  | Single_2023_November_DWDM_(blank)_1246A_Completed_DC BREAKER: 63 A X 4 POLE RELOCATE = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1246A | 1246A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0516: Pending DN | [5 empty] | 2024-06-12 |  | P1_Z_Jul | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A |  | 2024 Q2_2 | 1063B | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1063B Berjaya Times Square_0004582401310N_00045824027823 |  | Berjaya Time Square (Tx) 1063B | board expansion | BBand | N/A |  |  | Single_2024_May_DWDM_PFSRING101/C0607P_1063B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | PFSRING101/C0607P | DWDM-1063B | 1063B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-24 | Wk21 | 2024-05-24 |  |  | 0516: Waiting outbound | [5 empty] | 2024-06-07 |  | P1_Z_Jul | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
AREA 154/MAC Ring 15/ C21+ | #N/A | 65% | 2024 Q2_2 | 1458A | xD_DWDM-BRKRing_AREA 154/MAC Ring 15/ C21+_1458A Endah Parade_0004582401310N_00045824027823 | 65% | 1458A-MAG-001 Endah Parade | 1800vPro 1rack 2 subrack | BBand | 2024-04-17 |  |  | Single_2024_January_DWDM_(blank)_1458A_Completed_BATTERY BANK = 1 | Single | 2024 | January | DWDM | (blank) | DWDM-1458A | 1458A | Completed | BATTERY BANK = 1 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-08-08 |  | P1_Z_Jul | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
AREA 154/MAC Ring 15/ C21+ | #N/A | 65% | 2024 Q2_2 | 1855B | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1855B TPM_0004582401310N_00045824027823 | 65% | 1855B-MAC-001 TPM (AS) | 1800vPro 1rack 2 subrack | BBand | 2024-04-17 |  |  | Multiple_2023_December_DWDM_(blank)_1855B_Completed_DCPDB = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-1855B | 1855B | Completed | DCPDB = 1 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 | [9 empty] | 2024-08-08 |  | P1_Z_Jul | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
C0211+ | #N/A | 30% | 2024 Q2_2 | 1859A | xD_DWDM-BRKRing_C0211+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 30% | 1859A-MAG(M14)-001 Midvalleycas | 1800vPro 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4 | Single | 2024 | May | DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | DWDM-1859A | 1859A | PRPO | 1.Add modules = 2 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-30 | Wk22 | 2024-05-30 |  |  | 0524: Freezed. Pending DN | 2024-06-07 |  |  |  |  | 2024-08-08 |  | P1_IP_BR-Q2 | C0211+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0515+ | #N/A | 54% | 2024 Q2_2 | 1039A | xD_DWDM-BRKRing_C0515+_1039A Cheras Jaya_0004582401310N_00045824027823 | 54% | 1039A-MAG(M14)-001 Cheras Jaya | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-30 | Wk26 |  |  |  | Survey done | [5 empty] | 2024-08-08 |  | P1_IP_BR-Q2 | C0515+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0515+ | #N/A | 54% | 2024 Q2_2 | 2448A | xD_DWDM-BRKRing_C0515+_2448A Asmah Tower_0004582401310N_00045824027823 | 54% | 2448A-MAC-001 Asmah Tower | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  |  |  | Survey done | [5 empty] | 2024-08-08 |  | P1_IP_BR-Q2 | C0515+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0515+ | #N/A | 54% | 2024 Q2_2 | 2424A | xD_DWDM-BRKRing_C0515+_2424A PUAS Tmn Tun Perak_0004582401310N_00045824027823 | 54% | 2424A-MAC-001 PUAS Tmn Tun Perak | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  |  |  | Survey done | [5 empty] | 2024-08-08 |  | P1_IP_BR-Q2 | C0515+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0515+ | #N/A | 54% | 2024 Q2_2 | 2024A | xD_DWDM-BRKRing_C0515+_2024A Bdr Makhota Cheras_0004582401310N_00045824027823 | 54% | 2024A-MAC-001 Bdr Mahkota Cheras | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  |  |  | Survey done | [5 empty] | 2024-08-08 |  | P1_IP_BR-Q2 | C0515+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
C0515+ | #N/A | 54% | 2024 Q2_2 | 1902B | xD_DWDM-BRKRing_C0515+_1902B Bdr Sg Long3_0004582401310N_00045824027823 | 54% | 1902B-MAC-001 Bdr Sg Long 3 | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-30 | Wk26 |  |  |  | Survey done | [5 empty] | 2024-08-08 |  | P1_IP_BR-Q2 | C0515+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
MAC Ring 15/C21+ | #N/A |  | 2024 Q2_2 | 1745A | xD_DWDM-BRKRing_MAC Ring 15/C21+_1745A Baitumal_0004582401310N_00045824027823 |  | 1745A-MAG(M14)-001 Baitumal | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-30 | Wk26 |  |  |  |  | 2024-06-21 |  |  |  |  | 2024-08-08 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
MAC Ring 15/C21+ | #N/A |  | 2024 Q2_2 | 2502A | xD_DWDM-BRKRing_MAC Ring 15/C21+_2502A Bdar Tun Razak_0004582401310N_00045824027823 |  | 2502A-MAC-001 B'dar Tun Razak | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-07-30 | Wk31 | [9 empty] | 2024-08-15 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
MAC Ring 15/C21+ | #N/A |  | 2024 Q2_2 | 1974A | xD_DWDM-BRKRing_MAC Ring 15/C21+_1974A Jln Sg Besi_0004582401310N_00045824027823 |  | MIP2013 1974A-MAC-001 Jln Sg Besi | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-07-30 | Wk31 | [9 empty] | 2024-08-15 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
N104+ | #N/A | 42% | 2024 Q2_2 | 4995A | xD_DWDM-BRKRing_N104+_4995A UUMHW_0004582401310N_00045824027823 | 42% | 4995A-MAG-001 UUM Highway | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-25 | Wk26 |  |  |  | 0521: Pending TSSR approval | [5 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N104+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N104+ | #N/A | 42% | 2024 Q2_2 | 4992A | xD_DWDM-BRKRing_N104+_4992A Pendang_0004582401310N_00045824027823 | 42% | 4992A-MAG(M14)-001 Pendang | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | Outdoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 | 2024-05-30 |  |  | 0524: Waiitng outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Not freeze in KHE due to no DUID | [5 empty] | 2024-06-13 |  | P1_IP_BR-Q2 | N104+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N104+ | #N/A | 42% | 2024 Q2_2 | 4991A | xD_DWDM-BRKRing_N104+_4991A UUM_0004582401310N_00045824027823 | 42% | 4991A-MAC-001 UUM | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+_4991A_PRPO_1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 4. Add Module = 2 | Single | 2024 | May | DWDM | N104+ | DWDM-4991A | 4991A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 | 2024-05-29 |  |  | MOS freezed. Pending confirmation availability of material. | 2024-06-04 |  | 2024-06-12 |  |  | 2024-06-12 |  | P1_IP_BR-Q2 | N104+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | YES | #N/A | IP BREAK RING
N104+ | #N/A | 42% | 2024 Q2_2 | 4672A | xD_DWDM-BRKRing_N104+_4672A Changloon_0004582401310N_00045824027823 | 42% | 4672A-MAC-001 Changloon | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+_4672A_PRPO_1. New DCDPB =1 (Require 63A x 4 DC breaker) 2. New MGB = 1 | Single | 2024 | May | DWDM | N104+ | DWDM-4672A | 4672A | PRPO | 1. New DCDPB =1 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 | 2024-05-29 |  |  | 0524: Waiting outbound MOS freezed. Pending confirmation availability of material. | 2024-06-04 |  |  |  |  | 2024-06-12 |  | P1_IP_BR-Q2 | N104+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N104+ | #N/A | 42% | 2024 Q2_2 | 4665A | xD_DWDM-BRKRing_N104+_4665A Jitra_0004582401310N_00045824027823 | 42% | 4665A-MAC-001 Jitra | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+_4665A_PRPO_1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 | Single | 2024 | May | DWDM | N104+ | DWDM-4665A | 4665A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 | 2024-05-30 |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN | 2024-06-04 |  |  |  |  | 2024-06-13 |  | P1_IP_BR-Q2 | N104+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N107+ | #N/A | 38% | 2024 Q2_2 | 4998A | xD_DWDM-BRKRing_N107+_4998A Air Itam Kedah_0004582401310N_00045824027823 | 38% | 4998A-MAG(M14)-001 Air Itam Kedah | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | 1. Add Battery Bank = 1 | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-28 | Wk22 | 2024-05-28 |  |  | 0524: Waiting outbound 0521: Material shortage. Need to change to next week 0516: Waiting outbound. 0515:Plan after 21/5. Freezed. Pending DN | 2024-06-07 |  |  |  |  | 2024-06-11 |  | P1_Z_Oct | N107+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N107+ | #N/A | 38% | 2024 Q2_2 | 4606A | xD_DWDM-BRKRing_N107+_4606A Padang Besar_0004582401310N_00045824027823 | 38% | 4606A-MAG(M8)-001 Padang Besar | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.11 HW TSSR reject/Pending resubmission from partner | 1.6 Pending FF approval | 2024-06-28 | Wk26 | [9 empty] | 2024-08-15 |  | P1_Z_Oct | N107+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N107+ | #N/A | 38% | 2024 Q2_2 | 4604A | xD_DWDM-BRKRing_N107+_4604A Kuala Perlis_0004582401310N_00045824027823 | 38% | 4604A-MAC-001 Kuala Perlis(Trunk) | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-26 | Wk26 | [9 empty] | 2024-08-15 |  | P1_Z_Oct | N107+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N107+ | #N/A | 38% | 2024 Q2_2 | 4601A | xD_DWDM-BRKRing_N107+_4601A Federal Kangsar_0004582401310N_00045824027823 | 38% | 4601A-MAC-001 Federal Kangar | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-27 | Wk26 | [9 empty] | 2024-08-15 |  | P1_Z_Oct | N107+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N107+ | #N/A | 38% | 2024 Q2_2 | 4612A | xD_DWDM-BRKRing_N107+_4612A Jln Kaki Bkt_0004582401310N_00045824027823 | 38% | 4612A-MAC-001 Jln Kaki Bkt | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-27 | Wk26 | [9 empty] | 2024-08-15 |  | P1_Z_Oct | N107+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N107+ | #N/A | 38% | 2024 Q2_2 | 4613A | xD_DWDM-BRKRing_N107+_4613A Taman Bestari Perlis_0004582401310N_00045824027823 | 38% | 4613A-MAC-001 Taman Bestari Perlis | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-26 | Wk26 | [9 empty] | 2024-08-15 |  | P1_Z_Oct | N107+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4432A | xD_DWDM-BRKRing_N405+/N408+/N411+_4432A KTM Sg Siput_0004582401310N_00045824027823 | 60% | 4432A-MAG-001 KTM Singai Siput | 1800vPro 1rack 2 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-31 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN | Duplicate line 283 |  |  |  |  | 2024-06-14 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4455A | xD_DWDM-BRKRing_N405+/N408+/N411+_4455A KTM Taiping_0004582401310N_00045824027823 | 60% | 4455A-MAG(M14)-001 KTM Taiping | 1800vPro 1rack 2 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-06-25 | Wk26 | [9 empty] | 2024-08-15 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4374A | xD_DWDM-BRKRing_N405+/N408+/N411+_4374A LAP Talang_0004582401310N_00045824027823 | 60% | 4374A-MAC-001 LAP Talang | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-25 | Wk26 | [9 empty] | 2024-08-15 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4378A | xD_DWDM-BRKRing_N405+/N408+/N411+_4378A Jerlun Tower_0004582401310N_00045824027823 | 60% | MIP2018 4378A-MAC-001 Jerlun Tower | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-06-26 | Wk26 | [9 empty] | 2024-08-15 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4379A | xD_DWDM-BRKRing_N405+/N408+/N411+_4379A Bkt Mercu_0004582401310N_00045824027823 | 60% | 4379A-MAC-001 Bkt Mercu | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-26 | Wk26 | [9 empty] | 2024-08-15 |  | #N/A | #N/A | #N/A | #N/A | [9 empty] | #N/A | #N/A | #N/A
N408+ | #N/A | 60% | 2024 Q2_2 | 4493A | xD_DWDM-BRKRing_N408+_4493A KTM Ipoh_0004582401310N_00045824027823 | 60% | 4493A-MAG-001 KTM Ipoh | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending CME approval | 2024-06-27 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N408+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N408+ | #N/A | 60% | 2024 Q2_2 | 4506A | xD_DWDM-BRKRing_N408+_4506A Perak Taipu_0004582401310N_00045824027823 | 60% | 4506A-MAC-001 Perak Taipu | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending CME approval | 2024-06-27 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N408+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N408+ | #N/A | 60% | 2024 Q2_2 | 4546A | xD_DWDM-BRKRing_N408+_4546A KWSP Ipoh_0004582401310N_00045824027823 | 60% | 4546A-MAC-001 KWSP Ipoh | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-28 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N408+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N408+ | #N/A | 60% | 2024 Q2_2 | 4515A | xD_DWDM-BRKRing_N408+_4515A Tg Rambutan_0004582401310N_00045824027823 | 60% | 4515A-MAC-001 Tg Rambutan | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-28 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N408+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N411+ | #N/A | 37% | 2024 Q2_2 | 4373A | xD_DWDM-BRKRing_N411+_4373A KTM K Kangsar_0004582401310N_00045824027823 | 37% | 4373A-MAC-001 KTM K. Kangsar | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-06-25 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N411+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N411+ | #N/A | 37% | 2024 Q2_2 | 4377B | xD_DWDM-BRKRing_N411+_4377B Karai_0004582401310N_00045824027823 | 37% | 4377B-MAC-001 Karai | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | 2024-06-25 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N411+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
N411+ | #N/A | 37% | 2024 Q2_2 | 4433A | xD_DWDM-BRKRing_N411+_4433A LAP Sg Siput_0004582401310N_00045824027823 | 37% | 4433A-MAC-001 LAP Sg Siput | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending FF approval | 2024-06-26 | Wk26 | [9 empty] | 2024-08-15 |  | P1_IP_BR-Q2 | N411+ | IP BREAK RING | P1_IP_BR-Q2 | [9 empty] | #N/A | #N/A | IP BREAK RING
Formulas:
WorkWeek_Install = "Wk"&WEEKNUM([Plan MOS],21)
Integrated Date (30days + install) = [Plan MOS]+14
Integrated Date (30days + install) = [Plan Power Up]+14
WorkWeek_Integration = "Wk"&WEEKNUM([Integrated Date (30days + install)],21)

## IPRan_Project_DWDM_dependency
Batch | Ring | Project_IP | Chk | project
Q1 | C0210P | IP_BR | C0210P | P1_IP_BR-Q1
Q2 | C0211+ | IP_BR | C0211+ | P1_IP_BR-Q2
Q2 | C0515+ | IP_BR | C0515+ | P1_IP_BR-Q2
Q2 | CAR02-ii+ | IP_R_EXP | CAR02-ii+ | P1_IP_R_EXP-Q2
Q1 | CAR04 | PE-MCR | CAR04 | P1_PE-MCR-Q1
Q1 | CT0120 | IP_BR | CT0120 | P1_IP_BR-Q1
Q1 | E104 | IP_BR | E104 | P1_IP_BR-Q1
Q1 | E105 | IP_BR | E105 | P1_IP_BR-Q1
Q1 | E109 | IP_BR | E109 | P1_IP_BR-Q1
Q1 | E111 | IP_BR | E111 | P1_IP_BR-Q1
Q3 | E209 | IP_BR | E209 | P1_IP_BR-Q3
Q3 | E301 | IP_BR | E301 | P1_IP_BR-Q3
Q1 | EAR01 | IP_BR | EAR01 | P1_IP_BR-Q1
Q3 | EAR01_1 & EAR01_3 | IP_R_EXP | EAR01_1 & EAR01_3 | P1_IP_R_EXP-Q3
Q1 | EAR06 | IP_R_EXP | EAR06 | P1_IP_R_EXP-Q1
Q2 | N104+ | IP_BR | N104+ | P1_IP_BR-Q2
Q2 | N107+ | IP_BR | N107+ | P1_IP_BR-Q2
Q1 | N407 | IP_BR | N407 | P1_IP_BR-Q1
Q2 | N408+ | IP_BR | N408+ | P1_IP_BR-Q2
Q2 | N411+ | IP_BR | N411+ | P1_IP_BR-Q2
Q2 | NAR01_iii+ | IP_R_EXP | NAR01_iii+ | P1_IP_R_EXP-Q2
Q2 | NAR02_ii+ | IP_R_EXP | NAR02_ii+ | P1_IP_R_EXP-Q2
Q2 | NAR04_ii+ | IP_R_EXP | NAR04_ii+ | P1_IP_R_EXP-Q2
Q1 | S301 | IP_BR | S301 | P1_IP_BR-Q1
Q3 | S305 | IP_BR | S305 | P1_IP_BR-Q3
Q3 | S313P_2 | IP_BR | S313P_2 | P1_IP_BR-Q3
Q3 | S504M | IP_BR | S504M | P1_IP_BR-Q3
Q3 | SAR06 | IP_R_EXP | SAR06 | P1_IP_R_EXP-Q3
Q1 | ST21P | IP_BR | ST21P | P1_IP_BR-Q1
Q1 | ST21P_1 | IP_BR | ST21P_1 | P1_IP_BR-Q1
Q1 | ST27P | IP_BR | ST27P | P1_IP_BR-Q1
Q1 | C1103 | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | MAC RING 18-C24 | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | New Ring_5 | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | S313P_2_ | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | S501_1 | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | CT04+ | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | MAC RING 6,C09+ | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | N401+ | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | S309+ | IP_BR | #N/A | P1_IP_BR-Q1
Q1 | NAR01_i+ | IP_R_EXP | #N/A | P1_IP_R_EXP-Q1
Q1 | NAR01_ii+ | IP_R_EXP | #N/A | P1_IP_R_EXP-Q1
Q2 | AREA 154 | IP_BR | #N/A | P1_IP_BR-Q2
Q2 | MAC Ring 15/ C21+ | IP_BR | #N/A | P1_IP_BR-Q2
Q2 | N405+ | IP_BR | #N/A | P1_IP_BR-Q2
Q2 | CAR02-i+ | IP_R_EXP | #N/A | P1_IP_R_EXP-Q2
Q3 | SAR03_i & SAR03_iii | PE-MCR | #N/A | P1_PE-MCR-Q3

## Sheet1
xD_DWDM_BRKRing_N401_4684B Terap_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4965A Politeknik Kulim_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4689A Tmn Desa Impian_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4118A Machang Bubuk2_0004582401280Y_00045824026722
xD_DWDM-BRKRing_N104+_4991A UUM_0004582401310N_00045824027823

## Sheet2
xD_DWDM_BRKRing_C0407P_1266A Sucasa_0004582309050Y_00045824006623
xD_DWDM_BRKRing_C0407P_1745A Baitumal_0004582309050Y_00045824006623
xD_DWDM_BRKRing_CAR04_1745A Baitumal_0004582309050Y_00045824006623
xD_DWDM_BRKRing_MR9/C13_1295A Com Bkt Maluri_0004582309050Y_00045824006623
xD_DWDM_BRKRing_ST27P_1607A-MAG001 KM Plaza_0004582309010R_00045824006624
xD_DWDM_BRKRing_ST27P_1608A KTM Seremban_0004582309010R_00045824006624
xD_DWDM_BRKRing_ST27P_1610A Gun Hill_0004582309010R_00045824006624
xD_DWDM-BRKRing_C0103_1364B Bestari(Maxis)_0004582400320X_00045824009023
xD_DWDM_BRKRing_C0103_1049B-MCR 001 KPG_0004582400930A_00045824009023
xD_DWDM_BRKRing_C0147P_2021B_SBHT_0004582401280Z_45824026526
xD_DWDM_BRKRing_C0147P_1918A Damansara Intan_0004582401280Z_45824026526
xD_DWDM_BRKRing_C0147P_1197A JBA Effingham_0004582401280Z_45824026526
xD_DWDM_BRKRing_C0147P_1211A KDU_0004582401280Z_45824026526
xD_DWDM_BRKRing_NAR01_i_4966A_Kulim Hitech_0004582401260T_45824026527
xD_DWDM_BRKRing_E301_8712A Kg Jawa Pekan_0004582401310P_00045824026721
xD_DWDM_BRKRing_E301_8088A Sg Beto_0004582401310P_00045824026721
xD_DWDM_BRKRing_E301_8000A KTNE1_0004582401310P_00045824026721
xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8263A Pasir Mas Town_0004582401310P_00045824026721
xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8211A WCY_0004582401310P_00045824026721
xD_DWDM_BRKRing_SAR06_8000A KTN_0004582401310P_00045824026721
xD_DWDM_BRKRing_SAR04_1621A MSC SNW_0004582401310P_00045824026721
xD_DWDM_BRKRing_NAR01_ii_4938A_Tmn Orkid_0004582401280Y_00045824026722
xD_DWDM_BRKRing_NAR01_ii_4660A KTM Alor Star_0004582401280Y_00045824026722
xD_DWDM_BRKRing_NAR01_ii_4998A Air Itam Kedah_0004582401280Y_00045824026722
xD_DWDM_BRKRing_NAR01_ii_4606A Padang Besar_0004582401280Y_00045824026722
xD_DWDM_BRKRing_MAC RING 6/C09+_1192A Subang New Village_0004582401280Y_00045824026722
xD_DWDM_BRKRing_MAC RING 6/C09+_1230A P Indus Sg Buloh_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4952B Selama_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4684B Terap_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4965A Politeknik Kulim_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4689A Tmn Desa Impian_0004582401280Y_00045824026722
xD_DWDM_BRKRing_N401_4118A Machang Bubuk2_0004582401280Y_00045824026722
xD_DWDM-BRKRing_N407_4432A KTM Sg Siput_0004582401300R_00045824026922
xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922
xD_DWDM-BRKRing_NAR02_ii+_8000A MSC KTN_0004582401310N_00045824027823
xD_DWDM-BRKRing_NAR02_ii+_4985A Baling Town_0004582401310N_00045824027823
xD_DWDM-BRKRing_NAR02_ii+_8282B Pergau_0004582401310N_00045824027823
xD_DWDM-BRKRing_CAR02-ii+_1918A Damansara Intan_0004582401310N_00045824027823
xD_DWDM-BRKRing_NAR04_ii+_4432A KTM Sungai Siput_0004582401310N_00045824027823
xD_DWDM-BRKRing_N104+_4992A Pendang_0004582401310N_00045824027823
xD_DWDM-BRKRing_N104+_4991A UUM_0004582401310N_00045824027823
xD_DWDM-BRKRing_N104+_4672A Changloon_0004582401310N_00045824027823
xD_DWDM-BRKRing_N104+_4665A Jitra_0004582401310N_00045824027823
xD_DWDM-BRKRing_N107+_4998A Air Itam Kedah_0004582401310N_00045824027823
xD_DWDM-BRKRing_N405+/N408+/N411+_4432A KTM Sg Siput_0004582401310N_00045824027823

## CME 6 May (hidden)
Site ID | Project Type |  | Status (CME Remark) |  | Site ID | Project Type |  | Status |  | Type | Site ID | Request Date | Status | CME Required |  |  |  |  | Type | (All)
1002A | Sri Murni | IPRAN Only | Completed | IPRAN | 1006A | JBA GOMBAK | IPRAN Only | completed | IPRAN | IPRAN | 1002A | 2024-01-02 | Completed | BATTERY BANK = 2 | Status | Site ID | Request Date | CME Required
1006A | JBA GOMBAK | Y | WIP | DWDM | 1007A | Mimaland | Y | Completed | DWDM | DWDM | 1006A | 2023-12-21 | Completed | RECTIFIER + DCPDB = 1 | CME by regional | 1360A | 2024-05-02 | 1. Swap Cabine
1070A | Wisma Low Kang | Y | Drop | DWDM | 1071A | Chi Liung | IPRAN Only | Completed | IPRAN | #N/A |  |  | Open |  | CME by regional | 8403A | 2023-09-22 | Extend platform = 1 | Status | Site ID | Request Date | CME Required
1073A | KTM Padang Jawa | IPRAN Only | Completed | IPRAN | 1073A | KTM Padang Jawa | IPRAN Only | Completed | IPRAN | DWDM | 1007A | 2023-10-13 | Completed | DCPDB = 1 UNIT | Completed | 1002A | 2024-01-02 | BATTERY BANK = 2 | CME by regional | 1360A | 2024-05-02 | 1. Swap Cabine
1081A | JBA Bkt Lipat | Y | Completed | DWDM | 1073A | KTM Padang Jawa | Y | Drop | DWDM | DWDM | 1070A | 2024-01-24 | Drop | BATTERY BANK = 1 | Completed | 1006A | 2023-12-21 | RECTIFIER + DCPDB = 1 |  | 8403A | 2023-09-22 | Extend platform = 1
1085A | Pekan Meru | IPRAN Only | Completed | IPRAN | 1080A | WIT | Y | Completed | DWDM | IPRAN | 1071A | 2023-10-02 | Completed | DCPDB = 1 | Completed | 1007A | 2023-10-13 | DCPDB = 1 UNIT | Completed | 1002A | 2024-01-02 | BATTERY BANK = 2
1096A | Klang Perdana | IPRAN Only | Completed | IPRAN | 1081A | JBA Bkt Lipat | Y | Completed | DWDM | IPRAN | 1073A | 2024-01-02 | Completed | BATTERY BANK = 6 | Completed | 1071A | 2023-10-02 | DCPDB = 1 |  | 1006A | 2023-12-21 | RECTIFIER + DCPDB = 1
1099A | Hong Fatt Auto | Y | Re-visit (Pending Cutover) | DWDM | 1087A | Rantau Panjang | Y | Completed | DWDM | IPRAN | 1073A | 2023-10-31 | Completed | DCPDB = 1 | Completed | 1073A | 2023-10-31 | DCPDB = 1 |  | 1007A | 2023-10-13 | DCPDB = 1 UNIT
1110A | Berjaya Industrial Park | IPRAN Only | WIP | IPRAN | 1093A | Kian Hoe Huat | Y | Completed | DWDM | DWDM | 1073A | 2023-10-31 | Drop | NOT REQUIRED | Completed |  | 2024-01-02 | BATTERY BANK = 6 |  | 1071A | 2023-10-02 | DCPDB = 1
1154A | MAG Sekinchan | Y | Drop | DWDM | 1096A | Klang Perdana | IPRAN Only | Completed | IPRAN | DWDM | 1080A | 2023-09-27 | Completed | DCPDB = 1 | Completed | 1080A | 2023-09-27 | DCPDB = 1 |  | 1073A | 2023-10-31 | DCPDB = 1
1156A | Batang Berjuntai | Y | Drop | DWDM | 1145A | Batang Kali | Y | Completed | DWDM | DWDM | 1081A | 2024-01-02 | Completed | BATTERY BANK = 2 | Completed | 1081A | 2023-09-27 | DCPDB = 1 |  |  | 2024-01-02 | BATTERY BANK = 6
1169A | Tg Karang Trunk road | Y | Drop | DWDM | 1146A | Kuala Kubu Baru Tower | Y | Completed | DWDM | DWDM | 1081A | 2023-09-27 | Completed | DCPDB = 1 | Completed |  | 2024-01-02 | BATTERY BANK = 2 |  | 1080A | 2023-09-27 | DCPDB = 1
1360A | HICOM GLENMARIE | Y | Re-visit (Pending cabinet dismantle) | DWDM | 1153A | Permatang K Selangor | Y | Completed | DWDM | IPRAN | 1085A | 2024-01-02 | Completed | BATTERY BANK = 8 | Completed | 1085A | 2024-01-02 | BATTERY BANK = 8 |  | 1081A | 2023-09-27 | DCPDB = 1
1362B | KELANA BUSINESS CENTRE | Y | Completed | DWDM | 1169A | Tg Karang Trunk Road | Y | Completed | DWDM | DWDM | 1087A | 2023-09-27 | Completed | DCPDB = 1 | Completed | 1087A | 2023-09-27 | DCPDB = 1 |  |  | 2024-01-02 | BATTERY BANK = 2
1409A | MAG Kota Damansara | Y | Re-visit (Pending Cutover) | DWDM | 1172A | Glomac | Y | Completed | DWDM | DWDM | 1093A | 2023-10-02 | Completed | DCPDB = 1 | Completed | 1093A | 2023-10-02 | DCPDB = 1 |  | 1085A | 2024-01-02 | BATTERY BANK = 8
1458A | Endah Parade | Y | Completed | DWDM | 1196A | JBA Puchong | Y | Completed | DWDM | IPRAN | 1096A | 0 | Completed | RECTIFIER+ DCPDB = 1 | Completed | 1096A | 0 | RECTIFIER+ DCPDB = 1 |  | 1087A | 2023-09-27 | DCPDB = 1
1533A | Bukit Duyong | Y | Completed | DWDM | 1197A | JBAEFF | IPRAN Only | Completed | IPRAN | IPRAN | 1096A | 2023-10-02 | Completed | DCPDB = 1 | Completed |  | 2023-10-02 | DCPDB = 1 |  | 1093A | 2023-10-02 | DCPDB = 1
1553A | Umbai | Y | completed | DWDM | 1246A | BERJAYA PLAZA | Y | Completed | DWDM | DWDM | 1099A | 2023-10-06 | Completed | RECTIFIER + DCPDB = 1 | Completed | 1099A | 2023-10-06 | RECTIFIER + DCPDB = 1 |  | 1096A | 0 | RECTIFIER+ DCPDB = 1
1556A | Merlimau | Y | Completed | DWDM | 1298A | Kepong Knit | Y | Completed | DWDM | IPRAN | 1110A | 0 | Completed | 19" RACK = 1 | Completed | 1110A | 0 | 19" RACK = 1 |  |  | 2023-10-02 | DCPDB = 1
1591A | Parit Bakar | Y | Completed | DWDM | 1309B | Kuala Sungai Baru (KJS) | Y | Completed | DWDM | DWDM | 1145A | 2023-09-27 | Completed | DC BREAKER : 63A X 4 | Completed | 1145A | 2023-09-27 | DC BREAKER : 63A X 4 |  | 1099A | 2023-10-06 | RECTIFIER + DCPDB = 1
1599A | Gambir Town | Y | Completed | DWDM | 1342A | MBSA | IPRAN Only | Completed | IPRAN | DWDM | 1146A | 2023-09-27 | Completed | DC BREAKER: 63 A X 4 | Completed | 1146A | 2023-09-27 | DC BREAKER: 63 A X 4 |  | 1110A | 0 | 19" RACK = 1
1649A | Kuala Lukut | IPRAN Only | Completed | IPRAN | 1360A | Hicom Glenmarie | Y | Completed | DWDM | DWDM | 1153A | 2023-10-02 | Completed | DC BREAKER: 63 A X 4 | Completed | 1153A | 2023-10-02 | DC BREAKER: 63 A X 4 |  | 1145A | 2023-09-27 | DC BREAKER : 63A X 4
1736B | SH CITY COMMAND CENTRE | IPRAN Only | WIP | IPRAN | 1360A | HICOM GLENMARIE | Y | Drop | DWDM | DWDM | 1154A | 2023-10-02 | Drop | ODF CABINET = 1 | Completed | 1169A | 2023-10-02 | DCPDB = 1 |  | 1146A | 2023-09-27 | DC BREAKER: 63 A X 4
1760A | Mambau 1 | Y | WIP | DWDM | 1362B | Kelana Business Centre | Y | Completed | DWDM | DWDM | 1156A | 2023-12-15 | Drop | ODF CABINET = 1 | Completed | 1172A | 2023-10-19 | DC BREAKER : 63A X 4 |  | 1153A | 2023-10-02 | DC BREAKER: 63 A X 4
1855B | TPM | Y | Completed | DWDM | 1367A | WorldWideBusiness | IPRAN Only | Completed | IPRAN | DWDM | 1169A | 2023-10-02 | Drop | ODF CABINET = 1 | Completed | 1196A | 2023-11-20 | DC BREAKER: 63 A X 4 |  | 1169A | 2023-10-02 | DCPDB = 1
2227B | Sri Jeram | Y | Completed | DWDM | 1367A | WorldWideBusiness | Y | Drop | DWDM | DWDM | 1169A | 2023-10-02 | Completed | DCPDB = 1 | Completed | 1246A | 2023-11-20 | DC BREAKER: 63 A X 4 |  | 1172A | 2023-10-19 | DC BREAKER : 63A X 4
2356B | Simpang K Sungga | Y | Completed | DWDM | 1378B | PJS 10 | Y | Completed | DWDM | DWDM | 1172A | 2023-10-19 | Completed | DC BREAKER : 63A X 4 | Completed | 1298A | 2023-11-08 | DCPDB = 1 |  | 1196A | 2023-11-20 | DC BREAKER: 63 A X 4
2388B | Desa Muar | Y | Completed | DWDM | 1402A | Jln Industri Puchong | Y | Completed | DWDM | DWDM | 1196A | 2023-11-20 | Completed | DC BREAKER: 63 A X 4 | Completed | 1309B | 2023-11-08 | DCPDB = 1 UNIT |  | 1246A | 2023-11-20 | DC BREAKER: 63 A X 4
2402B | Pagoh Highway | Y | Completed | DWDM | 1406B | NS HWY KM 454.3 | IPRAN Only | Completed | IPRAN | #N/A |  |  | Open |  | Completed | 1342A | 2024-01-26 | DC BREAKER : 63A X 4 |  | 1298A | 2023-11-08 | DCPDB = 1
2536A | Centro IB | IPRAN Only | Completed | IPRAN | 1408A | Puchong Jaya | Y | Completed | DWDM | DWDM | 1246A | 2023-11-20 | Completed | DC BREAKER: 63 A X 4 | Completed | 1360A | 2023-10-31 | DC BREAKER: 63A X 2 |  | 1309B | 2023-11-08 | DCPDB = 1 UNIT
2977B | DiGi HQ (Lot 10) | IPRAN Only | Drop | IPRAN | 1413A | KTM Rawang | Y | Completed | DWDM | DWDM | 1298A | 2023-11-08 | Completed | DCPDB = 1 | Completed |  | 2024-01-02 | BATTERY BANK = 2 |  | 1342A | 2024-01-26 | DC BREAKER : 63A X 4
3092A | Bkt Tampoi | IPRAN Only | Completed | IPRAN | 1525A | Bang. Graha Maju | Y | Completed | DWDM | DWDM | 1309B | 2023-11-08 | Completed | DCPDB = 1 UNIT | Completed | 1362B | 2023-10-02 | DCPDB = 1 |  | 1360A | 2023-10-31 | DC BREAKER: 63A X 2
4034A | Bukit Relau | IPRAN Only | Completed | IPRAN | 1525A | Bang. Graha Maju | IPRAN Only | Completed | IPRAN | IPRAN | 1342A | 2024-01-26 | Completed | DC BREAKER : 63A X 4 | Completed |  | 2024-01-02 | RECTTIFIER MODULE = 1 |  |  | 2024-01-02 | BATTERY BANK = 2
4063A | Komplek Tabung Haji | IPRAN Only | Completed | IPRAN | 1533A | Bkt Duyung | Y | Completed | DWDM | DWDM | 1360A | 2024-01-02 | Completed | BATTERY BANK = 2 | Completed | 1367A | 2023-10-31 | DCPDB = 1 |  | 1362B | 2023-10-02 | DCPDB = 1
4085D | Kulim Hitech 2 (REL) | Y | Completed | DWDM | 1554A | Rumbia | Y | Completed | DWDM | DWDM | 1360A | 2023-10-31 | Completed | DC BREAKER: 63A X 2 | Completed | 1378B | 2023-10-31 | DC BREAKER: 63A X 2 |  |  | 2024-01-02 | RECTTIFIER MODULE = 1
4188A | Nibong Tebal 2 | Y | WIP | DWDM | 1556A | Merlimau | Y | Completed | DWDM | DWDM | 1360A | 2024-01-18 | Drop | NOT REQUIRED | Completed | 1402A | 2023-11-20 | DC BREAKER: 63 A X 4 |  | 1367A | 2023-10-31 | DCPDB = 1
4310A | Kg Matang Acheh-100Q4(Digi Trunk)_REL | IPRAN Only | TBA | IPRAN | 1556A | Merlimau | Y | Completed | DWDM | DWDM | 1362B | 2024-01-02 | Completed | RECTTIFIER MODULE = 1 | Completed | 1408A | 2023-11-20 | DCPDB = 1 |  | 1378B | 2023-10-31 | DC BREAKER: 63A X 2
4427B | Simpang Taiping | Y | WIP | DWDM | 1599A | Bkt Gambir Town | Y | Completed | DWDM | DWDM | 1362B | 2023-10-02 | Completed | DCPDB = 1 | Completed | 1409A | 2023-10-19 | RECTIFIER + DCPDB = 1 |  | 1402A | 2023-11-20 | DC BREAKER: 63 A X 4
4454B | Kubu Gajah RDD | Y | Completed | DWDM | 1610A | GUN HILL | IPRAN Only | Completed | IPRAN | IPRAN | 1367A | 2023-10-31 | Completed | DCPDB = 1 | Completed | 1413A | 2023-10-02 | DC BREAKER: 63 A X 4 |  | 1408A | 2023-11-20 | DCPDB = 1
4465A | Taman long Jaafar | Y | Completed | DWDM | 1611A | Mukim Labu | IPRAN Only | Completed | IPRAN | DWDM | 1367A | 2023-10-31 | Drop | NOT REQUIRED | Completed | 1458A | 2024-01-02 | BATTERY BANK = 1 |  | 1409A | 2023-10-19 | RECTIFIER + DCPDB = 1
4621A | Cayman | Y | Completed | DWDM | 1627B | Pulau Indah Highway(ZED) | Y | Completed | DWDM | DWDM | 1378B | 2023-10-31 | Completed | DC BREAKER: 63A X 2 | Completed | 1525A | 2023-10-31 | DC BREAKER: 16A X 2 |  | 1413A | 2023-10-02 | DC BREAKER: 63 A X 4
4625A | Sungai Petani | Y | Completed | DWDM | 1701A | Kerling (Trunk) | Y | Completed | DWDM | DWDM | 1402A | 2023-11-20 | Completed | DC BREAKER: 63 A X 4 | Completed |  |  | DC BREAKER: 63 A X 4 |  | 1458A | 2024-01-02 | BATTERY BANK = 1
4663A | Derga Jaya | Y | completed | DWDM | 1737A | BERNAMA | Y | Completed | DWDM | #N/A |  |  | Open |  | Completed | 1533A | 2023-10-02 | BATTERY RACK = 1 |  | 1525A | 2023-10-31 | DC BREAKER: 16A X 2
4685B | Kg Sungai Karangan | Y | Completed | DWDM | 1770B | Genting Sempah | Y | Completed | DWDM | DWDM | 1408A | 2023-11-20 | Completed | DCPDB = 1 | Completed |  |  | DCPDB = 1 |  |  |  | DC BREAKER: 63 A X 4
4686B | Terap | Y | WIP | DWDM | 1787B | Karak HW KM 33.9 | Y | Completed | DWDM | DWDM | 1409A | 2023-10-19 | Completed | RECTIFIER + DCPDB = 1 | Completed | 1553A | 2023-10-02 | RECTIFIER + DCPDB = 1 |  | 1533A | 2023-10-02 | BATTERY RACK = 1
4688A | 4688A-MAC-001 Lunas | Y | Completed | DWDM | 1851A | KL Plaza 2 | Y | Completed | DWDM | DWDM | 1413A | 2023-10-02 | Completed | DC BREAKER: 63 A X 4 | Completed | 1554A | 2023-10-22 | DCPDB = 1 |  |  |  | DCPDB = 1
4689A | TAMAN DESA IMPIAN | Y | Completed | DWDM | 1855B | TPM (AsiaSpace) | Y | Completed | DWDM | DWDM | 1458A | 2024-01-02 | Completed | BATTERY BANK = 1 | Completed | 1556A | 2023-09-27 | DC BREAKER : 63A X 4 |  | 1553A | 2023-10-02 | RECTIFIER + DCPDB = 1
4770A | 4770A-MAC-001 Toklin (Trunk) | Y | Completed | DWDM | 2070B | MAC GOMBAK TX | Y | Completed | DWDM | DWDM | 1525A | 2023-10-31 | Completed | DC BREAKER: 63 A X 4 | Completed |  | 2024-01-02 | BATTERY BANK = 6 |  | 1554A | 2023-10-22 | DCPDB = 1
4932A | Tok Acheh | Y | Completed | DWDM | 2086A | Balai Polis Bkt Tinggi | Y | Completed | DWDM | DWDM | 1525A | 2023-10-31 | Completed | DC BREAKER: 16A X 2 | Completed |  | 2024-01-18 | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2 |  | 1556A | 2023-09-27 | DC BREAKER : 63A X 4
4938A | 4938A-MAG001 Taman Orkid | Y | WIP | DWDM | 2227B | Taman Sri Jeram | Y | Completed | DWDM | DWDM | 1533A | 2023-10-02 | Completed | BATTERY RACK = 1 | Completed | 1591A | 2023-09-27 | BATTERY BANK = 3 |  |  | 2024-01-02 | BATTERY BANK = 6
4940A | 4940A-MAC-001 Semeling | Y | Completed | DWDM | 2356B | Simpang K Sungga | Y | Completed | DWDM | DWDM | 1533A | 2023-10-02 | Completed | DCPDB = 1 | Completed | 1599A | 2023-09-27 | BATTERY BANK = 3 |  |  | 2024-01-18 | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2
4946A | Bukit Selambau | Y | DROP | DWDM | 2388B | Tmn Desa Muar | Y | Completed | DWDM | DWDM | 1553A | 2023-10-02 | completed | RECTIFIER + DCPDB = 1 | Completed |  |  | DCPDB = 1 |  | 1591A | 2023-09-27 | BATTERY BANK = 3
4950B | Pulai | Y | completed | DWDM | 2632A | Ecopark | Y | Completed | DWDM | DWDM | 1554A | 2023-10-22 | Completed | DCPDB = 1 | Completed | 1610A | 2024-01-23 | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2 |  | 1599A | 2023-09-27 | BATTERY BANK = 3
4956B | Kuala Pegang | Y | Completed | DWDM | 2833A | First World Hotel Indoor (Roof top) | IPRAN Only | Completed | IPRAN | DWDM | 1556A | 2024-01-02 | Completed | BATTERY BANK = 6 | Completed | 1627B | 2023-09-27 | DCPDB = 1 UNIT |  |  |  | DCPDB = 1
4965A | POLITEKNIK KULIM | Y | Completed | DWDM | 2833A | First World Hotel Indoor (Roof top) | Y | Completed | DWDM | DWDM | 1556A | 2023-09-27 | Completed | DC BREAKER : 63A X 4 | Completed | 1649A | 0 | RECTIFIER+ DCPDB = 1 |  | 1610A | 2024-01-23 | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2
4973B | Tajar | Y | WIP | DWDM | 4000A | MSC Prai | Y | Completed | DWDM | DWDM | 1556A | 2024-01-18 | Completed | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2 | Completed | 1701A | 2023-09-27 | DC BREAKER: 63 A X 4 |  | 1627B | 2023-09-27 | DCPDB = 1 UNIT
4985A | Baling Town | Y | Completed | DWDM | 4031A | Georgetown Hotel | IPRAN Only | completed | IPRAN | DWDM | 1591A | 2023-09-27 | Completed | BATTERY BANK = 3 | Completed | 1736B | 0 | 19" RACK = 1 |  | 1649A | 0 | RECTIFIER+ DCPDB = 1
4986A | Binjul | Y | Completed | DWDM | 4118A | Machang Bubuk 2 | Y | completed | DWDM | DWDM | 1599A | 2023-09-27 | Completed | BATTERY BANK = 3 | Completed | 1737A | 2023-12-21 | DCPDB = 1 UNIT |  | 1701A | 2023-09-27 | DC BREAKER: 63 A X 4
4988A | Kupang | Y | Completed | DWDM | 4368A | TAR College Kampar | Y | Completed | DWDM | DWDM | 1599A | 2023-09-27 | Completed | DCPDB = 1 | Completed | 1760A | 2023-10-31 | CABINET DISMANTLE = 1 |  | 1736B | 0 | 19" RACK = 1
4992A | Pendang | IPRAN Only | Drop | IPRAN | 4440B | Tapah Road | Y | Completed | DWDM | IPRAN | 1610A | 2024-01-23 | Completed | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2 | Completed | 1770B | 2023-10-02 | AC BREAKER : 32 X 3 |  | 1737A | 2023-12-21 | DCPDB = 1 UNIT
4992A | Pendang | IPRAN Only | Completed | IPRAN | 4454B | Kubu Gajah RDD | Y | Completed | DWDM | #N/A |  |  | Open |  | Completed | 1787B | 2023-10-02 | DC BREAKER: 63A X 2 |  | 1760A | 2023-10-31 | CABINET DISMANTLE = 1
4998A | Air Itam Kedah | IPRAN Only | WIP | IPRAN | 4509A | LAP Tmn Taufik | Y | Completed | DWDM | DWDM | 1627B | 2023-09-27 | Completed | DCPDB = 1 UNIT | Completed | 1851A | 2023-11-20 | DC BREAKER: 63 A X 4 |  | 1770B | 2023-10-02 | AC BREAKER : 32 X 3
6040A | Bkt Resam | IPRAN Only | Drop | IPRAN | 4516A | Simpang Pulai | Y | Completed | DWDM | DWDM | 1649A | 0 | Completed | RECTIFIER+ DCPDB = 1 | Completed | 1855B | 2023-12-14 | DCPDB = 1 |  | 1787B | 2023-10-02 | DC BREAKER: 63A X 2
6043A | K.K.Kam | Y | Drop | DWDM | 4640A | SP Plaza | Y | Completed | DWDM | DWDM | 1701A | 2023-09-27 | Completed | DC BREAKER: 63 A X 4 | Completed |  | 2024-01-04 | RECTIFIER + DCPDB = 1 |  | 1851A | 2023-11-20 | DC BREAKER: 63 A X 4
6083A | Soga | Y | Re-visit (Pending Cutover) | DWDM | 4662A | Bkt Tinggi Jitra | Y | Completed | DWDM | DWDM | 1736B | 0 | Completed | 19" RACK = 1 | Completed | 2070B | 2023-10-02 | DCPDB = 1 |  | 1855B | 2023-12-14 | DCPDB = 1
6138A | Kahang | Y | WIP | DWDM | 4663A | Derga Jaya | Y | Completed | DWDM | DWDM | 1737A | 2023-12-21 | Completed | DCPDB = 1 UNIT | Completed | 2086A | 2023-10-13 | DC BREAKER: 63A X 2 |  |  | 2024-01-04 | RECTIFIER + DCPDB = 1
6283A | Larkin Industrial | Y | Re-visit (Pending Cutover) | DWDM | 4669A | Alor Janggus (Trunk) | Y | Completed | DWDM | DWDM | 1760A | 2023-10-31 | Completed | CABINET DISMANTLE = 1 | Completed | 2227B | 2023-09-27 | BATTERY BANK = 3 |  | 2070B | 2023-10-02 | DCPDB = 1
6336A | UTM 2 | IPRAN Only | WIP | IPRAN | 4678A | Jalan Langgar | Y | Completed | DWDM | DWDM | 1770B | 2023-10-02 | Completed | AC BREAKER : 32 X 3 | Completed |  |  | DCPDB = 1 UNIT |  | 2086A | 2023-10-13 | DC BREAKER: 63A X 2
6502A | Nusa Perintis(Watertank) | Y | Completed | DWDM | 4685B | Kg Sg Karangan(T flow) | Y | Completed | DWDM | DWDM | 1787B | 2023-10-02 | Completed | DC BREAKER: 63A X 2 | Completed | 2356B | 2023-09-01 | DC BREAKER : 63A X 8 |  | 2227B | 2023-09-27 | BATTERY BANK = 3
6576A | Jalan Seelong | Y | Drop | DWDM | 4686B | Terap | Y | Completed | DWDM | DWDM | 1851A | 2023-11-20 | Completed | DC BREAKER: 63 A X 4 | Completed |  | 2024-01-04 | RECTIFIER MODULE = 2 |  |  |  | DCPDB = 1 UNIT
7042A | Telipok | IPRAN Only | WIP | IPRAN | 4688A | Lunas | Y | Completed | DWDM | DWDM | 1855B | 2024-01-04 | Completed | RECTIFIER + DCPDB = 1 | Completed | 2388B | 2023-09-27 | BATTERY BANK = 3 |  | 2356B | 2023-09-01 | DC BREAKER : 63A X 8
7063A | Guang Ji Temple | IPRAN Only | WIP | IPRAN | 4689A | TAMAN DESA IMPIAN | Y | Completed | DWDM | DWDM | 1855B | 2023-12-14 | Completed | DCPDB = 1 | Completed |  |  | DC BREAKER = 63A X 4 |  |  | 2024-01-04 | RECTIFIER MODULE = 2
7570A | Kg Garinono | IPRAN Only | WIP | IPRAN | 4692A | MAC-001 Gurun | Y | Completed | DWDM | DWDM | 2070B | 2023-10-02 | Completed | DCPDB = 1 | Completed | 2402B | 2023-09-27 | BATTERY BANK = 3 |  | 2388B | 2023-09-27 | BATTERY BANK = 3
8025A | Risda | Y | Drop | DWDM | 4693A | KTM Gurun | Y | Completed | DWDM | DWDM | 2086A | 2023-10-13 | Completed | DC BREAKER: 63A X 2 | Completed | 2536A | 2024-01-02 | BATTERY BANK = 3 |  |  |  | DC BREAKER = 63A X 4
8035A | Balok Kg Chengal | Y | Completed | DWDM | 4863B | Wisma PKNK | Y | Completed | DWDM | DWDM | 2227B | 2023-09-27 | Completed | BATTERY BANK = 3 | Completed | 2632A | 2023-10-31 | AC BREAKER : 32 X 3 |  | 2402B | 2023-09-27 | BATTERY BANK = 3
8061A | Bkt Pelindung | Y | Completed | DWDM | 4950B | Pulai | Y | Completed | DWDM | DWDM | 2227B | 2023-09-27 | Completed | DCPDB = 1 UNIT | Completed | 2833A | 2023-10-02 | AC BREAKER : 32 X 1 |  | 2536A | 2024-01-02 | BATTERY BANK = 3
8128A | Kg Luit | Y | Completed | DWDM | 4956B | Kuala Pegang | Y | Completed | DWDM | DWDM | 2356B | 2024-01-04 | Completed | RECTIFIER MODULE = 2 | Completed |  |  | DC BREAKER: 16A X 2 |  | 2632A | 2023-10-31 | AC BREAKER : 32 X 3
8149A | Jenagur | IPRAN Only | Completed | IPRAN | 4965A | POLITEKNIK KULIM | Y | Completed | DWDM | DWDM | 2356B | 2023-09-01 | Completed | DC BREAKER : 63A X 8 | Completed | 3092A | 2024-01-02 | BATTERY BANK = 3 |  | 2833A | 2023-10-02 | AC BREAKER : 32 X 1
8191A | SG Semuji | Y | Completed | DWDM | 4968A | Inokom Kulim | Y | Completed | DWDM | DWDM | 2388B | 2023-09-27 | Completed | BATTERY BANK = 3 | Completed | 4000A | 2023-11-22 | DC BREAKER: 63A X 12 |  |  |  | DC BREAKER: 16A X 2
8321A | Tabung Haji Kemaman | Y | Completed | DWDM | 4973B | Tajar | Y | Completed | DWDM | DWDM | 2388B | 2023-09-27 | Completed | DC BREAKER = 63A X 4 | Completed | 4034A | 0 | BATTERY BANK = 4 |  | 3092A | 2024-01-02 | BATTERY BANK = 3
8330A | MCR Kemuning(LDX) | Y | Completed | DWDM | 4986A | Binjul | Y | Completed | DWDM | DWDM | 2402B | 2023-09-27 | Completed | BATTERY BANK = 3 | Completed | 4063A | 0 | BATTERY BANK = 1 |  | 4000A | 2023-11-22 | DC BREAKER: 63A X 12
8353A | Kg Manir | Y | Completed | DWDM | 4992A | Pendang | Y | Drop | DWDM | IPRAN | 2536A | 2024-01-02 | Completed | BATTERY BANK = 3 | Completed | 4085D | 2023-11-08 | RECTTIFIER MODULE = 2 |  | 4034A | 0 | BATTERY BANK = 4
8354A | KUSZA | Y | Completed | DWDM | 4992A | Pendang | IPRAN Only | Completed | IPRAN | DWDM | 2632A | 2023-10-31 | Completed | AC BREAKER : 32 X 3 | Completed | 4118A | 2023-12-19 | DCPDB = 1 |  | 4063A | 0 | BATTERY BANK = 1
8403A | Bkt Mentok | Y | Completed | DWDM | 6000A | MSC JB | Y | Completed | DWDM | IPRAN | 2833A | 2023-10-02 | Completed | DC BREAKER: 16A X 2 | Completed | 4188A | 2023-12-15 | RECTIFIER + DCPDB = 1 |  | 4085D | 2023-11-08 | RECTTIFIER MODULE = 2
8408A | Cheneh | Y | Completed | DWDM | 6019A | Hyatt | IPRAN Only | Completed | IPRAN | DWDM | 2833A | 2023-10-02 | Completed | AC BREAKER : 32 X 1 | Completed | 4310A | 2024-04-03 | ODF CABINET = I UNIT |  | 4118A | 2023-12-19 | DCPDB = 1
8434A | Felda Neram | Y | Completed | DWDM | 6026A | Grand Continental | Y | Completed | DWDM | IPRAN | 2977B | 0 | Drop | 19" RACK = 1 | Completed | 4368A | 2023-10-31 | DC BREAKER : 63A X 4 |  | 4188A | 2023-12-15 | RECTIFIER + DCPDB = 1
8473A | Felda Seberang Tayur(LDX) | Y | Completed | DWDM | 6138A | Kahang-100Q4 | Y | Completed | DWDM | IPRAN | 3092A | 2024-01-02 | Completed | BATTERY BANK = 3 | Completed | 4427B | 2023-12-15 | RECTIFIER + DCPDB = 1 |  | 4310A | 2024-04-03 | ODF CABINET = I UNIT
8709A | Bentong | Y | Completed | DWDM | 6283A | Larkin Industrial | Y | Completed | DWDM | DWDM | 4000A | 2023-11-22 | Completed | DC BREAKER: 63A X 12 | Completed | 4440B | 2023-10-31 | DC BREAKER: 63 A X 4 |  | 4368A | 2023-10-31 | DC BREAKER : 63A X 4
8712A | Kg Jawa Pekan | Y | Completed | DWDM | 6295A | Jln Permatang Kempas | IPRAN Only | Completed | IPRAN | #N/A |  |  | Open |  | Completed | 4454B | 2023-09-27 | DC BREAKER : 100A X 2 |  | 4427B | 2023-12-15 | RECTIFIER + DCPDB = 1
8850B | Kg Keldong | Y | Completed | DWDM | 6336A | UTM 2 | IPRAN Only | Completed | IPRAN | IPRAN | 4034A | 0 | Completed | BATTERY BANK = 4 | Completed |  |  | RECTIFIER + DCPDB = 1 |  | 4440B | 2023-10-31 | DC BREAKER: 63 A X 4
8936A | Sg Karang | Y | Completed | DWDM | 6369A | Sri Saujana | Y | Completed | DWDM | IPRAN | 4063A | 0 | Completed | BATTERY BANK = 1 | Completed | 4465A | 2023-11-01 | BATTERY BANK = 7 |  | 4454B | 2023-09-27 | DC BREAKER : 100A X 2
8953A | Balok Perdana | Y | Completed | DWDM | 6442A | Airport Senai | Y | Completed | DWDM | DWDM | 4085D | 2023-11-08 | Completed | RECTTIFIER MODULE = 2 | Completed | 4509A | 2023-10-31 | DCPDB = 1 |  |  |  | RECTIFIER + DCPDB = 1
8965A | Spg Lepas Hilir | Y | Completed | DWDM | 6502A | Nusa Perintis(Watertank) | Y | Completed | DWDM | DWDM | 4118A | 2023-12-19 | completed | DCPDB = 1 | Completed | 4516A | 2023-10-31 | DCPDB = 1 |  | 4465A | 2023-11-01 | BATTERY BANK = 7
8984A | Kota Perdana | IPRAN Only | Completed | IPRAN | 6576A | Jalan Seelong | Y | Completed | DWDM | DWDM | 4188A | 2023-12-15 | Completed | RECTIFIER + DCPDB = 1 | Completed | 4621A | 2023-12-15 | BATTERY BANK = 3 |  | 4509A | 2023-10-31 | DCPDB = 1
[5 empty] | 6955A | Putri Wangsa 2 | Y | Completed | DWDM | IPRAN | 4310A | 2024-04-03 | Completed | ODF CABINET = I UNIT | Completed | 4625A | 2023-12-15 | BATTERY BANK = 3 |  | 4516A | 2023-10-31 | DCPDB = 1
[5 empty] | 8023B | Balok Baru | Y | Drop | DWDM | DWDM | 4368A | 2023-10-31 | Completed | DC BREAKER : 63A X 4 | Completed | 4640A | 2023-11-01 | DCPDB = 1 |  | 4621A | 2023-12-15 | BATTERY BANK = 3
[5 empty] | 8025A | Pejabat Risda | Y | Completed | DWDM | DWDM | 4427B | 2023-12-15 | Completed | RECTIFIER + DCPDB = 1 | Completed | 4662A | 2023-10-06 | DCPDB = 1 |  | 4625A | 2023-12-15 | BATTERY BANK = 3
[5 empty] | 8061A | Bukit Pelindung | Y | Completed | DWDM | DWDM | 4440B | 2023-10-31 | Completed | DC BREAKER: 63 A X 4 | Completed | 4663A | 2023-12-19 | DC BREAKER : 100A X 2 |  | 4640A | 2023-11-01 | DCPDB = 1
[5 empty] | 8128A | Luit (ZED) | Y | Completed | DWDM | DWDM | 4454B | 2023-09-27 | Completed | RECTIFIER + DCPDB = 1 | Completed |  | 2023-12-21 | RECTIFIER MODULE = 1 |  | 4662A | 2023-10-06 | DCPDB = 1
[5 empty] | 8149A | Jenagur | Y | Drop | IPRAN | DWDM | 4454B | 2023-09-27 | Completed | DC BREAKER : 100A X 2 | Completed | 4669A | 2023-11-20 | DCPDB = 1 |  | 4663A | 2023-12-19 | DC BREAKER : 100A X 2
[5 empty] | 8191A | Sg Semuji(Shazan s Tower / ZED) | Y | Drop | DWDM | DWDM | 4465A | 2023-11-01 | Completed | BATTERY BANK = 7 | Completed | 4678A | 2023-10-06 | DCPDB = 1 |  |  | 2023-12-21 | RECTIFIER MODULE = 1
[5 empty] | 8211A | WAKAF CHE YEH | Y | Completed | DWDM | DWDM | 4509A | 2023-10-31 | Completed | DCPDB = 1 | Completed | 4685B | 2023-11-08 | DCPDB = 1 UNIT |  | 4669A | 2023-11-20 | DCPDB = 1
[5 empty] | 8224A | Pasir Puteh | Y | Completed | DWDM | DWDM | 4516A | 2023-10-31 | Completed | DCPDB = 1 | Completed |  |  | RECTTIFIER MODULE = 2 |  | 4678A | 2023-10-06 | DCPDB = 1
[5 empty] | 8268A | Bachok Town | Y | Completed | DWDM | DWDM | 4621A | 2023-12-15 | Completed | BATTERY BANK = 3 | Completed | 4686B | 2023-12-19 | DC BREAKER: 63 A X 4 |  | 4685B | 2023-11-08 | DCPDB = 1 UNIT
[5 empty] | 8350B | KUSTEM | Y | Drop | DWDM | DWDM | 4625A | 2023-12-15 | Completed | BATTERY BANK = 3 | Completed |  | 2023-12-21 | RECTIFIER + DCPDB = 1 |  |  |  | RECTTIFIER MODULE = 2
[5 empty] | 8353A | Kg Manir | Y | Completed | DWDM | DWDM | 4640A | 2023-11-01 | Completed | DCPDB = 1 | Completed | 4688A | 2023-11-08 | DCPDB = 1 |  | 4686B | 2023-12-19 | DC BREAKER: 63 A X 4
[5 empty] | 8354A | KUSZA Gong Badak | Y | Drop | DWDM | DWDM | 4662A | 2023-10-06 | Completed | DCPDB = 1 | Completed |  |  | RECTTIFIER MODULE = 1 |  |  | 2023-12-21 | RECTIFIER + DCPDB = 1
[5 empty] | 8403A | Bukit Mentok | Y | Completed | DWDM | DWDM | 4663A | 2023-12-21 | completed | RECTIFIER MODULE = 1 | Completed | 4689A | 2023-12-19 | DCPDB = 1 |  | 4688A | 2023-11-08 | DCPDB = 1
[5 empty] | 8429B | Bukit Payung (REL) | Y | Drop | DWDM | DWDM | 4663A | 2023-12-19 | Completed | DC BREAKER : 100A X 2 | Completed |  | 2023-12-21 | BATTERY BANK = 1 |  |  |  | RECTTIFIER MODULE = 1
[5 empty] | 8434A | Felda Neram | Y | Completed | DWDM | DWDM | 4669A | 2023-11-20 | Completed | DCPDB = 1 | Completed | 4692A | 2023-11-09 | DCPDB = 1 |  | 4689A | 2023-12-19 | DCPDB = 1
[5 empty] | 8473A | Felda Seberang Tayur | Y | Drop | DWDM | DWDM | 4678A | 2023-10-06 | Completed | DCPDB = 1 | Completed | 4693A | 2023-11-08 | DC BREAKER: 63 A X 4 |  |  | 2023-12-21 | BATTERY BANK = 1
[5 empty] | 8473A | Felda Seberang Tayur | Y | Completed | DWDM | DWDM | 4685B | 2023-11-08 | Completed | RECTTIFIER MODULE = 2 | Completed | 4770A | 2023-10-02 | RECTTIFIER MODULE = 2 |  | 4692A | 2023-11-09 | DCPDB = 1
[5 empty] | 8483A | T3_0467 Desa Solehah | Y | Completed | DWDM | DWDM | 4685B | 2023-11-08 | Completed | DCPDB = 1 UNIT | Completed | 4863B | 2023-11-30 | AC BREAKER : 32 X 3 |  | 4693A | 2023-11-08 | DC BREAKER: 63 A X 4
[5 empty] | 8712A | Kg Jawa Pekan | Y | Completed | DWDM | DWDM | 4686B | 2023-12-21 | Completed | RECTIFIER + DCPDB = 1 | Completed | 4932A | 2023-12-15 | BATTERY BANK = 2 |  | 4770A | 2023-10-02 | RECTTIFIER MODULE = 2
[5 empty] | 8850B | Kg Keldong | Y | Completed | DWDM | DWDM | 4686B | 2023-12-19 | Completed | DC BREAKER: 63 A X 4 | Completed | 4938A | 2023-11-08 | RECTIFIER + DCPDB = 1 |  | 4863B | 2023-11-30 | AC BREAKER : 32 X 3
[5 empty] | 8936A | Sg Karang | Y | Completed | DWDM | DWDM | 4688A | 2023-11-08 | Completed | RECTTIFIER MODULE = 1 | Completed | 4940A | 2023-10-02 | BATTERY BANK = 2 |  | 4932A | 2023-12-15 | BATTERY BANK = 2
[5 empty] | 8965A | Simpang Lepar Hilir | Y | Completed | DWDM | DWDM | 4688A | 2023-11-08 | Completed | DCPDB = 1 | Completed | 4950B | 2023-10-06 | DC BREAKER: 63 A X 4 |  | 4938A | 2023-11-08 | RECTIFIER + DCPDB = 1
[5 empty] | 8923B | TMN SEMARAK (REL) | Y | Drop | DWDM | DWDM | 4689A | 2023-12-21 | Completed | BATTERY BANK = 1 | Completed |  |  | RECTIFIER + DCPDB = 1 |  | 4940A | 2023-10-02 | BATTERY BANK = 2
[10 empty] | DWDM | 4689A | 2023-12-19 | Completed | DCPDB = 1 | Completed | 4956B | 2023-11-08 | DCPDB = 1 UNIT |  | 4950B | 2023-10-06 | DC BREAKER: 63 A X 4
[10 empty] | DWDM | 4692A | 2023-11-09 | Completed | DCPDB = 1 | Completed |  |  | RECTTIFIER MODULE = 2 |  |  |  | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 4693A | 2023-11-08 | Completed | DC BREAKER: 63 A X 4 | Completed | 4965A | 2023-12-21 | BATTERY BANK = 1 |  | 4956B | 2023-11-08 | DCPDB = 1 UNIT
[10 empty] | DWDM | 4770A | 2023-10-02 | Completed | RECTTIFIER MODULE = 2 | Completed |  |  | DCPDB = 1 |  |  |  | RECTTIFIER MODULE = 2
[10 empty] | DWDM | 4863B | 2023-11-30 | Completed | AC BREAKER : 32 X 3 | Completed | 4968A | 2023-11-08 | AC BREAKER : 32 X 3 |  | 4965A | 2023-12-21 | BATTERY BANK = 1
[10 empty] | DWDM | 4932A | 2023-12-15 | Completed | BATTERY BANK = 2 | Completed | 4973B | 2023-12-19 | MGB = 1 |  |  |  | DCPDB = 1
[10 empty] | DWDM | 4938A | 2023-11-08 | Completed | RECTIFIER + DCPDB = 1 | Completed |  | 2023-12-21 | RECTIFIER + DCPDB = 1 |  | 4968A | 2023-11-08 | AC BREAKER : 32 X 3
[10 empty] | DWDM | 4940A | 2023-10-02 | Completed | BATTERY BANK = 2 | Completed | 4985A | 2023-11-08 | RECTIFIER + DCPDB = 1 |  | 4973B | 2023-12-19 | MGB = 1
[10 empty] | DWDM | 4946A | 2023-10-31 | DROP | DROP | Completed | 4986A | 2023-11-08 | DCPDB = 1 UNIT |  |  | 2023-12-21 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 4950B | 2023-10-06 | completed | RECTIFIER + DCPDB = 1 | Completed |  |  | RECTTIFIER MODULE = 2 |  | 4985A | 2023-11-08 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 4950B | 2023-10-06 | Completed | DC BREAKER: 63 A X 4 | Completed | 4988A | 2023-10-02 | BATTERY BANK = 2 |  | 4986A | 2023-11-08 | DCPDB = 1 UNIT
[10 empty] | DWDM | 4956B | 2023-11-08 | Completed | RECTTIFIER MODULE = 2 | Completed | 4992A | N/A | DC BREAKER = 40 A |  |  |  | RECTTIFIER MODULE = 2
[10 empty] | DWDM | 4956B | 2023-11-08 | Completed | DCPDB = 1 UNIT | Completed |  | 0 | RECTIFIER + DCPDB = 1(PO OK) |  | 4988A | 2023-10-02 | BATTERY BANK = 2
[10 empty] | DWDM | 4965A | 2023-12-21 | Completed | BATTERY BANK = 1 | Completed | 4998A | 0 | BATTERY BANK = 3 |  | 4992A | N/A | DC BREAKER = 40 A
[10 empty] | DWDM | 4965A | 2023-12-21 | Completed | DCPDB = 1 | Completed | 6000A | 2023-09-27 | DC BREAKER: 63 A X 4 |  |  | 0 | RECTIFIER + DCPDB = 1(PO OK)
[10 empty] | DWDM | 4968A | 2023-11-08 | Completed | AC BREAKER : 32 X 3 | Completed | 6026A | 2023-11-20 | DC BREAKER: 63A X 3 |  | 4998A | 0 | BATTERY BANK = 3
[10 empty] | DWDM | 4973B | 2023-12-21 | Completed | RECTIFIER + DCPDB = 1 | Completed | 6083A | 2023-10-06 | RECTIFIER + DCPDB = 1 |  | 6000A | 2023-09-27 | DC BREAKER: 63 A X 4
[10 empty] | DWDM | 4973B | 2023-12-19 | Completed | MGB = 1 | Completed | 6138A | 2023-08-28 | MGB = 1 |  | 6026A | 2023-11-20 | DC BREAKER: 63A X 3
[10 empty] | DWDM | 4985A | 2023-11-08 | Completed | RECTIFIER + DCPDB = 1 | Completed |  | 2024-01-04 | DISMANTLE CABINET = 1 |  | 6083A | 2023-10-06 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 4986A | 2023-11-08 | Completed | RECTTIFIER MODULE = 2 | Completed | 6283A | 2023-11-20 | DCPDB = 1 |  | 6138A | 2023-08-28 | MGB = 1
[10 empty] | DWDM | 4986A | 2023-11-08 | Completed | DCPDB = 1 UNIT | Completed |  |  | RECTIFIER + DCPDB = 1 |  |  | 2024-01-04 | DISMANTLE CABINET = 1
[10 empty] | DWDM | 4988A | 2023-10-02 | Completed | BATTERY BANK = 2 | Completed | 6336A | 0 | 19" RACK = 1 |  | 6283A | 2023-11-20 | DCPDB = 1
[10 empty] | IPRAN | 4992A | 0 | Drop | NOT REQUIRED | Completed | 6369A | 2023-11-17 | DC BREAKER : 63A X 4 |  |  |  | RECTIFIER + DCPDB = 1
[10 empty] | IPRAN | 4992A | 0 | Completed | RECTIFIER + DCPDB = 1(PO OK) | Completed | 6442A | 2023-11-20 | DCPDB = 1 |  | 6336A | 0 | 19" RACK = 1
[10 empty] | DWDM | 4992A | N/A | Drop | NOT REQUIRED | Completed | 6502A | 2023-11-20 | BATTERY BANK = 1 |  | 6369A | 2023-11-17 | DC BREAKER : 63A X 4
[10 empty] | IPRAN | 4992A | N/A | Completed | DC BREAKER = 40 A | Completed |  |  | DC BREAKER: 63A X 3 |  | 6442A | 2023-11-20 | DCPDB = 1
[10 empty] | IPRAN | 4998A | 0 | Completed | BATTERY BANK = 3 | Completed | 6576A | 2023-11-20 | DC BREAKER: 63A X 2 |  | 6502A | 2023-11-20 | BATTERY BANK = 1
[10 empty] | DWDM | 6000A | 2023-09-27 | Completed | DC BREAKER: 63 A X 4 | Completed | 6955A | 2023-11-20 | DCPDB = 1 UNIT |  |  |  | DC BREAKER: 63A X 3
[10 empty] | #N/A |  |  | Open |  | Completed | 8025A | 2023-09-01 | MGB = 1 |  | 6576A | 2023-11-20 | DC BREAKER: 63A X 2
[10 empty] | DWDM | 6026A | 2023-11-20 | Completed | DC BREAKER: 63A X 3 | Completed | 8035A | 2023-09-27 | RECTIFIER MODULE = 2 |  | 6955A | 2023-11-20 | DCPDB = 1 UNIT
[10 empty] | IPRAN | 6040A | 2024-01-23 | Drop | RECTTIFIER MODULE = 1 | Completed | 8061A | 2023-09-27 | DC BREAKER = 63A X 4 |  | 8025A | 2023-09-01 | MGB = 1
[10 empty] | DWDM | 6043A | 2023-11-30 | Drop | RECTIFIER + DCPDB = 1 | Completed |  |  | RECTIFIER MODULE = 2 |  | 8035A | 2023-09-27 | RECTIFIER MODULE = 2
[10 empty] | DWDM | 6083A | 2023-10-06 | Completed | RECTIFIER + DCPDB = 1 | Completed | 8128A | 2023-09-27 | DCPDB = 1 |  | 8061A | 2023-09-27 | DC BREAKER = 63A X 4
[10 empty] | DWDM | 6138A | 2024-01-04 | Completed | DISMANTLE CABINET = 1 | Completed |  |  | RECTIFIER MODULE = 3 |  |  |  | RECTIFIER MODULE = 2
[10 empty] | DWDM | 6138A | 2023-08-28 | Completed | MGB = 1 | Completed | 8149A | 0 | RECTIFIER+ DCPDB = 1 |  | 8128A | 2023-09-27 | DCPDB = 1
[10 empty] | DWDM | 6283A | 2023-11-20 | Completed | RECTIFIER + DCPDB = 1 | Completed | 8191A | 2023-10-02 | RECTTIFIER MODULE = 3 |  |  |  | RECTIFIER MODULE = 3
[10 empty] | DWDM | 6283A | 2023-11-20 | Completed | DCPDB = 1 | Completed | 8211A | 2023-09-19 | DCPDB = 1 |  | 8149A | 0 | RECTIFIER+ DCPDB = 1
[10 empty] | #N/A |  |  | Open |  | Completed | 8224A | 2023-09-27 | DC BREAKER: 63 A X 4 |  | 8191A | 2023-10-02 | RECTTIFIER MODULE = 3
[10 empty] | IPRAN | 6336A | 0 | Completed | 19" RACK = 1 | Completed | 8268A | 2023-09-27 | MGB = 1 |  | 8211A | 2023-09-19 | DCPDB = 1
[10 empty] | #N/A |  |  | Open |  | Completed | 8321A | 2023-10-06 | RECTIFIER + DCPDB = 1 |  | 8224A | 2023-09-27 | DC BREAKER: 63 A X 4
[10 empty] | DWDM | 6369A | 2023-11-17 | Completed | DC BREAKER : 63A X 4 | Completed | 8330A | 2023-10-31 | BATTERY BANK = 1 |  | 8268A | 2023-09-27 | MGB = 1
[10 empty] | DWDM | 6442A | 2023-11-20 | Completed | DCPDB = 1 | Completed | 8353A | 2023-09-27 | DCPDB = 1 |  | 8321A | 2023-10-06 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 6502A | 2023-11-20 | Completed | BATTERY BANK = 1 | Completed |  |  | RECTIFIER MODULE = 1 |  | 8330A | 2023-10-31 | BATTERY BANK = 1
[10 empty] | DWDM | 6502A | 2023-11-20 | Completed | DC BREAKER: 63A X 3 | Completed | 8354A | 2023-09-27 | RECTIFIER MODULE = 2 |  | 8353A | 2023-09-27 | DCPDB = 1
[10 empty] | DWDM | 6576A | 2023-11-20 | Drop | RECTIFIER + DCPDB = 1 | Completed | 8403A | 2023-09-22 | RECTTIFIER MODULE = 2 |  |  |  | RECTIFIER MODULE = 1
[10 empty] | DWDM | 6576A | 2023-11-20 | Completed | DC BREAKER: 63A X 2 | Completed |  | 2024-04-22 | DC BREAKER : 100A X 2 |  | 8354A | 2023-09-27 | RECTIFIER MODULE = 2
[10 empty] | DWDM | 6955A | 2023-11-20 | Completed | DCPDB = 1 UNIT | Completed | 8408A | 2023-12-15 | BATTERY BANK = 2 |  | 8403A | 2023-09-22 | RECTTIFIER MODULE = 2
[10 empty] | IPRAN | 7042A | 0 | WIP | BATTERY BANK = 4 | Completed | 8434A | 2023-09-27 | DCPDB = 1 |  |  | 2024-04-22 | DC BREAKER : 100A X 2
[10 empty] | IPRAN | 7063A | 0 | WIP | BATTERY BANK = 8 | Completed |  |  | RECTIFIER MODULE = 2 |  | 8408A | 2023-12-15 | BATTERY BANK = 2
[10 empty] | IPRAN | 7570A | 0 | WIP | NEW DCPDB | Completed | 8473A | 2023-09-27 | DC BREAKER: 100A X 2 |  | 8434A | 2023-09-27 | DCPDB = 1
[10 empty] | DWDM | 8023B | 2023-09-27 | Drop | NOT REQUIRED | Completed |  |  | RECTTIFIER MODULE = 2 |  |  |  | RECTIFIER MODULE = 2
[10 empty] | DWDM | 8025A | 2023-09-04 | Drop | ODF CABINET = I UNIT | Completed | 8483A | 2023-09-18 | MGB = 1 |  | 8473A | 2023-09-27 | DC BREAKER: 100A X 2
[10 empty] | DWDM | 8025A | 2023-09-01 | Completed | MGB = 1 | Completed | 8709A | 2023-10-06 | RECTIFIER + DCPDB = 1 |  |  |  | RECTTIFIER MODULE = 2
[10 empty] | DWDM | 8035A | 2023-09-27 | Completed | RECTIFIER MODULE = 2 | Completed | 8712A | 2023-12-19 | DCPDB = 1 |  | 8483A | 2023-09-18 | MGB = 1
[10 empty] | DWDM | 8061A | 2023-09-27 | Completed | RECTIFIER MODULE = 2 | Completed |  | 2024-01-04 | BATTERY BANK = 2 |  | 8709A | 2023-10-06 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 8061A | 2023-09-27 | Completed | DC BREAKER = 63A X 4 | Completed | 8850B | 2023-08-29 | DC BREAKER: 63 A X 4 |  | 8712A | 2023-12-19 | DCPDB = 1
[10 empty] | DWDM | 8128A | 2023-09-27 | Completed | RECTIFIER MODULE = 3 | Completed |  | 2024-01-04 | RECTIFIER MODULE = 2 |  |  | 2024-01-04 | BATTERY BANK = 2
[10 empty] | DWDM | 8128A | 2023-09-27 | Completed | DCPDB = 1 | Completed | 8936A | 2023-09-27 | DC BREAKER : 100A X 2 |  | 8850B | 2023-08-29 | DC BREAKER: 63 A X 4
[10 empty] | IPRAN | 8149A | 0 | Completed | RECTIFIER+ DCPDB = 1 | Completed |  |  | RECTIFIER MODULE = 1 |  |  | 2024-01-04 | RECTIFIER MODULE = 2
[10 empty] | #N/A |  |  | Open |  | Completed | 8953A | 2023-09-27 | RECTIFIER + DCPDB = 1 |  | 8936A | 2023-09-27 | DC BREAKER : 100A X 2
[10 empty] | DWDM | 8191A | 2023-10-02 | Completed | RECTTIFIER MODULE = 3 | Completed | 8965A | 2023-09-27 | DCPDB = 1 |  |  |  | RECTIFIER MODULE = 1
[10 empty] | DWDM | 8191A | 2023-10-02 | Drop | NOT REQUIRED | Completed |  |  | RECTIFIER MODULE = 2 |  | 8953A | 2023-09-27 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 8211A | 2023-09-19 | Completed | DCPDB = 1 | Completed | 8984A | 0 | BATTERY BANK = 3 |  | 8965A | 2023-09-27 | DCPDB = 1
[10 empty] | DWDM | 8224A | 2023-09-27 | Completed | DC BREAKER: 63 A X 4 | Completed | 1070A | 2024-01-24 | BATTERY BANK = 1 |  |  |  | RECTIFIER MODULE = 2
[10 empty] | DWDM | 8268A | 2023-09-27 | Completed | MGB = 1 | Completed | 1073A | 2023-10-31 | NOT REQUIRED |  | 8984A | 0 | BATTERY BANK = 3
[10 empty] | DWDM | 8321A | 2023-10-06 | Completed | RECTIFIER + DCPDB = 1 | Completed | 1154A | 2023-10-02 | ODF CABINET = 1 | Drop | 1070A | 2024-01-24 | BATTERY BANK = 1
[10 empty] | DWDM | 8330A | 2023-10-31 | Completed | BATTERY BANK = 1 | Completed | 1156A | 2023-12-15 | ODF CABINET = 1 |  | 1073A | 2023-10-31 | NOT REQUIRED
[10 empty] | DWDM | 8350B | 2023-09-27 | Drop | NOT REQUIRED | Completed | 1169A | 2023-10-02 | ODF CABINET = 1 |  | 1154A | 2023-10-02 | ODF CABINET = 1
[10 empty] | DWDM | 8353A | 2023-09-27 | Completed | RECTIFIER MODULE = 1 | Completed | 1360A | 2024-01-18 | NOT REQUIRED |  | 1156A | 2023-12-15 | ODF CABINET = 1
[10 empty] | DWDM | 8353A | 2023-09-27 | Completed | DCPDB = 1 | Completed | 1367A | 2023-10-31 | NOT REQUIRED |  | 1169A | 2023-10-02 | ODF CABINET = 1
[10 empty] | DWDM | 8354A | 2023-09-27 | Completed | RECTIFIER MODULE = 2 | Completed | 2977B | 0 | 19" RACK = 1 |  | 1360A | 2024-01-18 | NOT REQUIRED
[10 empty] | DWDM | 8354A | 2023-09-27 | Drop | NOT REQUIRED | Completed | 4946A | 2023-10-31 | DROP |  | 1367A | 2023-10-31 | NOT REQUIRED
[10 empty] | DWDM | 8403A | 2023-09-22 | Completed | RECTTIFIER MODULE = 2 | Completed | 4992A | N/A | NOT REQUIRED |  | 2977B | 0 | 19" RACK = 1
[10 empty] | DWDM | 8403A | 2024-04-22 | Completed | DC BREAKER : 100A X 2 | Completed |  | 0 | NOT REQUIRED |  | 4946A | 2023-10-31 | DROP
[10 empty] | DWDM | 8408A | 2023-12-15 | Completed | BATTERY BANK = 2 | Completed | 6040A | 2024-01-23 | RECTTIFIER MODULE = 1 |  | 4992A | N/A | NOT REQUIRED
[10 empty] | DWDM | 8429B | 2023-09-27 | Drop | NOT REQUIRED | Completed | 6043A | 2023-11-30 | RECTIFIER + DCPDB = 1 |  |  | 0 | NOT REQUIRED
[10 empty] | DWDM | 8434A | 2023-09-27 | Completed | RECTIFIER MODULE = 2 | Completed | 6576A | 2023-11-20 | RECTIFIER + DCPDB = 1 |  | 6040A | 2024-01-23 | RECTTIFIER MODULE = 1
[10 empty] | DWDM | 8434A | 2023-09-27 | Completed | DCPDB = 1 | Completed | 8023B | 2023-09-27 | NOT REQUIRED |  | 6043A | 2023-11-30 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 8473A | 2023-09-27 | Completed | RECTTIFIER MODULE = 2 | Completed | 8025A | 2023-09-04 | ODF CABINET = I UNIT |  | 6576A | 2023-11-20 | RECTIFIER + DCPDB = 1
[10 empty] | DWDM | 8473A | 2023-09-27 | Drop | DCPDB = 1 | Completed | 8191A | 2023-10-02 | NOT REQUIRED |  | 8023B | 2023-09-27 | NOT REQUIRED
[10 empty] | DWDM | 8473A | 2023-09-27 | Completed | DC BREAKER: 100A X 2 | Completed | 8350B | 2023-09-27 | NOT REQUIRED |  | 8025A | 2023-09-04 | ODF CABINET = I UNIT
[10 empty] | DWDM | 8483A | 2023-09-18 | Completed | MGB = 1 | Completed | 8354A | 2023-09-27 | NOT REQUIRED |  | 8191A | 2023-10-02 | NOT REQUIRED
[10 empty] | DWDM | 8709A | 2023-10-06 | Completed | RECTIFIER + DCPDB = 1 | Completed | 8429B | 2023-09-27 | NOT REQUIRED |  | 8350B | 2023-09-27 | NOT REQUIRED
[10 empty] | DWDM | 8712A | 2024-01-04 | Completed | BATTERY BANK = 2 | Completed | 8473A | 2023-09-27 | DCPDB = 1 |  | 8354A | 2023-09-27 | NOT REQUIRED
[10 empty] | DWDM | 8712A | 2023-12-19 | Completed | DCPDB = 1 | Completed | 8923B | 2024-01-23 | ADD 100A X 2 BREAKER |  | 8429B | 2023-09-27 | NOT REQUIRED
[10 empty] | DWDM | 8850B | 2024-01-04 | Completed | RECTIFIER MODULE = 2 | Open | 1017E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 8473A | 2023-09-27 | DCPDB = 1
[10 empty] | DWDM | 8850B | 2023-08-29 | Completed | DC BREAKER: 63 A X 4 | Open | 1018E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 8923B | 2024-01-23 | ADD 100A X 2 BREAKER
[10 empty] | DWDM | 8936A | 2023-09-27 | Completed | RECTIFIER MODULE = 1 | Open | 1019E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1017E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 8936A | 2023-09-27 | Completed | DC BREAKER : 100A X 2 | Open | 1020E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 1018E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 8953A | 2023-09-27 | Completed | RECTIFIER + DCPDB = 1 | Open | 1063B | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) |  | 1019E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 8965A | 2023-09-27 | Completed | RECTIFIER MODULE = 2 | Open | 1127E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 1020E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 8965A | 2023-09-27 | Completed | DCPDB = 1 | Open | 1149E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 1063B | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | IPRAN | 8984A | 0 | Completed | BATTERY BANK = 3 | Open | 1150E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 1127E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 8923B | 2024-01-23 | Drop | ADD 100A X 2 BREAKER | Open | 1151E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 1149E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 1253A | 2024-04-24 | Open | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | Open | 1197A | 2024-05-02 | 1. Add Battery Bank = 2 |  | 1150E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 4863B | 2024-04-24 | Open | 1. Add Battery Bank = 1 | Open | 1203A | 2024-05-08 | 1. Add Battery Bank = 4 |  | 1151E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 2878A | 2024-04-24 | Open | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) | Open | 1230A | 2024-05-08 | 1. Add Battery Bank = 2 |  | 1197A | 2024-05-02 | 1. Add Battery Bank = 2
[10 empty] | DWDM | 8222A | 2024-04-24 | Open | 1. Add Battery Bank = 4 | Open | 1253A | 2024-04-24 | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) |  | 1203A | 2024-05-08 | 1. Add Battery Bank = 4
[10 empty] | DWDM | 8242B | 2024-04-24 | Open | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Open | 1266A | 2024-05-02 | 1.Add module = 1 |  | 1230A | 2024-05-08 | 1. Add Battery Bank = 2
[10 empty] | DWDM | 8229A | 2024-04-24 | Open | 1. Add Battery Bank = 3 | Open | 1271A | 2024-05-08 | 1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) |  | 1253A | 2024-04-24 | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker)
[10 empty] | DWDM | 8263A | 2024-04-24 | Open | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) | Open | 1359A | 2024-05-08 | 1. Swap breaker DC BREAKER: 63A X 2 |  | 1266A | 2024-05-02 | 1.Add module = 1
[10 empty] | DWDM | 1737A | 2024-04-24 | Open | 1. Replace CSU controller = 1 (Action FF) | Open | 1409A | 2024-05-02 | 1. Battery Bank = 6 |  | 1271A | 2024-05-08 | 1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 2402B | 2024-04-24 | Open | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | Open | 1475A | 2024-05-08 | 1.ODF Rack (Glass Door) |  | 1359A | 2024-05-08 | 1. Swap breaker DC BREAKER: 63A X 2
[10 empty] | IPRAN | 1127E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1553A | 2024-05-02 | 1. New plinth |  | 1409A | 2024-05-02 | 1. Battery Bank = 6
[10 empty] | IPRAN | 1017E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1554A | 2024-05-02 | 1.Add battery bank = 3 |  | 1475A | 2024-05-08 | 1.ODF Rack (Glass Door)
[10 empty] | IPRAN | 1018E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1560A | 2024-05-02 | 1.Add module = 1 |  | 1553A | 2024-05-02 | 1. New plinth
[10 empty] | IPRAN | 1019E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1563A | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) |  | 1554A | 2024-05-02 | 1.Add battery bank = 3
[10 empty] | IPRAN | 1020E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1607A | 2024-05-02 | 1. Decomm Cabinet |  | 1560A | 2024-05-02 | 1.Add module = 1
[10 empty] | IPRAN | 3864E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1610A | 2024-05-02 | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) |  | 1563A | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
[10 empty] | IPRAN | 1151E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1737A | 2024-04-24 | 1. Replace CSU controller = 1 (Action FF) |  | 1607A | 2024-05-02 | 1. Decomm Cabinet
[10 empty] | IPRAN | 1150E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1851A | 2024-05-08 | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) |  | 1610A | 2024-05-02 | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker)
[10 empty] | IPRAN | 2011E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) - (1x BLVD Power A, 1x LLVD Power B) | Open | 1859A | 2024-05-02 | 1.Add modules = 2 |  | 1737A | 2024-04-24 | 1. Replace CSU controller = 1 (Action FF)
[10 empty] | IPRAN | 1149E | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) | Open | 1899A | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) |  | 1851A | 2024-05-08 | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | IPRAN | 3404A | 2024-04-25 | Open | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) - NO NEED CME. | Open | 1918A | 2024-05-02 | 1. Add Battery Bank = 2 |  | 1859A | 2024-05-02 | 1.Add modules = 2
[10 empty] | DWDM | 8403A | 2023-09-22 | CME by regional | Extend platform = 1 | Open | 2011E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) - (1x BLVD Power A, 1x LLVD Power B) |  | 1899A | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | DWDM | 1553A | 2024-05-02 | Open | 1. New plinth | Open | 2021B | 2024-05-08 | 1.ODF Rack (Glass Door) |  | 1918A | 2024-05-02 | 1. Add Battery Bank = 2
[10 empty] | DWDM | 1409A | 2024-05-02 | Open | 1. Battery Bank = 6 | Open | 2402B | 2024-04-24 | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) |  | 2011E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) - (1x BLVD Power A, 1x LLVD Power B)
[10 empty] | DWDM | 1360A | 2024-05-02 | CME by regional | 1. Swap Cabine | Open | 2878A | 2024-04-24 | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) |  | 2021B | 2024-05-08 | 1.ODF Rack (Glass Door)
[10 empty] | DWDM | 6836A | 2024-05-02 | Open | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Open | 3404A | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) - NO NEED CME. |  | 2402B | 2024-04-24 | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4)
[10 empty] | DWDM | 4665A | 2024-05-02 | Open | 1. Add Battery Bank = 2 | Open | 3864E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) |  | 2878A | 2024-04-24 | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker)
[10 empty] | DWDM | 4672A | 2024-05-02 | Open | 1. New DCDPB =1 (Require 63A x 4 DC breaker) | Open | 4665A | 2024-05-02 | 1. Add Battery Bank = 2 |  | 3404A | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2) - NO NEED CME.
[10 empty] | DWDM | 4991A | 2024-05-02 | Open | 1. Add Battery Bank = 2 | Open | 4672A | 2024-05-02 | 1. New DCDPB =1 (Require 63A x 4 DC breaker) |  | 3864E | 2024-04-25 | 1.Swap Breaker = 2 (Require 16A x 2 to 10A x2)
[10 empty] | DWDM | 8208B | 2024-05-02 | Open | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Open | 4683A | 2024-05-02 | 1. Add Battery Bank = 3 |  | 4665A | 2024-05-02 | 1. Add Battery Bank = 2
[10 empty] | DWDM | 1063B | 2024-05-02 | Open | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Open | 4863B | 2024-04-24 | 1. Add Battery Bank = 1 |  | 4672A | 2024-05-02 | 1. New DCDPB =1 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 1197A | 2024-05-02 | Open | 1. Add Battery Bank = 2 | Open | 4991A | 2024-05-02 | 1. Add Battery Bank = 2 |  | 4683A | 2024-05-02 | 1. Add Battery Bank = 3
[10 empty] | DWDM | 1266A | 2024-05-02 | Open | 1.Add module = 1 | Open | 4998A | 2024-05-08 | 1. Add Battery Bank = 1 |  | 4863B | 2024-04-24 | 1. Add Battery Bank = 1
[10 empty] | DWDM | 1554A | 2024-05-02 | Open | 1.Add battery bank = 3 | Open | 6093A | 2024-05-08 | 1. Add Battery Bank = 1 |  | 4991A | 2024-05-02 | 1. Add Battery Bank = 2
[10 empty] | DWDM | 1560A | 2024-05-02 | Open | 1.Add module = 1 | Open | 6369A | 2024-05-08 | 1. Add Battery Bank = 6 |  | 4998A | 2024-05-08 | 1. Add Battery Bank = 1
[10 empty] | DWDM | 1563A | 2024-05-02 | Open | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Open | 6382A | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) |  | 6093A | 2024-05-08 | 1. Add Battery Bank = 1
[10 empty] | DWDM | 1607A | 2024-05-02 | Open | 1. Decomm Cabinet | Open | 6836A | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) |  | 6369A | 2024-05-08 | 1. Add Battery Bank = 6
[10 empty] | DWDM | 1610A | 2024-05-02 | Open | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Open | 8139B | 2024-05-02 | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) |  | 6382A | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 1899A | 2024-05-02 | Open | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Open | 8208B | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) |  | 6836A | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 1918A | 2024-05-02 | Open | 1. Add Battery Bank = 2 | Open | 8222A | 2024-04-24 | 1. Add Battery Bank = 4 |  | 8139B | 2024-05-02 | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 4683A | 2024-05-02 | Open | 1. Add Battery Bank = 3 | Open | 8224A | 2024-05-02 | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) |  | 8208B | 2024-05-02 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 6382A | 2024-05-02 | Open | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Open | 8229A | 2024-04-24 | 1. Add Battery Bank = 3 |  | 8222A | 2024-04-24 | 1. Add Battery Bank = 4
[10 empty] | DWDM | 8139B | 2024-05-02 | Open | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) | Open | 8242B | 2024-04-24 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) |  | 8224A | 2024-05-02 | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 8224A | 2024-05-02 | Open | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Open | 8263A | 2024-04-24 | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) |  | 8229A | 2024-04-24 | 1. Add Battery Bank = 3
[10 empty] | DWDM | 8294A | 2024-05-02 | Open | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) | Open | 8288B | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) |  | 8242B | 2024-04-24 | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 8322B | 2024-05-02 | Open | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) | Open | 8294A | 2024-05-02 | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) |  | 8263A | 2024-04-24 | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker)
[10 empty] | DWDM | 8439A | 2024-05-02 | Open | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Open | 8322B | 2024-05-02 | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) |  | 8288B | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | DWDM | 8513A | 2024-05-02 | Open | 1.Add battery bank = 2 | Open | 8367A | 2024-05-02 | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) |  | 8294A | 2024-05-02 | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker)
[10 empty] | DWDM | 8667A | 2024-05-02 | Open | 1.Add modules = 2 | Open | 8439A | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) |  | 8322B | 2024-05-02 | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker)
[10 empty] | DWDM | 1859A | 2024-05-02 | Open | 1.Add modules = 2 | Open | 8513A | 2024-05-02 | 1.Add battery bank = 2 |  | 8367A | 2024-05-02 | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | DWDM | 8288B | 2024-05-02 | Open | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Open | 8667A | 2024-05-02 | 1.Add modules = 2 |  | 8439A | 2024-05-02 | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | DWDM | 8367A | 2024-05-02 | Open | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | WIP | 7042A | 0 | BATTERY BANK = 4 |  | 8513A | 2024-05-02 | 1.Add battery bank = 2
[10 empty] | DWDM | 1271A | 2024-05-08 | Open | 1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | WIP | 7063A | 0 | BATTERY BANK = 8 |  | 8667A | 2024-05-02 | 1.Add modules = 2
[10 empty] | DWDM | 2021B | 2024-05-08 | Open | 1.ODF Rack (Glass Door) | WIP | 7570A | 0 | NEW DCPDB |  | (blank) | (blank) | (blank)
[10 empty] | DWDM | 4998A | 2024-05-08 | Open | 1. Add Battery Bank = 1 |  |  |  |  | WIP | 7042A | 0 | BATTERY BANK = 4
[10 empty] | DWDM | 1230A | 2024-05-08 | Open | 1. Add Battery Bank = 2 | [5 empty] | 7063A | 0 | BATTERY BANK = 8
[10 empty] | DWDM | 1475A | 2024-05-08 | Open | 1.ODF Rack (Glass Door) | [5 empty] | 7570A | 0 | NEW DCPDB
[10 empty] | DWDM | 1203A | 2024-05-08 | Open | 1. Add Battery Bank = 4 |  |  |  |  | Grand Total
[10 empty] | DWDM | 1359A | 2024-05-08 | Open | 1. Swap breaker DC BREAKER: 63A X 2
[10 empty] | DWDM | 1851A | 2024-05-08 | Open | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
[10 empty] | DWDM | 6369A | 2024-05-08 | Open | 1. Add Battery Bank = 6
[10 empty] | DWDM | 6093A | 2024-05-08 | Open | 1. Add Battery Bank = 1

## CME 14 MAY
Domain | Ring ID | Site ID |  | CME REMARKS | CME REQUIREMENT | Year | Month |  | Date Request
DWDM | 5GC | 1475A | Single | PRPO | 1.ODF Rack (Glass Door) | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door)
DWDM | C0103 | 1359A | Single | PRPO | 1. Swap breaker DC BREAKER: 63A X 2 | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2
DWDM | C0105P;CAR04;C0103;CT04;C0103 | 1049B | Single | PRPO | 1.Swap breaker = 16 (16x63A DC) | 2024 | May | 2024-05-01 | 2024-05-13 | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC)
DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | 1253A | Single | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | 2024 | April | 2024-04-01 | 2024-04-24 | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4
DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | 1851A | Multiple | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | 2024 | May | 2024-05-01 | 2024-05-08 | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder
DWDM | C0210P | 2878A | Single | PRPO | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) 2. Add Modules = 4 3. Battery Bank = 6 | 2024 | April | 2024-04-01 | 2024-04-24 | Single_2024_April_DWDM_C0210P_2878A_PRPO_1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) 2. Add Modules = 4 3. Battery Bank = 6
DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | 1859A | Single | PRPO | 1.Add modules = 2 2.Add battery bank = 4 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4
DWDM | C0407P | 1266A | Single | PRPO | 1.Add module = 1 2.Add battery bank = 1 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_C0407P_1266A_PRPO_1.Add module = 1 2.Add battery bank = 1
DWDM | C0407P | 1737A | Multiple | PRPO | 1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | 2024 | April | 2024-04-01 | 2024-04-24 | Multiple_2024_April_DWDM_C0407P_1737A_PRPO_1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1
DWDM | C0417P | 1203A | Single | PRPO | 1. Add Battery Bank = 4 2. Swap breaker DC BREAKER: 63A X 4 | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_C0417P_1203A_PRPO_1. Add Battery Bank = 4 2. Swap breaker DC BREAKER: 63A X 4
DWDM | C0417P;MAC RING 6/C09+;5GC | 2021B | Multiple | PRPO | 1.ODF Rack (Glass Door) | 2024 | May | 2024-05-01 | 2024-05-08 | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door)
DWDM | CT0120 | 2021B | Multiple | PRPO | 1.ODF Rack (Glass Door) | 2024 | May | 2024-05-01 | 2024-05-08 | Multiple_2024_May_DWDM_CT0120_2021B_PRPO_1.ODF Rack (Glass Door)
DWDM | CT0241P;C0417P | 1197A | Single | PRPO | 1. Add Battery Bank = 2 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_CT0241P;C0417P_1197A_PRPO_1. Add Battery Bank = 2
DWDM | CT0241P;C0417P;CAR02-ii+ | 1918A | Single | PRPO | 1. Add Battery Bank = 2 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2
DWDM | DWDM-120Ch | 1271A | Single | PRPO | 1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.battery bank = 6 | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_DWDM-120Ch_1271A_PRPO_1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.battery bank = 6
DWDM | DWDM-OLA1 | 8208B | Single | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) 2.Add Battery bank = 4 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_DWDM-OLA1_8208B_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) 2.Add Battery bank = 4
DWDM | E104 | 8294A | Single | PRPO | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 4 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_E104_8294A_PRPO_1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 4
DWDM | E104;EAR01 N EAR03 | 8263A | Single | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | 2024 | April | 2024-04-01 | 2024-04-24 | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5
DWDM | E104;EAR01 N EAR03 | 8288B | Single | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 7 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_E104;EAR01 N EAR03_8288B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 7
DWDM | E105 | 8139B | Single | PRPO | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.Add battery bank = 4 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_E105_8139B_PRPO_1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.Add battery bank = 4
DWDM | E105 | 8229A | Single | PRPO | 1. Add Battery Bank = 3 2 .Add Aircond = 1 (Action THOR) 3.Floor mounted DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | 2024 | April | 2024-04-01 | 2024-04-24 | Single_2024_April_DWDM_E105_8229A_PRPO_1. Add Battery Bank = 3 2 .Add Aircond = 1 (Action THOR) 3.Floor mounted DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
DWDM | E109 | 8222A | Single | PRPO | 1. Add Battery Bank = 4 2. Add Aircond = 1 (Action THOR) 3. DCPDB (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | 2024 | April | 2024-04-01 | 2024-04-24 | Single_2024_April_DWDM_E109_8222A_PRPO_1. Add Battery Bank = 4 2. Add Aircond = 1 (Action THOR) 3. DCPDB (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
DWDM | E109 | 8242B | Single | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | 2024 | April | 2024-04-01 | 2024-04-24 | Single_2024_April_DWDM_E109_8242B_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
DWDM | E109;EAR01;EAR01 N EAR03 | 8224A | Multiple | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | 2024 | May | 2024-05-01 | 2024-05-02 | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4
DWDM | E111 | 8322B | Single | PRPO | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_E111_8322B_PRPO_1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1
DWDM | E111 | 8439A | Single | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_E111_8439A_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
DWDM | E111;EAR01 N EAR03 | 8367A | Single | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_E111;EAR01 N EAR03_8367A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack
DWDM | E205 | 8403A | Multiple | PRPO | Extend platform = 1 | 2023 | September | 2023-09-01 | 2023-09-22 | Multiple_2023_September_DWDM_E205_8403A_PRPO_Extend platform = 1
DWDM | EAR06 | 8513A | Single | PRPO | 1.Add battery bank = 2 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_EAR06_8513A_PRPO_1.Add battery bank = 2
DWDM | EAR06 | 8667A | Single | PRPO | 1.Add modules = 2 2.Add battery bank = 6 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_EAR06_8667A_PRPO_1.Add modules = 2 2.Add battery bank = 6
DWDM | MAC RING 6/C09+ | 1230A | Single | PRPO | 1. Add Battery Bank = 2 2. Swap breaker DC BREAKER: 63A X 4 | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_MAC RING 6/C09+_1230A_PRPO_1. Add Battery Bank = 2 2. Swap breaker DC BREAKER: 63A X 4
DWDM | N103 | 4863B | Multiple | PRPO | 1. Add Battery Bank = 1 | 2024 | April | 2024-04-01 | 2024-04-24 | Multiple_2024_April_DWDM_N103_4863B_PRPO_1. Add Battery Bank = 1
DWDM | N104+ | 4665A | Single | PRPO | 1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_N104+_4665A_PRPO_1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1
DWDM | N104+ | 4672A | Single | PRPO | 1. New DCDPB =1 (Require 63A x 4 DC breaker) 2. New MGB = 1 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_N104+_4672A_PRPO_1. New DCDPB =1 (Require 63A x 4 DC breaker) 2. New MGB = 1
DWDM | N104+ | 4991A | Single | PRPO | 1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 4. Add Module = 2 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_N104+_4991A_PRPO_1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 4. Add Module = 2
DWDM | N104+;N107+ | 4998A | Single | PRPO | 1. Add Battery Bank = 1 | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1
DWDM | N106+ | 4683A | Single | PRPO | 1. Add Battery Bank = 3 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3
DWDM | PFSRING101/C0607P | 1063B | Single | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_PFSRING101/C0607P_1063B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
DWDM | PFSRING101/C0607P | 1899A | Single | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_PFSRING101/C0607P_1899A_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker)
DWDM | S301 | 1554A | Multiple | PRPO | 1.Add battery bank = 3 | 2024 | May | 2024-05-01 | 2024-05-02 | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3
DWDM | S301 | 1560A | Single | PRPO | 1.Add module = 1 2.Add battery bank = 2 3.Swap Breaker = 4 (Require 63A x 4 DC breaker) | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_S301_1560A_PRPO_1.Add module = 1 2.Add battery bank = 2 3.Swap Breaker = 4 (Require 63A x 4 DC breaker)
DWDM | S301 | 1563A | Single | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_S301_1563A_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
DWDM | S305 | 6093A | Single | PRPO | 1. Add Battery Bank = 1 2. DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 3. New MGB = 1 | 2024 | May | 2024-05-01 | 2024-05-08 | Single_2024_May_DWDM_S305_6093A_PRPO_1. Add Battery Bank = 1 2. DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 3. New MGB = 1
DWDM | S309 | 1556A | Multiple | PRPO | BATTERY BANK = 3 Remove battery = 1 | 2024 | May | 2024-05-01 | 2024-05-13 | Multiple_2024_May_DWDM_S309_1556A_PRPO_BATTERY BANK = 3 Remove battery = 1
DWDM | S309 | 2402B | Multiple | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | 2024 | April | 2024-04-01 | 2024-04-24 | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3
DWDM | ST21P | 6382A | Single | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) 2.Add top Fixing cable ladder = 1 | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_ST21P_6382A_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) 2.Add top Fixing cable ladder = 1
DWDM | ST21P;S504M | 6369A | Multiple | PRPO | 1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | 2024 | May | 2024-05-01 | 2024-05-08 | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery
DWDM | ST27P | 1607A | Single | PRPO | 1. Decomm Cabinet | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_ST27P_1607A_PRPO_1. Decomm Cabinet
DWDM | ST27P | 1610A | Single | PRPO | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 4.Relocate unuse battery to make space for Rectifier and DWDM rack | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_ST27P_1610A_PRPO_1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 4.Relocate unuse battery to make space for Rectifier and DWDM rack
DWDM | xx | 1553A | Multiple | PRPO | 1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | 2024 | May | 2024-05-01 | 2024-05-02 | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF
DWDM | (blank) | 1006A | Single | Completed | RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | 2023 | December | 2023-12-01 | 2023-12-21 | Single_2023_December_DWDM_(blank)_1006A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3
DWDM | (blank) | 1007A | Single | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | October | 2023-10-01 | 2023-10-13 | Single_2023_October_DWDM_(blank)_1007A_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 1070A | Single | Drop | BATTERY BANK = 1 | 2024 | January | 2024-01-01 | 2024-01-24 | Single_2024_January_DWDM_(blank)_1070A_Drop_BATTERY BANK = 1
DWDM | (blank) | 1073A | Single | Drop | NOT REQUIRED | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_1073A_Drop_NOT REQUIRED
DWDM | (blank) | 1080A | Single | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1080A_Completed_DCPDB = 1
DWDM | (blank) | 1081A | Multiple | Completed | BATTERY BANK = 2 | 2024 | January | 2024-01-01 | 2024-01-02 | Multiple_2024_January_DWDM_(blank)_1081A_Completed_BATTERY BANK = 2
DWDM | (blank) | 1081A | Multiple | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_1081A_Completed_DCPDB = 1
DWDM | (blank) | 1087A | Single | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1087A_Completed_DCPDB = 1
DWDM | (blank) | 1093A | Single | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1093A_Completed_DCPDB = 1
DWDM | (blank) | 1099A | Single | Completed | RECTIFIER + DCPDB = 1 BATTERTY BANK =3 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1099A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =3
DWDM | (blank) | 1145A | Single | Completed | DC BREAKER : 63A X 4 MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1145A_Completed_DC BREAKER : 63A X 4 MGB = 1
DWDM | (blank) | 1146A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1146A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1153A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1153A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1154A | Single | Drop | ODF CABINET = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1154A_Drop_ODF CABINET = 1
DWDM | (blank) | 1156A | Single | Drop | ODF CABINET = 1 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_1156A_Drop_ODF CABINET = 1
DWDM | (blank) | 1169A | Multiple | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_1169A_Completed_DCPDB = 1
DWDM | (blank) | 1169A | Multiple | Drop | ODF CABINET = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_1169A_Drop_ODF CABINET = 1
DWDM | (blank) | 1172A | Single | Completed | DC BREAKER : 63A X 4 MGB = 1 | 2023 | October | 2023-10-01 | 2023-10-19 | Single_2023_October_DWDM_(blank)_1172A_Completed_DC BREAKER : 63A X 4 MGB = 1
DWDM | (blank) | 1196A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_1196A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1246A | Single | Completed | DC BREAKER: 63 A X 4 POLE RELOCATE = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_1246A_Completed_DC BREAKER: 63 A X 4 POLE RELOCATE = 1
DWDM | (blank) | 1298A | Single | Completed | DCPDB = 1 CABLE LADDER = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_1298A_Completed_DCPDB = 1 CABLE LADDER = 1
DWDM | (blank) | 1309B | Single | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_1309B_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 1360A | Multiple | Completed | 1. Swap Cabine | 2024 | May | 2024-05-01 | 2024-05-02 | Multiple_2024_May_DWDM_(blank)_1360A_Completed_1. Swap Cabine
DWDM | (blank) | 1360A | Multiple | Completed | BATTERY BANK = 2 DECOM CABINET=1 | 2024 | January | 2024-01-01 | 2024-01-02 | Multiple_2024_January_DWDM_(blank)_1360A_Completed_BATTERY BANK = 2 DECOM CABINET=1
DWDM | (blank) | 1360A | Multiple | Completed | DC BREAKER: 63A X 2 POLE RELOCATE: 1 | 2023 | October | 2023-10-01 | 2023-10-31 | Multiple_2023_October_DWDM_(blank)_1360A_Completed_DC BREAKER: 63A X 2 POLE RELOCATE: 1
DWDM | (blank) | 1360A | Multiple | Drop | NOT REQUIRED | 2024 | January | 2024-01-01 | 2024-01-18 | Multiple_2024_January_DWDM_(blank)_1360A_Drop_NOT REQUIRED
DWDM | (blank) | 1362B | Multiple | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_1362B_Completed_DCPDB = 1
DWDM | (blank) | 1362B | Multiple | Completed | RECTTIFIER MODULE = 1 BATTERY BANK = 3 | 2024 | January | 2024-01-01 | 2024-01-02 | Multiple_2024_January_DWDM_(blank)_1362B_Completed_RECTTIFIER MODULE = 1 BATTERY BANK = 3
DWDM | (blank) | 1367A | Single | Drop | NOT REQUIRED | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_1367A_Drop_NOT REQUIRED
DWDM | (blank) | 1378B | Single | Completed | DC BREAKER: 63A X 2 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_1378B_Completed_DC BREAKER: 63A X 2
DWDM | (blank) | 1402A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_1402A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1406B | Single | Completed | DCPDB = 1 | N/A | N/A |  | #N/A | Single_N/A_N/A_DWDM_(blank)_1406B_Completed_DCPDB = 1
DWDM | (blank) | 1408A | Single | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_1408A_Completed_DCPDB = 1
DWDM | (blank) | 1409A | Single | Completed | RECTIFIER + DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-19 | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1
DWDM | (blank) | 1413A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1413A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1458A | Single | Completed | BATTERY BANK = 1 | 2024 | January | 2024-01-01 | 2024-01-02 | Single_2024_January_DWDM_(blank)_1458A_Completed_BATTERY BANK = 1
DWDM | (blank) | 1525A | Multiple | Completed | DC BREAKER: 16A X 2 | 2023 | October | 2023-10-01 | 2023-10-31 | Multiple_2023_October_DWDM_(blank)_1525A_Completed_DC BREAKER: 16A X 2
DWDM | (blank) | 1525A | Multiple | Completed | DC BREAKER: 63 A X 4 | 2023 | October | 2023-10-01 | 2023-10-31 | Multiple_2023_October_DWDM_(blank)_1525A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1533A | Multiple | Completed | BATTERY RACK = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_1533A_Completed_BATTERY RACK = 1
DWDM | (blank) | 1533A | Multiple | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_1533A_Completed_DCPDB = 1
DWDM | (blank) | 1553A | Multiple | Completed | RECTIFIER + DCPDB = 1 BATTERY BANK =3 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_1553A_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK =3
DWDM | (blank) | 1554A | Multiple | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-22 | Multiple_2023_October_DWDM_(blank)_1554A_Completed_DCPDB = 1
DWDM | (blank) | 1556A | Multiple | Completed | ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2 | 2024 | January | 2024-01-01 | 2024-01-18 | Multiple_2024_January_DWDM_(blank)_1556A_Completed_ADD DCPDB c/w 63A DC x 8&32A DC x 2&10A DC x 2
DWDM | (blank) | 1556A | Multiple | Completed | BATTERY BANK = 6 BATTERY RACK = 1 | 2024 | January | 2024-01-01 | 2024-01-02 | Multiple_2024_January_DWDM_(blank)_1556A_Completed_BATTERY BANK = 6 BATTERY RACK = 1
DWDM | (blank) | 1556A | Multiple | Completed | DC BREAKER : 63A X 4 MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_1556A_Completed_DC BREAKER : 63A X 4 MGB = 1
DWDM | (blank) | 1591A | Single | Completed | BATTERY BANK = 3 BATTERY RACK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1591A_Completed_BATTERY BANK = 3 BATTERY RACK = 1
DWDM | (blank) | 1599A | Multiple | Completed | BATTERY BANK = 3 BATTERY RACK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_1599A_Completed_BATTERY BANK = 3 BATTERY RACK = 1
DWDM | (blank) | 1599A | Multiple | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_1599A_Completed_DCPDB = 1
DWDM | (blank) | 1611A | Single | Completed | DCPDB = 1 | N/A | N/A |  | #N/A | Single_N/A_N/A_DWDM_(blank)_1611A_Completed_DCPDB = 1
DWDM | (blank) | 1627B | Single | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1627B_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 1649A | Single | Completed | RECTIFIER+ DCPDB = 1 BATTERY BANK = 3 | N/A | N/A |  | 0 | Single_N/A_N/A_DWDM_(blank)_1649A_Completed_RECTIFIER+ DCPDB = 1 BATTERY BANK = 3
DWDM | (blank) | 1701A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_1701A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1736B | Single | Completed | 19" RACK = 1 | N/A | N/A |  | 0 | Single_N/A_N/A_DWDM_(blank)_1736B_Completed_19" RACK = 1
DWDM | (blank) | 1737A | Multiple | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_1737A_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 1760A | Single | Completed | CABINET DISMANTLE = 1 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_1760A_Completed_CABINET DISMANTLE = 1
DWDM | (blank) | 1770B | Single | Completed | AC BREAKER : 32 X 3 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1770B_Completed_AC BREAKER : 32 X 3
DWDM | (blank) | 1787B | Single | Completed | DC BREAKER: 63A X 2 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_1787B_Completed_DC BREAKER: 63A X 2
DWDM | (blank) | 1851A | Multiple | Completed | DC BREAKER: 63 A X 4 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_1851A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 1855B | Multiple | Completed | DCPDB = 1 | 2023 | December | 2023-12-01 | 2023-12-14 | Multiple_2023_December_DWDM_(blank)_1855B_Completed_DCPDB = 1
DWDM | (blank) | 1855B | Multiple | Completed | RECTIFIER + DCPDB = 1 | 2024 | January | 2024-01-01 | 2024-01-04 | Multiple_2024_January_DWDM_(blank)_1855B_Completed_RECTIFIER + DCPDB = 1
DWDM | (blank) | 2070B | Single | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1
DWDM | (blank) | 2086A | Single | Completed | DC BREAKER: 63A X 2 | 2023 | October | 2023-10-01 | 2023-10-13 | Single_2023_October_DWDM_(blank)_2086A_Completed_DC BREAKER: 63A X 2
DWDM | (blank) | 2227B | Multiple | Completed | BATTERY BANK = 3 BATTERY RACK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_2227B_Completed_BATTERY BANK = 3 BATTERY RACK = 1
DWDM | (blank) | 2227B | Multiple | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_2227B_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 2356B | Multiple | Completed | DC BREAKER : 63A X 8 40 A X 12 MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-01 | Multiple_2023_September_DWDM_(blank)_2356B_Completed_DC BREAKER : 63A X 8 40 A X 12 MGB = 1
DWDM | (blank) | 2356B | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 6 | 2024 | January | 2024-01-01 | 2024-01-04 | Multiple_2024_January_DWDM_(blank)_2356B_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 6
DWDM | (blank) | 2388B | Multiple | Completed | BATTERY BANK = 3 BATTERY RACK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_2388B_Completed_BATTERY BANK = 3 BATTERY RACK = 1
DWDM | (blank) | 2388B | Multiple | Completed | DC BREAKER = 63A X 4 DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_2388B_Completed_DC BREAKER = 63A X 4 DCPDB = 1
DWDM | (blank) | 2402B | Multiple | Completed | BATTERY BANK = 3 BATTERY RACK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_2402B_Completed_BATTERY BANK = 3 BATTERY RACK = 1
DWDM | (blank) | 2632A | Single | Completed | AC BREAKER : 32 X 3 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_2632A_Completed_AC BREAKER : 32 X 3
DWDM | (blank) | 2833A | Single | Completed | AC BREAKER : 32 X 1 I-BEAM = 1 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_2833A_Completed_AC BREAKER : 32 X 1 I-BEAM = 1
DWDM | (blank) | 4000A | Single | Completed | DC BREAKER: 63A X 12 | 2023 | November | 2023-11-01 | 2023-11-22 | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12
DWDM | (blank) | 4085D | Single | Completed | RECTTIFIER MODULE = 2 BATTERY BANK = 2 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_4085D_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2
DWDM | (blank) | 4118A | Single | Completed | DCPDB = 1 | 2023 | December | 2023-12-01 | 2023-12-19 | Single_2023_December_DWDM_(blank)_4118A_Completed_DCPDB = 1
DWDM | (blank) | 4188A | Single | Completed | RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_4188A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3
DWDM | (blank) | 4368A | Single | Completed | DC BREAKER : 63A X 4 MGB = 1 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_4368A_Completed_DC BREAKER : 63A X 4 MGB = 1
DWDM | (blank) | 4427B | Single | Completed | RECTIFIER + DCPDB = 1 BATTERY BANK =3 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_4427B_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK =3
DWDM | (blank) | 4440B | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_4440B_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 4454B | Multiple | Completed | DC BREAKER : 100A X 2 I-BEAM = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_4454B_Completed_DC BREAKER : 100A X 2 I-BEAM = 1
DWDM | (blank) | 4454B | Multiple | Completed | RECTIFIER + DCPDB = 1 BATTERY BANK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_4454B_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK = 1
DWDM | (blank) | 4465A | Single | Completed | BATTERY BANK = 7 | 2023 | November | 2023-11-01 | 2023-11-01 | Single_2023_November_DWDM_(blank)_4465A_Completed_BATTERY BANK = 7
DWDM | (blank) | 4509A | Single | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_4509A_Completed_DCPDB = 1
DWDM | (blank) | 4516A | Single | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_4516A_Completed_DCPDB = 1
DWDM | (blank) | 4621A | Single | Completed | BATTERY BANK = 3 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_4621A_Completed_BATTERY BANK = 3
DWDM | (blank) | 4625A | Single | Completed | BATTERY BANK = 3 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_4625A_Completed_BATTERY BANK = 3
DWDM | (blank) | 4640A | Single | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-01 | Single_2023_November_DWDM_(blank)_4640A_Completed_DCPDB = 1
DWDM | (blank) | 4662A | Single | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-06 | Single_2023_October_DWDM_(blank)_4662A_Completed_DCPDB = 1
DWDM | (blank) | 4663A | Multiple | Completed | DC BREAKER : 100A X 2 | 2023 | December | 2023-12-01 | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4663A_Completed_DC BREAKER : 100A X 2
DWDM | (blank) | 4663A | Multiple | Completed | RECTIFIER MODULE = 1 BATTERY BANK = 3 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_4663A_Completed_RECTIFIER MODULE = 1 BATTERY BANK = 3
DWDM | (blank) | 4669A | Single | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_4669A_Completed_DCPDB = 1
DWDM | (blank) | 4678A | Single | Completed | DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-06 | Single_2023_October_DWDM_(blank)_4678A_Completed_DCPDB = 1
DWDM | (blank) | 4685B | Multiple | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4685B_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 4685B | Multiple | Completed | RECTTIFIER MODULE = 2 BATTERY BANK = 2 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4685B_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2
DWDM | (blank) | 4686B | Multiple | Completed | DC BREAKER: 63 A X 4 | 2023 | December | 2023-12-01 | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4686B_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 4686B | Multiple | Completed | RECTIFIER + DCPDB = 1 BATTERY BANK = 3 BATTERY RACK = 1 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_4686B_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK = 3 BATTERY RACK = 1
DWDM | (blank) | 4688A | Multiple | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4688A_Completed_DCPDB = 1
DWDM | (blank) | 4688A | Multiple | Completed | RECTTIFIER MODULE = 1 BATTERY BANK = 2 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4688A_Completed_RECTTIFIER MODULE = 1 BATTERY BANK = 2
DWDM | (blank) | 4689A | Multiple | Completed | BATTERY BANK = 1 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_4689A_Completed_BATTERY BANK = 1
DWDM | (blank) | 4689A | Multiple | Completed | DCPDB = 1 | 2023 | December | 2023-12-01 | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4689A_Completed_DCPDB = 1
DWDM | (blank) | 4692A | Single | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-09 | Single_2023_November_DWDM_(blank)_4692A _Completed_DCPDB = 1
DWDM | (blank) | 4693A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_4693A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 4770A | Single | Completed | RECTTIFIER MODULE = 2 BATTERY BANK = 2 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_4770A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2
DWDM | (blank) | 4863B | Multiple | Completed | AC BREAKER : 32 X 3 | 2023 | November | 2023-11-01 | 2023-11-30 | Multiple_2023_November_DWDM_(blank)_4863B_Completed_AC BREAKER : 32 X 3
DWDM | (blank) | 4932A | Single | Completed | BATTERY BANK = 2 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_4932A_Completed_BATTERY BANK = 2
DWDM | (blank) | 4938A | Single | Completed | RECTIFIER + DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1
DWDM | (blank) | 4940A | Single | Completed | BATTERY BANK = 2 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_4940A_Completed_BATTERY BANK = 2
DWDM | (blank) | 4946A | Single | Drop | DROP | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP
DWDM | (blank) | 4950B | Multiple | Completed | DC BREAKER: 63 A X 4 | 2023 | October | 2023-10-01 | 2023-10-06 | Multiple_2023_October_DWDM_(blank)_4950B_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 4950B | Multiple | Completed | RECTIFIER + DCPDB = 1 BATTERTY BANK =2 | 2023 | October | 2023-10-01 | 2023-10-06 | Multiple_2023_October_DWDM_(blank)_4950B_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =2
DWDM | (blank) | 4956B | Multiple | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4956B_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 4956B | Multiple | Completed | RECTTIFIER MODULE = 2 BATTERY BANK = 2 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4956B_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2
DWDM | (blank) | 4965A | Multiple | Completed | BATTERY BANK = 1 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_4965A_Completed_BATTERY BANK = 1
DWDM | (blank) | 4965A | Multiple | Completed | DCPDB = 1 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_4965A_Completed_DCPDB = 1
DWDM | (blank) | 4968A | Single | Completed | AC BREAKER : 32 X 3 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_4968A_Completed_AC BREAKER : 32 X 3
DWDM | (blank) | 4973B | Multiple | Completed | MGB = 1 | 2023 | December | 2023-12-01 | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4973B_Completed_MGB = 1
DWDM | (blank) | 4973B | Multiple | Completed | RECTIFIER + DCPDB = 1 | 2023 | December | 2023-12-01 | 2023-12-21 | Multiple_2023_December_DWDM_(blank)_4973B_Completed_RECTIFIER + DCPDB = 1
DWDM | (blank) | 4985A | Single | Completed | RECTIFIER + DCPDB = 1 BATTERTY BANK =2 | 2023 | November | 2023-11-01 | 2023-11-08 | Single_2023_November_DWDM_(blank)_4985A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =2
DWDM | (blank) | 4986A | Multiple | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4986A_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 4986A | Multiple | Completed | RECTTIFIER MODULE = 2 BATTERY BANK = 2 | 2023 | November | 2023-11-01 | 2023-11-08 | Multiple_2023_November_DWDM_(blank)_4986A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2
DWDM | (blank) | 4988A | Single | Completed | BATTERY BANK = 2 | 2023 | October | 2023-10-01 | 2023-10-02 | Single_2023_October_DWDM_(blank)_4988A_Completed_BATTERY BANK = 2
DWDM | (blank) | 4992A | Multiple | Completed | 1.Swap breaker = 4 (4x100A DC) | 2024 | May | 2024-05-01 | 2024-05-13 | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC)
DWDM | (blank) | 4992A | Multiple | Drop | NOT REQUIRED | N/A | N/A |  | N/A | Multiple_N/A_N/A_DWDM_(blank)_4992A_Drop_NOT REQUIRED
DWDM | (blank) | 6000A | Single | Completed | DC BREAKER: 63 A X 4 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 6026A | Single | Completed | DC BREAKER: 63A X 3 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_6026A_Completed_DC BREAKER: 63A X 3
DWDM | (blank) | 6043A | Single | Drop | RECTIFIER + DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-30 | Single_2023_November_DWDM_(blank)_6043A _Drop_RECTIFIER + DCPDB = 1
DWDM | (blank) | 6083A | Single | Completed | RECTIFIER + DCPDB = 1 BATTERTY BANK =3 | 2023 | November | 2023-11-01 | 2023-11-30 | Single_2023_November_DWDM_(blank)_6083A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =3
DWDM | (blank) | 6138A | Multiple | Completed | DISMANTLE CABINET = 1 | 2024 | January | 2024-01-01 | 2024-01-04 | Multiple_2024_January_DWDM_(blank)_6138A_Completed_DISMANTLE CABINET = 1
DWDM | (blank) | 6138A | Multiple | Completed | MGB = 1 | 2023 | August | 2023-08-01 | 2023-08-28 | Multiple_2023_August_DWDM_(blank)_6138A_Completed_MGB = 1
DWDM | (blank) | 6283A | Multiple | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_6283A_Completed_DCPDB = 1
DWDM | (blank) | 6283A | Multiple | Completed | RECTIFIER + DCPDB = 1 BATTERY BANK =1 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_6283A_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK =1
DWDM | (blank) | 6369A | Multiple | Completed | DC BREAKER : 63A X 4 MGB = 1 | 2023 | November | 2023-11-01 | 2023-11-17 | Multiple_2023_November_DWDM_(blank)_6369A_Completed_DC BREAKER : 63A X 4 MGB = 1
DWDM | (blank) | 6442A | Single | Completed | DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_6442A_Completed_DCPDB = 1
DWDM | (blank) | 6502A | Multiple | Completed | BATTERY BANK = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1
DWDM | (blank) | 6502A | Multiple | Completed | DC BREAKER: 63A X 3 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_6502A_Completed_DC BREAKER: 63A X 3
DWDM | (blank) | 6576A | Multiple | Completed | DC BREAKER: 63A X 2 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_6576A_Completed_DC BREAKER: 63A X 2
DWDM | (blank) | 6576A | Multiple | Drop | RECTIFIER + DCPDB = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Multiple_2023_November_DWDM_(blank)_6576A_Drop_RECTIFIER + DCPDB = 1
DWDM | (blank) | 6836A | Single | Completed | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | 2024 | May | 2024-05-01 | 2024-05-02 | Single_2024_May_DWDM_(blank)_6836A_Completed_1.Swap Breaker = 4 (Require 63A x 4 DC breaker)
DWDM | (blank) | 6955A | Single | Completed | DCPDB = 1 UNIT MGB = 1 | 2023 | November | 2023-11-01 | 2023-11-20 | Single_2023_November_DWDM_(blank)_6955A_Completed_DCPDB = 1 UNIT MGB = 1
DWDM | (blank) | 8023B | Single | Drop | NOT REQUIRED | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_8023B_Drop_NOT REQUIRED
DWDM | (blank) | 8025A | Multiple | Completed | MGB = 1 CABLE LADDER= 1 | 2023 | September | 2023-09-01 | 2023-09-01 | Multiple_2023_September_DWDM_(blank)_8025A_Completed_MGB = 1 CABLE LADDER= 1
DWDM | (blank) | 8025A | Multiple | Drop | ODF CABINET = I UNIT | 2023 | September | 2023-09-01 | 2023-09-04 | Multiple_2023_September_DWDM_(blank)_8025A_Drop_ODF CABINET = I UNIT
DWDM | (blank) | 8035A | Single | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 2 BATTERY RACK = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_8035A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 2 BATTERY RACK = 1
DWDM | (blank) | 8061A | Multiple | Completed | DC BREAKER = 63A X 4 DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8061A_Completed_DC BREAKER = 63A X 4 DCPDB = 1
DWDM | (blank) | 8061A | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 8 BATTERY RACK = 2 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8061A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 8 BATTERY RACK = 2
DWDM | (blank) | 8128A | Multiple | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8128A_Completed_DCPDB = 1
DWDM | (blank) | 8128A | Multiple | Completed | RECTIFIER MODULE = 3 BATTERY BANK = 3 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8128A_Completed_RECTIFIER MODULE = 3 BATTERY BANK = 3
DWDM | (blank) | 8191A | Multiple | Completed | RECTTIFIER MODULE = 3 BATTERY BANK = 2 | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_8191A_Completed_RECTTIFIER MODULE = 3 BATTERY BANK = 2
DWDM | (blank) | 8191A | Multiple | Drop | NOT REQUIRED | 2023 | October | 2023-10-01 | 2023-10-02 | Multiple_2023_October_DWDM_(blank)_8191A_Drop_NOT REQUIRED
DWDM | (blank) | 8211A | Single | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-19 | Single_2023_September_DWDM_(blank)_8211A _Completed_DCPDB = 1
DWDM | (blank) | 8224A | Multiple | Completed | DC BREAKER: 63 A X 4 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8224A_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 8268A | Single | Completed | MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_8268A_Completed_MGB = 1
DWDM | (blank) | 8321A | Single | Completed | RECTIFIER + DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-06 | Single_2023_October_DWDM_(blank)_8321A_Completed_RECTIFIER + DCPDB = 1
DWDM | (blank) | 8330A | Single | Completed | BATTERY BANK = 1 | 2023 | October | 2023-10-01 | 2023-10-31 | Single_2023_October_DWDM_(blank)_8330A_Completed_BATTERY BANK = 1
DWDM | (blank) | 8350B | Single | Drop | NOT REQUIRED | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_8350B_Drop_NOT REQUIRED
DWDM | (blank) | 8353A | Multiple | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8353A_Completed_DCPDB = 1
DWDM | (blank) | 8353A | Multiple | Completed | RECTIFIER MODULE = 1 BATTERY BANK = 2 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8353A_Completed_RECTIFIER MODULE = 1 BATTERY BANK = 2
DWDM | (blank) | 8354A | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 4 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8354A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 4
DWDM | (blank) | 8354A | Multiple | Drop | NOT REQUIRED | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8354A_Drop_NOT REQUIRED
DWDM | (blank) | 8403A | Multiple | Completed | DC BREAKER : 100A X 2 | 2024 | April | 2024-04-01 | 2024-04-22 | Multiple_2024_April_DWDM_(blank)_8403A_Completed_DC BREAKER : 100A X 2
DWDM | (blank) | 8403A | Multiple | Completed | RECTTIFIER MODULE = 2 Extend platform = 1 (PMC) | 2023 | September | 2023-09-01 | 2023-09-22 | Multiple_2023_September_DWDM_(blank)_8403A_Completed_RECTTIFIER MODULE = 2 Extend platform = 1 (PMC)
DWDM | (blank) | 8408A | Single | Completed | BATTERY BANK = 2 | 2023 | December | 2023-12-01 | 2023-12-15 | Single_2023_December_DWDM_(blank)_8408A_Completed_BATTERY BANK = 2
DWDM | (blank) | 8429B | Single | Drop | NOT REQUIRED | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED
DWDM | (blank) | 8434A | Multiple | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8434A_Completed_DCPDB = 1
DWDM | (blank) | 8434A | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 4 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8434A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 4
DWDM | (blank) | 8473A | Multiple | Completed | DC BREAKER: 100A X 2 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8473A_Completed_DC BREAKER: 100A X 2
DWDM | (blank) | 8473A | Multiple | Completed | RECTTIFIER MODULE = 2 BATTERY BANK = 2 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8473A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2
DWDM | (blank) | 8473A | Multiple | Drop | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8473A_Drop_DCPDB = 1
DWDM | (blank) | 8483A | Single | Completed | MGB = 1 | 2023 | September | 2023-09-01 | 2023-09-18 | Single_2023_September_DWDM_(blank)_8483A_Completed_MGB = 1
DWDM | (blank) | 8709A | Single | Completed | RECTIFIER + DCPDB = 1 | 2023 | October | 2023-10-01 | 2023-10-06 | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1
DWDM | (blank) | 8712A | Multiple | Completed | BATTERY BANK = 2 | 2024 | January | 2024-01-01 | 2024-01-04 | Multiple_2024_January_DWDM_(blank)_8712A_Completed_BATTERY BANK = 2
DWDM | (blank) | 8712A | Multiple | Completed | DCPDB = 1 | 2023 | December | 2023-12-01 | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_8712A_Completed_DCPDB = 1
DWDM | (blank) | 8850B | Multiple | Completed | DC BREAKER: 63 A X 4 | 2023 | August | 2023-08-01 | 2023-08-29 | Multiple_2023_August_DWDM_(blank)_8850B_Completed_DC BREAKER: 63 A X 4
DWDM | (blank) | 8850B | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 3 | 2024 | January | 2024-01-01 | 2024-01-04 | Multiple_2024_January_DWDM_(blank)_8850B_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 3
DWDM | (blank) | 8923B | Single | Drop | ADD 100A X 2 BREAKER ADD GROUNDING X 1 ADD PLINTH X 1 ADD ODF PANEL X 1 | 2024 | January | 2024-01-01 | 2024-01-23 | Single_2024_January_DWDM_(blank)_8923B_Drop_ADD 100A X 2 BREAKER ADD GROUNDING X 1 ADD PLINTH X 1 ADD ODF PANEL X 1
DWDM | (blank) | 8936A | Multiple | Completed | DC BREAKER : 100A X 2 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8936A_Completed_DC BREAKER : 100A X 2
DWDM | (blank) | 8936A | Multiple | Completed | RECTIFIER MODULE = 1 BATTERY BANK = 3 Power Cable route = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8936A_Completed_RECTIFIER MODULE = 1 BATTERY BANK = 3 Power Cable route = 1
DWDM | (blank) | 8953A | Single | Completed | RECTIFIER + DCPDB = 1 BATTERY BANK = 3 | 2023 | September | 2023-09-01 | 2023-09-27 | Single_2023_September_DWDM_(blank)_8953A_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK = 3
DWDM | (blank) | 8965A | Multiple | Completed | DCPDB = 1 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8965A_Completed_DCPDB = 1
DWDM | (blank) | 8965A | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 3 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM_(blank)_8965A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 3
DWDM Total | (blank) | 8965A | Multiple | Completed | RECTIFIER MODULE = 2 BATTERY BANK = 3 | 2023 | September | 2023-09-01 | 2023-09-27 | Multiple_2023_September_DWDM Total_(blank)_8965A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 3
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
_______
Formulas:
Date Request = [Date Request, row above]

## Master Data_Ori
270 | 270 | 266 | 270 | 270 | 270 | 267 | 270 | 270 | 270 | 13 | 61 | 33 | 270 | 270 | 188 | 188 | 188 | 188 | 270 | 188 | 188 | 227 | 270 | 270 | 270 | 88 | 88 | 270 | 33 | 61 |  | 27 | 135 | 129 | 228 | 215 | 206 | 206 |  | 108 | 22 | 39 | 112 | 127 | 193 | 136 | 41 | 63
Ring ID | Actual Utilisation | Forecaseted Utilisation | Batch | Site ID | DUID2 | Utilisation2 | Site Name | SOW | Subcon | Plan Survey Date | Survey Date | TSSR Date | CME Tracker Zul | CME Request | Request Yr | Request Month | DWDM | Project/ Ring | DWDM | Site ID | Status | Type | Proposed Cabinet type | TSSR Status 13/5/2024 | TSSR Status 17/5/2024 | Plan MOS | WorkWeek_Install | Material On Site | Issue Remarks - Rodney | Issue Remarks (Stella) | Remarks (Ummu) | Plan Power Up | Power Up | Plan Integration | Plan Integration (Yaohan) | Integration | Integrated Date | WorkWeek_Integration | Priority Rollout | Follow-up (Stella) | Remarks (Stella) | Column2 | Migration | Break Ring Status | Break Ring Date | Remarks | NFS | Plan RFS | Filter
N401 | 55.59% | #N/A | Pending Po | 4686B | MAC | #N/A |  | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4686B_Completed_DC BREAKER: 63 A X 4 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4686B | 4686B | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | #N/A |  |  |  | #N/A | [5 empty] | #N/A |  |  |  | #N/A
N401 | 55.59% | #N/A | Pending Po | 4965A | MAC | #N/A |  | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4965A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4965A | 4965A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | #N/A |  |  |  | #N/A | [5 empty] | #N/A |  |  |  | #N/A
N401 | 55.59% | #N/A | Pending Po | 4118A | MAC001 Machang Bubuk 2 | #N/A | Machang Bubuk 2 | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Single_2023_December_DWDM_(blank)_4118A_Completed_DCPDB = 1 | Single | 2023 | December | DWDM | (blank) | DWDM-4118A | 4118A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | #N/A |  |  |  | #N/A | [5 empty] | #N/A |  |  |  | #N/A
N401 | 55.59% | #N/A | Pending Po | 4689A | MAC001 Tmn Desa Impian | #N/A | Tmn Desa Impian | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4689A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4689A | 4689A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | #N/A |  |  |  | #N/A | [5 empty] | #N/A |  |  |  | #N/A
N401 | 55.59% | #N/A | Pending Po | 4952B | MAG001 Selama | #N/A | Selama | 1800VPRO 1 subrack | Fo&T |  |  | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | #N/A |  |  |  | #N/A | [5 empty] | #N/A |  |  |  | #N/A
N401 | 55.59% | #N/A | Pending Po | 4000A | MCR002 PRI | #N/A | MSC Prai | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | N/A | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | #N/A |  |  |  | #N/A | [5 empty] | #N/A |  |  |  | #N/A
C0105P | #N/A | 98.91% | 2024 Q1 | 1049B | xD_DWDM_BRKRing_C0105P_1049B MCR KPG_0004582309050Y_00045824006623 | 98.91% | 1049B-MCR-002-KPG | 1800VPRO 1 rack 4subrack | Advance |  | 2024-01-30 |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-10 | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1253A | xD_DWDM_BRKRing_C0204_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 73.65% | 1253A Plaza Pengkalan | 9800M12 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | Indoor Rack | 1.7 TSSR Approved | 1.7 TSSR Approved |  |  |  | Technical Request On HOLD |  |  | 2024-05-20 |  |  | Pending ES PO |  |  |  | P2 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1261A | xD_DWDM_BRKRing_C0204_1261A KWSP_0004582309050Y_00045824006623 | 73.65% | 1261A KWSP | 9800M12 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR |  |  |  | Technical Request On HOLD | [5 empty] | Pending ES PO |  |  |  | P2 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1851A | xD_DWDM_BRKRing_C0204_18451A KL Plaza2_0004582309050Y_00045824006623 | 73.65% | 1851A-MAG(M14)-001 KL Plaza 2 | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval |  |  |  | Technical Request On HOLD | [5 empty] | Pending ES PO |  |  |  | P2 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0204 | 25.96% | 73.65% | 2024 Q1 | 1869A | xD_DWDM_BRKRing_C0204_1869A Daya Bumi_0004582309050Y_00045824006623 | 73.65% | 1869A Dayabumi | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending CME approval |  |  |  | Technical Request On HOLD | [5 empty] | Pending ES PO |  |  |  | P2 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0210P | #N/A | 149.5% | 2024 Q1 | 1253A | xD_DWDM_BRKRing_C0210P_1253A Plaza Pengkalan_0004582309010S_00045824006622 | 149.5% | 1253A Plaza Pengkalan | 1800 1rack 2 subrack | Advance |  | 2024-01-27 |  | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | #N/A | #N/A | #N/A | 2024-04-23 | Wk17 | 2024-04-23 | [6 empty] | Pending ES PO |  |  |  | P3 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-31 | #N/A
C0210P | #N/A | 149.5% | 2024 Q1 | 1859A | xD_DWDM_BRKRing_C0210P_1859A Midvalleycas_0004582309010S_00045824006622 | 149.5% | 1859A Midvalleycas | 1800 1rack 3 subrack | Advance |  | 2024-01-26 | 2024-02-07 | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4 | Single | 2024 | May | DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | DWDM-1859A | 1859A | PRPO | 1.Add modules = 2 | #N/A | #N/A | #N/A | 2024-04-24 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  |  |  | P3 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-31 | #N/A
C0210P | #N/A | 149.5% | 2024 Q1 | 2878A | xD_DWDM_BRKRing_C0210P_2878A Mont Kiara_0004582309050Y_00045824006623 | 149.5% | 2878A Mont Kiara | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-26 | 2024-02-07 | Single_2024_April_DWDM_C0210P_2878A_PRPO_1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) 2. Add Modules = 4 3. Battery Bank = 6 | Single | 2024 | April | DWDM | C0210P | DWDM-2878A | 2878A | PRPO | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  |  |  | P3 | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-31 | #N/A
C0407P | 41.97% | 73.2% | 2024 Q1 | 1266A | xD_DWDM_BRKRing_C0407P_1266A Sucasa_0004582309050Y_00045824006623 | 73.2% | 1266A Sucasa | 9800M12 1 rack 1 subrack | BBand |  | 2023-12-01 | 2024-02-15 | Single_2024_May_DWDM_C0407P_1266A_PRPO_1.Add module = 1 2.Add battery bank = 1 | Single | 2024 | May | DWDM | C0407P | DWDM-1266A | 1266A | PRPO | 1.Add module = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 |  |  |  | 0524: Waiting outbound MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0407P | 41.97% | 73.2% | 2024 Q1 | 1304A | xD_DWDM_BRKRing_C0407P_1304A MMA_0004582309050Y_00045824006623 | 73.2% | 1304A MMA | 9800M12 1 rack 1 subrack | BBand |  | 2023-12-07 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-03-26 | Wk13 | 2024-03-26 | [6 empty] | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0407P | 41.97% | 73.2% | 2024 Q1 | 1737A | xD_DWDM_BRKRing_C0407P_1737A Bernama_0004582309050Y_00045824006623 | 73.2% | 1737A Bernama | 9800M12 1 rack 1 subrack | BBand |  | 2023-12-07 | 2023-12-21 | Multiple_2024_April_DWDM_C0407P_1737A_PRPO_1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | Multiple | 2024 | April | DWDM | C0407P | DWDM-1737A | 1737A | PRPO | 1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0407P | 41.97% | 73.2% | 2024 Q1 | 1745A | xD_DWDM_BRKRing_C0407P_1745A Baitumal_0004582309050Y_00045824006623 | 73.2% | 1745A Baitamal | 9800M12 1 rack 1 subrack | BBand |  | 2023-11-30 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | swap emerson rectifier c/w 6 bank battery | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-07-11 | Wk28 |  |  |  | 0517: Remove unused rack by CME MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-11 | #N/A
C0417P | 30.12% | 98.46% | 2024 Q1 | 1006A | xD_DWDM_BRKRing_C0417P_1006A JBA Gombak_0004582309050Y_00045824006623 | 98.46% | 1006A JBA Gombak | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | Single_2023_December_DWDM_(blank)_1006A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-1006A | 1006A | Completed | RECTIFIER + DCPDB = 1 | Indoor | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | 2024-05-20 | Wk21 |  |  | Spillover to June | 0523: RN created. Need to replan 0520: Key issue. Need to return and reschedule 0516: Waiting outbound |  |  |  | Pending ES PO |  |  |  | P2 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-21 | #N/A
C0417P | 30.12% | 98.46% | 2024 Q1 | 1203A | xD_DWDM_BRKRing_C0417P_1203A JBA Sri Damansara_0004582309050Y_00045824006623 | 98.46% | 1203A JBA Sri Damansara | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_May_DWDM_C0417P_1203A_PRPO_1. Add Battery Bank = 4 2. Swap breaker DC BREAKER: 63A X 4 | Single | 2024 | May | DWDM | C0417P | DWDM-1203A | 1203A | PRPO | 1. Add Battery Bank = 4 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-21 | Wk21 |  |  |  | 0523: Need to rearrange with crane 0521: Access issue. Slippery and need crane to unload @ survey again to check access for material 0516: Waiting outbound |  |  |  | Pending ES PO |  |  |  | P2 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-21 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1006A | xD_DWDM_BRKRing_CAR04_1006A JBA Gombak_0004582309050Y_00045824006623 | 85.39% | 1006A JBA Gombak | 98001 rack 1 subrack | BBand |  | 2023-12-07 | 21/1/2/2023 | Single_2023_December_DWDM_(blank)_1006A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-1006A | 1006A | Completed | RECTIFIER + DCPDB = 1 | Indoor Rack | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 |  |  | 0517: Done int |  |  |  |  | Y |  |  | P1_Z_June | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1049B | xD_DWDM_BRKRing_CAR04_1049B KPG_0004582309050Y_00045824006623 | 85.39% | 1049B MCR KPG | 98001 rack 1 subrack | BBand |  | 2024-02-13 | 2024-02-15 | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done | [7 empty] | P1_Z_June | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1304A | xD_DWDM_BRKRing_CAR04_1304A MMA_0004582309050Y_00045824006623 | 85.39% | 1304A MMA | 98001 rack 1 subrack | BBand |  | 2024-12-07 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-03-26 | Wk13 | 2024-03-26 | [10 empty] | P1_Z_June | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1458A | xD_DWDM_BRKRing_CAR04_1458A Endah Parade_0004582309050Y_00045824006623 | 85.39% | 1458A Endah Parade | 98001 rack 1 subrack | BBand |  | 2024-12-07 | 2023-12-21 | Single_2024_January_DWDM_(blank)_1458A_Completed_BATTERY BANK = 1 | Single | 2024 | January | DWDM | (blank) | DWDM-1458A | 1458A | Completed | BATTERY BANK = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-23 | Wk17 | 2024-04-23 |  |  | 0517: Done int |  |  |  |  | Y |  |  | P1_Z_June | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1475A | xD_DWDM_BRKRing_CAR04_1475A SKB_0004582309050Y_00045824006623 | 85.39% | 1475A SKB | 98001 rack 1 subrack | BBand |  | 2024-02-13 | 2024-02-15 | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | 1.ODF Rack (Glass Door) | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-19 | Wk25 |  |  |  | 0517: Pending re-survey. Plan WK21 | [7 empty] | P1_Z_June | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1745A | xD_DWDM_BRKRing_CAR04_1745A Baitumal_0004582309050Y_00045824006623 | 85.39% | 1745A Baitumal | 98001 rack 1 subrack | BBand |  | 2023-11-30 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.4 Pending FF and CME Planner approval | 1.7 TSSR Approved | 2024-07-11 | Wk28 |  |  |  | 0517: Remove unused rack by CME MOS freezed. Pending confirmation availability of material. | [7 empty] | P1_Z_June | #N/A |  |  |  |  | #N/A |  | Y | 2024-05-24 | #N/A
CT0241P | 466.7% | 103.4% | 2024 Q1 | 1197A | xD_DWDM_BRKRing_CT0241P_1197A JBA Effingham_0004582309050Y_00045824006623 | 103.4% | 1197A JBA Effingham | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_May_DWDM_CT0241P;C0417P_1197A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P | DWDM-1197A | 1197A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A | Plan RFS MAY2024 (ZTE) | Y | 2023-05-21 | #N/A
CT0241P | 466.7% | 103.4% | 2024 Q1 | 1211A | xD_DWDM_BRKRing_CT0241P_1211A KDU_0004582309050Y_00045824006623 | 103.4% | 1211A KDU | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-17 | Wk20 | 2024-05-17 |  |  | 0520: TI done 0517: TI WIP // 0516: Waiting outbound |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A | Plan RFS MAY2024 (ZTE) | Y | 2023-05-21 | #N/A
CT0241P | 466.7% | 103.4% | 2024 Q1 | 1918A | xD_DWDM_BRKRing_CT0241P_1918A Damansara Intan_0004582309050Y_00045824006623 | 103.4% | 1918A - Damansara Intan | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-27 |  | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P;CAR02-ii+ | DWDM-1918A | 1918A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-23 | Wk21 | 2024-05-23 |  |  | 0521: RAD change to 23/5 due to system issue . Rescheduled 0520: RAD changed to 21/5 0517: Need to change RAD to 21/5 0516: Waiting outbound |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A | Plan RFS MAY2024 (ZTE) | Y | 2023-05-21 | #N/A
E104 | 27.23% | 51.85% | 2024 Q1 | 8263A | xD_DWDM_BRKRing_E104_8263AMAG(M14)- 001 Pmas_0004582309010R_00045824006624 | 51.85% | 8263AMAG(M14)- 001 Pmas | 1800VPRO 1 rack 2 subrack | Advance |  | 2024-01-30 |  | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | Single | 2024 | April | DWDM | E104;EAR01 N EAR03 | DWDM-8263A | 8263A | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-23 | Wk17 | 2024-04-23 | [6 empty] | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-03-26 | #N/A
E104 | 27.23% | 51.85% | 2024 Q1 | 8269B | xD_DWDM_BRKRing_E104_8269B-MAC001 Chetok_0004582309010R_00045824006624 | 51.85% | 8269B-MAC001 Chetok | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-04 | Wk23 |  | Outdoor |  | 0520: RAD changed to 4/6 0517: Need to change RAD // 0516: Waiting outbound. Not freeze in KHE due to no DUID |  |  |  | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-06-14 | #N/A
E104 | 27.23% | 51.85% | 2024 Q1 | 8288B | xD_DWDM_BRKRing_E104_8288B-MAG001 Panau_0004582309010R_00045824006624 | 51.85% | 8288B-MAG001 Panau | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_May_DWDM_E104;EAR01 N EAR03_8288B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 7 | Single | 2024 | May | DWDM | E104;EAR01 N EAR03 | DWDM-8288B | 8288B | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-22 | Wk17 | 2024-04-23 | [6 empty] | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-06-14 | #N/A
E104 | 27.23% | 51.85% | 2024 Q1 | 8294A | xD_DWDM_BRKRing_E104_8294A-MAC001 Kangkong_0004582309010R_00045824006624 | 51.85% | 8294A-MAC001 Kangkong | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_May_DWDM_E104_8294A_PRPO_1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 4 | Single | 2024 | May | DWDM | E104 | DWDM-8294A | 8294A | PRPO | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) | Outdoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-06-05 | Wk23 |  | outdoor |  | 0517: Need to change RAD // 0516: Waiting outbound (not freeze in KHE. Only in KM2) 0515: Pending DN |  |  |  | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-06-14 | #N/A
E105 | 91.65% | 112.8% | 2024 Q1 | 8139B | xD_DWDM_BRKRing_E105_8139B-MAC001 CBC_0004582309010R_00045824006624 | 112.8% | 8139B-MAC001 CBC | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | Single_2024_May_DWDM_E105_8139B_PRPO_1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.Add battery bank = 4 | Single | 2024 | May | DWDM | E105 | DWDM-8139B | 8139B | PRPO | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) | Outdoor | 1.33 FF reject/Pending resubmission from partner | 1.6 Pending FF approval | 2024-07-11 | Wk28 |  | CME -Plinth |  | 0521: F/u w/ CME |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-24 | #N/A
E105 | 91.65% | 112.8% | 2024 Q1 | 8211A | xD_DWDM_BRKRing_E105_8211A-MAG(M8)- 001 WCY_0004582309010R_00045824006624 | 112.8% | 8211A-MAG(M8)- 001 WCY | 1800VPRO 1 rack 2 subrack | FO&T |  | 2023-12-19 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | [9 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-24 | #N/A
E105 | 91.65% | 112.8% | 2024 Q1 | 8212A | xD_DWDM_BRKRing_E105_8212A-MAC001 Wbharu_0004582309010R_00045824006624 | 112.8% | 8212A-MAC001 Wbharu | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-04-24 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-24 | #N/A
E105 | 91.65% | 112.8% | 2024 Q1 | 8229A | xD_DWDM_BRKRing_E105_8229A-MAC001 Tumpat_0004582309010R_00045824006624 | 112.8% | 8229A-MAC001 Tumpat | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | Single_2024_April_DWDM_E105_8229A_PRPO_1. Add Battery Bank = 3 2 .Add Aircond = 1 (Action THOR) 3.Floor mounted DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | April | DWDM | E105 | DWDM-8229A | 8229A | PRPO | 1. Add Battery Bank = 3 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-24 | #N/A
E109 | 60.29% | 71.65% | 2024 Q1 | 8222A | xD_DWDM_BRKRing_E109_8222A-MAC001 Peringat_0004582309010R_00045824006624 | 71.65% | 8222A-MAC001 Peringat | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_April_DWDM_E109_8222A_PRPO_1. Add Battery Bank = 4 2. Add Aircond = 1 (Action THOR) 3. DCPDB (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | April | DWDM | E109 | DWDM-8222A | 8222A | PRPO | 1. Add Battery Bank = 4 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-04-26 | #N/A
E109 | 60.29% | 71.65% | 2024 Q1 | 8224A | xD_DWDM_BRKRing_E109_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 71.65% | 8224A-MAG-001 Pasir Puteh | 1800VPRO 1 rack 2 subrack | Advance |  |  |  | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-06 | Wk23 |  |  |  | 0520: RAD changed to 6/6 0517: Need to change RAD // 0516: Waiting outbound |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-03-26 | #N/A
E109 | 60.29% | 71.65% | 2024 Q1 | 8242B | xD_DWDM_BRKRing_E109_8242B-MAC001 JKKrai_0004582309010R_00045824006624 | 71.65% | 8242B-MAC001 JKKrai | 1800VPRO 1 rack 1 subrack | Advance |  | 2024-01-30 |  | Single_2024_April_DWDM_E109_8242B_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | April | DWDM | E109 | DWDM-8242B | 8242B | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-04-26 | #N/A
E111 | 70.34% | 121.3% | 2024 Q1 | 8317A | xD_DWDM_BRKRing_E111_8317A-MAC-001 Kampung Pak Wong_0004582309010R_00045824006624 | 121.3% | 8317A-MAC-001 Kampung Pak Wong | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.6 Pending CME approval | 1.6 Pending CME approval | 2024-06-19 | Wk25 |  | CME- Dismantle cage | [5 empty] | Pending ES PO |  |  |  | P0 | [7 empty] | Y | May | #N/A
E111 | 70.34% | 121.3% | 2024 Q1 | 8322B | xD_DWDM_BRKRing_E111_8322B-MAC001 Padang Luas_0004582309010R_00045824006624 | 121.3% | 8322B-MAC001 Padang Luas | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | Single_2024_May_DWDM_E111_8322B_PRPO_1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1 | Single | 2024 | May | DWDM | E111 | DWDM-8322B | 8322B | PRPO | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1 | Outdoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  |  |  | P0 | [7 empty] | Y | May | #N/A
E111 | 70.34% | 121.3% | 2024 Q1 | 8367A | xD_DWDM_BRKRing_E111_8367A-MAG001 B.Kechil_0004582309010R_00045824006624 | 121.3% | 8367A-MAG001 B.Kechil | 1800VPRO 1 rack 1 subrack | FO&T |  | 2024-02-07 |  | Single_2024_May_DWDM_E111;EAR01 N EAR03_8367A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | Single | 2024 | May | DWDM | E111;EAR01 N EAR03 | DWDM-8367A | 8367A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-08 | Wk19 | 2024-05-09 | [6 empty] | Pending ES PO |  |  |  | P0 | [7 empty] | Y | May | #N/A
E111 | 70.34% | 121.3% | 2024 Q1 | 8407A | xD_DWDM_BRKRing_E111_8407A-MAC001 Jerteh_0004582309010R_00045824006624 | 121.3% | 8407A-MAC001 Jerteh | 1800VPRO 1 rack 1 subrack | FO&T |  | 2023-12-21 | 2024-02-16 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.112 CD TSSR reject/Pending resubmission from partner | 1.112 CD TSSR reject/Pending resubmission from partner | 2024-06-19 | Wk25 | [7 empty] | Pending ES PO |  |  |  | P0 | [7 empty] | Y | May | #N/A
E111 | 70.34% | 121.3% | 2024 Q1 | 8439A | xD_DWDM_BRKRing_E111_8439A-MAC001 A.Lintang_0004582309010R_00045824006624 | 121.3% | 8439A-MAC001 A.Lintang | 1800VPRO 1 rack 1 subrack | FO&T |  | 2024-02-07 |  | Single_2024_May_DWDM_E111_8439A_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | E111 | DWDM-8439A | 8439A | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-08 | Wk19 | 2024-05-08 | [6 empty] | Pending ES PO |  |  |  | P0 | [7 empty] | Y | May | #N/A
EAR01 | #N/A | #N/A | 2024 Q1 | 4000A | xD_DWDM_BRKRing_EAR01_4000A-MCR-001 PRI_0004582309010R_00045824006624 | #N/A | 4000A-MCR-001 PRI | Board expansion | Fo&T |  | N/A | N/A | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-18 | Wk12 | 2024-03-19 | [6 empty] | Pending ES PO | Y | 2024-03-19 | Wk12 | P1 | [7 empty] | Y | 2024-04-19 | #N/A
EAR01 | #N/A | #N/A | 2024 Q1 | 8000A | xD_DWDM_BRKRing_EAR01_8000A-MCR001 KTN_0004582309010R_00045824006624 | #N/A | 8000A-MCR001 KTN | Board expansion | Fo&T |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-08 | [6 empty] | Pending ES PO | N/A |  |  | P1 | [7 empty] | Y | 2024-04-19 | #N/A
EAR01 | #N/A | #N/A | 2024 Q1 | 8224A | xD_DWDM_BRKRing_EAR01_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | #N/A | 8224A-MAG-001 Pasir Puteh | 9800 M24 1 rack 1 subrack | Fo&T |  | 2023-12-21 | 2024-02-16 | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-09 | Wk19 | 2024-05-09 | [6 empty] | Pending ES PO |  |  |  | P1 | [7 empty] | Y | 2024-04-19 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 1475A | xD_DWDM_BRKRing_EAR06_1475A-MSC MSK_0004582309010R_00045824006624 | 91.72% | 1475A-MSC MSK | Board expansion | Fo&T |  | N/A | N/A | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-18 | Wk12 | 2024-03-19 | [6 empty] | Pending ES PO | Y | 2024-03-19 | Wk12 | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8000A | xD_DWDM_BRKRing_EAR06_8000A-MSC Kuantan_0004582309010R_00045824006624 | 91.72% | 8000A-MSC Kuantan | 9800 1subrack | Fo&T |  | 2024-02-02 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack | 1.4 Pending FF and CME Planner approval | 1.4 Pending FF and CME Planner approval | 2024-05-08 | Wk19 | 2024-05-08 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8105A | xD_DWDM_BRKRing_EAR06_8105A-MAG 001 South Of Raub_0004582309010R_00045824006624 | 91.72% | 8105A-MAG 001 South Of Raub | 9800 1subrack | Fo&T |  | 2024-03-13 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.4 Pending FF and CME Planner approval | 2024-06-06 | Wk23 |  |  |  | 0524: Freezed. Pending DN 0521: Need to freeze |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8112A | xD_DWDM_BRKRing_EAR06_8112A-MAG 001 Bukit Istana_0004582309010R_00045824006624 | 91.72% | 8112A-MAG 001 Bukit Istana | 9800 1subrack | Fo&T |  | 2024-02-06 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-04-24 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8145Z | xD_DWDM_BRKRing_EAR06_8145Z-MAG 001 T3E 0160 Kg Paya Luas_0004582309010R_00045824006624 | 91.72% | 8145Z-MAG 001 T3E 0160 Kg Paya Luas | 9800 1subrack | Fo&T |  | 2024-02-06 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.4 Pending FF and CME Planner approval | 1.6 Pending FF approval | 2024-04-25 | Wk17 | 2024-04-24 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8173A | xD_DWDM_BRKRing_EAR06_8173A-MAG 001 Bandar Pusat Jengka_0004582309010R_00045824006624 | 91.72% | 8173A-MAG 001 Bandar Pusat Jengka | 9800 1subrack | Fo&T |  | 2024-02-06 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.4 Pending FF and CME Planner approval | 1.7 TSSR Approved | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8513A | xD_DWDM_BRKRing_EAR06_8513A-MAG002 Senggora_0004582309010R_00045824006624 | 91.72% | 8513A-MAG002 Senggora | 9800 1subrack | Fo&T |  | 2024-02-02 |  | Single_2024_May_DWDM_EAR06_8513A_PRPO_1.Add battery bank = 2 | Single | 2024 | May | DWDM | EAR06 | DWDM-8513A | 8513A | PRPO | 1.Add battery bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-08 | Wk19 | 2024-05-07 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8667A | xD_DWDM_BRKRing_EAR06_8667A-MAG 001 Kg Jerangsang_0004582309010R_00045824006624 | 91.72% | 8667A-MAG 001 Kg Jerangsang | 9800 1subrack | Fo&T |  | 2024-02-07 |  | Single_2024_May_DWDM_EAR06_8667A_PRPO_1.Add modules = 2 2.Add battery bank = 6 | Single | 2024 | May | DWDM | EAR06 | DWDM-8667A | 8667A | PRPO | 1.Add modules = 2 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-09 | Wk19 | 2024-05-09 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
EAR06 | 53.85% | 91.72% | 2024 Q1 | 8709A | xD_DWDM_BRKRing_EAR06_8709A-MAG002 Bentong_0004582309010R_00045824006624 | 91.72% | 8709A-MAG002 Bentong | 9800 1 subrack | Fo&T |  | N/A | N/A | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | RECTIFIER + DCPDB = 1 | Subrack only | 1.11 HW TSSR reject/Pending resubmission from partner | 1.4 Pending FF and CME Planner approval | 2024-06-06 | Wk23 |  |  |  | 0524: Freezed. Pending DN 0521: Need to freeze |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-15 | #N/A
MAC RING 9/C13 | 23.36% | 70.55% | 2024 Q1 | 1295A | xD_DWDM_BRKRing_MR9/C13_1295A Com Bkt Maluri_0004582309050Y_00045824006623 | 70.55% | 1295A-MAC-001 | 1800VPRO 1 rack 1 subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-05-28 | Wk22 |  |  |  | 0524: Waiting outbound 0523: Freezed. Pending DN |  |  |  | Pending ES PO |  |  |  | P1 | #N/A |  |  |  |  | #N/A |  | Y | 2024-06-14 | #N/A
N106+ | #N/A | #N/A | 2024 Q1 | 4683A | xD_DWDM_BRKRing_N106+_4683A Bkt Tok Alang_0004582309010S_00045824006622 | #N/A | 4683A Bkt Tok Alang | 1800VPRO 1 rack 1 subrack | FO&T | Week 12 March | 2024-03-20 |  | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3 | Single | 2024 | May | DWDM | N106+ | DWDM-4683A | 4683A | PRPO | 1. Add Battery Bank = 3 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-07 | Wk19 | 2024-05-07 | [7 empty] | Y | 2024-05-07 | Wk19 | P1 | 0 | [6 empty] | Y | May | #N/A
N106+ | #N/A | #N/A | 2024 Q1 | 4966A | xD_DWDM_BRKRing_N106+_4966A Kulim Hitech_0004582309010S_00045824006622 | #N/A | 4966A Kulim Hitech | 1800V PRO 1 rack 2 subrack | FO&T | Week 12 March | 2024-03-20 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only, require 9800 door | 1.33 FF reject/Pending resubmission from partner | 1.33 FF reject/Pending resubmission from partner | 2024-05-07 | Wk19 | 2024-05-09 | [5 empty] | June Plan |  |  |  |  | P1 | 0 | [6 empty] | Y | May | #N/A
N113(ii) | #N/A | #N/A | 2023 | 4663A | xD_DWDM_BRKRing_N113_4663A Derga Jaya_0004582306610C_00045823162822 | #N/A | 4663A Derga Jaya | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4663A_Completed_DC BREAKER : 100A X 2 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4663A | 4663A | Completed | DC BREAKER : 100A X 2 | #N/A | #N/A | #N/A | 2024-02-22 | Wk8 | 2024-02-23 | CME | OUTDOOR |  |  |  | 2024-03-13 | #N/A | Y | 2024-03-13 | Wk11 | P1 | 2024-03-13 09:41 |  |  |  |  | #N/A |  |  |  | #N/A
N113(ii) | #N/A | #N/A | 2023 | 4973B | xD_DWDM_BRKRing_N113_4973B Tajar_0004582306610C_00045823162822 | #N/A | 4973B Tajar | 1800VPRO 1 rack 1 subrack | Fo&T |  |  | 2023-12-19 | Multiple_2023_December_DWDM_(blank)_4973B_Completed_MGB = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4973B | 4973B | Completed | MGB = 1 | #N/A | #N/A | #N/A | 2024-02-22 | Wk8 | 2024-02-22 | CME |  |  |  |  | Plan | #N/A | Y | 2024-04-24 | Wk17 | P1 | [5 empty] | #N/A |  |  |  | #N/A
N115 | 23.69% | #N/A | 2023_2024 | 4770A | xD_DWDM_BRKRing_N115_4770A Tok Lin_0004582309010S_00045824006622 | #N/A | 4770A Tok Lin | 1800VPRO 1 rack 1 subrack |  |  |  |  | Single_2023_October_DWDM_(blank)_4770A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4770A | 4770A | Completed | RECTTIFIER MODULE = 2 | #N/A | #N/A | #N/A | [13 empty] | #N/A | 0 |  |  |  | Completed | 2023-12-21 | Mitigation | Y |  | #N/A
NT09P | 0.801% | #N/A | 2023_2024 | 4640A | xD_DWDM_BRKRing_NT09P_4640A Sp Plaza_0004582309010S_00045824006622 | #N/A | 4640A Sp Plaza | 1800VPRO 1 rack 1 subrack |  |  |  |  | Single_2023_November_DWDM_(blank)_4640A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4640A | 4640A | Completed | DCPDB = 1 | #N/A | 1.7 TSSR Approved | #N/A | [13 empty] | P1 | 0 | [6 empty] | Y |  | #N/A
S301 | 63.36% | #N/A | 2024 Q1 | 1554A | xD_DWDM_BRKRing_S301_1554AMAG(M14)-001 Rumbia_0004582309010R_00045824006624 | #N/A | 1554AMAG(M14)-001 Rumbia | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-01-24 |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | Subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P1 | [7 empty] | Y | 2024-06-13 | #N/A
S301 | 63.36% | #N/A | 2024 Q1 | 1560A | xD_DWDM_BRKRing_S301_1560A-MAC001 Bkt Tiga_0004582309010R_00045824006624 | #N/A | 1560A-MAC001 Bkt Tiga | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-02 | 2024-02-15 | Single_2024_May_DWDM_S301_1560A_PRPO_1.Add module = 1 2.Add battery bank = 2 3.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | May | DWDM | S301 | DWDM-1560A | 1560A | PRPO | 1.Add module = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-27 | Wk22 |  |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P1 | [7 empty] | Y | 2024-06-13 | #N/A
S301 | 63.36% | #N/A | 2024 Q1 | 1563A | xD_DWDM_BRKRing_S301_1563A-MAC001 Bkt Iman_0004582309010R_00045824006624 | #N/A | 1563A-MAC001 Bkt Iman | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-02 | 2024-02-15 | Single_2024_May_DWDM_S301_1563A_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | May | DWDM | S301 | DWDM-1563A | 1563A | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-28 | Wk22 |  |  |  | 0523: Pending DN 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P1 | [7 empty] | Y | 2024-06-13 | #N/A
S301 | 63.36% | #N/A | 2024 Q1 | 1621A | xD_DWDM_BRKRing_S301_1621A-MCR001 SNW_0004582309010R_00045824006624 | #N/A | 1621A-MCR001 SNW | 1800VPRO 1 rack 2 subrack | BBand |  | 2024-01-23 |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.4 Pending FF and CME Planner approval | 1.6 Pending CME approval | 2024-07-11 | Wk28 |  |  |  | 0517: F/u w/ Zul for TSSR |  |  |  | Pending ES PO |  |  |  | P1 | [7 empty] | Y | 2024-06-13 | #N/A
S309 | 38.82% | 53.25% | 2024 Q1 | 1553A | xD_DWDM_BRKRing_S309_1553AMAG(M14)-001 Umbai_0004582309010R_00045824006624 | 53.25% | 1553AMAG(M14)-001 Umbai | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-05 | 2024-02-08 | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | Indoor | 1.112 CD TSSR reject/Pending resubmission from partner | 1.7 TSSR Approved | [5 empty] | 0523: CME Plinth |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-06-13 | #N/A
S309 | 38.82% | 53.25% | 2024 Q1 | 1556A | xD_DWDM_BRKRing_S309_1556A-MAC001 Merlimau_0004582309010R_00045824006624 | 53.25% | 1556A-MAC001 Merlimau | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-03-05 |  | Multiple_2024_May_DWDM_S309_1556A_PRPO_BATTERY BANK = 3 Remove battery = 1 | Multiple | 2024 | May | DWDM | S309 | DWDM-1556A | 1556A | PRPO | BATTERY BANK = 3 | Subrack only | 1.6 Pending FF approval | 1.7 TSSR Approved | 2024-06-12 | Wk24 |  |  |  | 0524: Waiting outbound. Need to reconfirm with faizal 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-06-13 | #N/A
S309 | 38.82% | 53.25% | 2024 Q1 | 1599A | xD_DWDM_BRKRing_S309_1599A-MAC001 Bkt Gambir Town_0004582309010R_00045824006624 | 53.25% | 1599A-MAC001 Bkt Gambir Town | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-02-01 |  | Multiple_2023_September_DWDM_(blank)_1599A_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-1599A | 1599A | Completed | BATTERY BANK = 3 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | 2024-06-19 | Wk25 | [7 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-06-13 | #N/A
S309 | 38.82% | 53.25% | 2024 Q1 | 2402B | xD_DWDM_BRKRing_S309_2402B-MAG001 Pagoh Highway_0004582309010R_00045824006624 | 53.25% | 2402B-MAG001 Pagoh Highway | 1800VPRO 1 rack 1 subrack | BBand |  | 2024-01-23 |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | Subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-23 | Wk17 | 2024-04-23 | [6 empty] | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-06-13 | #N/A
SAR01 | 43.19% | 78.56% | 2024 Q1 | 1552A | xD_DWDM_BRKRing_SAR01_1552A-MAG(M8)-001 Tanjung Bidara_0004582309010R_00045824006624 | 78.56% | 1552A-MAG(M8)-001 Tanjung Bidara | Board expansion | Bband |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-21 | Wk12 | 2024-04-05 |  |  | 0517: PO for remob to install SFP and patching |  |  |  | Pending ES PO | Y | 2024-04-05 | Wk14 | P0 | [7 empty] | Y | 2024-04-26 | #N/A
SAR01 | 43.19% | 78.56% | 2024 Q1 | 1621A | xD_DWDM_BRKRing_SAR01_1621A-MCR Senawang_0004582309010R_00045824006624 | 78.56% | 1621A-MCR Senawang | Board expansion | Bband |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-22 | Wk12 | 2024-04-05 | [6 empty] | Pending ES PO | Y | 2024-04-05 | Wk14 | P0 | [7 empty] | Y | 2024-04-26 | #N/A
SAR01 | 43.19% | 78.56% | 2024 Q1 | 1640A | xD_DWDM_BRKRing_SAR01_1640A-MAG(M8)-001 Politeknik Port Dickson_0004582309010R_00045824006624 | 78.56% | 1640A-MAG(M8)-001 Politeknik Port Dickson | Board expansion | Bband |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-22 | Wk12 | 2024-04-05 |  |  | 0517: PO for remob to install SFP and patching |  |  |  | Pending ES PO | Y | 2024-04-05 | Wk14 | P0 | [7 empty] | Y | 2024-04-26 | #N/A
SAR01 | 43.19% | 78.56% | 2024 Q1 | 2021B | xD_DWDM_BRKRing_SAR01_2021B-Subang Hi-Tech_0004582309010R_00045824006624 | 78.56% | 2021B-Subang Hi-Tech | Board expansion | Bband |  | N/A | N/A | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | 0 | 0. No Survey required | 0. No Survey required | 2024-03-21 | Wk12 | 2023-12-21 | [6 empty] | Pending ES PO | Y | 2023-12-21 | Wk51 | P0 | [7 empty] | Y | 2024-04-26 | #N/A
Spare | #N/A | #N/A | 2023 | 2021B | xD_DWDM_BRKRing_Spare_2021B SBHT_0004582307400B_0004582307400C_00045823174223 | #N/A | 2021B SBHT | Board expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-12 |  |  |  | N/A | N/A | N/A | Completed | Y | 2023-12-12 | Wk50 | #N/A |  |  |  |  | N/A | 0 |  |  |  | #N/A
ST21P_1 | 51.9% | #N/A | 2024 Q1 | 6063A | xD_DWDM_BRKRing_ST21P_1_6063A-MAC-001 KTM Plentong_0004582309010R_00045824006624 | #N/A | 6063A-MAC-001 KTM Plentong | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-27 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending CME approval | 1.6 Pending CME approval | 2024-04-25 | Wk17 | 2024-04-25 | [6 empty] | Pending ES PO | Y | 2024-05-08 | Wk19 | P2 | [7 empty] | Y | 2024-05-15 | #N/A
ST21P_1 | 51.9% | #N/A | 2024 Q1 | 6382A | xD_DWDM_BRKRing_ST21P_1_6382A-MAC-001 KTM Pasir Gudang_0004582309010R_00045824006624 | #N/A | 6382A-MAC-001 KTM Pasir Gudang | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-28 | 2024-02-15 | Single_2024_May_DWDM_ST21P_6382A_PRPO_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) 2.Add top Fixing cable ladder = 1 | Single | 2024 | May | DWDM | ST21P | DWDM-6382A | 6382A | PRPO | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.6 Pending FF approval | 1.7 TSSR Approved | 2024-06-04 | Wk23 |  |  |  | 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-05-15 | #N/A
ST21P | 73.72% | 110.6% | 2024 Q1 | 6000A | xD_DWDM_BRKRing_ST21P_6000A-MCR002 JBR_0004582309010R_00045824006624 | 110.6% | 6000A-MCR002 JBR | 1800VPRO 1 rack 2 subrack | BBand |  | 2024-01-23 |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | Subrack only | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | 2024-06-07 | Wk23 |  |  |  | 0524: Freezed. Pending DN |  |  |  | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-05-15 | #N/A
ST21P | 73.72% | 110.6% | 2024 Q1 | 6312A | xD_DWDM_BRKRing_ST21P_6312A-MAC-001 Jln Cenderai_0004582309010R_00045824006624 | 110.6% | 6312A-MAC-001 Jln Cenderai | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-30 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-06 | Wk23 |  |  |  | 0524: Pending DN 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-05-15 | #N/A
ST21P | 73.72% | 110.6% | 2024 Q1 | 6369A | xD_DWDM_BRKRing_ST21P_6369A-MAG001 Sri Saujana_0004582309010R_00045824006624 | 110.6% | 6369A-MAG001 Sri Saujana | 1800VPRO 1 rack 2 subrack | BBand |  | 2023-12-30 |  | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | Multiple | 2024 | May | DWDM | ST21P;S504M | DWDM-6369A | 6369A | PRPO | 1. Add Battery Bank = 6 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-04-26 | Wk17 | 2024-04-26 | [6 empty] | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-05-15 | #N/A
ST21P | 73.72% | 110.6% | 2024 Q1 | 6400A | xD_DWDM_BRKRing_ST21P_6400A-MAC-001 Jln Perak_0004582309010R_00045824006624 | 110.6% | 6400A-MAC-001 Jln Perak | 1800VPRO 1 rack 1 subrack | BBand |  | 2023-12-30 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.4 Pending FF and CME Planner approval | 1.4 Pending FF and CME Planner approval | 2024-07-11 | Wk28 |  |  |  | 0523: plinth issue (outdoor cabinet) |  |  |  | Pending ES PO |  |  |  | P2 | [7 empty] | Y | 2024-05-15 | #N/A
ST27P | #N/A | 102.8% | 2024 Q1 | 1607A | xD_DWDM_BRKRing_ST27P_1607A-MAG001 KM Plaza_0004582309010R_00045824006624 | 102.8% | 1607A-MAG001 KM Plaza | 1800VPRO 1 rack 1 subrack | Bband |  | 2023-12-21 | 2024-02-15 | Single_2024_May_DWDM_ST27P_1607A_PRPO_1. Decomm Cabinet | Single | 2024 | May | DWDM | ST27P | DWDM-1607A | 1607A | PRPO | 1. Decomm Cabinet | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-27 | Wk22 |  |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-17 | #N/A
ST27P | #N/A | 102.8% | 2024 Q1 | 1608A | xD_DWDM_BRKRing_ST27P_1608A KTM Seremban_0004582309010R_00045824006624 | 102.8% | 1608A KTM Seremban | 1800VPRO 1 rack 1 subrack | Bband |  | 2023-12-21 | 2024-02-15 | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending FF approval | 1.7 TSSR Approved | 2024-05-28 | Wk22 |  |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-17 | #N/A
ST27P | #N/A | 102.8% | 2024 Q1 | 1610A | xD_DWDM_BRKRing_ST27P_1610A Gun Hill_0004582309010R_00045824006624 | 102.8% | 1610A Gun Hill | 1800VPRO 1 rack 1 subrack | Bband |  | 2023-12-21 | 2024-02-15 | Single_2024_May_DWDM_ST27P_1610A_PRPO_1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 4.Relocate unuse battery to make space for Rectifier and DWDM rack | Single | 2024 | May | DWDM | ST27P | DWDM-1610A | 1610A | PRPO | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | 0520: Freeze to 24/5. Need faizal to replan 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. |  |  |  | Pending ES PO |  |  |  | P3 | [7 empty] | Y | 2024-05-17 | #N/A
Area139 | #N/A | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_Area139_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4000A MSC Prai | 9800 SFP only | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | #N/A | #N/A | #N/A |  |  | 2024-03-22 | Plan Outbound | Invalid |  |  | N/A |  | Completed | N/A | 2024-01-31 | Wk5 | P0 |  |  | CME completed12/Jan | [6 empty] | #N/A
Area139 | #N/A | #N/A | 2023 | 4946A | xD_DWDM-BRKRing_Area139_4946A Bukit Selambau_0004582306610A_0004582306610D_00045823162822 | #N/A | 4946A Bukit Selambau | 9800 SFP only | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | N/A |  | Completed | N/A | 2024-01-31 | Wk5 | P0 | [9 empty] | #N/A
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1049B | xD_DWDM-BRKRing_C0103_1049B MCR KPG_0004582400320X_00045824009023 | #N/A | 1049B-MCR001 KPG | Board expansion | Advance |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-24 | Wk21 |  |  |  | 0523: Waiting outbound 0516: Pending DN. Freezed to lock material. Need to reconfirm from Amir | [7 empty] | P2 | 0 | [7 empty] | 2024-05-28 | #N/A
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1207A | xD_DWDM-BRKRing_C0103_1207A Sg Buloh New Village_0004582400320X_00045824009023 | #N/A | 1207A-MAC-001 Sg Buloh New Village | 1800 1 rack 1subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.6 Pending CME approval | 2024-05-17 | Wk20 | 2024-05-17 |  |  | 0520: TI done 0517: Waiting outbound // 0516: Pending TSSR approval. DN issued (Waiting outbound) | [7 empty] | P2 | 0 | [7 empty] | 2024-05-28 | #N/A
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1359A | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | #N/A | 1359A-MAC-001 Mutiara Subang | 1800 1 rack 1subrack | Advance |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | 1. Swap breaker DC BREAKER: 63A X 2 | Indoor | 1.4 Pending FF and CME Planner approval | 1.7 TSSR Approved | 2024-05-16 | Wk20 | 2024-05-16 |  |  | 0520: TI done 0517: TI WIP // 0516: Waiting outbound | [7 empty] | P2 | 0 | [7 empty] | 2024-05-28 | #N/A
C0103 (C0126) | #N/A | #N/A | 2024 Q1 | 1364B | xD_DWDM-BRKRing_C0103_1364B Bestari(Maxis)_0004582400320X_00045824009023 | #N/A | 1364B-MAC-001 Bestari (Maxis) | 1800 1 rack 1subrack | Advance |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-05-28 | Wk22 |  |  |  | 0524: Pending DN. If 30/5 is failed, change date to 3 june / 7 june | [7 empty] | P2 | 0 | [7 empty] | 2024-05-28 | #N/A
C0607P | 55.22% | #N/A | 2023 | 1196A | xD_DWDM-BRKRing_C0607P_1196A JBA Puchong_0004582306610C_00045823162822 | #N/A | 1196A JBA Puchong | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1196A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | November | DWDM | (blank) | DWDM-1196A | 1196A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | Y |  | Completed | Y | 2023-11-23 | Wk47 | P1_Z_Oct |  |  |  | Y | Completed | 2024-05-07 | 2024-05-07 |  |  | #N/A
C0607P | 55.22% | #N/A | 2023 | 1402A | xD_DWDM-BRKRing_C0607P_1402A Jalan Industry Puchong_0004582306610C_00045823162822 | #N/A | 1402A Jalan Industry Puchong | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1402A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | November | DWDM | (blank) | DWDM-1402A | 1402A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | Y |  | Completed | Y | 2023-11-23 | Wk47 | P1_Z_Oct |  |  |  | Y | Completed | 2024-05-07 | 2024-05-07 |  |  | #N/A
C0607P | 55.22% | #N/A | 2023 | 1408A | xD_DWDM-BRKRing_C0607P_1408A Puchong Jaya_0004582306610C_00045823162822 | #N/A | 1408A Puchong Jaya | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1408A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1408A | 1408A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | Pending EB CRQ |  |  |  |  | Replan | 2024-02-16 | Y | 2024-02-22 | Wk8 | P1_Z_Oct | 2024-02-19 11:12 |  |  | Y | Completed | 2024-05-07 | 2024-05-07 |  |  | #N/A
C0702P | 91.22% | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_C0702P_1096A MAG KlangPerdana_0004582304330Y_00045823098821 | #N/A | 1096A MAG KlangPerdana | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | 1.7 TSSR Approved | #N/A |  |  | 2023-11-23 | Pending PFS Swap | postpone pending solution from customer |  |  |  | 2024-02-15 | TBC |  |  |  | P1 | [5 empty] | 0 | 0702 shortage |  |  | #N/A
C0702P | 91.22% | #N/A | 2023 | 1153A | xD_DWDM-BRKRing_C0702P_1153A MAC PermatangKSelangor_0004582304330Y_00045823098821 | #N/A | 1153A MAC PermatangKSelangor | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1153A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-1153A | 1153A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  |  |  |  | Y |  | 2024-01-18 | Y | 2023-11-24 | Wk47 | P1 | [5 empty] | 0 |  |  |  | #N/A
C0702P | 91.22% | #N/A | 2023 | 1154A | xD_DWDM-BRKRing_C0702P_1154A MAGSekinchan_0004582304330Y_00045823098821 | #N/A | 1154A MAGSekinchan | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1154A_Drop_ODF CABINET = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1154A | 1154A | Drop | ODF CABINET = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y |  | 2024-01-18 | Y | 2023-11-23 | Wk47 | P1 | [5 empty] | 0 |  |  |  | #N/A
C0702P | 91.22% | #N/A | 2023 | 1156A | xD_DWDM-BRKRing_C0702P_1156A MAC BtgBerjuntai_0004582304330Y_00045823098821 | #N/A | 1156A MAC BtgBerjuntai | 1800 Rack and subrack | BBand |  |  |  | Single_2023_December_DWDM_(blank)_1156A_Drop_ODF CABINET = 1 | Single | 2023 | December | DWDM | (blank) | DWDM-1156A | 1156A | Drop | ODF CABINET = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  |  |  |  | Y |  | 2024-01-18 | Y | 2023-11-24 | Wk47 | P1 | [5 empty] | 0 |  |  |  | #N/A
C0702P | 91.22% | #N/A | 2023 | 1169A | xD_DWDM-BRKRing_C0702P_1169A MAC TgKrngTrunkRd_0004582304330Y_00045823098821 | #N/A | 1169A MAC TgKrngTrunkRd | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1169A_Completed_DCPDB = 1 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1169A | 1169A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  | Plan 23/1 |  |  | Y | 2024-01-22 | 2024-01-18 | Y | 2024-01-23 | Wk4 | P1 | 2024-01-23 10:40 |  |  |  |  | 0 |  |  |  | #N/A
C0704P | 29.33% | #N/A | 2023 | 1073A | xD_DWDM-BRKRing_C0704P_1073A KTM PadangJawa_0004582306610C_00045823162822 | #N/A | 1073A KTM PadangJawa | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1073A_Drop_NOT REQUIRED | Single | 2023 | October | DWDM | (blank) | DWDM-1073A | 1073A | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  | Pending Fiberail Access |  | 2024-01-26 |  | 2024-01-26 | TBC | Y | 2024-01-29 | Wk5 | #N/A | 2024-01-29 09:52 |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A
C0704P | 29.33% | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_C0704P_1096A Klang Perdana_0004582306610C_00045823162822 | #N/A | 1096A Klang Perdana | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-23 | Pending PFS Swap | postpone pending solution from customer |  |  |  | 2024-02-15 | TBC |  |  |  | #N/A |  |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A
C0704P | 29.33% | #N/A | 2023 | 1342A | xD_DWDM-BRKRing_C0704P_1342A MBSA_0004582306610C_00045823162822 | #N/A | 1342A MBSA | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2024-02-20 | Access | Access |  |  |  |  | TBC | Y | 2024-02-20 | Wk8 | #N/A |  |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A
C0704P | 29.33% | #N/A | 2023 | 1367A | xD_DWDM-BRKRing_C0704P_1367A Worldwide Biz_0004582306610C_00045823162822 | #N/A | 1367A Worldwide Biz | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1367A_Drop_NOT REQUIRED | Single | 2023 | October | DWDM | (blank) | DWDM-1367A | 1367A | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  |  |  | 2024-01-05 |  | 2024-01-05 | Completed | Y | 2024-01-16 | Wk3 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-10-23 | Completed |  |  | #N/A
C0704P | 29.33% | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_C0704P_2021B SBHT_0004582306610C_00045823162822 | #N/A | 2021B SBHT | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A |  |  | 2023-12-04 |  |  |  | 2024-01-09 |  | 2024-01-09 | Completed | Y | 2023-12-12 | Wk50 | #N/A |  |  |  | Y | Completed | 2023-10-23 | Completed |  |  | #N/A
C0713P | 61.78% | #N/A | 2023 | 1071A | xD_DWDM-BRKRing_C0713P_1071A_Chi Liung Plaza_0004582304330V_00045823098821 | #N/A | Chi Liung Plaza | 9800 Rack with subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-20 |  |  |  | 4//1/2024 | Y | 4//1/2024 | 2024-01-08 | Y | 2024-01-10 | Wk2 | P0 |  |  | CME completed12/Jan |  |  |  | Schedule for migration |  |  | #N/A
C0713P | 61.78% | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_C0713P_1096A_KlangPerdana_0004582304330V_00045823098821 | #N/A | KlangPerdana | 9800 Board Expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y |  | Completed | Y | 2023-11-23 | Wk47 | P0 | [6 empty] | Schedule for migration |  |  | #N/A
C0713P | 61.78% | #N/A | 2023 | 1342A | xD_DWDM-BRKRing_C0713P_1342A_MBSA_00045823098821 | #N/A | MBSA | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | N/A | Services only | Services only |  |  | N/A |  | 2024-01-08 | N/A | 2024-01-08 | Wk2 | P0 | [6 empty] | Schedule for migration |  |  | #N/A
C0713P | 61.78% | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_C0713P_2021B_SBHT_0004582304330V_00045823098821 | #N/A | SBHT | 9800 Board Expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-12 |  |  |  |  | Y |  | Completed | Y | 2023-12-12 | Wk50 | P0 | [6 empty] | Schedule for migration |  |  | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 1049B | xD_DWDM-BRKRing_CAR01_1049B MCR KPG_0004582400460T_00045824009529 | #N/A | 1049B MCR KPG | Board expansion | BBand |  | N/A | N/A | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A | 2024-03-22 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | 0 | [7 empty] | 2024-04-19 | #N/A
CAR01 | #N/A | #N/A | 2023 | 1049B | xD_DWDM-BRKRing_CAR01_1049B_KPG_0004582304330V_00045823098821 | #N/A | KPG | 9800 Board Expansion | BBand |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2023 | 1058A | xD_DWDM-BRKRing_CAR01_1058A_Pekan Meru_00045823098821 | #N/A | Pekan Meru | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2023 | 1071A | xD_DWDM-BRKRing_CAR01_1071A_Chi Liung Plaza_00045823098821 | #N/A | Chi Liung Plaza | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 1085A | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 | #N/A | 1085A Pekan Meru | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-22 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | 0 | [7 empty] | 2024-04-19 | #N/A
CAR01 | #N/A | #N/A | 2023 | 1096A | xD_DWDM-BRKRing_CAR01_1096A_KlangPerdana_00045823098821 | #N/A | KlangPerdana | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2023 | 1359A | xD_DWDM-BRKRing_CAR01_1359A_Mutiara Subang_00045823098821 | #N/A | Mutiara Subang | Services only | BBand |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 1409A | xD_DWDM-BRKRing_CAR01_1409A Kota Damansara_0004582400460T_00045824009529 | #N/A | 1409A Kota Damansara | Board expansion | BBand |  | N/A | N/A | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-20 | Wk12 | 2024-03-21 | [7 empty] | Y | 2024-03-21 | Wk12 | P0 | 0 | [7 empty] | 2024-04-19 | #N/A
CAR01 | #N/A | #N/A | 2023 | 1409A | xD_DWDM-BRKRing_CAR01_1409A_Kota Damansara_00045823098821 | #N/A | Kota Damansara | Services only | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 2021B | xD_DWDM-BRKRing_CAR01_2021B SBHT_0004582400460T_00045824009529 | #N/A | 2021B SBHT | Board expansion | BBand |  | N/A | N/A | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-20 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | 0 | [7 empty] | 2024-04-19 | #N/A
CAR01 | #N/A | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_CAR01_2021B_SBHT_0004582304330V_00045823098821 | #N/A | SBHT | 9800 Board Expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2023 | 2631A | xD_DWDM-BRKRing_CAR01_2631A_Samarinda_00045823098821 | #N/A | Samarinda | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 2777C | xD_DWDM-BRKRing_CAR01_2777C JBA Bukit Lipat_0004582400460T_00045824009529 | #N/A | 2777C JBA Bukit Lipat | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-03-21 | Wk12 | 2024-03-25 | [7 empty] | Y | 2024-03-25 | Wk13 | P0 | 0 | [7 empty] | 2024-04-19 | #N/A
CAR01 | #N/A | #N/A | 2023 | 2777C | xD_DWDM-BRKRing_CAR01_2777C_JBABkitLipat_0004582304330V_00045823098821 | #N/A | JBABkitLipat | 9800 Board Expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-12-18 | Wk51 | P0 |  |  |  | Y | Completed | 2023-12-18 | Completed |  |  | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1253A | xD_DWDM-BRKRing_CAR04_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 85.39% | Plaza Pengkalan 1253A | Services only | BBand |  | N/A | N/A | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1261A | xD_DWDM-BRKRing_CAR04_1261A KWSP_0004582309050Y_00045824006623 | 85.39% | KWSP 1261A | Services only | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1266A | xD_DWDM-BRKRing_CAR04_1266A Sucasa_0004582309050Y_00045824006623 | 85.39% | Sucasa 1266A | Services only | BBand |  | N/A | N/A | Single_2024_May_DWDM_C0407P_1266A_PRPO_1.Add module = 1 2.Add battery bank = 1 | Single | 2024 | May | DWDM | C0407P | DWDM-1266A | 1266A | PRPO | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1271A | xD_DWDM-BRKRing_CAR04_1271A Risda_0004582309050Y_00045824006623 | 85.39% | Risda 1271A | Services only | BBand |  | N/A | N/A | Single_2024_May_DWDM_DWDM-120Ch_1271A_PRPO_1.swap rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 4 3.battery bank = 6 | Single | 2024 | May | DWDM | DWDM-120Ch | DWDM-1271A | 1271A | PRPO | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1461A | xD_DWDM-BRKRing_CAR04_1461A Shaw Parade_0004582309050Y_00045824006623 | 85.39% | Shaw parade 1461A | Services only | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1737A | xD_DWDM-BRKRing_CAR04_1737A Bernama_0004582309050Y_00045824006623 | 85.39% | Bernama 1737A | Services only | BBand |  | N/A | N/A | Multiple_2024_April_DWDM_C0407P_1737A_PRPO_1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | Multiple | 2024 | April | DWDM | C0407P | DWDM-1737A | 1737A | PRPO | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1851A | xD_DWDM-BRKRing_CAR04_1851A KL Plaza_0004582309050Y_00045824006623 | 85.39% | KL Plaze 1851A | Services only | BBand |  | N/A | N/A | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [10 empty] | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR04 | 43.4% | 85.39% | 2024 Q1 | 1855B | xD_DWDM-BRKRing_CAR04_1855B TPM_0004582309050Y_00045824006623 | 85.39% | TPM 1855B | Services only | BBand |  | N/A | N/A | Multiple_2023_December_DWDM_(blank)_1855B_Completed_DCPDB = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-1855B | 1855B | Completed | No CME | #N/A | #N/A | #N/A |  | N/A | N/A | [7 empty] | Y |  |  | P1_Z_June | 0 | [6 empty] | Y | 2024-05-24 | #N/A
CAR11 | 52.48% | #N/A | 2024 Q1 | 1049B | xD_DWDM-BRKRing_CAR11_1049B MCR Kepong_0004582400700P_00045824009527 | #N/A | 1049B-MCR-002 KPG | Board expansion | BBand |  | N/A | N/A | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-22 | Wk17 | 2024-04-22 | [7 empty] | Y | 2024-04-22 | Wk17 | P0 | 0 | [7 empty] | 2024-04-18 | #N/A
CAR11 | 52.48% | #N/A | 2024 Q1 | 2070B | xD_DWDM-BRKRing_CAR11_2070B Gombak_0004582400700P_00045824009527 | #N/A | 2070B-MAG-001 Gombak Tx | Board expansion | BBand |  | N/A | N/A | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2070B | 2070B | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-22 | Wk17 | 2024-04-22 | [7 empty] | Y | 2024-04-22 | Wk17 | P0 | 0 | [7 empty] | 2024-04-18 | #N/A
CAR11 | 52.48% | #N/A | 2024 Q1 | 8709A | xD_DWDM-BRKRing_CAR11_8709A Bentong_0004582400700P_00045824009527 | #N/A | 8709A-MAG-003 Bentong | Board expansion | BBand |  | N/A | N/A | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-18 | Wk16 | 2024-04-18 | [7 empty] | Y | 2024-04-29 | Wk18 | P0 | 0 | [7 empty] | 2024-04-18 | #N/A
CT0120 | 79.05% | #N/A | 2023 | 2632A | xD_DWDM-BRKRing_CT0120_2632A Ecopark_0004582304160F_0004582308742 | #N/A | 2632A Ecopark | 1800 Rack and subrack | Advance |  |  |  | Single_2023_October_DWDM_(blank)_2632A_Completed_AC BREAKER : 32 X 3 | Single | 2023 | October | DWDM | (blank) | DWDM-2632A | 2632A | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A | 2024-05-21 | Wk21 | 2024-03-27 | replace outdoor (syabas) | Entrance issue (gate) | 0523: Replaced old outdoor rack |  |  | 2024-04-23 | TBC | Y | 2024-04-25 | Wk17 | P2 | [5 empty] | 0 |  |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8923B | xD_DWDM-BRKRing_E212_8923B Tmn Semarak_0004582304160F_00045823087420 | 107.7% | 8923B Tmn Semarak | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_January_DWDM_(blank)_8923B_Drop_ADD 100A X 2 BREAKER ADD GROUNDING X 1 ADD PLINTH X 1 ADD ODF PANEL X 1 | Single | 2024 | January | DWDM | (blank) | DWDM-8923B | 8923B | Drop | ADD 100A X 2 BREAKER | #N/A | #N/A | #N/A |  |  |  | Site Dropped | Resurvey AC |  |  |  |  | TBC | N/A |  |  | #N/A |  |  |  | N/A | Completed | 2024-02-22 | Completed |  |  | #N/A
EAR04 | #N/A | #N/A | 2023 | 1049B | xD_DWDM-BRKRing_EAR04_1049B_KPG_00045823098821 | #N/A | KPG | Services only | FO&T |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A
EAR04 | #N/A | #N/A | 2023 | 1475A | xD_DWDM-BRKRing_EAR04_1475A_MSC MSK_00045823098821 | #N/A | MSC MSK | Services only | FO&T |  |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A
EAR04 | #N/A | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_EAR04_2021B_SBHT_00045823098821 | #N/A | SBHT | Services only | FO&T |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A
EAR04 | #N/A | #N/A | 2023 | 8000A | xD_DWDM-BRKRing_EAR04_8000A_MSC KTN_00045823098821 | #N/A | MSC KTN | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A
EAR04 | #N/A | #N/A | 2023 | 8703A | xD_DWDM-BRKRing_EAR04_8703A_KG Awah_00045823098821 | #N/A | KG Awah | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-10-25 | Wk43 | #N/A |  |  |  | N/A | Completed | 2023-10-25 | Completed |  |  | #N/A
MCR144 | #N/A | #N/A | 2023 | 1007A | xD_DWDM-BRKRing_MCR144_1007A MAC Mimaland_0004582304330Y_00045823098821 | #N/A | 1007A MAC Mimaland | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1007A_Completed_DCPDB = 1 UNIT MGB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1007A | 1007A | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  |  |  |  | Y |  | Completed | Y | 2023-10-10 | Wk41 | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
MCR144 | #N/A | #N/A | 2023 | 1770B | xD_DWDM-BRKRing_MCR144_1770B MAC GentingSempah_0004582304330Y_00045823098821 | #N/A | 1770B MAC GentingSempah | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1770B_Completed_AC BREAKER : 32 X 3 | Single | 2023 | October | DWDM | (blank) | DWDM-1770B | 1770B | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | Y |  | Completed | Y | 2023-10-17 | Wk42 | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
MCR144 | #N/A | #N/A | 2023 | 1787B | xD_DWDM-BRKRing_MCR144_1787B MAC KarakHW_0004582304330Y_00045823098821 | #N/A | 1787B MAC KarakHW | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_1787B_Completed_DC BREAKER: 63A X 2 | Single | 2023 | October | DWDM | (blank) | DWDM-1787B | 1787B | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | Y |  | Completed | Y | 2023-10-17 | Wk42 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
MCR144 | #N/A | #N/A | 2023 | 2070B | xD_DWDM-BRKRing_MCR144_2070B MAC Gombak_0004582304330Y_00045823098821 | #N/A | 2070B MAC Gombak | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2070B | 2070B | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | Y |  | Completed | Y | 2023-10-19 | Wk42 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
MCR144 | #N/A | #N/A | 2023 | 2086A | xD_DWDM-BRKRing_MCR144_2086A Balai Polis Bkt Tinggi_0004582304330Y_00045823098821 | #N/A | 2086A Balai Polis Bkt Tinggi | 1800 Rack and subrack | Bband |  |  |  | Single_2023_October_DWDM_(blank)_2086A_Completed_DC BREAKER: 63A X 2 | Single | 2023 | October | DWDM | (blank) | DWDM-2086A | 2086A | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  |  | 2023-10-18 |  |  |  |  | Y |  | Completed | Y | 2023-10-18 | Wk42 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
MCR144 | #N/A | #N/A | 2023 | 8709A | xD_DWDM-BRKRing_MCR144_8709A MAG Bentong_0004582304330Y_00045823098821 | #N/A | 8709A MAG Bentong | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-16 |  |  |  |  | Y |  | Completed | Y | 2023-10-16 | Wk42 | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 1172A | xD_DWDM-BRKRing_MCR18/C24_1172A Glomac_0004582306610C_00045823162822 | #N/A | 1172A Glomac | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | N/A |  |  |  |  | N/A |  | 2024-02-12 | N/A | 2023-11-14 | Wk46 | P2 | [9 empty] | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 1360A | xD_DWDM-BRKRing_MCR18/C24_1360B Hicom Glenmarie_0004582306610C_00045823162822 | #N/A | 1360B Hicom Glenmarie | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_(blank)_1360A_Completed_1. Swap Cabine | Multiple | 2024 | May | DWDM | (blank) | DWDM-1360A | 1360A | Completed | 1. Swap Cabine | #N/A | #N/A | #N/A |  |  | 2024-05-11 | CME - Decom | OUTDOOR | 0524: Plan to power up and int on 30/5 0517: Pending access |  |  | Replan | 2024-02-12 |  |  |  | P2 | [5 empty] | 0 |  |  |  | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 1362B | xD_DWDM-BRKRing_MCR18/C24_1362B Kelana Business_0004582306610C_00045823162822 | #N/A | 1362B Kelana Business | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1362B_Completed_DCPDB = 1 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1362B | 1362B | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | Pending PFS Swap | Pending PFS Swap | 0517: Pending PFS swap. F/u w/ Nazwan |  |  | 2024-02-12 | 2024-02-12 |  |  |  | P2 | 2024-02-15 09:54 |  |  |  |  | 0 |  |  |  | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 1378B | xD_DWDM-BRKRing_MCR18/C24_1378B PJS 10_0004582304330Y_00045823098821 | #N/A | 1378B PJS 10 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1378B_Completed_DC BREAKER: 63A X 2 | Single | 2023 | October | DWDM | (blank) | DWDM-1378B | 1378B | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  |  | 2023-11-23 | CRQ approved, apply BM Access, Plan 7th May | 29/1: Key issue | 0521: CD give permision to drill the padlock 0517: Key issue. Need to f/u with Zul | 2024-01-09 |  | 2024-02-12 | 2024-02-12 |  |  |  | P2 | 2024-02-15 09:54 |  | No key | [6 empty] | #N/A
MCR18/C24 | #N/A | #N/A | 2023 | 2021B | xD_DWDM-BRKRing_MCR18/C24_2021B SBHT_0004582306610C_00045823162822 | #N/A | 2021B SBHT | 1800 Rack and subrack | Bband |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A |  |  | 2023-11-07 |  |  |  | 2024-01-09 | Y | 2024-01-09 | 2024-02-12 | Y | 2023-12-12 | Wk50 | P2 |  | Integrated but plan next date | completed | [6 empty] | #N/A
N103 | 57.39% | #N/A | 2023 | 4660A | xD_DWDM-BRKRing_N103_4660A KTM Alorstar_0004582306610C_00045823162822 | #N/A | 4660A KTM Alorstar | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  | Request DCPDB, subrack can move to existing rack 12/1: Pending odf panel 16/1: bring ODF panel & travel |  | 2024-01-12 |  | 2024-01-12 | 2024-02-07 | Y | 2024-01-18 | Wk3 | P1 | 2024-01-17 09:48 |  |  |  |  | 0 |  |  |  | #N/A
N103 | 57.39% | #N/A | 2023 | 4669A | xD_DWDM-BRKRing_N103_4669A Alor Janggus_0004582306610C_00045823162822 | #N/A | 4669A Alor Janggus | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4669A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4669A | 4669A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 | CME | 12/1: Pending odf panel 16/1: bring ODF panel & travel 23/1: Pending CME 30/1: Pending DCPDB 7/2: Pending DCPDB |  |  | Y | 2024-03-15 | 2024-02-07 | Y | 2024-03-12 | Wk11 | P1 | [5 empty] | 0 |  |  |  | #N/A
N103 | 57.39% | #N/A | 2023 | 4863B | xD_DWDM-BRKRing_N103_4863B Wisma PKNK_0004582306610C_00045823162822 | #N/A | 4863B Wisma PKNK | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2024_April_DWDM_N103_4863B_PRPO_1. Add Battery Bank = 1 | Multiple | 2024 | April | DWDM | N103 | DWDM-4863B | 4863B | PRPO | 1. Add Battery Bank = 1 | #N/A | #N/A | #N/A | 2024-05-08 | Wk19 | 2024-05-08 |  | OUTDOOR |  |  |  | Replan | 2024-02-07 | Y | 2024-05-09 | Wk19 | P1 | [5 empty] | 0 |  |  |  | #N/A
N103 | 57.39% | #N/A | 2023 | 4998A | xD_DWDM-BRKRing_N103_4998A Air Itam Kedah_0004582306610C_00045823162822 | #N/A | 4998A Air Itam Kedah | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | 1. Add Battery Bank = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  | 12/1: Pending odf panel 16/1: bring ODF panel & travel |  |  | Y | 2024-01-12 | 2024-01-16 | Y | 2024-01-17 | Wk3 | P1 | 2024-01-17 09:48 |  |  |  |  | 0 |  |  |  | #N/A
N106 | 40.89% | #N/A | 2023 | 4085D | xD_DWDM-BRKRing_N106_4085D Kulim Hitech2_0004582306610C_00045823162822 | #N/A | 4085D Kulim Hitech2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4085D_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | November | DWDM | (blank) | DWDM-4085D | 4085D | Completed | RECTTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  |  | 2023-11-08 |  |  |  |  | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A
N106 | 40.89% | #N/A | 2023 | 4683A | xD_DWDM-BRKRing_N106_4683A Bkt Tok Alang_0004582306610C_00045823162822 | #N/A | 4683A Bkt Tok Alang | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3 | Single | 2024 | May | DWDM | N106+ | DWDM-4683A | 4683A | PRPO | 1. Add Battery Bank = 3 | #N/A | #N/A | #N/A |  |  | 2023-11-09 |  |  |  |  | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A
N106 | 40.89% | #N/A | 2023 | 4946A | xD_DWDM-BRKRing_N106_4946A Bukit Selambau_0004582306610C_00045823162822 | #N/A | 4946A Bukit Selambau | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | DROP | #N/A | #N/A | #N/A |  |  | 2023-11-09 |  |  |  |  | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A
N106 | 40.89% | #N/A | 2023 | 4966A | xD_DWDM-BRKRing_N106_4966A Kulim Hi Tech_0004582306610C_00045823162822 | #N/A | 4966A Kulim Hi Tech | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-08 |  |  |  |  | Y |  | Completed | Y | 2023-11-16 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-11-16 | Completed |  |  | #N/A
N113 | 41.2% | #N/A | 2023 | 4662A | xD_DWDM-BRKRing_N113_4662A MAC BktTinggiJitra_0004582304330Y_00045823098821 | #N/A | 4662A MAC BktTinggiJitra | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4662A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4662A | 4662A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-25 |  |  |  |  | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
N113 | 41.2% | #N/A | 2023 | 4678A | xD_DWDM-BRKRing_N113_4678A MAC JlnLanggar_0004582304330Y_00045823098821 | #N/A | 4678A MAC JlnLanggar | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4678A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4678A | 4678A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-23 |  |  |  |  | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
N113 | 41.2% | #N/A | 2023 | 4992A | xD_DWDM-BRKRing_N113_4992A MAG Pendang_0004582304330Y_00045823098821 | #N/A | 4992A MAG Pendang | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | #N/A | #N/A | #N/A |  |  | 2023-10-25 |  |  |  |  | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
N113 | 41.2% | #N/A | 2023 | 4995A | xD_DWDM-BRKRing_N113_4995A MAG UUMHW_0004582304330Y_00045823098821 | #N/A | 4995A MAG UUMHW | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-23 |  |  |  |  | Y | 04/01/2024-5/1/2024 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
N114M | 10.29% | #N/A | 2023 | 4660A | xD_DWDM-BRKRing_N114M_4660A Ktm Astar_000458237400E_00045823174223 | #N/A | 4660A Ktm Astar | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  |  |  |  | Y | 2024-01-18 | 2024-01-18 | Y | 2024-01-18 | Wk3 | #N/A |  |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A
N114M | 10.29% | #N/A | 2023 | 4692A | xD_DWDM-BRKRing_N114M_4692A Gurun_0004582306610C_00045823162822 | #N/A | 4692A Gurun | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  | 23/1: Pending power tap |  |  |  | 2024-01-29 | 2024-02-06 | Y | 2024-01-29 | Wk5 | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A
N114M | 10.29% | #N/A | 2023 | 4938A | xD_DWDM-BRKRing_N114M_4938A Tmn Orkid_000458237400E_00045823174223 | #N/A | 4938A Tmn Orkid | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 | CME - Special Power Cable | 16mm power cable required, 40m breaker x 4 1/2: Pending power cable 16mm2 6/2: Pending power cable 16mm2 |  |  |  | 2024-03-07 | 2024-02-06 | Y | 2024-03-07 | Wk10 | #N/A |  |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A
N114M | 10.29% | #N/A | 2023 | 4938A | xD_DWDM-BRKRing_N114M_4938A Tmn Orkid2_000458237400E_00045823174223 | #N/A | 4938A Tmn Orkid2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 | CME - Special Power Cable | 6/2: Pending power cable 16mm2 |  |  |  | 2024-03-07 | #N/A | Y | 2024-03-07 | Wk10 | #N/A |  |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A
N114M | 10.29% | #N/A | 2023 | 4940A | xD_DWDM-BRKRing_N114M_4940A Semeling_0004582306610C_00045823162822 | #N/A | 4940A Semeling | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4940A_Completed_BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4940A | 4940A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | [5 empty] | 2024-01-30 | 2024-02-06 | Y | 2024-01-30 | Wk5 | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-27 | Completed |  |  | #N/A
N115 | 23.69% | #N/A | 2023 | 4770A | xD_DWDM-BRKRing_N115_4770A Toklin_0004582304160F_00045823087420 | #N/A | 4770A Toklin | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4770A_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4770A | 4770A | Completed | RECTTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-12-21 | Completed |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_N201_4000A MSC Prai_000458237400E_00045823174223 | #N/A | 4000A MSC Prai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  |  | 2023-11-20 |  |  |  |  | Y | 2024-01-31 | Completed | Y | 2023-11-19 | Wk46 | P?? |  |  | CME completed12/Jan |  |  | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4685B | xD_DWDM-BRKRing_N201_4685B Kg Sungai Karangan_000458237400E_00045823174223 | #N/A | 4685B Kg Sungai Karangan | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4685B_Completed_DCPDB = 1 UNIT MGB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4685B | 4685B | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  |  | 2023-11-30 |  |  |  |  | Y | 2024-02-01 | 2024-01-30 | Y | 2024-02-01 | Wk5 | P?? | [5 empty] | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4950B | xD_DWDM-BRKRing_N201_4950B Pulai_000458237400E_00045823174223 | #N/A | 4950B Pulai | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_October_DWDM_(blank)_4950B_Completed_DC BREAKER: 63 A X 4 | Multiple | 2023 | October | DWDM | (blank) | DWDM-4950B | 4950B | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-23 | [5 empty] | 2024-02-06 | 2024-01-30 | Y | 2024-02-06 | Wk6 | P?? | 2024-02-06 09:38 |  |  |  |  | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4956B | xD_DWDM-BRKRing_N201_4956B Kuala Pegang_000458237400E_00045823174223 | #N/A | 4956B Kuala Pegang | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4956B_Completed_DCPDB = 1 UNIT MGB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4956B | 4956B | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  |  | 2023-11-23 | [5 empty] | 2024-02-05 | 2024-01-30 | Y | 2024-02-05 | Wk6 | P?? | 2024-02-05 09:37 |  |  |  |  | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4968A | xD_DWDM-BRKRing_N201_4968A Inokom Kulim_000458237400E_00045823174223 | #N/A | 4968A Inokom Kulim | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4968A_Completed_AC BREAKER : 32 X 3 | Single | 2023 | November | DWDM | (blank) | DWDM-4968A | 4968A | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  | 12/1: Pending DCPDB, odf panel 16/1: bring ODF panel & travel |  |  | Y | 2024-01-30 | 2024-01-30 | Y | 2024-01-30 | Wk5 | P?? | 2024-01-26 09:59 |  |  |  |  | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4985A | xD_DWDM-BRKRing_N201_4985A Baling Town_000458237400E_00045823174223 | #N/A | 4985A Baling Town | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4985A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =2 | Single | 2023 | November | DWDM | (blank) | DWDM-4985A | 4985A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y | 2024-02-07 | 2024-01-30 | Y | 2024-02-07 | Wk6 | P?? | 2024-02-07 09:48 |  |  |  |  | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4986A | xD_DWDM-BRKRing_N201_4986A Binjul_000458237400E_00045823174223 | #N/A | 4986A Binjul | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4986A_Completed_DCPDB = 1 UNIT MGB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4986A | 4986A | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  |  | 2023-11-24 | [5 empty] | 2024-02-02 | 2024-01-30 | Y | 2024-02-02 | Wk5 | P?? | 2024-02-02 11:21 |  |  |  |  | 0 |  |  |  | #N/A
N201 | 63.25% | #N/A | 2023 | 4988A | xD_DWDM-BRKRing_N201_4988A Kupang_000458237400E_00045823174223 | #N/A | 4988A Kupang | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4988A_Completed_BATTERY BANK = 2 | Single | 2023 | October | DWDM | (blank) | DWDM-4988A | 4988A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y | 2024-02-05 | 2024-01-30 | Y | 2024-02-05 | Wk6 | P?? | 2024-02-05 09:37 |  |  |  |  | 0 |  |  |  | #N/A
N302 | 67.19% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_N302_4000A MSC Prai_0004582306610C_00045823162822 | #N/A | 4000A MSC Prai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  |  | 2023-11-20 |  | 23/1: Pending power tap |  | 2024-01-16 |  | 2024-01-31 | 2024-02-16 | Y | 2024-01-31 | Wk5 | #N/A | 2024-01-26 09:59 |  | CME completed12/Jan | Y | Completed | 2024-04-25 | 2024-04-25 |  |  | #N/A
N302 | 67.19% | #N/A | 2023 | 4188A | xD_DWDM-BRKRing_N302_4188A Nibong tebal2_0004582306610C_00045823162822 | #N/A | 4188A Nibong tebal2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4188A_Completed_RECTIFIER + DCPDB = 1 RECTIFIER MODULE = 3 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-4188A | 4188A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y | 2024-01-16 | 2024-01-16 | Y | 2024-01-16 | Wk3 | #N/A | 2024-01-16 10:25 |  |  | Y | Completed | 2024-04-25 | 2024-04-25 |  |  | #N/A
N302 | 67.19% | #N/A | 2023 | 4241A | xD_DWDM-BRKRing_N302_4241A Juru Tower_0004582306610C_00045823162822 | #N/A | 4241A Juru Tower | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-20 |  |  |  |  | Y | 2024-01-16 | 2024-01-16 | Y | 2024-01-17 | Wk3 | #N/A | 2024-01-17 09:48 |  |  | Y | Completed | 2024-04-25 | 2024-04-25 |  |  | #N/A
N404 | 33.59% | #N/A | 2023 | 4427B | xD_DWDM-BRKRing_N404_4427B MAC SimpangTaiping_0004582304330Y_00045823098821 | #N/A | 4427B MAC SimpangTaiping | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4427B_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK =3 | Single | 2023 | December | DWDM | (blank) | DWDM-4427B | 4427B | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-15 | Wk3 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A
N404 | 33.59% | #N/A | 2023 | 4454B | xD_DWDM-BRKRing_N404_4454B MAC KubuGajah_0004582304330Y_0004582307060Z_00045823098821 | #N/A | 4454B MAC KubuGajah | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_4454B_Completed_DC BREAKER : 100A X 2 I-BEAM = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-4454B | 4454B | Completed | DC BREAKER : 100A X 2 | #N/A | #N/A | #N/A |  |  | 2023-11-10 |  |  |  |  | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-15 | Wk3 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A
N404 | 33.59% | #N/A | 2023 | 4455A | xD_DWDM-BRKRing_N404_4455A MAG KTMTaiping_0004582304330Y_00045823098821 | #N/A | 4455A MAG KTMTaiping | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-12 | Wk2 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A
N404 | 33.59% | #N/A | 2023 | 4457A | xD_DWDM-BRKRing_N404_4457A MAC KamuntingIndst_0004582304330Y_00045823098821 | #N/A | 4457A MAC KamuntingIndst | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-18 |  |  |  |  | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-12 | Wk2 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A
N404 | 33.59% | #N/A | 2023 | 4465A | xD_DWDM-BRKRing_N404_4465A MAC TmnLongJaafar_0004582304330Y_00045823098821 | #N/A | 4465A MAC TmnLongJaafar | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4465A_Completed_BATTERY BANK = 7 | Single | 2023 | November | DWDM | (blank) | DWDM-4465A | 4465A | Completed | BATTERY BANK = 7 | #N/A | #N/A | #N/A |  |  | 2023-10-18 |  | 12/1: Plan next week |  |  | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-15 | Wk3 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A
N404 | 33.59% | #N/A | 2023 | 4952B | xD_DWDM-BRKRing_N404_4952B MAG Selama_0004582304330Y_00045823098821 | #N/A | 4952B MAG Selama | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | Y | 9/1/2024-11/1/2024 | 2024-01-12 | Y | 2024-01-12 | Wk2 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2024-02-21 | Completed |  |  | #N/A
N406 | 17.94% | #N/A | 2023 | 4432A | xD_DWDM-BRKRing_N406_4432A MAG KTMSgSiput_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4432A MAG KTMSgSiput | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-03-20 | Wk12 | 2024-03-22 | [5 empty] | 2024-03-14 | NO EQUIPMENT REDELPOY TO KUSZA (E212) | Y | 2024-03-22 | Wk12 | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A
N406 | 17.94% | #N/A | 2023 | 4493A | xD_DWDM-BRKRing_N406_4493A MAG KTMIpoh_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4493A MAG KTMIpoh | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  |  | Material relocation |  |  |  |  | 2024-03-14 | NO EQUIPMENT REDELPOY TO BKT PAYUNG 2 (E212) |  |  |  | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A
N406 | 17.94% | #N/A | 2023 | 4496A | xD_DWDM-BRKRing_N406_4496A MAC LapTasek1N2_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4496A MAC LapTasek1N2 | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-02-23 | Wk8 | 2024-02-23 | [5 empty] | 2024-03-14 |  | Y | 2024-03-13 | Wk11 | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A
N406 | 17.94% | #N/A | 2023 | 4536A | xD_DWDM-BRKRing_N406_4536A MAC TasekIndst_0004582304330Y_0004582304330X_00045823098821 | #N/A | 4536A MAC TasekIndst | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  |  | Material relocation |  |  |  |  | 2024-03-14 | NO EQUIPMENT REDELPOY TO TMN SEMARAK (E212) |  |  |  | #N/A |  |  |  | Y | Completed | 0 | Completed |  |  | #N/A
N601 | 43.15% | #N/A | 2023 | 4368A | xD_DWDM-BRKRing_N601_4368A Tar College_0004582306900G_00045823168029 | #N/A | 4368A Tar College | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4368A_Completed_DC BREAKER : 63A X 4 MGB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4368A | 4368A | Completed | DC BREAKER : 63A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-21 | EB site- CRQ |  |  |  | Y | 2024-01-29 | 2024-02-05 | Y | 2024-01-29 | Wk5 | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
N601 | 43.15% | #N/A | 2023 | 4440B | xD_DWDM-BRKRing_N601_4440B Tapah Road_0004582306900G_00045823168029 | #N/A | 4440B Tapah Road | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4440B_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-4440B | 4440B | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | EB site- CRQ |  |  |  | Y | 2024-01-17 | Completed | Y | 2024-01-16 | Wk3 | #N/A |  |  | completed | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
N601 | 43.15% | #N/A | 2023 | 4509A | xD_DWDM-BRKRing_N601_4509A Tamn Taufik_0004582306900G_00045823168029 | #N/A | 4509A Tamn Taufik | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4509A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4509A | 4509A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | EB site- CRQ | 23/1: Pending DCPDB 6/2: Plan 7/2 due to site key not available |  |  |  | 2024-02-06 | 2024-02-07 | Y | 2024-02-07 | Wk6 | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
N601 | 43.15% | #N/A | 2023 | 4516A | xD_DWDM-BRKRing_N601_4516A Simpang Pulai_0004582306900G_00045823168029 | #N/A | 4516A Simpang Pulai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4516A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-4516A | 4516A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | EB site- CRQ | 23/1: Pending DCPDB |  |  |  | 2024-02-07 | 2024-02-07 | Y | 2024-02-06 | Wk6 | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
N601 | 43.15% | #N/A | 2023 | 4521A | xD_DWDM-BRKRing_N601_4521A MSC Ipoh_0004582306900G_00045823168029 | #N/A | 4521A MSC Ipoh | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-21 |  |  |  | 2024-01-29 |  | 2024-01-29 | 2024-02-07 | Y | 2024-01-30 | Wk5 | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4000A | xD_DWDM-BRKRing_Nar01i_4000A Msc Prai | #N/A | 4000A Msc Prai | 9800 Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4521A | xD_DWDM-BRKRing_Nar01i_4521A Msc Ipoh | #N/A | 4521A Msc Ipoh | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4946A | xD_DWDM-BRKRing_Nar01i_4946A Bkt Selambau | #N/A | 4946A Bkt Selambau | 9800 Board expansion | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01i | #N/A | #N/A | Pending Po | 4966A | xD_DWDM-BRKRing_Nar01i_4966A Kulim Hitech | #N/A | 4966A Kulim Hitech | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01i | #N/A | #N/A | Pending PO | 4992A | xD_DWDM-BRKRing_Nar01i_4992A Pendang | #N/A | 4992A Pendang | 9800 Board expansion | FO&T |  |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4606A | xD_DWDM-BRKRing_Nar01ii_4606A Padang Besar | #N/A | 4606A Padang Besar | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4938A | xD_DWDM-BRKRing_Nar01ii_4638A Tmn Orkid | #N/A | 4638A Tmn Orkid | 9800 Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4660A | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | #N/A | 4660A Ktm Astar | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
Nar01ii | #N/A | #N/A | Pending PO | 4998A | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | #N/A | 4660A Ktm Astar | 9800 Board expansion | FO&T |  |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | No CME | #N/A | #N/A | #N/A |  |  |  | Pending PO | Pending PO |  |  |  |  | Pending PO |  |  |  | #N/A | [5 empty] | 0 |  |  |  | #N/A
NAR03 | 49.46% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_NAR03_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4000A MSC Prai | 9800 SFP only | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-20 | [5 empty] | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | P0 | 2024-01-17 09:48 | [8 empty] | #N/A
NAR03 | 49.46% | #N/A | 2023 | 4331A | xD_DWDM-BRKRing_NAR03_4331A Bagan Serai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4331A Bagan Serai | 9800 SFP only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | P0 | 2024-01-17 09:48 | [8 empty] | #N/A
NAR06 | 22.23% | #N/A | 2023 | 1049B | xD_DWDM-BRKRing_NAR06_1049B Kpg_0004582306610A_0004582306610D_00045823162822 | #N/A | 1049B Kpg | 9800 SFP only | FO&T |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-15 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | N/A | 2024-01-24 | Wk4 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
NAR06 | 22.23% | #N/A | 2023 | 1701A | xD_DWDM-BRKRing_NAR06_1801A Kerling Trnk_0004582306610A_0004582306610D_00045823162822 | #N/A | 1801A Kerling Trnk | 9800 SFP only | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_1701A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-1701A | 1701A | Completed | No CME | #N/A | #N/A | #N/A |  |  | N/A | Material combined to Nar06 kepong | Material combined to Nar06 kepong |  |  | N/A | 2024-01-08 | 2024-01-10 | N/A | 2024-01-24 | Wk4 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
NAR06 | 22.23% | #N/A | 2023 | 4412A | xD_DWDM-BRKRing_NAR06_4412A KTM Sungkai_0004582306610A_0004582306610D_00045823162822 | #N/A | 4412A KTM Sungkai | 9800 SFP only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | N/A | Material combined to Nar06 kepong | Material combined to Nar06 kepong |  |  | N/A | 2024-01-08 | 2024-01-10 | N/A | 2024-01-24 | Wk4 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
NAR06 | 22.23% | #N/A | 2023 | 4440B | xD_DWDM-BRKRing_NAR06_4440B Tapah Road_0004582306610A_0004582306610D_00045823162822 | #N/A | 4440B Tapah Road | 9800 Board expansion | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4440B_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-4440B | 4440B | Completed | No CME | #N/A | #N/A | #N/A |  |  | 2024-01-23 | Invalid Config | Invalid Config |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
NAR06 | 22.23% | #N/A | 2023 | 4521A | xD_DWDM-BRKRing_NAR06_4521A MSC IPOH_0004582306610A_0004582306610D_00045823162822 | #N/A | 4521A MSC IPOH | 9800 Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-21 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-12 | Wk2 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
NAR06 | 22.23% | #N/A | 2023 | 4521A | xD_DWDM-BRKRing_NAR06_4521A MSC IPOH_0004582306610A_0004582306610D_00045823162822 | #N/A | 4521A MSC IPOH | 9800 SFP only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-21 |  |  |  |  | N/A | 2024-01-08 | 2024-01-10 | Y | 2024-01-24 | Wk4 | #N/A |  |  |  | Y | Completed | 2024-01-24 | Completed |  |  | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6000A | xD_DWDM-BRKRing_New Ring_5/S406_6000A MSC JB_0004582306610B_00045823162821 | #N/A | 6000A MSC JB | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-12-05 | [5 empty] | 2024-02-15 | 2024-02-14 | Y | 2024-02-15 | Wk7 | P1 | 2024-02-15 09:54 |  |  |  |  | 0 |  |  |  | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6026A | xD_DWDM-BRKRing_New Ring_5/S406_6026A Grand Cont Hotel_0004582306610B_00045823162821 | #N/A | 6026A Grand Cont Hotel | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6026A_Completed_DC BREAKER: 63A X 3 | Single | 2023 | November | DWDM | (blank) | DWDM-6026A | 6026A | Completed | DC BREAKER: 63A X 3 | #N/A | #N/A | #N/A |  |  | 2023-12-07 | [5 empty] | 2024-02-15 | 2024-02-14 | Y | 2024-02-19 | Wk8 | P1 | 2024-02-15 09:54 |  |  |  |  | 0 |  |  |  | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6043A | xD_DWDM-BRKRing_New Ring_5/S406_6043A KK Kam_0004582306610B_00045823162821 | #N/A | 6043A KK Kam | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  | 2024-01-10 | Y | 2024-01-10 | 2024-02-14 | Y | 2024-01-11 | Wk2 | P1 | 2024-01-15 11:00 | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6283A | xD_DWDM-BRKRing_New Ring_5/S406_6283A Larkin Indst_0004582306610B_00045823162821 | #N/A | 6283A Larkin Indst | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6283A_Completed_DCPDB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6283A | 6283A | Completed | DCPDB = 1 | #N/A | 1.7 TSSR Approved | #N/A |  |  | 2023-12-08 | CME Done | Pending CRQ |  |  |  | 2024-03-12 | 2024-02-14 | Y |  |  | P1 | 2024-03-14 09:26 |  |  |  |  | 0 |  |  |  | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6502A | xD_DWDM-BRKRing_New Ring_5/S406_6502A Nusa Perintis_0004582306610B_00045823162821 | #N/A | 6502A Nusa Perintis | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6502A | 6502A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-08 |  |  |  |  | Y |  | 2024-02-14 | Y | 2024-01-10 | Wk2 | P1 |  | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A
New Ring5/S406 | #N/A | #N/A | 2023 | 6836A | xD_DWDM-BRKRing_New Ring_5/S406_6836A Menara Ansar_0004582306610B_0004582316282 | #N/A | 6836A Menara Ansar | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_(blank)_6836A_Completed_1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Single | 2024 | May | DWDM | (blank) | DWDM-6836A | 6836A | Completed | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-04-24 | Wk17 | 2024-04-24 |  | 29/1: TSSR pending Haji approval |  | 2024-01-18 |  |  | 2024-02-14 | Y | 2024-05-09 | Wk19 | P1 | 2024-02-02 11:13 |  |  |  |  | 0 |  |  |  | #N/A
NT09P | 0.801% | #N/A | 2023 | 4000A | xD_DWDM-BRKRing_NT09P_4000A MSC Prai_000458237400E_00045823174223 | #N/A | 4000A MSC Prai | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  |  | Completed | Invalid Config | Invalid Config |  |  | N/A |  | 2024-02-05 | N/A | 2024-01-31 | Wk5 | P1 |  |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A
NT09P | 0.801% | #N/A | 2023 | 4621A | xD_DWDM-BRKRing_NT09P_4621A Cayman Shop Comp_000458237400E_00045823174223 | #N/A | 4621A Cayman Shop Comp | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4621A_Completed_BATTERY BANK = 3 | Single | 2023 | December | DWDM | (blank) | DWDM-4621A | 4621A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  |  |  |  | Y | 2024-01-30 | 2024-02-05 | Y | 2024-01-30 | Wk5 | P1 | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A
NT09P | 0.801% | #N/A | 2023 | 4625A | xD_DWDM-BRKRing_NT09P_4625A KTM Sg Petani_000458237400E_00045823174223 | #N/A | 4625A KTM Sg Petani | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4625A_Completed_BATTERY BANK = 3 | Single | 2023 | December | DWDM | (blank) | DWDM-4625A | 4625A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y | 2024-01-31 | 2024-02-05 | Y | 2024-01-31 | Wk5 | P1 |  |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A
NT09P | 0.801% | #N/A | 2023 | 4640A | xD_DWDM-BRKRing_NT09P_4640A SP Plaza_0004582304160F_00045823087420 | #N/A | 4640A SP Plaza | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4640A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4640A | 4640A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  | 12/1: Pending DCPDB, ODF panel 16/1: pending DCPDB |  | 2024-02-01 |  | 2024-02-01 | 2024-02-05 | Y | 2024-02-01 | Wk5 | P1 | 2024-01-26 09:59 |  |  | Y | Completed | 2024-03-19 | Completed |  |  | #N/A
NT09P | 0.801% | #N/A | 2023 | 4693A | xD_DWDM-BRKRing_NT09P_4693A Ktm Gurun_000458237400E_00045823174223 | #N/A | 4693A Ktm Gurun | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4693A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | November | DWDM | (blank) | DWDM-4693A | 4693A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  | 12/1: Pending odf panel 16/1: bring ODF panel & travel |  |  | Y | 2024-01-29 | 2024-02-05 | Y | 2024-01-29 | Wk5 | P1 | 2024-01-29 09:59 |  | CME completed12/Jan | Y | Completed | 2024-03-19 | Completed |  |  | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1246A | xD_DWDM-BRKRing_PFSRING101/C0607P_1246A Kompleks Nagaria_0004582306610C_00045823162822 | #N/A | 1246A Kompleks Nagaria | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_1246A_Completed_DC BREAKER: 63 A X 4 POLE RELOCATE = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1246A | 1246A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-12-08 | [5 empty] | 2024-02-16 | 2024-02-16 | Y | 2024-01-09 | Wk2 | P1 | [5 empty] | 0 |  |  |  | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1475A | xD_DWDM-BRKRing_PFSRING101/C0607P_1475A Sri Kembangan_0004582306610C_00045823162822 | #N/A | 1475A Sri Kembangan | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A |  |  | 2023-12-04 |  | Pending power up |  | 2024-01-10 | Y | 2024-01-22 | 2024-02-16 | Y | 2024-01-24 | Wk4 | P1 | 2024-01-26 09:54 |  |  |  |  | 0 |  |  |  | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1851A | xD_DWDM-BRKRing_PFSRING101/C0607P_1851A KL Plaza2_0004582306610C_00045823162822 | #N/A | 1851A KL Plaza2 | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A |  |  | 2023-11-24 | [5 empty] | 2024-02-16 | 2024-02-16 | Y | 2024-02-20 | Wk8 | P1 | 2024-02-19 11:08 |  |  |  |  | 0 |  |  |  | #N/A
PFSRING101/C0607P | #N/A | #N/A | 2023 | 1899A | xD_DWDM-BRKRing_PFSRING101/C0607P_1899A Berjaya Times Square CAS_0004582306610C_00045823162822 | #N/A | 1899A Berjaya Times Square | 1800 Rack and subrack | BBand |  | 2024-03-07 |  | Single_2024_May_DWDM_PFSRING101/C0607P_1899A_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | PFSRING101/C0607P | DWDM-1899A | 1899A | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Indoor | 1.6 Pending FF approval | #N/A | 2024-05-09 | Wk19 | 2024-05-09 | Access - BM (CD acknowledged) | Access |  |  |  |  | 2024-02-16 |  |  |  | P1 | [5 empty] | 0 |  |  |  | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 1015A | xD_DWDM-BRKRing_Ring58/C1103_1015A Awana Golf_0004582307100Y_00045823168326 | #N/A | 1015A Awana Golf | 1800 subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-05-09 | Wk19 | 2024-05-09 | Access issue | Access | Installation complete |  |  |  | TBC |  |  |  | P1_Z_Aug | [5 empty] | 0 |  |  |  | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 1016A | xD_DWDM-BRKRing_Ring58/C1103_1016A Genting Ria_0004582307100Y_00045823168326 | #N/A | 1016A Genting Ria | 1800 subrack | BBand | 2024-04-26 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-05 | Wk23 |  | OUTDOOR | OUTDOOR | 0524: Freezed. Pending Dn. Not yet freeze in KHE. No DUID 0523: Need to freeze |  |  |  | 2024-02-16 |  |  |  | P1_Z_Aug | [5 empty] | 0 |  |  |  | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 1770B | xD_DWDM-BRKRing_Ring58/C1103_1770B Genting Sempah_0004582307100Y_00045823168326 | #N/A | 1770B Genting Sempah | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1770B_Completed_AC BREAKER : 32 X 3 | Single | 2023 | October | DWDM | (blank) | DWDM-1770B | 1770B | Completed | AC BREAKER : 32 X 3 | #N/A | #N/A | #N/A |  |  | 2023-12-15 |  |  |  | 2024-01-16 |  | 2024-01-16 | 2024-02-15 | Y | 2024-01-17 | Wk3 | P1_Z_Aug | 2024-01-17 09:35 | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 2070B | xD_DWDM-BRKRing_Ring58/C1103_2070B Gombak_0004582307100Y_00045823168326 | #N/A | 2070B Gombak | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_2070B_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2070B | 2070B | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-25 |  |  |  |  | Y |  | 2024-02-16 | Y | 2023-11-06 | Wk45 | P1_Z_Aug |  | Integrated but plan next date | completed |  |  | 0 |  |  |  | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 2833A | xD_DWDM-BRKRing_Ring58/C1103_2833A First World Hotel_0004582307100Y_00045823168326 | #N/A | 2833A First World Hotel | 1800 subrack (outdoor rack) | BBand |  |  |  | Single_2023_October_DWDM_(blank)_2833A_Completed_AC BREAKER : 32 X 1 I-BEAM = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-2833A | 2833A | Completed | AC BREAKER : 32 X 1 | #N/A | #N/A | #N/A | 2024-06-06 | Wk23 |  | Access issue | OUTDOOR | 0523: Change RAD to 6/6 0520: Waiting outbound 0517: Need to freeze |  |  |  | TBC |  |  |  | P1_Z_Aug | [5 empty] | 0 |  |  |  | #N/A
Ring58/C1103 | #N/A | #N/A | 2023 | 8709A | xD_DWDM-BRKRing_Ring58/C1103_8709A Bentong_0004582307100Y_00045823168326 | #N/A | 8709A Bentong | 1800 subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_8709A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8709A | 8709A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-25 |  |  |  |  | Y | 2024-02-16 | 2024-02-16 | Y | 2024-01-09 | Wk2 | P1_Z_Aug | [5 empty] | 0 |  |  |  | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1525A | xD_DWDM-BRKRing_S313P_2_2_1525A Graha Maju_0004582304160F_00045823087420 | #N/A | 1525A Graha Maju | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1525A_Completed_DC BREAKER: 16A X 2 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1525A | 1525A | Completed | DC BREAKER: 16A X 2 | #N/A | #N/A | #N/A |  |  | 2023-11-24 | Pending PFS Swap | 7/2: Pending IPRan PFS Swap |  |  | Y | 2024-03-11 | 2024-01-19 | Y | 2024-02-07 | Wk6 | P3 | 2024-02-15 09:54 |  | CME completed12/Jan |  |  | 0 |  |  |  | #N/A
S406 | #N/A | #N/A | 2023 | 6442A | xD_DWDM-BRKRing_S406_6442A Senai Airport_0004582306610B_00045823162821 | #N/A | 6442A Senai Airport | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6442A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-6442A | 6442A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-06 | [5 empty] | 2024-02-23 | 2024-02-15 | Y | 2024-02-15 | Wk7 | P0 | [5 empty] | 0 |  |  |  | #N/A
S406 | #N/A | #N/A | 2023 | 6576A | xD_DWDM-BRKRing_S406_6576A Jln Seelong_0004582306610B_00045823162821 | #N/A | 6576A Jln Seelong | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6576A_Completed_DC BREAKER: 63A X 2 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6576A | 6576A | Completed | DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  |  | 2024-02-16 |  | plan MOS TBC | 0517: F/u w/ FF (Alarm High temperature) |  |  | 2024-02-24 | 2024-02-15 | Y | 2024-02-20 | Wk8 | P0 | [5 empty] | 0 |  |  |  | #N/A
S602M | 69.74% | 103% | 2023 | 6000A | xD_DWDM-BRKRing_S602M_6000A MSC JB_0004582306610B_00045823162821 | 103% | 6000A MSC JB | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-12-14 |  | 7/2: integrate together with S602M, SAR05, S406 [only S406 done power up] |  |  | 2024-02-14 | 2024-02-15 | 2024-02-15 | Y | 2024-02-19 | Wk8 | #N/A | 2024-02-15 09:54 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
S602M | 69.74% | 103% | 2023 | 6369A | xD_DWDM-BRKRing_S602M_6369A Sri Saujana_0004582306610B_00045823162821 | 103% | 6369A Sri Saujana | Spare | BBand |  |  |  | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | Multiple | 2024 | May | DWDM | ST21P;S504M | DWDM-6369A | 6369A | PRPO | 1. Add Battery Bank = 6 | #N/A | #N/A | #N/A |  |  |  | Spare - Kuan Yen Request onhold | Kuan Yen Request onhold |  | 2024-01-09 |  | 2024-01-09 | 2024-02-15 | Y | 2024-02-05 | Wk6 | #N/A | 2024-02-05 09:37 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
S602M | 69.74% | 103% | 2023 | 6955A | xD_DWDM-BRKRing_S602M_6955A Putri Wangsa2_0004582306610B_00045823162821 | 103% | 6955A Putri Wangsa2 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6955A_Completed_DCPDB = 1 UNIT MGB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-6955A | 6955A | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  |  | 2023-12-06 |  |  |  |  | Y | 2024-01-10 | 2024-01-17 | Y | 2024-01-08 | Wk2 | #N/A |  |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 1690A | xD_DWDM-BRKRing_SAR01_1690A BktPelandok_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1690A BktPelandok | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-22 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A
SAR04 | 78.07% | 74.54% | 2024 Q1 | 1659A | xD_DWDM-BRKRing_SAR04_1659A Bahau Tower_0004582400710C_00045824009526 | 74.54% | 1659A-MAG-001 Bahau Tower | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-18 | Wk16 | 2024-04-18 | [7 empty] | Y | 2024-04-18 | Wk16 | P0 | 0 | [7 empty] | 2024-04-25 | #N/A
SAR04 | 78.07% | 74.54% | 2024 Q1 | 6442A | xD_DWDM-BRKRing_SAR04_6442A Senai Airport_0004582400710C_00045824009526 | 74.54% | 6442A-MAG-001 Senai Airport | Board expansion | BBand |  | N/A | N/A | Single_2023_November_DWDM_(blank)_6442A_Completed_DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-6442A | 6442A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-23 | Wk17 | 2024-04-23 | [7 empty] | Y | 2024-04-23 | Wk17 | P0 | 0 | [7 empty] | 2024-04-25 | #N/A
SAR04 | 78.07% | 74.54% | 2024 Q1 | 6911C | xD_DWDM-BRKRing_SAR04_6911C KTM Labis_0004582400710C_00045824009526 | 74.54% | 6911C-MAG-001 KTM Labis | Board expansion | BBand |  | N/A | N/A | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-04-24 | Wk17 | 2024-04-24 | [7 empty] | Y | 2024-04-24 | Wk17 | P0 | 0 | [7 empty] | 2024-04-25 | #N/A
C0114 | 34.86% | #N/A | 2023 | 2021B | xD-DWDM_BRKRingC0114_2021B SUBANG HITECH_00045823086827 | #N/A | 2021B SUBANG HITECH | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | Y |  | Completed | N/A | 2023-07-09 | Wk27 | #N/A |  |  |  | Y | Completed | 2023-07-09 | Completed |  |  | #N/A
C0114 | 34.86% | #N/A | 2023 | 2631A | xD-DWDM_BRKRingC0114_2631A SAMARINDA_00045823086827 | #N/A | 2631A SAMARINDA | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | Y |  | Completed | N/A | 2023-07-09 | Wk27 | #N/A |  |  |  | Y | Completed | 2023-07-09 | Completed |  |  | #N/A
C0501P | 34.97% | #N/A | 2023 | 1110A | xD-DWDM_BRKRingC0501P_1110A BERJAYA INDUSTRIAL PARK_0045823085921 | #N/A | 1110A BERJAYA INDUSTRIAL PARK | 9800 Board expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | Completed |  |  |  |  | Y |  | Completed | Y | 2023-07-06 | Wk27 | #N/A |  |  |  | Y | Completed | 2023-07-06 | Completed |  |  | #N/A
C0501P | 34.97% | #N/A | 2023 | 2021B | xD-DWDM_BRKRingC0501P_2021B SUBANG HITECH_0045823085921 | #N/A | 2021B SUBANG HITECH | 9800 Board expansion | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | Completed |  |  |  |  | Y |  | Completed | Y | 2023-07-06 | Wk27 | #N/A |  |  |  | Y | Completed | 2023-07-06 | Completed |  |  | #N/A
CT04 | #N/A | #N/A | 2023 | 1049B | xD-DWDM-BRKRing_1049B-002 MSC KEPONG_00045823053925 | #N/A | 1049B-002 MSC KEPONG | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | #N/A | #N/A | #N/A |  |  | 2023-09-26 |  | Plan power up 24/1 |  | 2024-01-09 | Y | 2024-01-22 | 2024-01-09 | Y | 2024-01-29 | Wk5 | P1 | 2024-01-29 09:52 | [8 empty] | #N/A
CT04 | #N/A | #N/A | 2023 | 1412A | xD-DWDM-BRKRing_1412A BKT TADUN_00045823053925 | #N/A | 1412A BKT TADUN | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  |  |  |  | Y | 2024-01-12 | 2024-01-12 | Y | 2024-01-15 | Wk3 | P1 | 2024-01-15 11:00 | Reminder | [7 empty] | #N/A
CT04 | #N/A | #N/A | 2023 | 1413A | xD-DWDM-BRKRing_1413A KTM RAWANG_00045823053925 | #N/A | 1413A KTM RAWANG | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1413A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-1413A | 1413A | Completed | DC BREAKER: 63 A X 4 | #N/A | 1.7 TSSR Approved | #N/A | 2024-06-11 | Wk24 |  | Access issue - CD Desmond | Casualty | 0521: Fiberail need 5 days to approved 0517: Pending fibrerail access approval |  | N/A |  | TBC |  |  |  | P1 |  |  | CME completed12/Jan | [6 empty] | #N/A
C0103 | 7.548% | #N/A | 2023 | 1049B | xD-DWDM-BRKRing_C0103_1049B Kepong_0004582304150Y_00045823087420 | #N/A | 1049B Kepong | 9800 Board Expansion | Advance |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | Y |  | Completed | Y | 2023-10-17 | Wk42 | P2 |  |  |  | Y | Completed | 2023-10-24 | Completed |  |  | #N/A
C0103 | 7.548% | #N/A | 2023 | 1359A | xD-DWDM-BRKRing_C0103_1359A MutiaraSubang_0004582304150Y_00045823087420 | #N/A | 1359A MutiaraSubang | 9800 Rack with subrack | Advance |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | 1. Swap breaker DC BREAKER: 63A X 2 | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | Y |  | Completed | Y | 2023-10-17 | Wk42 | P2 |  |  |  | Y | Completed | 2023-10-24 | Completed |  |  | #N/A
C0103 | 7.548% | #N/A | 2023 | 1409A | xD-DWDM-BRKRing_C0103_1409A Damansara_0004582304150Y_00045823087420 | #N/A | 1409A Damansara | 9800 Board Expansion | Advance |  |  |  | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | Y |  | Completed | Y | 2023-10-17 | Wk42 | P2 |  |  |  | Y | Completed | 2023-10-24 | Completed |  |  | #N/A
C0803 | 39.99% | #N/A | 2023 | 1066A | xD-DWDM-BRKRing_C0803_1066A Sungai Choh_0004582304160F_0004582308742 | #N/A | 1066A Sungai Choh | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-12 | CRQ | Plan 17/1 |  |  | Y | 4//1/2024 | 2024-01-08 | Y | 2024-01-16 | Wk3 | #N/A | 2024-01-16 10:25 |  |  | Y | Completed | 2024-01-30 | Completed |  |  | #N/A
C0803 | 39.99% | #N/A | 2023 | 1070A | xD-DWDM-BRKRing_C0803_1070A Wsma LowKang_0004582304160F_0004582308742 | #N/A | 1070A Wsma LowKang | 1800 Rack and subrack | BBand |  |  |  | Single_2024_January_DWDM_(blank)_1070A_Drop_BATTERY BANK = 1 | Single | 2024 | January | DWDM | (blank) | DWDM-1070A | 1070A | Drop | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-07 | breaker swap | CME WIP |  | 4//1/2024 |  | 4//1/2024 | 2024-01-08 | Y | 2024-01-19 | Wk3 | #N/A | 2024-01-19 11:08 |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A
C0803 | 39.99% | #N/A | 2023 | 1145A | xD-DWDM-BRKRing_C0803_1145A BatangKali_0004582304160F_0004582308742 | #N/A | 1145A BatangKali | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1145A_Completed_DC BREAKER : 63A X 4 MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1145A | 1145A | Completed | DC BREAKER : 63A X 4 | #N/A | #N/A | #N/A |  |  | 2023-10-11 | Construction | Construction |  | 4//1/2024 | Y | 4//1/2024 | 2024-01-08 | Y | 2024-01-04 | Wk1 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A
C0803 | 39.99% | #N/A | 2023 | 1146A | xD-DWDM-BRKRing_C0803_1146A KubuBaru_0004582304160F_0004582308742 | #N/A | 1146A KubuBaru | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1146A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-1146A | 1146A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-10-12 |  |  |  | 2024-01-05 | Y | 2024-01-05 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A
C0803 | 39.99% | #N/A | 2023 | 1701A | xD-DWDM-BRKRing_C0803_1701A Kerling Trnk_0004582304160F_0004582308742 | #N/A | 1701A Kerling Trnk | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1701A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-1701A | 1701A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-10-13 | WIP | Plan 17/1 |  | 2024-01-05 |  | 2024-01-05 | 2024-01-08 | Y | 2024-01-17 | Wk3 | #N/A | 2024-01-17 09:35 |  | CME completed12/Jan | Y | Completed | 2024-01-30 | Completed |  |  | #N/A
C0803 | 39.99% | #N/A | 2023 | 2038A | xD-DWDM-BRKRing_C0803_2038A AntraGapi_0004582304160F_0004582308742 | #N/A | 2038A AntraGapi | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2024-01-09 |  |  |  | 2024-01-09 | Y | 2024-01-09 | 2024-01-09 | Y | 2024-01-10 | Wk2 | #N/A |  |  |  | Y | Completed | 2024-01-30 | Completed |  |  | #N/A
CT0120 | 79.05% | #N/A | 2023 | 1099A | xD-DWDM-BRKRing_CT0120_1099A HongFatt_0004582304160F_0004582308742 | #N/A | 1099A HongFatt | 1800 Rack and subrack | Advance |  |  |  | Single_2023_October_DWDM_(blank)_1099A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =3 | Single | 2023 | October | DWDM | (blank) | DWDM-1099A | 1099A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-06 | CME RFS - 19/3/2024 (Haji) |  |  |  |  | 2024-04-23 | TBC |  |  |  | P2 | 2024-02-19 11:09 |  |  |  |  | 0 |  |  |  | #N/A
CT0120 | 79.05% | #N/A | 2023 | 1409A | xD-DWDM-BRKRing_CT0120_1409A Damansara_0004582304160F_0004582308742 | #N/A | 1409A Damansara | 1800 Rack and subrack | Advance |  |  |  | Single_2023_October_DWDM_(blank)_1409A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1409A | 1409A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-07 | CME RFS - 19/3/2024 (Haji) |  |  |  |  | 2024-04-24 | TBC |  |  |  | P2 | 2024-02-19 11:09 |  |  |  |  | 0 |  |  |  | #N/A
CT01P | 18.34% | #N/A | 2023 | 1049B | xD-DWDM-BRKRing_CT01P_1049B Kpg_000458237400E_00045823174223 | #N/A | 1049B Kpg | 1800 Rack and subrack | Bband |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | #N/A | #N/A | #N/A |  |  | 2023-12-06 |  | Plan power up 24/1 |  | 2024-01-09 | Y | 2024-01-26 | 2024-01-09 | Y | 2024-01-26 | Wk4 | #N/A | 2024-01-29 09:52 |  |  | Y | Completed | 2024-01-31 | Completed |  |  | #N/A
CT01P | 18.34% | #N/A | 2023 | 1298A | xD-DWDM-BRKRing_CT01P_1298A Kpg Knit_000458237400E_00045823174223 | #N/A | 1298A Kpg Knit | 1800 Rack and subrack | Bband |  |  |  | Single_2023_November_DWDM_(blank)_1298A_Completed_DCPDB = 1 CABLE LADDER = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1298A | 1298A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  | 2024-01-05 | Y | 2024-01-05 | 2024-01-08 | Y | 2024-01-05 | Wk1 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2024-01-31 | Completed |  |  | #N/A
CT01P | 18.34% | #N/A | 2023 | 1309A | xD-DWDM-BRKRing_CT01P_1309A Ivory_000458237400E_00045823174223 | #N/A | 1309A Ivory | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2024-01-17 | WIP | WIP |  | 2024-01-17 | Y | 2024-01-17 |  | Y | 2024-01-17 | Wk3 | #N/A | 2024-01-17 09:35 |  |  | Y | Completed | 2024-01-31 | Completed |  |  | #N/A
CT11P | #N/A | #N/A | 2023 | 1050B | xD-DWDM-BRKRing_CT11P_1050B MAH_00045823086823 | #N/A | 1050B MAH | Decomm | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-11-14 | Wk46 | #N/A |  |  |  | N/A | Completed | 2023-12-19 | Completed |  |  | #N/A
CT11P | #N/A | #N/A | 2023 | 1080A | xD-DWDM-BRKRing_CT11P_1080A WIT KLANG_00045823086823 | #N/A | 1080A WIT KLANG | Services only - Redeploy rack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1080A_Completed_DCPDB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1080A | 1080A | Completed | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | Y |  | 2023-10-31 | Y | 2023-11-14 | Wk46 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-12-21 | Completed |  |  | #N/A
CT11P | #N/A | #N/A | 2023 | 1087A | xD-DWDM-BRKRing_CT11P_1087A RANTAU PANJANG_00045823086823 | #N/A | 1087A RANTAU PANJANG | Services only - Redeploy rack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1087A_Completed_DCPDB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1087A | 1087A | Completed | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-11 |  |  |  |  | Y |  | 2023-10-31 | Y | 2023-11-14 | Wk46 | #N/A |  |  | CME completed12/Jan | Y | Completed | 2023-12-21 | Completed |  |  | #N/A
CT11P | #N/A | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_CT11P_8000A MSC KUANTAN_00045823086823 | #N/A | 8000A MSC KUANTAN | Decomm | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-11-14 | Wk46 | #N/A |  |  |  | N/A | Completed | 2023-12-19 | Completed |  |  | #N/A
E107 | 22.89% | #N/A | 2023 | 8211A | xD-DWDM-BRKRing_E107_8211A WCY_0004582304150Y_00045823087420 | #N/A | 8211A WCY | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  |  | Y |  | Completed | Y | 2023-08-24 | Wk34 | #N/A |  |  |  | Y | Completed | 2023-08-24 | Completed |  |  | #N/A
E107 | 22.89% | #N/A | 2023 | 8263A | xD-DWDM-BRKRing_E107_8217A PASIR MAS_0004582304150Y_00045823087420 | #N/A | 8217A PASIR MAS | 9800 Board Expansion | FO&T |  |  |  | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | Single | 2024 | April | DWDM | E104;EAR01 N EAR03 | DWDM-8263A | 8263A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  |  | Y |  | Completed | Y | 2023-08-24 | Wk34 | #N/A |  |  |  | Y | Completed | 2023-08-24 | Completed |  |  | #N/A
E107 | 22.89% | #N/A | 2023 | 8217A | xD-DWDM-BRKRing_E107_8217A PG TEMBAK_0004582304150Y_00045823087420 | #N/A | 8217A PG TEMBAK | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  |  | Y |  | Completed | Y | 2023-08-24 | Wk34 | #N/A |  |  |  | Y | Completed | 2023-08-24 | Completed |  |  | #N/A
E110 | 58.21% | 57.48% | 2023 | 8211A | xD-DWDM-BRKRing_E110_8211A WCY_0004582304160F_0004582308742 | 57.48% | 8211A WCY | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-04 |  |  |  | 2024-01-08 |  | 2024-01-08 | 2024-01-08 | Y | 2024-01-15 | Wk3 | #N/A | 2024-01-15 10:56 | Reminder |  | Y | Completed | 2023-07-06 | Completed |  |  | #N/A
E110 | 58.21% | 57.48% | 2023 | 8224A | xD-DWDM-BRKRing_E110_8224A Pasir Puteh_0004582304160F_0004582308742 | 57.48% | 8224A Pasir Puteh | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | #N/A | #N/A | #N/A |  |  | 2023-10-04 |  |  |  |  | Y | 2024-01-08 | 2024-01-08 | Y | 2024-01-15 | Wk3 | #N/A |  | 9/1: pending break ring | CME completed12/Jan | Y | Completed | 2023-07-06 | Completed |  |  | #N/A
E110 | 58.21% | 57.48% | 2023 | 8268A | xD-DWDM-BRKRing_E110_8268A Bachok_0004582304160F_0004582308742 | 57.48% | 8268A Bachok | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8268A_Completed_MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-8268A | 8268A | Completed | MGB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-05 |  |  |  |  | Y | 2024-01-08 | 2024-01-08 | Y | 2024-01-15 | Wk3 | #N/A |  | 10/1: pending break ring | CME completed12/Jan | Y | Completed | 2023-07-06 | Completed |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_E202_8000A MSC Kuantan_0004582304160F_0004582308742 | #N/A | 8000A MSC Kuantan | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-13 |  | 12/1: Plan next week 16/1: bring ODF panel & travel |  |  | Y | 2024-01-22 | 2024-01-26 | Y | 2024-01-22 | Wk4 | #N/A | 2024-01-22 11:43 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8023B | xD-DWDM-BRKRing_E202_8023B Balok Baru_0004582304160F_0004582308742 | #N/A | 8023B Balok Baru | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8023B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8023B | 8023B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  | 12/1: Plan next week 16/1: bring ODF panel & travel |  |  | Y | 2024-02-01 | 2024-01-26 | Y | 2024-02-01 | Wk5 | #N/A | 2024-01-26 09:59 |  | Huawei provide breaker | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8035A | xD-DWDM-BRKRing_E202_8035A Balok Kg Chengal_0004582304160F_0004582308742 | #N/A | 8035A Balok Kg Chengal | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8035A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 2 BATTERY RACK = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-8035A | 8035A | Completed | RECTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  |  | 2023-10-12 |  |  |  |  | Y | 2024-02-02 | 2024-01-26 | Y | 2024-02-02 | Wk5 | #N/A | 2024-02-02 11:21 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8061A | xD-DWDM-BRKRing_E202_8061A Bkt Pelindung_0004582304160F_0004582308742 | #N/A | 8061A Bkt Pelindung | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8061A_Completed_DC BREAKER = 63A X 4 DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8061A | 8061A | Completed | DC BREAKER = 63A X 4 | #N/A | #N/A | #N/A |  |  | 2023-10-13 |  | 30/1: Pending power tap 1/2: Pending power tap |  |  |  | 2024-02-06 | 2024-01-26 | Y | 2024-02-06 | Wk6 | #N/A | 2024-02-06 09:38 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8408A | xD-DWDM-BRKRing_E202_8408A Cheneh_0004582304160F_0004582308742 | #N/A | 8408A Cheneh | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_8408A_Completed_BATTERY BANK = 2 | Single | 2023 | December | DWDM | (blank) | DWDM-8408A | 8408A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  |  | 2023-10-24 |  | 29/1: Reschedule 30/1: plan 31/1, wrong site key given |  |  | Y | 2024-01-31 | 2024-01-26 | Y | 2024-01-31 | Wk5 | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8434A | xD-DWDM-BRKRing_E202_8434A Felda Neram_0004582304160F_0004582308742 | #N/A | 8434A Felda Neram | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8434A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8434A | 8434A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-12 |  | Pending DCPDB 1/2: Pending power tap |  |  |  | 2024-02-07 | 2024-01-26 | Y | 2024-02-07 | Wk6 | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8936A | xD-DWDM-BRKRing_E202_8936A Sg Karang_0004582304160F_0004582308742 | #N/A | 8936A Sg Karang | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8936A_Completed_DC BREAKER : 100A X 2 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8936A | 8936A | Completed | DC BREAKER : 100A X 2 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  | 30/1: Unable reach site owner |  |  | Y | 2024-02-15 | 2024-01-26 | Y | 2024-02-02 | Wk5 | #N/A | 2024-02-02 11:21 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E202 | 44.31% | #N/A | 2023 | 8953A | xD-DWDM-BRKRing_E202_8953A Balok Perdana_0004582304160F_0004582308742 | #N/A | 8953A Balok Perdana | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8953A_Completed_RECTIFIER + DCPDB = 1 BATTERY BANK = 3 | Single | 2023 | September | DWDM | (blank) | DWDM-8953A | 8953A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y | 2024-02-15 | 2024-01-26 | Y | 2024-02-01 | Wk5 | #N/A | 2024-01-26 09:59 |  |  | Y | Completed | 2024-03-30 | 2024-03-26 |  |  | #N/A
E205 | 75.08% | #N/A | 2023 | 8321A | xD-DWDM-BRKRing_E205_8321A Tabung Hji Kemaman_0004582304160F_0004582308742 | #N/A | 8321A Tabung Hji Kemaman | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_8321A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8321A | 8321A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  |  | Material relocation | EQ mapping removed |  |  |  |  | Relocate to N201 - MSC Prai (4000A) |  | 2024-04-17 | Wk16 | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A
E205 | 75.08% | #N/A | 2023 | 8330A | xD-DWDM-BRKRing_E205_8330A Kemuning_0004582304160F_0004582308742 | #N/A | 8330A Kemuning | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_8330A_Completed_BATTERY BANK = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-8330A | 8330A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A |  |  |  | Material relocation | EQ mapping removed |  |  |  |  | TBC |  | 2024-04-17 | Wk16 | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A
E205 | 75.08% | #N/A | 2023 | 8403A | xD-DWDM-BRKRing_E205_8403A Bkt Mentok_0004582304160F_0004582308742 | #N/A | 8403A Bkt Mentok | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_E205_8403A_PRPO_Extend platform = 1 | Multiple | 2023 | September | DWDM | E205 | DWDM-8403A | 8403A | PRPO | Extend platform = 1 | #N/A | #N/A | #N/A |  |  |  | Extend platform - CME to check | OUTDOOR |  |  |  |  | Relocate to 4770A |  | 2024-04-17 | Wk16 | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A
E205 | 75.08% | #N/A | 2023 | 8473A | xD-DWDM-BRKRing_E205_8473A FeldaSeberangTayur_0004582304160F_0004582308742 | #N/A | 8473A FeldaSeberangTayur | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8473A_Completed_DC BREAKER: 100A X 2 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8473A | 8473A | Completed | DC BREAKER: 100A X 2 | #N/A | #N/A | #N/A |  |  |  | Material relocation | OUTDOOR |  |  |  |  | Relocate to E212 - Tmn Semarak (8923B) |  | 2024-04-17 | Wk16 | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A
E205 | 75.08% | #N/A | 2023 | 8483A | xD-DWDM-BRKRing_E205_8483 Desa Solehah_0004582304160F_0004582308742 | #N/A | 8483 Desa Solehah | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8483A_Completed_MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-8483A | 8483A | Completed | MGB = 1 | #N/A | #N/A | #N/A | 2024-03-21 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-04-17 | Wk16 | #N/A |  |  |  |  | Completed | 0 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8314A | xD-DWDM-BRKRing_E212_8314A Gong Terap_0004582304160F_0004582308742 | 107.7% | 8314A Gong Terap | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-23 |  | 16/1: bring ODF panel & travel |  |  | Y | 2024-01-15 | 2024-02-17 | Y | 2024-01-17 | Wk3 | #N/A | 2024-01-17 09:48 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8344A | xD-DWDM-BRKRing_E212_8344A Felda Belara_0004582304160F_0004582308742 | 107.7% | 8344A Felda Belara | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-11 |  | 16/1: bring ODF panel & travel 18/1: accessories boxes not found at site |  |  | Y | 2024-01-29 | 2024-02-17 | Y | 2024-01-29 | Wk5 | #N/A | 2024-01-29 09:59 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8350B | xD-DWDM-BRKRing_E212_8350B Kustem_0004582304160F_0004582308742 | 107.7% | 8350B Kustem | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8350B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8350B | 8350B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  |  | 2023-12-15 |  | 16/1: bring ODF panel & travel |  |  | Y | 2024-01-30 | 2024-02-15 | Y | 2024-01-30 | Wk5 | #N/A | 2024-01-30 10:58 |  | Huawei provide breaker | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8353A | xD-DWDM-BRKRing_E212_8353A Kg Manir_0004582304160F_0004582308742 | 107.7% | 8353A Kg Manir | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8353A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8353A | 8353A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  |  |  |  | Y | 2024-02-01 | 2024-01-24 | Y | 2024-01-29 | Wk5 | #N/A |  | next week |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8354A | xD-DWDM-BRKRing_E212_8354A Kusza_0004582304160F_0004582308742 | 107.7% | 8354A Kusza | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8354A_Completed_RECTIFIER MODULE = 2 BATTERY BANK = 4 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8354A | 8354A | Completed | RECTIFIER MODULE = 2 | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  |  |  |  | Y | 2024-01-31 | 2024-01-29 | Y | 2024-01-31 | Wk5 | #N/A | 2024-01-26 09:59 | EB CRQ Approval |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8361A | xD-DWDM-BRKRing_E212_8361A Batu Rakit_0004582304160F_0004582308742 | 107.7% | 8361A Batu Rakit | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-11 |  | 16/1: bring ODF panel & travel |  |  | Y | 2024-01-15 | 2024-01-17 | Y | 2024-01-18 | Wk3 | #N/A | 2024-01-17 09:48 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E212 | 79.14% | 107.7% | 2023 | 8429B | xD-DWDM-BRKRing_E212_8429B B Payung2_0004582304160F_0004582308742 | 107.7% | 8429B B Payung2 | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8429B | 8429B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  |  | 2023-11-10 |  | 16/1: bring ODF panel & travel |  |  | Y | 2024-01-15 | 2024-01-16 | Y | 2024-01-17 | Wk3 | #N/A | 2024-01-16 10:25 |  |  | Y | Completed | 2024-02-22 | Completed |  |  | #N/A
E404 | 55.78% | 59.03% | 2023 | 8025A | xD-DWDM-BRKRing_E404_8025A Risda_0004582304160F_0004582308742 | 59.03% | 8025A Risda | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8025A_Completed_MGB = 1 CABLE LADDER= 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8025A | 8025A | Completed | MGB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-12 |  | 7/2: Pending ODF Rack |  |  |  | 2024-02-07 | 2024-02-07 | Y | 2024-02-14 | Wk7 | #N/A |  |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A
E404 | 55.78% | 59.03% | 2023 | 8059A | xD-DWDM-BRKRing_E404_8059A Bkt Sulai_0004582304160F_0004582308742 | 59.03% | 8059A Bkt Sulai | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-24 |  | 16/1: bring ODF panel & travel |  |  | Y | 2024-01-23 | 2024-01-23 | Y | 2024-01-23 | Wk4 | #N/A | 2024-01-23 10:39 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A
E404 | 55.78% | 59.03% | 2023 | 8128A | xD-DWDM-BRKRing_E404_8128A Kg Luit_0004582304160F_0004582308742 | 59.03% | 8128A Kg Luit | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8128A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8128A | 8128A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-11 |  | 7/2: Pending power tap |  |  |  | 2024-03-12 | 2024-02-07 | Y | 2024-02-12 | Wk7 | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A
E404 | 55.78% | 59.03% | 2023 | 8191A | xD-DWDM-BRKRing_E404_8191A Sg Semuji_0004582304160F_0004582307060Z_0004582308742 | 59.03% | 8191A Sg Semuji | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_October_DWDM_(blank)_8191A_Completed_RECTTIFIER MODULE = 3 BATTERY BANK = 2 | Multiple | 2023 | October | DWDM | (blank) | DWDM-8191A | 8191A | Completed | RECTTIFIER MODULE = 3 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  |  |  |  | Y | 2024-02-01 | 2024-01-23 | Y | 2024-02-01 | Wk5 | #N/A |  |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A
E404 | 55.78% | 59.03% | 2023 | 8513A | xD-DWDM-BRKRing_E404_8513A Senggora_0004582304160F_0004582308742 | 59.03% | 8513A Senggora | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_EAR06_8513A_PRPO_1.Add battery bank = 2 | Single | 2024 | May | DWDM | EAR06 | DWDM-8513A | 8513A | PRPO | 1.Add battery bank = 2 | #N/A | #N/A | #N/A |  |  | 2023-10-24 |  | 16/1: bring ODF panel & travel |  |  | Y | 2024-02-07 | 2024-01-23 | Y | 2024-02-01 | Wk5 | #N/A | 2024-01-30 10:58 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A
E404 | 55.78% | 59.03% | 2023 | 8965A | xD-DWDM-BRKRing_E404_8965A Spg Lepar Hilir_0004582304160F_0004582308742 | 59.03% | 8965A Spg Lepar Hilir | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8965A_Completed_DCPDB = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8965A | 8965A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-11 |  | 7/2: Pending power tap |  |  |  | 2024-03-12 | 2024-02-07 | Y | 2024-02-13 | Wk7 | #N/A | 2024-02-07 09:48 |  |  | Y | Completed | 2024-05-07 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 1475A | xD-DWDM-BRKRing_E407_1475A MSC SRI KEMBANGAN_00045823086828 | #N/A | 1475A MSC SRI KEMBANGAN | Services only | FO&T |  |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_E407_8000A MSC KUANTAN_00045823086828 | #N/A | 8000A MSC KUANTAN | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 |  |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8025A | xD-DWDM-BRKRing_E407_8025A RISDA_00045823086828 | #N/A | 8025A RISDA | Services only | FO&T |  |  |  | Multiple_2023_September_DWDM_(blank)_8025A_Completed_MGB = 1 CABLE LADDER= 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-8025A | 8025A | Completed | No CME | #N/A | #N/A | #N/A |  |  | Completed | [6 empty] | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8046A | xD-DWDM-BRKRing_E407_8046A BANDAR INDERA MAHKOTA_00045823086828 | #N/A | 8046A BANDAR INDERA MAHKOTA | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8050A | xD-DWDM-BRKRing_E407_8050A PERMATANG BADAK_00045823086828 | #N/A | 8050A PERMATANG BADAK | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8059A | xD-DWDM-BRKRing_E407_8059A BUKIT SULAI_00045823086828 | #N/A | 8059A BUKIT SULAI | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8314A | xD-DWDM-BRKRing_E407_8314A GONG TERAP_00045823086828 | #N/A | 8314A GONG TERAP | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E407 | 24.73% | #N/A | 2023 | 8344A | xD-DWDM-BRKRing_E407_8344A FELDA BELARA_00045823086828 | #N/A | 8344A FELDA BELARA | Services only | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | Completed |  |  |  |  | N/A |  | Completed | N/A | 2023-08-10 | Wk32 | #N/A |  |  |  | Y | Completed | 2023-08-10 | Completed |  |  | #N/A
E408 | 20.5% | #N/A | 2023 | 8033A | xD-DWDM-BRKRing_E408_8033A Kg Pandan_0004582304150Y_00045823087420 | #N/A | 8033A Kg Pandan | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-07-21 | Wk29 | #N/A |  |  |  | N/A | Completed | 2023-07-21 | Remote ATP submission |  |  | #N/A
E408 | 20.5% | #N/A | 2023 | 8933A | xD-DWDM-BRKRing_E408_8933A Bt6 Jln Gambang_0004582304150Y_00045823087420 | #N/A | 8933A Bt6 Jln Gambang | 9800 Board Expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-12-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-07-21 | Wk29 | #N/A |  |  |  | N/A | Completed | 2023-07-21 | Remote ATP submission |  |  | #N/A
EAR02 | #N/A | #N/A | 2023 | 4000A | xD-DWDM-BRKRing_EAR02_2_4000A Prai_0004582304160E_00045823087420 | #N/A | 4000A Prai | 9800 Rack with subrack | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A |  |  | 2023-11-14 |  |  |  |  | Y | 2024-01-09 | Completed | Y | 2024-01-17 | Wk3 | P0 |  |  | CME completed12/Jan |  |  | 0 | 2024-03-27 |  |  | #N/A
EAR02 | #N/A | #N/A | 2023 | 8000A | xD-DWDM-BRKRing_EAR02_2_8000A Kuantan_0004582304160E_00045823087420 | #N/A | 8000A Kuantan | 9800 Rack with subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-14 |  |  |  |  | Y |  | No PO - Design Change | Y | 2024-01-17 | Wk3 | P0 | [6 empty] | 2024-03-27 |  |  | #N/A
EAR02 | #N/A | #N/A | 2023 | 8429B | xD-DWDM-BRKRing_EAR02_2_8429B BktPayung_0004582304160E_00045823087420 | #N/A | 8429B BktPayung | 9800 Rack with subrack | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8429B | 8429B | Drop | NOT REQUIRED | #N/A | #N/A | #N/A |  |  | 2023-11-15 |  |  |  |  | Y | 2024-01-09 | 2024-01-17 | Y | 2024-01-17 | Wk3 | P0 | [5 empty] | 0 | 2024-03-27 |  |  | #N/A
MR20/C26 | #N/A | #N/A | 2023 | 1081A | xD-DWDM-BRKRing_MR20/C26_1081A BktLipat_0004582304160F_0004582308742 | #N/A | 1081A BktLipat | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_January_DWDM_(blank)_1081A_Completed_BATTERY BANK = 2 | Multiple | 2024 | January | DWDM | (blank) | DWDM-1081A | 1081A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  |  | 2023-11-24 |  | Plan 24/1 |  |  |  | 2024-01-22 | 2024-02-23 | Y | 2024-01-23 | Wk4 | P1 | 2024-01-22 11:43 |  |  |  |  | 0 | 2024-05-15 |  |  | #N/A
MR20/C26 | #N/A | #N/A | 2023 | 1085A | xD-DWDM-BRKRing_MR20/C26_1085A PekanMeru_0004582304160F_0004582308742 | #N/A | 1085A PekanMeru | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-06 |  |  |  |  | Y |  | 2024-02-23 | Y | 2023-12-08 | Wk49 | P1 |  | Integrated but plan next date | completed |  |  | 0 | 2024-05-15 |  |  | #N/A
MR20/C26 | #N/A | #N/A | 2023 | 1093A | xD-DWDM-BRKRing_MR20/C26_1093A KianHoeHuat_0004582304160F_0004582308742 | #N/A | 1093A KianHoeHuat | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1093A_Completed_DCPDB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1093A | 1093A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-24 | [5 empty] | 2024-02-23 | 2024-02-23 | Y | 2024-02-01 | Wk5 | P1 | [5 empty] | 0 | 2024-05-15 |  |  | #N/A
MR20/C26 | #N/A | #N/A | 2023 | 1104A | xD-DWDM-BRKRing_MR20/C26_1104A SurauAlAmin_0004582304160F_0004582308742 | #N/A | 1104A SurauAlAmin | 1800 Rack and subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-10-06 |  |  |  |  | Y | 2024-01-09 | 2024-02-23 | Y | 2024-01-18 | Wk3 | P1 |  | Integrated but plan next date | completed |  |  |  | 2024-05-15 |  |  | #N/A
MR20/C26 | #N/A | #N/A | 2023 | 1627B | xD-DWDM-BRKRing_MR20/C26_1627B IndahHighway_0004582304160F_0004582308742 | #N/A | 1627B IndahHighway | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1627B_Completed_DCPDB = 1 UNIT MGB = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1627B | 1627B | Completed | DCPDB = 1 UNIT | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  |  |  | 2024-01-08 |  | 2024-01-08 | 2024-02-23 | Y | 2024-01-18 | Wk3 | P1 | 2024-01-17 09:35 | [5 empty] | 2024-05-15 |  |  | #N/A
N106(ii) | #N/A | #N/A | 2023 | 4085D | xD-DWDM-BRKRing_N106_4085D Kulim Hitech 2 | #N/A | 4085D Kulim Hitech2 | Services only | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4085D_Completed_RECTTIFIER MODULE = 2 BATTERY BANK = 2 | Single | 2023 | November | DWDM | (blank) | DWDM-4085D | 4085D | Completed | No CME | #N/A | 1.7 TSSR Approved | #N/A |  |  | N/A | Invalid PO | Invalid PO |  |  | N/A |  | #N/A | N/A |  |  | P1 | [5 empty] | #N/A |  |  |  | #N/A
N106(ii) | #N/A | #N/A | 2023 | 4683A | xD-DWDM-BRKRing_N106_4683A Bkt Tok Alang | #N/A | 4683A Bkt Tok Alang | 1800 Rack and subrack | FO&T |  |  |  | Single_2024_May_DWDM_N106+_4683A_PRPO_1. Add Battery Bank = 3 | Single | 2024 | May | DWDM | N106+ | DWDM-4683A | 4683A | PRPO | 1. Add Battery Bank = 3 | #N/A | 1.7 TSSR Approved | #N/A |  |  | N/A | Invalid PO | Invalid PO |  |  | N/A |  | #N/A | N/A |  |  | P1 | [5 empty] | #N/A |  |  |  | #N/A
N106 | 40.89% | #N/A | 2023 | 4946A | xD-DWDM-BRKRing_N106_4946A Bkt Selambau_000458237400E_00045823174223 | #N/A | 4946A Bkt Selambau | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | DROP | #N/A | #N/A | #N/A |  |  | 2023-12-06 |  |  |  |  | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-12-21 |  |  |  | #N/A
N106 | 40.89% | #N/A | 2023 | 4966A | xD-DWDM-BRKRing_N106_4966A Kulim Hitech_000458237400E_00045823174223 | #N/A | 4966A Kulim Hitech | 1800 Rack and subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-12-06 |  |  |  |  | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-12-21 |  |  |  | #N/A
N115 | 23.69% | #N/A | 2023 | 4688A | xD-DWDM-BRKRing_N115_4668A Lunas_0004582306610C_00045823162822 | #N/A | 4668A Lunas | 1800 Rack and subrack | FO&T |  |  |  | Multiple_2023_November_DWDM_(blank)_4688A_Completed_DCPDB = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-4688A | 4688A | Completed | DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-24 | [5 empty] | 2024-02-07 | Completed | Y | 2024-02-07 | Wk6 | #N/A | 2024-02-07 09:48 |  |  |  | Completed | 2023-12-21 |  |  |  | #N/A
N115 | 23.69% | #N/A | 2023 | 4932A | xD-DWDM-BRKRing_N115_4932A Bkt Tok Acheh_0004582306610C_00045823162822 | #N/A | 4932A Bkt Tok Acheh | 1800 Rack and subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4932A_Completed_BATTERY BANK = 2 | Single | 2023 | December | DWDM | (blank) | DWDM-4932A | 4932A | Completed | BATTERY BANK = 2 | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | Y |  | Completed | Y | 2023-11-19 | Wk46 | #N/A |  |  |  | Y | Completed | 2023-12-21 | Completed |  |  | #N/A
S201 | 31.14% | #N/A | 2023 | 1621A | xD-DWDM-BRKRing_S201_1621A Senawang_0004582304070S_00045823086826 | #N/A | 1621A Senawang | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-12-12 |  | Continue 16/1 |  | 2024-01-12 | Y | 2024-01-12 | 2024-01-12 | Y | 2024-01-16 | Wk3 | P0 | 2024-01-16 10:25 | [8 empty] | #N/A
S201 | 31.14% | #N/A | 2023 | 1760A | xD-DWDM-BRKRing_S201_1760A Mambau1_0004582304070S_00045823086826 | #N/A | 1760A Mambau1 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1760A_Completed_CABINET DISMANTLE = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1760A | 1760A | Completed | CABINET DISMANTLE = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-15 |  |  |  |  | Y |  | Completed | Y | 2023-11-20 | Wk47 | P0 | [5 empty] | 0 |  |  |  | #N/A
S201 | 31.14% | #N/A | 2023 | 1760A | xD-DWDM-BRKRing_S201_1760A Mambau2_0004582304070S_00045823086826 | #N/A | 1760A Mambau2 | 1800 Rack and subrack | BBand |  |  |  | Single_2023_October_DWDM_(blank)_1760A_Completed_CABINET DISMANTLE = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1760A | 1760A | Completed | CABINET DISMANTLE = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-15 |  |  |  |  | Y |  | Completed | Y | 2023-11-20 | Wk47 | P0 | [5 empty] | 0 |  |  |  | #N/A
S201 | 31.14% | #N/A | 2023 | 3433C | xD-DWDM-BRKRing_S201_3433C Bkt Pelandok_0004582304070S_00045823086826 | #N/A | 3433C Bkt Pelandok | 1800 Rack and subrack | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-22 |  |  |  |  | Y |  | Completed | Y | 2023-11-22 | Wk47 | P0 | [9 empty] | #N/A
S307 | 64.45% | #N/A | 2023 | 6405A | xD-DWDM-BRKRing_S307_6405A Sri Bunian_0004582304160E_00045823087420 | #N/A | 6405A Sri Bunian | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-17 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-17 | Wk42 | #N/A |  |  |  |  | Completed | 2023-10-17 |  |  |  | #N/A
S307 | 64.45% | #N/A | 2023 | 6502A | xD-DWDM-BRKRing_S307_6502A Nusa Perintis_0004582304160E_00045823087420 | #N/A | 6502A Nusa Perintis | 9800 SFP only | BBand |  |  |  | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6502A | 6502A | Completed | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-12 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-17 | Wk42 | #N/A |  |  |  |  | Completed | 2023-10-17 |  |  |  | #N/A
S309 | 38.82% | 53.25% | 2023 | 1553A | xD-DWDM-BRKRing_S309_1553A Umbai_0004582304160F_0004582308742 | 53.25% | 1553A Umbai | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | #N/A | #N/A | #N/A |  |  |  | Space | Space |  |  |  |  | Re-survey |  |  |  | P3 | [5 empty] | 0 |  |  |  | #N/A
S309 | 38.82% | 53.25% | 2023 | 1556A | xD-DWDM-BRKRing_S309_1556A Merlimau_0004582304160F_0004582308742 | 53.25% | 1556A Merlimau | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_S309_1556A_PRPO_BATTERY BANK = 3 Remove battery = 1 | Multiple | 2024 | May | DWDM | S309 | DWDM-1556A | 1556A | PRPO | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-10-11 | [6 empty] | Completed | Y | 2023-11-07 | Wk45 | P3 |  |  |  |  | Completed | 2023-11-07 |  |  |  | #N/A
S309 | 38.82% | 53.25% | 2023 | 1599A | xD-DWDM-BRKRing_S309_1599A Gambir Town_0004582304160F_0004582308742 | 53.25% | 1599A Gambir Town | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_September_DWDM_(blank)_1599A_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-1599A | 1599A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-10-11 |  |  |  |  | Y |  | Completed | Y | 2023-11-07 | Wk45 | P3 |  |  |  | N/A | Completed | 2023-11-07 |  |  |  | #N/A
S309 | 38.82% | 53.25% | 2023 | 2402B | xD-DWDM-BRKRing_S309_2402B Pagoh highway_0004582304160F_0004582308742 | 53.25% | 2402B Pagoh highway | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | #N/A | #N/A | #N/A |  |  | 2023-10-13 |  |  |  |  | Y |  | Completed | Y | 2023-11-07 | Wk45 | P3 |  |  |  | N/A | Completed | 2023-11-07 |  |  |  | #N/A
S313P_2 | 61.69% | 127.3% | 2023 | 1512A | xD-DWDM-BRKRing_S313P_2_1512A BKTRAMBAI_00045823087420 | 127.3% | 1512A BKTRAMBAI | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | #N/A |  |  |  |  | Completed | 2023-11-07 | Completed |  |  | #N/A
S313P_2 | 61.69% | 127.3% | 2023 | 1553A | xD-DWDM-BRKRing_S313P_2_1553A UMBAI_00045823087420 | 127.3% | 1553A UMBAI | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | #N/A |  |  |  |  | Completed | 2023-11-07 | Completed |  |  | #N/A
S313P_2 | 61.69% | 127.3% | 2023 | 1554A | xD-DWDM-BRKRing_S313P_2_1554A RUMBIA_00045823087420 | 127.3% | 1554A RUMBIA | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-06 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | #N/A |  |  |  |  | Completed | 2023-11-07 | Completed |  |  | #N/A
S313P_2 | 61.69% | 127.3% | 2023 | 1621A | xD-DWDM-BRKRing_S313P_2_1621A MSC Senawang_00045823087420 | 127.3% | 1621A MSC Senawang | Services only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1533A | xD-DWDM-BRKRing_S313P_2_2_DUYONG_0004582304160F_00045823087420 | #N/A | DUYONG | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_October_DWDM_(blank)_1533A_Completed_BATTERY RACK = 1 | Multiple | 2023 | October | DWDM | (blank) | DWDM-1533A | 1533A | Completed | BATTERY RACK = 1 | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  | 30/1: Plan 2/2 |  |  |  | 2024-02-07 | 2024-01-19 | Y | 2024-02-07 | Wk6 | P3 | 2024-02-07 09:50 |  |  |  |  | 0 |  |  |  | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1554A | xD-DWDM-BRKRing_S313P_2_2_RUMBIA_0004582304160F_00045823087420 | #N/A | RUMBIA | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | #N/A | #N/A | #N/A |  |  | 2023-10-10 |  |  |  |  | Y | 8/1/2024-9/1/2024 | 2024-01-19 | Y | 2024-01-15 | Wk3 | P3 | 2024-01-15 11:00 | Reminder |  |  |  | 0 |  |  |  | #N/A
S313P_2_2 | #N/A | #N/A | 2023 | 1553A | xD-DWDM-BRKRing_S313P_2_2_UMBAI_0004582304160F_00045823087420 | #N/A | UMBAI | 1800 Rack and subrack | BBand |  |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | #N/A | #N/A | #N/A |  |  |  | Space | Space |  |  |  |  | Re-survey |  |  |  | P3 | [5 empty] | 0 |  |  |  | #N/A
S313P_2 | 61.69% | 127.3% | 2023 | 2021B | xD-DWDM-BRKRing_S313P_2_2021B SBHT_00045823087420 | 127.3% | 2021B SBHT | Services only | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-11-07 |  |  |  |  | N/A |  | Completed | N/A | 2023-11-07 | Wk45 | #N/A |  |  |  | Y | Completed | 2023-11-07 | Completed |  |  | #N/A
S501 | 21.55% | 52.03% | 2023 | 1591A | xD-DWDM-BRKRing_S501_1_1591A Parit Bakar_0004582304160F_0004582308742 | 52.03% | 1591A Parit Bakar | 1800 Rack and subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_1591A_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Single | 2023 | September | DWDM | (blank) | DWDM-1591A | 1591A | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-11-22 | Pending CME - Umbai |  |  |  | Y | 2024-01-24 | 2024-01-23 | Y | 2023-11-22 | Wk47 | P0 |  | Integrated but plan next date | completed |  |  | 0 | Replan migration - Umbai CME |  |  | #N/A
S501 | 21.55% | 52.03% | 2023 | 2227B | xD-DWDM-BRKRing_S501_1_1591A Sri Jeram_0004582304160F_0004582308742 | 52.03% | 1591A Sri Jeram | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_September_DWDM_(blank)_2227B_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-2227B | 2227B | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-10-12 | Pending CME - Umbai | 29/1: Do after network freeze (1st week of Feb) 30/1: Plan 1/2 1/2: Plan 2/2 |  |  |  | 2024-02-01 | 2024-02-15 | Y | 2024-02-02 | Wk5 | P0 | 2024-02-02 11:13 |  | WIP |  |  | 0 | Replan migration - Umbai CME |  |  | #N/A
S501 | 21.55% | 52.03% | 2023 | 2388B | xD-DWDM-BRKRing_S501_1_2388B Desa Muar_0004582304160F_0004582308742 | 52.03% | 2388B Desa Muar | 1800 Rack and subrack | BBand |  |  |  | Multiple_2023_September_DWDM_(blank)_2388B_Completed_BATTERY BANK = 3 BATTERY RACK = 1 | Multiple | 2023 | September | DWDM | (blank) | DWDM-2388B | 2388B | Completed | BATTERY BANK = 3 | #N/A | #N/A | #N/A |  |  | 2023-10-12 | Pending CME - Umbai |  |  |  |  | 2024-02-14 | 2024-02-15 | Y | 2024-02-02 | Wk5 | P0 | 2024-02-02 11:13 |  | Swap breaker issue |  |  | 0 | Replan migration - Umbai CME |  |  | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 1552A | xD-DWDM-BRKRing_SAR01_1552A TanjungBidara_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1552A TanjungBidara | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-21 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 1554A | xD-DWDM-BRKRing_SAR01_1554A Rumbia_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1554A Rumbia | 9800 SFP only | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 1621A | xD-DWDM-BRKRing_SAR01_1621A Senawang_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1621A Senawang | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 1640A | xD-DWDM-BRKRing_SAR01_1640A Politenik PD_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 1640A Politenik PD | 9800 SFP only | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-12 | Wk11 | 2024-03-22 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A
SAR01 | 43.19% | 78.56% | 2023 | 2021B | xD-DWDM-BRKRing_SAR01_2021B SBHT_0004582304070Q_0004582304070T_00045823086825 | 78.56% | 2021B SBHT | 9800 SFP only | BBand |  |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | #N/A | #N/A | #N/A |  |  | 2023-10-19 |  |  |  |  | N/A |  | Completed | N/A | 2023-10-26 | Wk43 | P0 |  |  |  |  | Completed | 2023-10-26 | Completed |  |  | #N/A
SAR03ii | #N/A | #N/A | 2023 | 2402B | xD-DWDM-BRKRing_SAR03ii_2402B PagohHighway_0004582304160E_00045823087420 | #N/A | 2402B PagohHighway | 9800 Rack with subrack | BBand |  |  |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | #N/A | #N/A | #N/A |  |  | 2023-11-23 |  |  |  |  | Y |  | Completed | Y | 2023-12-08 | Wk49 | #N/A |  | Integrated but plan next date | completed | Y | completed | 2024-01-23 | Completed |  |  | #N/A
SAR03iii | #N/A | #N/A | 2023 | 1554A | xD-DWDM-BRKRing_SAR03iii_1554A Rumbia_0004582304160E_00045823087420 | #N/A | 1554A Rumbia | 9800 Rack with subrack | BBand |  |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | #N/A | #N/A | #N/A |  |  | 2023-11-15 |  |  |  |  | Y |  | Completed | Y | 2023-12-08 | Wk49 | #N/A |  |  | completed | Y | completed | 2024-01-23 | Completed |  |  | #N/A
SAR05 | #N/A | 99.18% | 2023 | 1621A | xD-DWDM-BRKRing_SAR05_1621A Senawang_0004582304160E_00045823087420 | 99.18% | 1621A Senawang | 9800 Rack with subrack | Bband |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  |  | 2023-11-15 |  |  |  |  | Y |  | Completed | Y | 2024-01-22 | Wk4 | #N/A |  |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
SAR05 | #N/A | 99.18% | 2023 | 6000A | xD-DWDM-BRKRing_SAR05_6000A JB_0004582304160E_00045823087420 | 99.18% | 6000A JB | 9800 Rack with subrack | BBand |  |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A |  |  | 2023-11-16 |  |  |  |  | Y |  | 2024-01-17 | Y | 2024-01-23 | Wk4 | #N/A |  |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
SAR05 | #N/A | 99.18% | 2023 | 6083A | xD-DWDM-BRKRing_SAR05_6083A Soga_0004582304160E_00045823087420 | 99.18% | 6083A Soga | 9800 Rack with subrack | BBand |  |  |  | Single_2023_November_DWDM_(blank)_6083A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =3 | Single | 2023 | November | DWDM | (blank) | DWDM-6083A | 6083A | Completed | RECTIFIER + DCPDB = 1 | #N/A | #N/A | #N/A |  |  | 2023-11-17 | [5 empty] | 2024-02-15 | 2024-02-15 | Y | 2024-02-01 | Wk5 | #N/A |  |  |  | Y | Completed | 2024-03-05 | Completed |  |  | #N/A
| #N/A | 99.18% |  | 1195A | #N/A | 99.18% |  | site drop | N/A |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A |  | N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A |  |  |  | #N/A
CAR01 | #N/A | #N/A | 2024 Q1 | 1085 | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 |  | 1085A Pekan Meru | Board expansion | BBand |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-03-20 | Wk12 | 2024-03-22 | [7 empty] | Y | 2024-03-22 | Wk12 | P0 | [9 empty] | #N/A
PFSRING101/C0607P | #N/A |  | 2023 | 1063B | xD_DWDM_BRKRing_PFSRING101/C0607_1063B_Berjya Times Square Rooftop_0004582306610C_00045823162822 |  | 1063B Berjaya Times Square Rooftop | 1800 Rack and subrack | BBand |  |  |  | Single_2024_May_DWDM_PFSRING101/C0607P_1063B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | PFSRING101/C0607P | DWDM-1063B | 1063B | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | 1.7 TSSR Approved | #N/A | 2024-05-24 | Wk21 |  |  |  | 0521: Pending DN 0517: Need to freeze // Return material due to lift breakdown | [7 empty] | P1 | [9 empty] | #N/A
C0103 | 7.548% | #N/A | 2024 Q2 | 1049B | xD_DWDM_BRKRing_C0103_1049B-MCR 001 KPG_0004582400930A_00045824009023 | #N/A | 1049B-MCR 001 KPG | Board expansion | Advance |  |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-24 | Wk21 |  |  |  | DN combined w/ xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922 | [7 empty] | P2 | [9 empty] | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 2021B | xD_DWDM_BRKRing_CAR05_2021B SBHT_0004582401290A_00045824026525 | #N/A | 2021B Subang Hitech | Board expansion | BBand | N/A | N/A |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1110A | xD_DWDM_BRKRing_CAR05_1110A Berjaya Indst Park_0004582401290A_00045824026525 | #N/A | 1110A Berjaya industrial Park | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1128A | xD_DWDM_BRKRing_CAR05_1128A Kg Ola Lempik_0004582401290A_00045824026525 | #N/A | 1128A Kg Ola Lempik | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-10 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1037A | xD_DWDM_BRKRing_CAR05_1037A_JBA Bangi_0004582401290A_00045824026525 | #N/A | 1037A JBA Bangi | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1039A | xD_DWDM_BRKRing_CAR05_1039A JBA Cheras Jaya_0004582401290A_00045824026525 | #N/A | 1039A JBA Cheras Jaya | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1475A | xD_DWDM_BRKRing_CAR05_1475A MSC MSK_0004582401290A_00045824026525 | #N/A | 1475A MSC MSK | Board expansion | BBand | N/A | N/A |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-13 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1120A | xD_DWDM_BRKRing_CAR05_1120A Kota Kemuning_0004582401290A_00045824026525 | #N/A | 1120A Kota Kemuning | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 1122A | xD_DWDM_BRKRing_CAR05_1122A Jenjarum_0004582401290A_00045824026525 | #N/A | 1122A Jenjarum | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
CAR05 | 80.84% | #N/A | 2024 Q2 | 2048B | xD_DWDM_BRKRing_CAR05_2048B Sg Merab_0004582401290A_00045824026525 | #N/A | 2048B Sg Merab | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-08 | Wk19 | 2024-05-06 | [10 empty] | P1_Z_Oct | [8 empty] | 2024-05-23 | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 2021B | xD_DWDM_BRKRing_C0147P_2021B_SBHT_0004582401280Z_45824026526 | 22% | 2021B SBHT | 1800vPro 1 Subrack | BBand | 2024-04-04 |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | #N/A | #N/A | #N/A | 2024-05-28 | Wk22 | [11 empty] | #N/A | [9 empty] | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1918A | xD_DWDM_BRKRing_C0147P_1918A Damansara Intan_0004582401280Z_45824026526 | 22% | 1918A Damansara Intan | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P;CAR02-ii+ | DWDM-1918A | 1918A | PRPO | 1. Add Battery Bank = 2 | #N/A | #N/A | #N/A | 2024-05-29 | Wk22 |  |  |  | MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1336A | xD_DWDM_BRKRing_C0147P_1336A Balai Islam TTDI_0004582401280Z_45824026526 | 22% | 1336A Balai Islam TTDI | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-11 | Wk28 |  |  |  | 0523: Pending survey | [7 empty] | #N/A | [9 empty] | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 2831A | xD_DWDM_BRKRing_C0147P_2831A One Utama Ph2_0004582401280Z_45824026526 | 22% | 2831A One Utama Phase 2 | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-07-11 | Wk28 |  |  |  | 0523: Pending suervey | [7 empty] | #N/A | [9 empty] | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1197A | xD_DWDM_BRKRing_C0147P_1197A JBA Effingham_0004582401280Z_45824026526 | 22% | 1197A JBA Effingham | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | Single_2024_May_DWDM_CT0241P;C0417P_1197A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P | DWDM-1197A | 1197A | PRPO | 1. Add Battery Bank = 2 | #N/A | #N/A | #N/A | 2024-05-30 | Wk22 |  |  |  | MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
C0147P | 30.12% | 22% | 2024 Q2 | 1211A | xD_DWDM_BRKRing_C0147P_1211A KDU_0004582401280Z_45824026526 | 22% | 1211A KDU | 1800vPro 1rack 1Subrack | BBand | 2024-04-15 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-05-29 | Wk22 |  |  |  | MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
NAR01_i | #N/A | 22% | 2024 Q2 | 4966A | xD_DWDM_BRKRing_NAR01_i_4966A_Kulim Hitech_0004582401260T_45824026527 | 22% | 4966A-MAG001 Kulim Hitech | 9800M12 1 subrack | FO&T | 2024-04-04 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Submission using N106 | 1.33 FF reject/Pending resubmission from partner | 1.33 FF reject/Pending resubmission from partner | 2024-05-30 | Wk22 |  |  |  | Pending TSSR. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
NAR01_i | #N/A | 22% | 2024 Q2 | 4946A | xD_DWDM_BRKRing_NAR01_i_4946A_Bukit Selambau_0004582401260T_45824026527 | 22% | 4946A-MAG-001 Bukit Selambau | 9800M12 1 subrack | FO&T | 2024-04-04 |  |  | Single_2023_October_DWDM_(blank)_4946A_Drop_DROP | Single | 2023 | October | DWDM | (blank) | DWDM-4946A | 4946A | Drop | DROP | Subrack | 1.4 Pending FF and CME Planner approval | 1.4 Pending FF and CME Planner approval | 2024-05-19 | Wk20 |  |  |  | 0523: EB site. Need to install after calendar freeze 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
NAR01_i | #N/A | 22% | 2024 Q2 | 4992A | xD_DWDM_BRKRing_NAR01_i_4992A_Pendang_0004582401260T_45824026527 | 22% | 4992A-MAG-001 Pendang | 9800M12 1 subrack | FO&T | 2024-04-04 |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_i | #N/A | #N/A | 2024 Q2 | 4000A | xD_DWDM_BRKRing_NAR01_i_4000A_Prai_0004582401260T_45824026527 | #N/A | 4000A-MSCPrai | Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A |  |  | #N/A | [9 empty] | #N/A
NAR01_i | #N/A | #N/A | 2024 Q2 | 4521A | xD_DWDM_BRKRing_NAR01_i_4521A_Msc Ipoh_0004582401260T_45824026527 | #N/A | 4521A-MSC Menglembu | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A |  |  | #N/A | [9 empty] | #N/A
E209 | 67.37% | 70.37% | 2024 Q2 | 8368A | xD_DWDM_BRKRing_E209_8368A Serating_0004582401310P_00045824026721 | 70.37% | 8368A-MAC-001 Serating | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-15 | Wk20 | 2024-05-16 |  |  | 0520: TI done | [7 empty] | #N/A | [9 empty] | #N/A
E209 | 67.37% | 70.37% | 2024 Q2 | 8429B | xD_DWDM_BRKRing_E209_8429B BPayung2_0004582401310P_00045824026721 | 70.37% | 8429B-MAG(M14)-001 Bpayung 2 | Board expansion | FO&T |  |  |  | Single_2023_September_DWDM_(blank)_8429B_Drop_NOT REQUIRED | Single | 2023 | September | DWDM | (blank) | DWDM-8429B | 8429B | Drop | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-15 | Wk20 | 2024-05-15 |  |  | 0520: TI done | [7 empty] | #N/A | [9 empty] | #N/A
E301 | 75.11% | 85.02% | 2024 Q2 | 8712A | xD_DWDM_BRKRing_E301_8712A Kg Jawa Pekan_0004582401310P_00045824026721 | 85.02% | 8712A-MAC-001 Kg. Jawa Pekan | 9800M24 1 rack 2subrack | FO&T | 2024-04-05 |  |  | Multiple_2024_January_DWDM_(blank)_8712A_Completed_BATTERY BANK = 2 | Multiple | 2024 | January | DWDM | (blank) | DWDM-8712A | 8712A | Completed | BATTERY BANK = 2 | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-05-29 | Wk22 |  |  |  | Pending TSSR. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
E301 | 75.11% | 85.02% | 2024 Q2 | 8088A | xD_DWDM_BRKRing_E301_8088A Sg Beto_0004582401310P_00045824026721 | 85.02% | 8088A-MAG-001 Sg. Beto | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-29 | Wk22 |  |  |  | Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
E301 | 75.11% | 85.02% | 2024 Q2 | 8000A | xD_DWDM_BRKRing_E301_8000A KTNE1_0004582401310P_00045824026721 | 85.02% | 8000A-MCR-002 KTN E1 | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 |  |  |  | Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 4000A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_4000A Msc Prai_0004582401310P_00045824026721 | 64% | 4000A MSC Prai | 9800M12 1subrack | FO&T | 2024-04-05 |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | #N/A | 2024 Q2 | 8000A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8000A MSC KTN_0004582401310P_00045824026721 | #N/A | 8000A MSC Kuantan | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A |  |  | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8282B | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8282B Pergau_0004582401310P_00045824026721 | 64% | 8282B-MAG(M14)-001 Pergau | 9800M12 1subrack | FO&T | 2024-04-05 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8285A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8285A Bukit Bunga_0004582401310P_00045824026721 | 64% | 8285A-MAG(M14)-001 Bukit Bunga | 9800M12 1rack 1subrack | FO&T | 2024-04-05 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8288B | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8288B Panau_0004582401310P_00045824026721 | 64% | 8288B-MAG(M14)-001 Panau | 9800M12 1rack 1subrack | FO&T | 2024-04-06 |  |  | Single_2024_May_DWDM_E104;EAR01 N EAR03_8288B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 7 | Single | 2024 | May | DWDM | E104;EAR01 N EAR03 | DWDM-8288B | 8288B | PRPO | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | #N/A | 2024 Q2 | 8263A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8263A Pasir Mas Town_0004582401310P_00045824026721 | #N/A | 8263A-MAG(M14)-001 Pasir Mas Town | Board expansion | FO&T |  |  |  | Single_2024_April_DWDM_E104;EAR01 N EAR03_8263A_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) 2. Battery Bank = 5 | Single | 2024 | April | DWDM | E104;EAR01 N EAR03 | DWDM-8263A | 8263A | PRPO | No CME | #N/A | #N/A | #N/A | 2024-05-28 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | #N/A | 2024 Q2 | 8211A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8211A WCY_0004582401310P_00045824026721 | #N/A | 8211A-MAG(M8)-001 WCY | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | #N/A | #N/A | #N/A | 2024-05-28 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8224A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8224A Pasir Puteh_0004582401310P_00045824026721 | 64% | 8224A-MAG(M14)-001 Pasir Puteh | 9800M12 1rack 1subrack | FO&T | 2024-04-06 |  |  | Multiple_2024_May_DWDM_E109;EAR01;EAR01 N EAR03_8224A_PRPO_1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) 2.Add modules = 3 3.Add battery bank = 4 | Multiple | 2024 | May | DWDM | E109;EAR01;EAR01 N EAR03 | DWDM-8224A | 8224A | PRPO | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
EAR01_1 & EAR01_3 | #N/A | 64% | 2024 Q2 | 8367A | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8367A B.Kechil_0004582401310P_00045824026721 | 64% | 8367A-MAG(M14)-001 B. Kechil | 9800M12 1rack 1subrack | FO&T | 2024-04-06 |  |  | Single_2024_May_DWDM_E111;EAR01 N EAR03_8367A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | Single | 2024 | May | DWDM | E111;EAR01 N EAR03 | DWDM-8367A | 8367A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 1621A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1621A SNW_0004582401310P_00045824026721 | 61% | MIP2013 1621A-MCR-001 SNW | 9800M12 1rack 1subrack | BBand | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | 2024-04-24 | Wk17 |  | Material not arrived yet | [9 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6000A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6000A MSC JBR_0004582401310P_00045824026721 | 61% | MIP2013 6000A-MCR-001 JBR | 9800M12 1subrack | BBand | 2024-04-22 |  |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | DC BREAKER: 63 A X 4 | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 1554A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1554A Rumbia_0004582401310P_00045824026721 | 61% | 1554A-MAG(M14)-001 Rumbia | 9800M12 1subrack | BBand | 2024-04-04 |  |  | Multiple_2024_May_DWDM_S301_1554A_PRPO_1.Add battery bank = 3 | Multiple | 2024 | May | DWDM | S301 | DWDM-1554A | 1554A | PRPO | 1.Add battery bank = 3 | #N/A | #N/A | #N/A | 2024-05-29 | Wk22 |  |  |  | 0523: Freezed. Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 1553A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1553A Umbai_0004582401310P_00045824026721 | 61% | 1553A-MAG(M14)-001 Umbai | 9800M12 1subrack | BBand | 2024-04-01 |  |  | Multiple_2024_May_DWDM_xx_1553A_PRPO_1.New plinth 2.New Rectifier (outdoor) 3.Battery bank = 3 4.lock bar cabinet = 5 5.Cable ladder 6.Intertie ODF | Multiple | 2024 | May | DWDM | xx | DWDM-1553A | 1553A | PRPO | 1.New plinth | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6104A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6104A Bkt Kelicap_0004582401310P_00045824026721 | 61% | 6104A-MAG(M8)-001 Bkt Kelicap | 9800M12 1rack 1subrack | BBand | 2024-04-22 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6405A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6405A Sri Bunian_0004582401310P_00045824026721 | 61% | MIP2016 6405A-MAG-001 Sri Bunian | 9800M12 1subrack | BBand | 2024-04-22 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
SAR03_i&SAR03iii | #N/A | 61% | 2024 Q2 | 6502A | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6502A Nusa Perintis_0004582401310P_00045824026721 | 61% | 6502A-MAG-001 Nusa Perintis | 9800M12 1subrack | BBand | 2024-04-22 |  |  | Multiple_2023_November_DWDM_(blank)_6502A_Completed_BATTERY BANK = 1 | Multiple | 2023 | November | DWDM | (blank) | DWDM-6502A | 6502A | Completed | BATTERY BANK = 1 | #N/A | #N/A | #N/A | [13 empty] | #N/A | [9 empty] | #N/A
SAR06 | 58.87% | 71.67% | 2024 Q2 | 6000A | xD_DWDM_BRKRing_SAR06_6000A MSC JB_0004582401310P_00045824026721 | 71.67% | 6000A-MCR-001 JBR | Board expansion | BBand | N/A | N/A |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0523: Freezed. Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
SAR06 | 58.87% | 71.67% | 2024 Q2 | 8000A | xD_DWDM_BRKRing_SAR06_8000A KTN_0004582401310P_00045824026721 | 71.67% | 8000A-MCR-001 KTN | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 |  | Material shortage |  | 0516: Waiting outbound // 0515: Freeze on 23/5. Need to recheck material availability | [7 empty] | #N/A | [9 empty] | #N/A
SAR06 | 58.87% | 71.67% | 2024 Q2 | 6707A | xD_DWDM_BRKRing_SAR06_6707A Jambi_0004582401310P_00045824026721 | 71.67% | 6707A_MAG_001 Jambi | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-05 | Wk23 |  |  |  | 0524: Pending DN Freezed to lock material | [7 empty] | #N/A | [9 empty] | #N/A
SAR04 | 78.07% | 74.54% | 2024 Q2 | 1621A | xD_DWDM_BRKRing_SAR04_1621A MSC SNW_0004582401310P_00045824026721 | 74.54% | MIP2013 1621A-MCR-001 SNW | 9800M24 1subrack | BBand | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | subrack only | 1.4 Pending FF and CME Planner approval | 1.6 Pending CME approval | 2024-05-28 | Wk22 |  |  |  | Freezed to lock material | [7 empty] | P0 | [9 empty] | #N/A
SAR04 | 78.07% | 74.54% | 2024 Q2 | 6000A | xD_DWDM_BRKRing_SAR04_6000A MSC JB_0004582401310P_00045824026721 | 74.54% | MIP2013 6000A-MCR-001 JBR | Board expansion | BBand | N/A | N/A |  | Single_2023_September_DWDM_(blank)_6000A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | September | DWDM | (blank) | DWDM-6000A | 6000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-06 | Wk23 |  |  |  | 0523: Freezed. Pending DN | [7 empty] | P0 | [9 empty] | #N/A
CAR11 | 52.48% | #N/A | 2024 Q2 | 8000A | xD_DWDM_BRKRing_CAR11_8000A MSC KTN_0004582401310P_00045824026721 | #N/A | MIP2013 8000A-MCR-002 KTN | Board expansion | BBand | N/A | N/A |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-06-04 | Wk23 |  |  |  | 0524: Pending DN Freezed to lock material | [7 empty] | P0 | [9 empty] | #N/A
S305 | 57.52% | 120.3% | 2024 Q2 | 6701A | xD_DWDM_BRKRing_S305_6701A Parit Subang_0004582401310P_00045824026721 | 120.3% | 6701A-MAC-001 Parit Sulong | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S305 | 57.52% | 120.3% | 2024 Q2 | 6093A | xD_DWDM_BRKRing_S305_6093A Sri Medan_0004582401310P_00045824026721 | 120.3% | 6093A-MAC-001 Sri Medan | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Single_2024_May_DWDM_S305_6093A_PRPO_1. Add Battery Bank = 1 2. DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 3. New MGB = 1 | Single | 2024 | May | DWDM | S305 | DWDM-6093A | 6093A | PRPO | 1. Add Battery Bank = 1 | indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | [13 empty] | #N/A | [9 empty] | #N/A
S305 | 57.52% | 120.3% | 2024 Q2 | 6088A | xD_DWDM_BRKRing_S305_6088A ABI_0004582401310P_00045824026721 | 120.3% | 6088A-MAC-001 ABI | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S305 | 57.52% | 120.3% | 2024 Q2 | 2402B | xD_DWDM_BRKRing_S305_2402B Pagoh Highway_0004582401310P_00045824026721 | 120.3% | 2402B-MAG(M14)-001 Pagoh Highway | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Multiple_2024_April_DWDM_S309_2402B_PRPO_1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) 2. Battery Bank = 3 | Multiple | 2024 | April | DWDM | S309 | DWDM-2402B | 2402B | PRPO | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S305 | 57.52% | 120.3% | 2024 Q2 | 6104A | xD_DWDM_BRKRing_S305_6104A Bkt Kelicap_0004582401310P_00045824026721 | 120.3% | 6104A-MAG(M8)-001 Bkt Kelicap | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6151A | xD_DWDM_BRKRing_S504M_6151A Mersing_0004582401310P_00045824026721 | 114.5% | 6151A-MAC-001 Mersing | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6166A | xD_DWDM_BRKRing_S504M_6166A Felda Nitar2_0004582401310P_00045824026721 | 114.5% | 6166A-MAC-001 Felda Nitar2 | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6160A | xD_DWDM_BRKRing_S504M_6160A Bkt Tinggi Maxis_0004582401310P_00045824026721 | 114.5% | 6160A-MAC-001 Bkt Tinggi(Maxis) | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6138A | xD_DWDM_BRKRing_S504M_6138A Kahang Maxis_0004582401310P_00045824026721 | 114.5% | 6138A-MAC-001 Kahang Maxis | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Multiple_2024_January_DWDM_(blank)_6138A_Completed_DISMANTLE CABINET = 1 | Multiple | 2024 | January | DWDM | (blank) | DWDM-6138A | 6138A | Completed | DISMANTLE CABINET = 1 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6134A | xD_DWDM_BRKRing_S504M_6134A Kluang Indst(Profina)_0004582401310P_00045824026721 | 114.5% | 6134A-MAC-001 Kluang Industry (Profina) | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6616A | xD_DWDM_BRKRing_S504M_6616A Sri Permai_0004582401310P_00045824026721 | 114.5% | 6616A-MAC-001 Sri Permai | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6369A | xD_DWDM_BRKRing_S504M_6369A Sri Saujana_0004582401310P_00045824026721 | 114.5% | 6369A-MAG-002 Sri Saujana | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | Multiple_2024_May_DWDM_ST21P;S504M_6369A_PRPO_1. Add Battery Bank = 6 2. Replace faulty CSU controller = 1 (Under FF) 3. Rearrange battery | Multiple | 2024 | May | DWDM | ST21P;S504M | DWDM-6369A | 6369A | PRPO | 1. Add Battery Bank = 6 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | [13 empty] | #N/A | [9 empty] | #N/A
S504M | 55.81% | 114.5% | 2024 Q2 | 6126A | xD_DWDM_BRKRing_S504M_6126A KTM Kluang_0004582401310P_00045824026721 | 114.5% | 6126A-MAG(M8)-001 KTM Kluang | 1800vpro 1 rack 1 subrack | BBand | 2024-04-25 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4938A | xD_DWDM_BRKRing_NAR01_ii_4938A_Tmn Orkid_0004582401280Y_00045824026722 | #N/A | 4938A-MAG001 Taman Orkid | Board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4938A_Completed_RECTIFIER + DCPDB = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-4938A | 4938A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-29 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4660A | xD_DWDM_BRKRing_NAR01_ii_4660A KTM Alor Star_0004582401280Y_00045824026722 | #N/A | 4660A-MAG-001 KTM Alor Setar | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4998A | xD_DWDM_BRKRing_NAR01_ii_4998A Air Itam Kedah_0004582401280Y_00045824026722 | #N/A | 4998A-MAG-001 Air Itam Kedah | Board expansion | FO&T |  |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-31 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
NAR01_ii | #N/A | #N/A | 2024 Q2 | 4606A | xD_DWDM_BRKRing_NAR01_ii_4606A Padang Besar_0004582401280Y_00045824026722 | #N/A | 4606A-MAG(M8)- 001 Padang Besar | Board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
CT04 | #N/A | #N/A | 2024 Q2 | 1049B | xD_DWDM_BRKRing_CT04_1049B KPG_0004582401280Y_00045824026722 | #N/A | 1049B-MCR 001 KPG | 1800vPro 2 subrack | BBand | 2024-04-17 |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved |  |  |  | Material on hold - Sean | [9 empty] | #N/A | [9 empty] | #N/A
CT04 | #N/A | #N/A | 2024 Q2 | 1413A | xD_DWDM_BRKRing_CT04_1413A KTM Rawang_0004582401280Y_00045824026722 | #N/A | 1413A-MAC-001 KTM Rawang | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | Single_2023_October_DWDM_(blank)_1413A_Completed_DC BREAKER: 63 A X 4 | Single | 2023 | October | DWDM | (blank) | DWDM-1413A | 1413A | Completed | DC BREAKER: 63 A X 4 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR |  |  |  | Material on hold - Sean | [9 empty] | #N/A | [9 empty] | #N/A
CT04 | #N/A | #N/A | 2024 Q2 | 1412A | xD_DWDM_BRKRing_CT04_1412 Bkt Tadun_0004582401280Y_00045824026722 | #N/A | 1412A-MAC-001 Bkt Tadun | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR |  |  |  | Material on hold - Sean | [9 empty] | #N/A | [9 empty] | #N/A
MAC RING 6/C09+ | #N/A | 29% | 2024 Q2 | 2021B | xD_DWDM_BRKRing_MAC RING 6/C09+_2021B SBHT_0004582401280Y_00045824026722 | 29% | 2021B-MCR 001 SHT | 1800vPro 1rack 1subrack | BBand | 2024-04-04 |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | 1.ODF Rack (Glass Door) | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | [13 empty] | #N/A | [9 empty] | #N/A
MAC RING 6/C09+ | #N/A | 29% | 2024 Q2 | 1192A | xD_DWDM_BRKRing_MAC RING 6/C09+_1192A Subang New Village_0004582401280Y_00045824026722 | 29% | 1192A-MAC 001 Subang New Village | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Outdoor (delivery require Crane) | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | 2024-06-30 | Wk26 |  |  |  | 0524: Sharing rack with Advance. Need to f/u w/ Advance (need to recheck) Not freeze in KHE | [7 empty] | #N/A | [9 empty] | #N/A
MAC RING 6/C09+ | #N/A | 29% | 2024 Q2 | 1230A | xD_DWDM_BRKRing_MAC RING 6/C09+_1230A P Indus Sg Buloh_0004582401280Y_00045824026722 | 29% | 1230A-MAC 001 P indus Sg Buloh | 1800vPro 1rack 1subrack | BBand | 2024-04-03 |  |  | Single_2024_May_DWDM_MAC RING 6/C09+_1230A_PRPO_1. Add Battery Bank = 2 2. Swap breaker DC BREAKER: 63A X 4 | Single | 2024 | May | DWDM | MAC RING 6/C09+ | DWDM-1230A | 1230A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-07-11 | Wk28 |  |  |  | 0523: CME need to decom rack MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4952B | xD_DWDM_BRKRing_N401_4952B Selama_0004582401280Y_00045824026722 | 52% | 4952B-MAG 001 Selama | 1800vPro 1rack 1subrack | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-28 | Wk22 |  |  |  | MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4000A | xD_DWDM_BRKRing_N401_4000A MSC Prai_0004582401280Y_00045824026722 | 52% | 4000A-MCR 002 PRI | 1800vPro 1subrack | FO&T | 2024-04-17 |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | subrack only | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | [13 empty] | #N/A | [9 empty] | #N/A
N401 | 55.59% | 52% | 2024 Q2 | 4686B | xD_DWDM_BRKRing_N401_4684B Terap_0004582401280Y_00045824026722 | 52% | 4686B-MAC-001 Terap | 1800vPro 1rack 1subrack | FO&T |  |  |  | Multiple_2023_December_DWDM_(blank)_4686B_Completed_DC BREAKER: 63 A X 4 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4686B | 4686B | Completed | DC BREAKER: 63 A X 4 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-28 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN // 0515: Need 4WD | [7 empty] | #N/A | [9 empty] | YES
N401 | 55.59% | 52% | 2024 Q2 | 4965A | xD_DWDM_BRKRing_N401_4965A Politeknik Kulim_0004582401280Y_00045824026722 | 52% | 4965A-MAC-001 Politeknik Kulim | 1800vPro 1rack 1subrack | FO&T |  |  |  | Multiple_2023_December_DWDM_(blank)_4965A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4965A | 4965A | Completed | BATTERY BANK = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN // 0515: Need 4WD | [7 empty] | #N/A | [9 empty] | YES
N401 | 55.59% | 52% | 2024 Q2 | 4689A | xD_DWDM_BRKRing_N401_4689A Tmn Desa Impian_0004582401280Y_00045824026722 | 52% | 4689A-MAC 001 Tmn Desa Impian | 1800vPro 1rack 1subrack | FO&T |  |  |  | Multiple_2023_December_DWDM_(blank)_4689A_Completed_BATTERY BANK = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-4689A | 4689A | Completed | BATTERY BANK = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | YES
N401 | 55.59% | 52% | 2024 Q2 | 4118A | xD_DWDM_BRKRing_N401_4118A Machang Bubuk2_0004582401280Y_00045824026722 | 52% | 4118A-MAC 001 Machang Bubuk 2 | 1800vPro 1rack 1subrack | FO&T |  |  |  | Single_2023_December_DWDM_(blank)_4118A_Completed_DCPDB = 1 | Single | 2023 | December | DWDM | (blank) | DWDM-4118A | 4118A | Completed | DCPDB = 1 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | YES
C0103 (C0126) | #N/A | #N/A | 2024 Q2 | 1359A | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | #N/A | 1359A-MAC-001 Mutiara Subang | Board expansion | Advance |  |  |  | Single_2024_May_DWDM_C0103_1359A_PRPO_1. Swap breaker DC BREAKER: 63A X 2 | Single | 2024 | May | DWDM | C0103 | DWDM-1359A | 1359A | PRPO | No CME | Indoor | 1.4 Pending FF and CME Planner approval | 1.7 TSSR Approved | 2024-05-16 | Wk20 | 2024-05-16 |  |  | 0520: TI done 0517: TI WIP // 0516: Waiting outbound | [7 empty] | #N/A | [9 empty] | #N/A
N407 | 51.3% | 53% | 2024 Q2 | 4493A | xD_DWDM-BRKRing_N407_4493A KTM Ipoh_0004582401300R_00045824026922 | 53% | 4493A KTM Ipoh | 1800 Vpro 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N407 | 51.3% | 53% | 2024 Q2 | 4432A | xD_DWDM-BRKRing_N407_4432A KTM Sg Siput_0004582401300R_00045824026922 | 53% | 4432A KTM SG SIPUT | 1800 Vpro 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-31 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
N407 | 51.3% | 53% | 2024 Q2 | 4515A | xD_DWDM-BRKRing_N407_4515A Tg Rambutan_0004582401300R_00045824026922 | 53% | 4515A TG RAMBUTAN | 1800 Vpro 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N407 | 51.3% | 53% | 2024 Q2 | 4498A | xD_DWDM-BRKRing_N407_4498A Lap Tambun1 N 2_0004582401300R_00045824026922 | 53% | 4498A LAP Tambun 1&2 | 1800 Vpro 1 subrack | FO&T | 2024-04-19 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N407 | 51.3% | 53% | 2024 Q2 | 4541A | xD_DWDM-BRKRing_N407_4541A Bercham Industry_0004582401300R_00045824026922 | 53% | 4541A Bercham Industry | 1800 Vpro 1 subrack | FO&T | 2024-04-19 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
C0103 | 7.548% | 23% | 2024 Q2_2 | 1049B | xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922 | 23% | 1049B-MCR 001 KPG | 1800 Vpro 1 subrack | Advance | 2024-04-15 |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | 1.Swap breaker = 16 (16x63A DC) | subrack only | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-24 | Wk21 |  |  |  | 0523: Partial DN. Need to raise 2nd to outbound SFP | [7 empty] | P2 | [9 empty] | #N/A
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 4000A | xD_DWDM-BRKRing_NAR02_ii+_4000A MSC Prai_0004582401310N_00045824027823 |  | 4000A MSC Prai | board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A |  |  | #N/A | [9 empty] | #N/A
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 8000A | xD_DWDM-BRKRing_NAR02_ii+_8000A MSC KTN_0004582401310N_00045824027823 |  | 8000A MSC Kuantan | board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 4985A | xD_DWDM-BRKRing_NAR02_ii+_4985A Baling Town_0004582401310N_00045824027823 |  | 4985A-MAG-001 Baling Town | board expansion | FO&T |  |  |  | Single_2023_November_DWDM_(blank)_4985A_Completed_RECTIFIER + DCPDB = 1 BATTERTY BANK =2 | Single | 2023 | November | DWDM | (blank) | DWDM-4985A | 4985A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-29 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Only shortage patchcord. Inbound 20/5 // 0515:MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
NAR02_ii+ | #N/A |  | 2024 Q2_2 | 8282B | xD_DWDM-BRKRing_NAR02_ii+_8282B Pergau_0004582401310N_00045824027823 |  | 8282B-MAG(M14)-001 Pergau | board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-28 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Freezed to lock material. Need to reconfirm from Mok | [7 empty] | #N/A | [9 empty] | #N/A
CAR02-i+/CAR02-ii+ | #N/A |  | 2024 Q2_2 | 1049B | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1049B KPG_0004582401310N_00045824027823 | 23% | 1049B Kepong | board expansion | BBand | N/A |  |  | Single_2024_May_DWDM_C0105P;CAR04;C0103;CT04;C0103_1049B_PRPO_1.Swap breaker = 16 (16x63A DC) | Single | 2024 | May | DWDM | C0105P;CAR04;C0103;CT04;C0103 | DWDM-1049B | 1049B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-09 | Wk19 | 2024-05-14 | [10 empty] | #N/A | [9 empty] | #N/A
CAR02-i+/CAR02-ii+ | #N/A |  | 2024 Q2_2 | 2021B | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_2021B SBHT_0004582401310N_00045824027823 | 23% | 2021B Subang Hi-Tech | board expansion | BBand | N/A |  |  | Multiple_2024_May_DWDM_C0417P;MAC RING 6/C09+;5GC_2021B_PRPO_1.ODF Rack (Glass Door) | Multiple | 2024 | May | DWDM | C0417P;MAC RING 6/C09+;5GC | DWDM-2021B | 2021B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-09 | Wk19 | 2024-05-15 |  |  | 0520: TI done Installation not done - pending diagram | [7 empty] | #N/A | [9 empty] | #N/A
CAR02-i+/CAR02-ii+ | #N/A | 34% | 2024 Q2_2 | 1253A | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1253A Plaza Pengkalan_0004582401310N_00045824027823 | 34% | 1253A-MAG(M14)-001 Plaza Pengkalan | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_April_DWDM_C0204;C0210P;CAR02-i+/CAR02-ii+_1253A_PRPO_1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) 2. Add Modules = 5 3. Battery Bank = 4 | Single | 2024 | April | DWDM | C0204;C0210P;CAR02-i+/CAR02-ii+ | DWDM-1253A | 1253A | PRPO | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | 0 | 1.1 Pending partner to submit TSSR | 1.4 Pending FF and CME Planner approval | 2024-06-04 | Wk23 |  |  |  | 0524: Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
CAR02-i+/CAR02-ii+ | #N/A | 34% | 2024 Q2_2 | 1851A | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1851A KL Plaza2_0004582401310N_00045824027823 | 34% | 1851A-MAG(M14)-001 KL Plaza 2 | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-05 | Wk23 |  |  |  | 0523: Freezed. Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
CAR02-i+/CAR02-ii+ | #N/A | 34% | 2024 Q2_2 | 1859A | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 34% | 1859A-MAG(M14)-001 Midvalleycas | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4 | Single | 2024 | May | DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | DWDM-1859A | 1859A | PRPO | 1.Add modules = 2 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-06 | Wk23 |  |  |  | 0524: Pending Advance integrate to add subrack. Freezed. Pending DN. | [7 empty] | #N/A | [9 empty] | #N/A
CAR02-ii+ | #N/A | 22% | 2024 Q2_2 | 1918A | xD_DWDM-BRKRing_CAR02-ii+_1918A Damansara Intan_0004582401310N_00045824027823 | 22% | 1918A-MAG(M14)-001 Damansara Intan | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_May_DWDM_CT0241P;C0417P;CAR02-ii+_1918A_PRPO_1. Add Battery Bank = 2 | Single | 2024 | May | DWDM | CT0241P;C0417P;CAR02-ii+ | DWDM-1918A | 1918A | PRPO | 1. Add Battery Bank = 2 | Existing | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
CAR02-ii+ | #N/A | 22% | 2024 Q2_2 | 1172A | xD_DWDM-BRKRing_CAR02-ii+_1172A Glomac_0004582401310N_00045824027823 | 22% | 1172A-MAG(M14)-001 Glomac | 9800M12 1 subrack | BBand | 2024-04-16 |  |  | Single_2023_October_DWDM_(blank)_1172A_Completed_DC BREAKER : 63A X 4 MGB = 1 | Single | 2023 | October | DWDM | (blank) | DWDM-1172A | 1172A | Completed | DC BREAKER : 63A X 4 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4000A | xD_DWDM-BRKRing_NAR01_iii+_4000A MSC Prai_0004582401310N_00045824027823 | 76% | 4000A MSC Prai | 9800M12 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2023_November_DWDM_(blank)_4000A_Completed_DC BREAKER: 63A X 12 | Single | 2023 | November | DWDM | (blank) | DWDM-4000A | 4000A | Completed | DC BREAKER: 63A X 12 | 0 | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4493A | xD_DWDM-BRKRing_NAR01_iii+_4493A KTM Ipoh_0004582401310N_00045824027823 | 76% | 4493A KTM IPOH | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4606A | xD_DWDM-BRKRing_NAR01_iii+_4606A Padang Besar_0004582401310N_00045824027823 | 76% | 4606A-MAG(M8)-001 Padang Besar | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4995A | xD_DWDM-BRKRing_NAR01_iii+_4995A UUM HW_0004582401310N_00045824027823 | 76% | 4995A-MAG(M14)-001 UUM Highway | 9800M12 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR01_iii+ | #N/A | 76% | 2024 Q2_2 | 4992A | xD_DWDM-BRKRing_NAR01_iii+_4992A Pendang_0004582401310N_00045824027823 | 76% | 4992A-MAG(M14)-001 Pendang | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR04_ii+ | #N/A |  | 2024 Q2_2 | 4521A | xD_DWDM-BRKRing_NAR04_ii+_4521A Ipoh_0004582401310N_00045824027823 |  | 4521A - IPOH | board expansion | FO&T |  |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-14 | Wk20 | 2024-05-14 | [7 empty] | N/A |  |  | #N/A | [9 empty] | #N/A
NAR04_ii+ | #N/A | 52% | 2024 Q2_2 | 4455A | xD_DWDM-BRKRing_NAR04_ii+_4455A KTM Taiping_0004582401310N_00045824027823 | 52% | 4455A-MAG(M14)-001 KTM Taiping | 9800M12 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
NAR04_ii+ | #N/A | 52% | 2024 Q2_2 | 4432A | xD_DWDM-BRKRing_NAR04_ii+_4432A KTM Sungai Siput_0004582401310N_00045824027823 | 52% | 4432A-MAG(M14)-001 KTM Sungai Siput | 9800M12 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-31 | Wk22 |  |  |  | 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
C0211+ | #N/A | 30% | 2024 Q2_2 | 2888A | xD_DWDM-BRKRing_C0211+_2888A Plaza Central_0004582401310N_00045824027823 | 30% | 2888A-MAC-001 Plaza Central | 9800M12 1 subrack | BBand | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | 0517: Pending survey. Access issue to survey | [7 empty] | #N/A | [9 empty] | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A | 65% | 2024 Q2_2 | 1475A | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1475A SKB_0004582401310N_00045824027823 | 65% | 1475A SKB | 1800vPro 1rack 2 subrack | BBand | 2024-04-17 |  |  | Single_2024_May_DWDM_5GC_1475A_PRPO_1.ODF Rack (Glass Door) | Single | 2024 | May | DWDM | 5GC | DWDM-1475A | 1475A | PRPO | 1.ODF Rack (Glass Door) | Indoor | 1.32 CME Planner reject/Pending resubmission from partner | 1.32 CME Planner reject/Pending resubmission from partner | [13 empty] | P1_Z_Jul | [9 empty] | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A | 65% | 2024 Q2_2 | 1851A | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1851A KL Plaza2_0004582401310N_00045824027823 | 65% | 1851A-MAG(M14)-001 KL Plaza 2 | 1800vPro 1 subrack | BBand | 2024-04-16 |  |  | Multiple_2024_May_DWDM_C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+_1851A_PRPO_1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 3 3.Propose new cable ladder | Multiple | 2024 | May | DWDM | C0204;CAR02-i+/CAR02-ii+;1063B/AREA 154/C0211+/C0515+ | DWDM-1851A | 1851A | PRPO | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | [13 empty] | P1_Z_Jul | [9 empty] | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A |  | 2024 Q2_2 | 1246A | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1246A Berjaya Plaza_0004582401310N_00045824027823 |  | BERJAYA PLAZA 1246A | board expansion | BBand | N/A |  |  | Single_2023_November_DWDM_(blank)_1246A_Completed_DC BREAKER: 63 A X 4 POLE RELOCATE = 1 | Single | 2023 | November | DWDM | (blank) | DWDM-1246A | 1246A | Completed | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-30 | Wk22 |  |  |  | 0516: Pending DN | [7 empty] | P1_Z_Jul | [9 empty] | #N/A
1063B/AREA 154/C0211+/C0515+ | #N/A |  | 2024 Q2_2 | 1063B | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1063B Berjaya Times Square_0004582401310N_00045824027823 |  | Berjaya Time Square (Tx) 1063B | board expansion | BBand | N/A |  |  | Single_2024_May_DWDM_PFSRING101/C0607P_1063B_PRPO_1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | Single | 2024 | May | DWDM | PFSRING101/C0607P | DWDM-1063B | 1063B | PRPO | No CME | NA | 0. No Survey required | 0. No Survey required | 2024-05-24 | Wk21 |  |  |  | 0516: Waiting outbound | [7 empty] | P1_Z_Jul | [9 empty] | #N/A
AREA 154/MAC Ring 15/ C21+ | #N/A | 65% | 2024 Q2_2 | 1458A | xD_DWDM-BRKRing_AREA 154/MAC Ring 15/ C21+_1458A Endah Parade_0004582401310N_00045824027823 | 65% | 1458A-MAG-001 Endah Parade | 1800vPro 1rack 2 subrack | BBand | 2024-04-17 |  |  | Single_2024_January_DWDM_(blank)_1458A_Completed_BATTERY BANK = 1 | Single | 2024 | January | DWDM | (blank) | DWDM-1458A | 1458A | Completed | BATTERY BANK = 1 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | P1_Z_Jul | [9 empty] | #N/A
AREA 154/MAC Ring 15/ C21+ | #N/A | 65% | 2024 Q2_2 | 1855B | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1855B TPM_0004582401310N_00045824027823 | 65% | 1855B-MAC-001 TPM (AS) | 1800vPro 1rack 2 subrack | BBand | 2024-04-17 |  |  | Multiple_2023_December_DWDM_(blank)_1855B_Completed_DCPDB = 1 | Multiple | 2023 | December | DWDM | (blank) | DWDM-1855B | 1855B | Completed | DCPDB = 1 | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | P1_Z_Jul | [9 empty] | #N/A
C0211+ | #N/A | 30% | 2024 Q2_2 | 1859A | xD_DWDM-BRKRing_C0211+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 30% | 1859A-MAG(M14)-001 Midvalleycas | 1800vPro 1 subrack | BBand | 2024-04-16 |  |  | Single_2024_May_DWDM_C0210P;CAR02-i+/CAR02-ii+;C0211+_1859A_PRPO_1.Add modules = 2 2.Add battery bank = 4 | Single | 2024 | May | DWDM | C0210P;CAR02-i+/CAR02-ii+;C0211+ | DWDM-1859A | 1859A | PRPO | 1.Add modules = 2 | Subrack only | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-06-06 | Wk23 |  |  |  | 0524: Freezed. Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
C0515+ | #N/A | 54% | 2024 Q2_2 | 1039A | xD_DWDM-BRKRing_C0515+_1039A Cheras Jaya_0004582401310N_00045824027823 | 54% | 1039A-MAG(M14)-001 Cheras Jaya | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | Survey done | [7 empty] | #N/A | [9 empty] | #N/A
C0515+ | #N/A | 54% | 2024 Q2_2 | 2448A | xD_DWDM-BRKRing_C0515+_2448A Asmah Tower_0004582401310N_00045824027823 | 54% | 2448A-MAC-001 Asmah Tower | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | Survey done | [7 empty] | #N/A | [9 empty] | #N/A
C0515+ | #N/A | 54% | 2024 Q2_2 | 2424A | xD_DWDM-BRKRing_C0515+_2424A PUAS Tmn Tun Perak_0004582401310N_00045824027823 | 54% | 2424A-MAC-001 PUAS Tmn Tun Perak | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | Survey done | [7 empty] | #N/A | [9 empty] | #N/A
C0515+ | #N/A | 54% | 2024 Q2_2 | 2024A | xD_DWDM-BRKRing_C0515+_2024A Bdr Makhota Cheras_0004582401310N_00045824027823 | 54% | 2024A-MAC-001 Bdr Mahkota Cheras | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | Survey done | [7 empty] | #N/A | [9 empty] | #N/A
C0515+ | #N/A | 54% | 2024 Q2_2 | 1902B | xD_DWDM-BRKRing_C0515+_1902B Bdr Sg Long3_0004582401310N_00045824027823 | 54% | 1902B-MAC-001 Bdr Sg Long 3 | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | Survey done | [7 empty] | #N/A | [9 empty] | #N/A
MAC Ring 15/C21+ | #N/A |  | 2024 Q2_2 | 1745A | xD_DWDM-BRKRing_MAC Ring 15/C21+_1745A Baitumal_0004582401310N_00045824027823 |  | 1745A-MAG(M14)-001 Baitumal | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.1 Pending partner to submit TSSR | 1.7 TSSR Approved | [13 empty] | #N/A | [9 empty] | #N/A
MAC Ring 15/C21+ | #N/A |  | 2024 Q2_2 | 2502A | xD_DWDM-BRKRing_MAC Ring 15/C21+_2502A Bdar Tun Razak_0004582401310N_00045824027823 |  | 2502A-MAC-001 B'dar Tun Razak | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
MAC Ring 15/C21+ | #N/A |  | 2024 Q2_2 | 1974A | xD_DWDM-BRKRing_MAC Ring 15/C21+_1974A Jln Sg Besi_0004582401310N_00045824027823 |  | MIP2013 1974A-MAC-001 Jln Sg Besi | 1800vPro 1rack 1 subrack | BBand | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N104+ | #N/A | 42% | 2024 Q2_2 | 4995A | xD_DWDM-BRKRing_N104+_4995A UUMHW_0004582401310N_00045824027823 | 42% | 4995A-MAG-001 UUM Highway | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [5 empty] | 0521: Pending TSSR approval | [7 empty] | #N/A | [9 empty] | #N/A
N104+ | #N/A | 42% | 2024 Q2_2 | 4992A | xD_DWDM-BRKRing_N104+_4992A Pendang_0004582401310N_00045824027823 | 42% | 4992A-MAG(M14)-001 Pendang | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | Multiple_2024_May_DWDM_(blank)_4992A_Completed_1.Swap breaker = 4 (4x100A DC) | Multiple | 2024 | May | DWDM | (blank) | DWDM-4992A | 4992A | Completed | 1.Swap breaker = 4 (4x100A DC) | Outdoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 |  |  |  | 0524: Waiitng outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN. Not freeze in KHE due to no DUID | [7 empty] | #N/A | [9 empty] | #N/A
N104+ | #N/A | 42% | 2024 Q2_2 | 4991A | xD_DWDM-BRKRing_N104+_4991A UUM_0004582401310N_00045824027823 | 42% | 4991A-MAC-001 UUM | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+_4991A_PRPO_1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 4. Add Module = 2 | Single | 2024 | May | DWDM | N104+ | DWDM-4991A | 4991A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | YES
N104+ | #N/A | 42% | 2024 Q2_2 | 4672A | xD_DWDM-BRKRing_N104+_4672A Changloon_0004582401310N_00045824027823 | 42% | 4672A-MAC-001 Changloon | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+_4672A_PRPO_1. New DCDPB =1 (Require 63A x 4 DC breaker) 2. New MGB = 1 | Single | 2024 | May | DWDM | N104+ | DWDM-4672A | 4672A | PRPO | 1. New DCDPB =1 (Require 63A x 4 DC breaker) | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-29 | Wk22 |  |  |  | 0524: Waiting outbound MOS freezed. Pending confirmation availability of material. | [7 empty] | #N/A | [9 empty] | #N/A
N104+ | #N/A | 42% | 2024 Q2_2 | 4665A | xD_DWDM-BRKRing_N104+_4665A Jitra_0004582401310N_00045824027823 | 42% | 4665A-MAC-001 Jitra | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+_4665A_PRPO_1. Add Battery Bank = 2 2. New DCDPB =1 (Require 63A x 4 DC breaker) 3. New MGB = 1 | Single | 2024 | May | DWDM | N104+ | DWDM-4665A | 4665A | PRPO | 1. Add Battery Bank = 2 | Indoor | 1.7 TSSR Approved | 1.7 TSSR Approved | 2024-05-30 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
N107+ | #N/A | 38% | 2024 Q2_2 | 4998A | xD_DWDM-BRKRing_N107+_4998A Air Itam Kedah_0004582401310N_00045824027823 | 38% | 4998A-MAG(M14)-001 Air Itam Kedah | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | Single_2024_May_DWDM_N104+;N107+_4998A_PRPO_1. Add Battery Bank = 1 | Single | 2024 | May | DWDM | N104+;N107+ | DWDM-4998A | 4998A | PRPO | 1. Add Battery Bank = 1 | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-31 | Wk22 |  |  |  | 0524: Waiting outbound 0521: Material shortage. Need to change to next week 0516: Waiting outbound. 0515:Plan after 21/5. Freezed. Pending DN | [7 empty] | P1_Z_Oct | [9 empty] | #N/A
N107+ | #N/A | 38% | 2024 Q2_2 | 4606A | xD_DWDM-BRKRing_N107+_4606A Padang Besar_0004582401310N_00045824027823 | 38% | 4606A-MAG(M8)-001 Padang Besar | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.11 HW TSSR reject/Pending resubmission from partner | 1.11 HW TSSR reject/Pending resubmission from partner | [13 empty] | P1_Z_Oct | [9 empty] | #N/A
N107+ | #N/A | 38% | 2024 Q2_2 | 4604A | xD_DWDM-BRKRing_N107+_4604A Kuala Perlis_0004582401310N_00045824027823 | 38% | 4604A-MAC-001 Kuala Perlis(Trunk) | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | P1_Z_Oct | [9 empty] | #N/A
N107+ | #N/A | 38% | 2024 Q2_2 | 4601A | xD_DWDM-BRKRing_N107+_4601A Federal Kangsar_0004582401310N_00045824027823 | 38% | 4601A-MAC-001 Federal Kangar | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | P1_Z_Oct | [9 empty] | #N/A
N107+ | #N/A | 38% | 2024 Q2_2 | 4612A | xD_DWDM-BRKRing_N107+_4612A Jln Kaki Bkt_0004582401310N_00045824027823 | 38% | 4612A-MAC-001 Jln Kaki Bkt | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | P1_Z_Oct | [9 empty] | #N/A
N107+ | #N/A | 38% | 2024 Q2_2 | 4613A | xD_DWDM-BRKRing_N107+_4613A Taman Bestari Perlis_0004582401310N_00045824027823 | 38% | 4613A-MAC-001 Taman Bestari Perlis | 1800vPro 1rack 1 subrack | FO&T | 2024-04-17 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | P1_Z_Oct | [9 empty] | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4432A | xD_DWDM-BRKRing_N405+/N408+/N411+_4432A KTM Sg Siput_0004582401310N_00045824027823 | 60% | 4432A-MAG-001 KTM Singai Siput | 1800vPro 1rack 2 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | Indoor | 1.6 Pending FF approval | 1.6 Pending FF approval | 2024-05-31 | Wk22 |  |  |  | 0524: Waiting outbound 0517: Main eqt shortage. Only can outbound 27th onwards 0516: Pending DN | [7 empty] | #N/A | [9 empty] | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4455A | xD_DWDM-BRKRing_N405+/N408+/N411+_4455A KTM Taiping_0004582401310N_00045824027823 | 60% | 4455A-MAG(M14)-001 KTM Taiping | 1800vPro 1rack 2 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4374A | xD_DWDM-BRKRing_N405+/N408+/N411+_4374A LAP Talang_0004582401310N_00045824027823 | 60% | 4374A-MAC-001 LAP Talang | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4378A | xD_DWDM-BRKRing_N405+/N408+/N411+_4378A Jerlun Tower_0004582401310N_00045824027823 | 60% | MIP2018 4378A-MAC-001 Jerlun Tower | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N405+/N408+/N411+ | #N/A | 60% | 2024 Q2_2 | 4379A | xD_DWDM-BRKRing_N405+/N408+/N411+_4379A Bkt Mercu_0004582401310N_00045824027823 | 60% | 4379A-MAC-001 Bkt Mercu | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N408+ | #N/A | 60% | 2024 Q2_2 | 4493A | xD_DWDM-BRKRing_N408+_4493A KTM Ipoh_0004582401310N_00045824027823 | 60% | 4493A-MAG-001 KTM Ipoh | 1800vPro 1rack 1 subrack | FO&T | 2024-04-16 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N408+ | #N/A | 60% | 2024 Q2_2 | 4506A | xD_DWDM-BRKRing_N408+_4506A Perak Taipu_0004582401310N_00045824027823 | 60% | 4506A-MAC-001 Perak Taipu | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N408+ | #N/A | 60% | 2024 Q2_2 | 4546A | xD_DWDM-BRKRing_N408+_4546A KWSP Ipoh_0004582401310N_00045824027823 | 60% | 4546A-MAC-001 KWSP Ipoh | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N408+ | #N/A | 60% | 2024 Q2_2 | 4515A | xD_DWDM-BRKRing_N408+_4515A Tg Rambutan_0004582401310N_00045824027823 | 60% | 4515A-MAC-001 Tg Rambutan | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N411+ | #N/A | 37% | 2024 Q2_2 | 4373A | xD_DWDM-BRKRing_N411+_4373A KTM K Kangsar_0004582401310N_00045824027823 | 37% | 4373A-MAC-001 KTM K. Kangsar | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N411+ | #N/A | 37% | 2024 Q2_2 | 4377B | xD_DWDM-BRKRing_N411+_4377B Karai_0004582401310N_00045824027823 | 37% | 4377B-MAC-001 Karai | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
N411+ | #N/A | 37% | 2024 Q2_2 | 4433A | xD_DWDM-BRKRing_N411+_4433A LAP Sg Siput_0004582401310N_00045824027823 | 37% | 4433A-MAC-001 LAP Sg Siput | 1800vPro 1rack 1 subrack | FO&T | 2024-04-18 |  |  | #N/A | #N/A |  |  |  |  | DWDM- |  |  |  | 0 | 1.1 Pending partner to submit TSSR | 1.1 Pending partner to submit TSSR | [13 empty] | #N/A | [9 empty] | #N/A
Formulas:
WorkWeek_Install = "Wk"&WEEKNUM([Plan MOS],21)
WorkWeek_Integration = "Wk"&WEEKNUM([Integrated Date],21)