## IPBREAK RING AND SWAP Y23-Y24
408 | 408 | 408 | 408 | 408 | 408 | 408 | 408 | 404 | 404 | 404 | 404 | 408 | 408 | 408 | 408 | 408 | 26 | 408 | 247 | 264 | 0 | 264 | 0 | 263 | 0 | 262 | 177 | 157 |  | 0 | 0 | 0 | 0 | 184 |  | 18824681.656 | 16283515.1747
NO | PROJECT CATEGORY | ACTIVITY NAME | REQUIRED DWDM / LL / OPM | BOQ BATCH | Rollout Batch | HW ES BOQ MIP# | CD ES PO# | CD ES PO Date | HW EQ BOQ MIP# | CD EQ PO# | CD EQ PO Date | Region | State | Site ID | Site Name | NE ID | Node Qty | Ring ID | Subcon | Survey Plan | Survey Completed | TSSR Plan | TSSR Submitted | CME REQUIREMENT | Others | Install | SWAP/MIGRATION PLAN DATE | SWAP/MIGRATION COMPLETION DATE | PROJECT REMARKS | MRCF | FAD | ATF | DISMANTLE | HL Baseline RFS | ***Remark*** | ACCRUAL ES (MYR) | ACCRUAL EQ (MYR)
1 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1071A | CHI LIUNG PLAZA | Chi Liung | 3 | CAR07, Area70 | BBAND | 2023-08-30 |  | 2023-09-06 |  | NA |  | 2023-10-19 | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 28201.81 | 20094.6123
2 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1071A | CHI LIUNG PLAZA | Chi Liung | 3 | CAR07, Area70 | BBAND | 2023-08-30 |  | 2023-09-06 |  | NA |  | 2023-10-19 | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 28201.81 | 20094.6123
3 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1071A | CHI LIUNG PLAZA | Chi Liung | 3 | CAR07, Area70 | BBAND | 2023-08-30 |  | 2023-09-06 |  | NA |  | 2023-10-19 | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 28201.81 | 20094.6123
4 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1073A | KTM Padang Jawa | KTM Padang Jawa | 2 | CAR07, Area70 | BBAND | 2023-10-03 |  | 2023-10-10 |  | New rectifier c/w DCPD |  | 2024-01-26 | 2024-03-14 | 2024-03-14 | [5 empty] | Mar |  | 28201.81 | 20094.6123
5 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1073A | KTM Padang Jawa | KTM Padang Jawa | 2 | CAR07, Area70 | BBAND | 2023-10-03 |  | 2023-10-10 |  | New rectifier c/w DCPD |  | 2024-01-26 | 2024-03-14 | 2024-03-14 | [5 empty] | Mar |  | 28201.81 | 20094.6123
6 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1342A | MBSA | MBSA | 1 | CAR07, Area70 | BBAND | 2023-11-16 |  | 2023-11-23 |  | Swap breaker 25A to 16Ax2 |  | 2024-02-21 | 2024-02-22 | 2024-02-23 | [5 empty] | Feb |  | 28201.81 | 20094.6123
7 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1342A | MBSA | MBSA | 1 | CAR07, Area70 | BBAND | 2023-11-16 |  | 2023-11-23 |  | Swap breaker 25A to 16Ax2 |  | 2024-02-21 | 2024-02-22 | 2024-02-23 | [5 empty] | Feb |  | 28201.81 | 20094.6123
8 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1367A | WorldWideBusiness | WorldWideBusiness | 1 | CAR07, Area70 | BBAND | 2023-08-30 |  | 2023-09-06 |  | NA |  | 2023-10-23 | 2024-01-17 | 2024-01-17 | [5 empty] | Jan |  | 28201.81 | 20094.6123
9 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 2536A | Centro IB | Centro IB | 1 | CAR07, Area70 | BBAND | 2023-10-03 |  | 2023-10-10 |  | NA |  | 2023-10-23 | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 28201.81 | 20094.6123
10 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1096A | Klang Perdana | Klang Perdana | 1 | CAR07, Area76 | BBAND | 2023-08-30 |  | 2023-09-06 |  | cabinet rectifier module -Pending DCPDB -Complete |  | 2023-12-13 | 2024-05-28 | 2024-05-28 | The slot blocked by IPCORE activity |  |  |  |  | Apr |  | 28201.81 | 20094.6123
11 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1362A | Electroscon | Electroscon | 1 | CAR07, Area76 | BBAND | 2023-08-30 |  | 2023-09-06 |  | NA |  | 2023-10-24 | 2024-05-28 | 2024-05-28 | The slot blocked by IPCORE activity |  |  |  |  | Apr |  | 28201.81 | 20094.6123
12 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1702A | Bkt. Tagar (Trunk) | Bkt. Tagar (Trunk) | 1 | CAR07, Area76 | BBAND | 2023-10-18 |  | 2023-10-25 |  | NA |  | 2023-12-15 | 2024-01-17 | 2024-01-17 | [5 empty] | Jan |  | 28201.81 | 20094.6123
13 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1236A | Labu Lanjut | Labu Lanjut | 2 | Central LL2, Area 77 | BBAND | 2023-10-03 |  | 2023-10-10 |  | NA |  | 2023-10-20 | 2023-11-21 | 2023-11-21 | [7 empty] | 28201.81 | 20094.6123
14 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1236A | Labu Lanjut | Labu Lanjut | 2 | Central LL2, Area 77 | BBAND | 2023-10-03 |  | 2023-10-10 |  | NA |  | 2023-10-20 | 2023-11-21 | 2023-11-21 | [7 empty] | 28201.81 | 20094.6123
15 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Negeri Sembilan | 1610A | GUN HILL | GUN HILL | 2 | SAR02, Area98 | BBAND | 2023-10-03 |  | 2023-10-10 |  | Proposed to install new DCPDB (wallmount) |  | 2023-10-23 | 2024-04-18 | 2024-04-18 | [5 empty] | Apr |  | 28201.81 | 20094.6123
16 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Negeri Sembilan | 1610A | GUN HILL | GUN HILL | 2 | SAR02, Area98 | BBAND | 2023-10-03 |  | 2023-10-10 |  | Proposed to install new DCPDB (wallmount) |  | 2023-10-23 | 2024-04-18 | 2024-04-18 | [5 empty] | Apr |  | 28201.81 | 20094.6123
17 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Melaka | 1525A | Bang. Graha Maju | Bang. Graha Maju | 1 | SAR03, Area90 | BBAND | 2023-10-06 |  | 2023-10-13 |  | NA |  | 2023-12-15 | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 28201.81 | 20094.6123
18 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Johor | 6040A | BUKIT RESAM | Bkt Resam | 2 | SAR03, Area97 | BBAND | 2023-10-10 |  | 2023-10-17 |  | 1 rectifier module |  | 2023-12-26 | 2024-04-24 | 2024-04-24 | [5 empty] | Mar |  | 28201.81 | 20094.6123
19 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Johor | 6040A | BUKIT RESAM | Bkt Resam | 2 | SAR03, Area97 | BBAND | 2023-10-10 |  | 2023-10-17 |  | 1 rectifier module |  | 2023-12-26 | 2024-04-24 | 2024-04-24 |  | NA | Pending Approval |  |  | Mar |  | 28201.81 | 20094.6123
20 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Johor | 6295A | Jln Permatang Kempas | Jln Permatang Kempas | 1 | SAR03, Area97 | BBAND | 2023-10-31 |  | 2023-11-07 |  | swap existing 2x32A breaker with 2x16A at DCPDB |  | 2023-12-14 | 2024-04-24 | 2024-04-24 |  | NA | Pending Approval |  |  | Mar |  | 28201.81 | 20094.6123
21 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Johor | 6336A | UTM 2 | UTM 2 | 2 | SAR04, Area91 | BBAND | 2023-10-31 |  | 2023-11-07 |  | 19 Rack |  |  | 2024-06-05 |  | The slot blocked by IPCORE activity | NA | Pending Approval |  |  | May |  | 28201.81 | 20094.6123
22 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Southern | Johor | 6336A | UTM 2 | UTM 2 | 2 | SAR04, Area91 | BBAND | 2023-10-31 |  | 2023-11-07 |  | 19 Rack |  |  | 2024-06-05 |  | The slot blocked by IPCORE activity | NA | Pending Approval |  |  | May |  | 28201.81 | 20094.6123
23 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1002A | Sri Murni | Sri Murni | 2 | CAR03, Area 151 | FO&T | 2023-09-11 |  | 2023-09-18 |  | NA |  | 2023-10-24 | 2023-11-16 | 2023-11-16 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
24 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1002A | Sri Murni | Sri Murni | 2 | CAR03, Area 151 | FO&T | 2023-09-11 |  | 2023-09-18 |  | NA |  | 2023-10-24 | 2023-11-16 | 2023-11-16 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
25 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1006A | JBA Gombak | JBA GOMBAK | 2 | CAR04, Area 154 | FO&T | 2023-11-29 |  | 2023-12-06 |  | DCPDB + MGB |  | 2023-12-12 | 2024-05-10 | 2024-05-10 |  | NA | Pending Approval |  |  | May |  | 28201.81 | 20094.6123
26 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Central | Selangor | 1006A | JBA Gombak | JBA GOMBAK | 2 | CAR04, Area 154 | FO&T | 2023-11-29 |  | 2023-12-06 |  | DCPDB + MGB |  | 2023-12-12 | 2024-05-10 | 2024-05-10 |  | NA | Pending Approval |  |  | May |  | 28201.81 | 20094.6123
27 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Perak | 4310A | Matang Acheh | Kg Matang Acheh-100Q4(Digi Trunk)_REL | 1 | NAR03, Area134 | FO&T | 2023-09-11 |  | 2023-09-18 |  | to install new class rack |  |  | 2024-05-16 | 2024-05-16 |  | NA | Pending Approval |  |  | May |  | 28201.81 | 20094.6123
28 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Perak | 4401B | Kg Temerloh | Kg Temerloh-100Q4 RDD | 1 | NAR03, Area134 | FO&T | 2023-09-11 |  | 2023-09-18 |  | NA |  | 2023-10-24 | 2024-05-16 | 2024-05-16 |  | NA | Pending Approval |  |  | May |  | 28201.81 | 20094.6123
29 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4001A | Crown Prince Hotel V6 | Crown Prince Hotel V6 | 1 | Northern LL2, Area124 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-26 | 2023-12-21 | 2023-12-21 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
30 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4012A | Prime Plaza | Prime Plaza | 2 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-24 | 2023-11-16 | 2023-11-16 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
31 |  | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | DROP | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4012A | Prime Plaza | Prime Plaza | 2 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | DROP | DROP | DROP |  |  | DROP | DROP | DROP | DROP | DROP |  | Drop - PFS | 28201.81 | 20094.6123
32 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4015A | Axis Complex V4 | Axis Complex V4 | 2 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-24 | 2023-11-21 | 2023-11-21 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
33 |  | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | DROP | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4015A | Axis Complex V4 | Axis Complex V4 | 2 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | DROP | DROP | DROP |  |  | DROP | DROP | DROP | DROP | DROP |  | Drop - PFS | 28201.81 | 20094.6123
34 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4031A | GeorgeTownHotel (Trunk) | GeorgeTownHotel (Trunk) | 1 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | New Sub DCPDB |  | 2023-11-10 | 2024-04-19 | 2024-04-19 |  | NA | Pending Approval |  |  | Apr |  | 28201.81 | 20094.6123
35 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4034A | Bukit Relau | Bukit Relau | 1 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-25 | 2023-01-04 | 2023-01-04 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
36 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4054A | Sunway Hotel | Sunway Hotel | 1 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-26 | 2023-11-16 | 2023-11-16 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
37 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4056A | Vistana Hotel | Vistana Hotel | 2 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-26 | 2023-11-21 | 2023-11-21 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
38 |  | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | DROP | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4056A | Vistana Hotel | Vistana Hotel | 2 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | DROP | DROP | DROP |  |  | DROP | DROP | DROP | DROP | DROP |  | Drop - PFS | 28201.81 | 20094.6123
39 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Northern | Pulau Pinang | 4063A | Komplek Tabung Haji | Komplek Tabung Haji | 1 | Northern-PRI PFS, Area125 | FO&T | 2023-09-25 |  | 2023-10-02 |  | NA |  | 2023-10-25 | 2024-04-19 | 2024-04-19 |  | NA | Pending Approval |  |  | Apr |  | 28201.81 | 20094.6123
40 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Sabah | Sabah | 7042A | LTP Telipok Maxis | Telipok | 1 | Sabah, Area147 | FO&T | 2023-09-15 |  | 2023-09-22 |  | NA |  | 2023-12-04 | 2023-12-05 | 2023-12-05 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
41 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Sabah | Sabah | 7063A | Guang Ji Temple | Guang Ji Temple | 1 | Sabah, Area147 | FO&T | 2023-09-15 |  | 2023-09-22 |  | NA |  | 2023-12-11 | 2023-12-12 | 2023-12-12 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
42 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Sabah | Sabah | 7155A | Maxi Propose Tuaran | Maxi Purpose Tuaran | 1 | Sabah, Area147 | FO&T | 2023-09-15 |  | 2023-09-22 |  | NA |  | 2023-12-07 | 2023-12-08 | 2023-12-08 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
43 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Sabah | Sabah | 7169A | UMW INANAM | UMWINANAM | 1 | Sabah, Area147 | FO&T | 2023-09-15 |  | 2023-09-22 |  | NA |  | 2023-12-07 | 2023-12-07 | 2023-12-07 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
44 | PFS Swap | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | YR23 B1 | Spillover | MIP2023.62 | ML201325 | 2023-09-15 | MIP2023.62 | ML189533 | 2023-07-25 | Sabah | Sabah | 7256A | Tmn Kingfisher | Tmn Kingfisher | 1 | Sabah, Area147 | FO&T | 2023-09-15 |  | 2023-09-22 |  | NA |  | 2023-12-05 | 2023-12-06 | 2023-12-06 |  | NA | Pending Approval |  |  |  |  | 28201.81 | 20094.6123
45 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 1336A | Balai Islam TTDI | Balai Islam TTDI | [10 empty] | 2024-01-18 | 2024-01-18 | [5 empty] | Jan
46 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 1211A | KDU | KDU | [10 empty] | 2024-01-18 | 2024-01-18 | [5 empty] | Jan
47 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 2831A | One Utama Phase 2 | One Utama Phase 2 | [10 empty] | 2024-01-18 | 2024-01-18 | [5 empty] | Jan
48 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 1197A | JBAEFF | JBAEFF | [10 empty] | 2024-01-18 | 2024-01-18 | [5 empty] | Jan
49 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 1197A | JBAEFF | JBAEFF | [10 empty] | 2024-01-18 | 2024-01-18 | [5 empty] | Jan
50 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 2977B | DiGi HQ (Lot 10) | DiGi HQ (Lot 10) | [10 empty] | 2024-01-09 | 2024-01-09 | [5 empty] | Jan
51 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.44 | [5 empty] | Central | Selangor | 1611A | Mukim Labu | Mukim Labu | [10 empty] | 2024-01-09 | 2024-01-09 | [5 empty] | Jan
52 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.51 | [5 empty] | Central | Selangor | 1407A | Menara Luxor | Menara Luxor | [10 empty] | 2024-05-23 | [6 empty] | May
53 | PFS Swap | PFS Swap YR22 | N/A | YR23 | Spillover | MIP2022.51 | [5 empty] | Central | Selangor | 1186A | Tropicana2 | Tropicana2 | [10 empty] | 2024-05-23 | [6 empty] | May
54 | MAG Swap | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | YR23 B1 | Spillover | MIP2023.114 | ML189832 | 2023-07-31 | MIP2023.114 | ML189833 | 2023-07-26 | Central | Selangor | 1037A | JBA Bangi | JBA Bangi | 1 |  | FO&T | 2023-09-20 |  | 2023-09-27 |  |  |  | 2023-11-06 | 2023-12-15 | 2023-12-15 |  | NA |  | Pending Approval |  |  |  | 85115.35 | 134835.788
55 | MAG Swap | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | YR23 B1 | Spillover | MIP2023.114 | ML189832 | 2023-07-31 | MIP2023.114 | ML189833 | 2023-07-26 | Central | Selangor | 1085A | Pekan Meru | Pekan Meru | 1 |  | FO&T | 2023-09-12 |  | 2023-09-19 |  | New ODF rack |  | 2023-11-07 | 2024-03-19 | 2024-03-20 |  | NA |  | Pending Approval |  | Mar |  | 85115.35 | 134835.788
56 | MAG Swap | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | YR23 B1 | Spillover | MIP2023.114 | ML189832 | 2023-07-31 | MIP2023.114 | ML189833 | 2023-07-26 | Central | Selangor | 1110A | Berjaya Industrial Park | Berjaya Industrial Park | 1 |  | BBAND | 2023-09-20 |  | 2023-09-27 |  | New 19” Rack |  |  | 2024-05-15 | 2024-05-15 |  | NA |  | Pending Approval |  | Jun |  | 85115.35 | 134835.788
57 | MAG Swap | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | YR23 B1 | Spillover | MIP2023.114 | ML189832 | 2023-07-31 | MIP2023.114 | ML189833 | 2023-07-26 | Central | Selangor | 1128A | Kg Ola Lempik | Kg Ola Lempik | 1 |  | BBAND | 2023-10-03 |  | 2023-10-10 |  |  |  | 2023-11-08 | 2023-11-09 | 2023-11-09 |  | NA |  | Pending Approval |  |  |  | 85115.35 | 134835.788
58 | MAG Swap | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | YR23 B1 | Spillover | MIP2023.165 | ML201324 | 2023-09-15 | MIP2023.165 | ML203364 | 2023-09-25 | Central | Selangor | 1039A | Cheras Jaya 2202 | Cheras Jaya 2202 | 1 |  | FO&T | 2023-09-25 |  | 2023-10-02 |  |  |  | 2023-12-05 | 2023-12-06 | 2023-12-06 |  | NA |  | Pending Approval |  |  |  | 85115.35 | 124846.73
59 | MAG Swap | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | YR23 B1 | Spillover | MIP2023.165 | ML201324 | 2023-09-15 | MIP2023.165 | ML203364 | 2023-09-25 | Central | Selangor | 1096A | Klang Perdana | Klang Perdana | 1 |  | BBAND | 2023-09-11 |  | 2023-09-18 |  | Rectifier cabinet & 3 module |  | 2023-12-08 | 2024-04-05 | 2024-04-05 |  | NA |  | Pending Approval |  | Apr |  | 85115.35 | 124846.73
60 | MAG Swap | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | YR23 B1 | Spillover | MIP2023.165 | ML201324 | 2023-09-15 | MIP2023.165 | ML203364 | 2023-09-25 | Northern | Kedah | 4998A | Air Itam Kedah | Air Itam Kedah | 1 |  | FO&T | 2023-09-25 |  | 2023-10-02 |  |  |  | 2023-12-08 | 2023-12-22 | 2023-12-22 |  | NA |  | Pending Approval |  |  |  | 85115.35 | 124846.73
61 | MAG Swap | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | YR23 B1 | Spillover | MIP2023.165 | ML201324 | 2023-09-15 | MIP2023.165 | ML203364 | 2023-09-25 | Northern | Perak | 4455A | KTM Taiping | KTM Taiping | 1 |  | FO&T | 2023-09-25 |  | 2023-10-02 |  |  |  | 2023-12-06 | 2023-12-08 | 2023-12-08 |  | NA |  | Pending Approval |  |  |  | 85115.35 | 124846.73
62 | MAG Swap | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | YR23 B1 | Spillover | MIP2023.165 | ML201324 | 2023-09-15 | MIP2023.165 | ML203364 | 2023-09-25 | Northern | Kedah | 4992A | Pendang | Pendang | 1 |  | FO&T | 2023-10-03 |  | 2023-10-10 |  | Plinth/cooling outdoor/2 rectifier/3bank battery, Cooling cabinet 40amp x2 |  |  | 2024-06-06 |  |  | NA |  | Pending Approval |  | Jun |  | 85115.35 | 124846.73
63 | MAG Swap | MIP2023.236 CD Digi NIC ES BOQ- Swap from existing CX600 to NE8000 M14 (1554A-MAG-002) | N/A | YR23 B1 | Spillover | MIP2023.236 | ML207411 | 2023-10-17 | MIP2023.114 | ML189833 | 2023-07-26 | Southern | Melaka | 1554A | Rumbia | Rumbia | 1 |  | BBAND | 2023-11-08 |  | 2023-11-08 |  | To swap 25A to 32Ax2 |  | 2023-01-23 | 2024-02-06 | 2024-02-06 |  | NA |  | Pending Approval |  | Feb |  | 85115.35 | 134835.788
64 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7032A | RAC Radian Court | Radiant Court | 1 | Sabah, Area147 | FO&T | 2024-03-04 | 2024-03-04 | 2024-03-15 | 2023-03-21 |  |  |  | 2024-05-21 | [6 empty] | May |  | 28201.81 | 22609.3525
65 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7038A | Lokkawi | Lokkawi | 1 | Sabah, Area147 | FO&T | 2024-03-04 | 2024-03-06 | 2024-03-18 | 2024-03-22 |  |  |  | 2024-05-20 | [6 empty] | May |  | 28201.81 | 22609.3525
66 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7702A | BONGAWAN TRUNK_RTN02 | Bongawan | 1 | Sabah, Area147 | FO&T | 2024-03-04 | 2024-03-06 | 2024-03-18 | 2024-03-22 |  |  |  | Jun | [6 empty] | May |  | 28201.81 | 22609.3525
67 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7703A | Beaufort Trunk | Beaufort | 1 | Sabah, Area147 | FO&T | 2024-03-04 | 2024-03-06 | 2024-03-18 | 2024-03-22 | [10 empty] | May |  | 28201.81 | 22609.3525
68 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7704A | Menumbok | Menumbok | 1 | Sabah, Area147 | FO&T | 2024-03-04 | 2024-03-06 | 2024-03-18 | 2024-03-22 | [10 empty] | May |  | 28201.81 | 22609.3525
69 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7013A | Jln Airport | Jln Airport | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-07 | 2024-03-18 | 2024-03-22 |  |  |  | Jun | [6 empty] | May |  | 28201.81 | 22609.3525
70 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7035A | Wisma Shing Yin | Wisma Shing Yin | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-06 | 2024-03-15 | 2024-03-22 |  |  |  | 2024-05-23 | [6 empty] | May |  | 28201.81 | 22609.3525
71 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7084A | IOFC | IOFC | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-05 | 2024-03-15 | 2024-03-22 | [10 empty] | Jun |  | 28201.81 | 22609.3525
72 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Labuan | 7705A | Kg Bebuluh Laut | Labuan Trunk | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-05 | 2024-03-15 | 2024-03-22 |  |  |  | 2024-05-24 | [6 empty] | Jun |  | 28201.81 | 22609.3525
73 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7037A | Wisma Muis | Wisma Muis | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-04 | 2024-03-15 | 2024-03-21 |  |  |  | Jun | [6 empty] | Jun |  | 28201.81 | 22609.3525
74 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7039A | Donggongon | Donggongon | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-04 | 2024-03-15 | 2024-03-22 |  |  |  | Jun | [6 empty] | Jun |  | 28201.81 | 22609.3525
75 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7267A | Tmn Penampang PH2 | Tmn Penampang PH2 | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-04 | 2024-03-15 | 2023-03-21 |  |  |  | Jun | [6 empty] | Jun |  | 28201.81 | 22609.3525
76 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Sabah | Sabah | 7701A | PAPAR TRUNK-RTN01 | Papar Trunk | 1 | Sabah, Area147 | FO&T | 2024-02-28 | 2024-03-09 | 2024-03-15 | 2024-03-22 |  |  |  | Jun | [6 empty] | Jun |  | 28201.81 | 22609.3525
77 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1304A | MMA | MMA | 1 | Area154, | BBAND | 2024-02-27 | 2024-03-08 | 2024-03-11 | 2024-03-15 | [10 empty] | Jun |  | 28201.81 | 22609.3525
78 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1822B | Mardi(ZED) | Mardi(ZED) | 1 | Area69, | BBAND | 2024-03-01 | 2024-03-29 | 2024-04-03 | 2024-04-08 |  |  |  | 2024-05-23 | [6 empty] | Jun |  | 28201.81 | 22609.3525
79 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1184A | Indah Villa | Indah Villa | 2 | Area79 | BBAND | 2024-03-05 | pending access | [12 empty] | Jun |  | 28201.81 | 22609.3525
80 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1184A | Indah Villa | Indah Villa | 2 | Area79 | BBAND | 2024-03-05 | pending access | [12 empty] | Jun |  | 28201.81 | 22609.3525
81 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1409A | Kota Damansara | Kota Damansara | 2 | C0105P, Area74 | BBAND | 2024-02-28 | 2024-03-11 | 2024-03-15 | 2024-03-20 | [10 empty] | Jun |  | 28201.81 | 22609.3525
82 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1409A | Kota Damansara | Kota Damansara | 2 | C0105P, Area74 | BBAND | 2024-02-28 | 2024-03-11 | 2024-03-15 | 2024-03-20 | [10 empty] | Jun |  | 28201.81 | 22609.3525
83 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | Plaza Pengkalen | 2 | C0207, Area79 | BBAND | 2024-03-08 | pending access | pending access | [11 empty] | Jun |  | 28201.81 | 22609.3525
84 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | Plaza Pengkalen | 2 | C0207, Area79 | BBAND | 2024-03-08 | pending access | pending access | [11 empty] | Jun |  | 28201.81 | 22609.3525
85 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 2878A | Mont Kiara | Mont Kiara | 1 | C0210P, Area79 | BBAND | 2024-03-05 | pending access | pending access | [11 empty] | Jun |  | 28201.81 | 22609.3525
86 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1271A | Risda | Risda Ampang | 2 | C0314P, Area151 | BBAND | 2024-03-07 | 2024-03-08 | 2024-03-15 | 2024-03-20 | [10 empty] | Jun |  | 28201.81 | 22609.3525
87 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1271A | Risda | Risda Ampang | 2 | C0314P, Area151 | BBAND | 2024-03-07 | 2024-03-08 | 2024-03-15 | 2024-03-20 | [10 empty] | Jun |  | 28201.81 | 22609.3525
88 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1437A | Deliq | Deliq | 1 | CT0212P, Area79 | BBAND | 2024-03-08 | pending access | [5 empty] | 2024-05-21 | [6 empty] | Jun |  | 28201.81 | 22609.3525
89 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1259A | Miharja | Miharja | 1 | CT0212P, Area79 | BBAND | 2024-03-06 | 2024-03-06 | 2024-03-10 | 2024-03-15 | [10 empty] | Jun |  | 28201.81 | 22609.3525
90 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1745A | Baitumal | Baitulmal | 1 | CT0212P, Area79 | BBAND | 2024-02-28 | 2024-03-04 | 2024-03-15 | 2024-03-21 | [10 empty] | Jun |  | 28201.81 | 22609.3525
91 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1918A | Damansara Intan | Damansara Intan | 2 | CT0239P, Area79 | BBAND | 2024-03-08 | 2024-03-08 | 2024-03-22 | 2024-03-22 |  |  |  | Jun | [6 empty] | Jun |  | 28201.81 | 22609.3525
92 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1918A | Damansara Intan | Damansara Intan | 2 | CT0239P, Area79 | BBAND | 2024-03-08 | 2024-03-08 | 2024-03-22 | 2024-03-22 |  |  |  | Jun | [6 empty] | Jul |  | 28201.81 | 22609.3525
93 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1899A | Berjaya Time Square Indoor -CAS | Berjaya Time Square Indoor -CAS | 2 | CT0242P, Area79 | BBAND | 2024-03-06 | 2024-03-07 | 2024-03-21 | 2024-03-21 | [10 empty] | Jul |  | 28201.81 | 22609.3525
94 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1896A | Berjaya Times Square CAS 2 | Berjaya Times Square CAS 2 | 1 | CT0242P, Area79 | BBAND | 2024-03-06 | 2024-03-07 | 2024-03-15 | 2024-03-20 | [10 empty] | Jul |  | 28201.81 | 22609.3525
95 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1899A | Berjaya Time Square Indoor -CAS | Berjaya Time Square Indoor -CAS | 2 | CT0242P, Area79 | BBAND | 2024-03-06 | 2024-03-07 | 2024-03-21 | 2024-03-21 | [10 empty] | Jul |  | 28201.81 | 22609.3525
96 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1461A | Shaw Parade | Shaw Parade(RT) | 1 | CT0242P, Area79 | BBAND | 2024-03-01 | Pending access | [12 empty] | Jul |  | 28201.81 | 22609.3525
97 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1246A | Complex Nagaria | BERJAYA PLAZA | 1 | CT0242P, Area79 | BBAND | 2024-02-28 | 2024-03-08 | 2024-03-15 | 2024-03-20 |  |  |  | Jun | [6 empty] | Jul |  | 28201.81 | 22609.3525
98 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1063B | BERJAYA TIMES SQUARE | BERJAYA TIME SQUARE | 2 | CT0242P, Area79 | BBAND | 2024-03-06 | 2024-03-08 | 2024-03-15 | 2024-03-21 | [10 empty] | Jul |  | 28201.81 | 22609.3525
99 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1063B | BERJAYA TIMES SQUARE | BERJAYA TIME SQUARE | 2 | CT0242P, Area79 | BBAND | 2024-03-06 | 2024-03-08 | 2024-03-15 | 2024-03-21 | [10 empty] | Jul |  | 28201.81 | 22609.3525
100 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1722E | UE3 Plaza | UE3 Plaza | 2 | CT0242P, Area79 | BBAND | 2024-02-29 | Pending access | [12 empty] | Jul |  | 28201.81 | 22609.3525
101 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Central | Selangor | 1722E | UE3 Plaza | UE3 Plaza | 2 | CT0242P, Area79 | BBAND | 2024-02-29 | Pending access | [12 empty] | Jul |  | 28201.81 | 22609.3525
102 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Southern | Johor | 6126A | KTM KLUANG | KTM Kluang | 1 | Area92, | BBAND | 2024-03-01 | 2024-03-18 | 2024-03-26 | 2024-04-02 | [10 empty] | Jul |  | 28201.81 | 22609.3525
103 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Southern | Johor | 6106A | Parit Raja Industry | Parit Raja Industry | 1 | Area92, | BBAND | 2024-03-01 | 2024-03-18 | 2024-03-26 | 2024-04-04 | [10 empty] | Jul |  | 28201.81 | 22609.3525
104 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Southern | Negeri Sembilan | 1608A | KTM SEREMBAN | KTM Seremban | 1 | Area98, ST27P | BBAND | 2024-03-01 | 2024-03-15 | 2024-03-25 | 2024-04-04 |  |  |  | 2024-04-18 | 2024-04-18 | [5 empty] | Jul |  | 28201.81 | 22609.3525
105 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Southern | Johor | 6708A | Kg Penyabong (trunk) | Kg Penyabong (trunk) | 1 | Area81, SL732P | BBAND | 2024-02-28 | 2024-03-15 | 2024-03-27 | 2024-04-04 |  |  |  | 2024-06-04 | [6 empty] | Jul |  | 28201.81 | 22609.3525
106 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Southern | Melaka | 2337B | Kg Padang Ayer Molek | Kg Padang Ayer Molek | 1 | Area90, SAR03 | BBAND | 2024-03-04 | 2024-03-15 | 2024-03-21 | 2024-04-04 | [10 empty] | Jul |  | 28201.81 | 22609.3525
107 | PFS Swap | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.331 | ML229739 | 2024-02-20 | MIP2023.331 | ML220139 | 2023-12-20 | Southern | Johor | 6405A | Sri Bunian | Sri Bunian | 1 | Aea97, S311PM | BBAND | 2024-03-01 | 2024-03-20 | 2024-03-28 | 2024-04-03 | [10 empty] | Jul |  | 28201.81 | 22609.3525
108 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Eastern | Kelantan | 8223A | Jalan Pengkalan Chepa |  | 1 |  | Advance | 2024-02-21 | 2024-02-21 | 2024-03-13 | TBC |  |  |  | 2024-06-26 | [6 empty] | Jul | from 1878B re-deploy to 8223A Jalan Pengkalan Chepa | 23125.5538 | 21324.2305
109 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1360A | Hicom Glenmarie | Hicom Glenmarie | 1 |  | Advance | 2024-02-26 | 2024-03-12 | WIP | TBC |  |  |  | 2024-06-25 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
110 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 2632A | Ecopark | Ecopark | 1 |  | Advance | 2024-02-21 | 2024-02-21 | WIP | TBC |  |  |  | 2024-05-28 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
111 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1775A | Kuvithiru Printers | Kuvithiru Printers | 1 |  | Advance | 2024-02-26 | 2024-03-06 | WIP | TBC |  |  |  | 2024-06-20 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
112 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 |  |  | 8020A |  |  | 1 |  | Advance | 2024-02-26 | Site Drop | [5 empty] | 2024-06-26 | [6 empty] | Jul | from 1058A re-deploy to 8020A | 23125.5538 | 21324.2305
113 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1157A | Sg. Nibong | Sg. Nibong | 1 |  | Advance | 2024-02-27 | 2024-02-28 | WIP | TBC | [10 empty] | Jul |  | 23125.5538 | 21324.2305
114 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1777A | Sek 4 Bdr Baru Bangi | Sek 4 Bdr Baru Bangi | 1 |  | Advance | 2024-02-29 | 2024-02-29 | WIP | TBC |  |  |  | 2024-05-16 | 2024-05-16 | [5 empty] | Jul |  | 23125.5538 | 21324.2305
115 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Wilayah Persekutuan Putrajaya | 3440A | Jln Mega Mendung | Jln Mega Mendung | 1 |  | Advance | 2024-03-07 | Celcom Ptw | [5 empty] | 2024-06-26 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
116 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1627B | Pulau Indah Highway(ZED) | Pulau Indah Highway(ZED) | 1 |  | Advance | 2024-03-11 | 2024-03-05 | WIP | TBC |  |  |  | 2024-05-15 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
117 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Southern | Negeri Sembilan | 1698A | JBA Seremban 2 |  | 1 |  | Advance | 2024-03-08 | Site Drop | [5 empty] | 2024-06-13 | [6 empty] | Jul | FROM 2884B re-deploy to 1698A JBA Seremban 2 | 23125.5538 | 21324.2305
118 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1195A | Jln 19 Shoplot | Jln 19 Shoplot | 1 |  | Advance | 2024-03-05 | 2024-01-04 | WIP | TBC |  |  |  | 2024-06-21 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
119 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Wilayah Persekutuan Putrajaya | 1880B | KG LIMAU MANIS (CELCOM) | KG LIMAU MANIS (CELCOM) | 1 |  | Advance | 2024-03-05 | 2024-03-06 | WIP | TBC |  |  |  | 2024-05-23 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
120 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1723A | Tmn Sri Petaling | Tmn Sri Petaling | 1 |  | Advance | 2024-03-01 | WIP | [5 empty] | 2024-06-12 | [6 empty] | Jul |  | 23125.5538 | 21324.2305
121 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1040A | 13Cheras | 13Cheras | 1 |  | Advance | 2024-03-05 | 2024-03-01 | WIP | TBC | [10 empty] | Jul |  | 23125.5538 | 21324.2305
122 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1090A | Hin Hua | Hin Hua | 1 |  | Advance | 2024-03-06 | Access Approval Pending | [5 empty] | 2024-06-27 | [6 empty] | May |  | 23125.5538 | 21324.2305
123 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 3411B | REKO SENTRAL | REKO SENTRAL | 1 |  | Advance | 2024-02-29 | Owner Issue | [5 empty] | 2024-06-25 | [6 empty] | May |  | 23125.5538 | 21324.2305
124 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 2278A | Psiaran Sg Long 7A | Psiaran Sg Long 7A | 1 |  | Advance | 2024-03-07 | WIP | [12 empty] | May |  | 23125.5538 | 21324.2305
125 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1902B | Bdr Sg Long 3 | Bdr Sg Long 3 | 1 |  | Advance | 2024-03-07 | 2024-02-26 | 2024-03-13 | TBC | [10 empty] | May |  | 23125.5538 | 21324.2305
126 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1967A | KAP Sport | KAP Sport | 1 |  | Advance | 2024-03-08 | 2024-02-28 | 2024-03-13 | TBC | [10 empty] | May |  | 23125.5538 | 21324.2305
127 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1007A | Mimaland | Mimaland | 1 |  | Advance | 2024-02-28 | 2024-03-01 | WIP | TBC |  |  |  | 2024-06-24 | [6 empty] | May |  | 23125.5538 | 21324.2305
128 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1121A | Bkt Changgang | Bkt Changgang | 1 |  | Advance | 2024-03-07 | WIP | [5 empty] | 2024-06-20 | [6 empty] | May |  | 23125.5538 | 21324.2305
129 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Negeri Sembilan | 1661A | PAJAM | PAJAM | 1 |  | Advance | 2024-03-15 | 2024-03-06 | 2024-03-13 | TBC |  |  |  | 2024-05-23 | 2024-05-23 | [5 empty] | May |  | 23125.5538 | 21324.2305
130 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1223A | Kg Tunku | Kg Tunku | 1 |  | Advance | 2024-03-14 | Pending | [5 empty] | 2024-06-10 | [6 empty] | May |  | 23125.5538 | 21324.2305
131 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 3412A | RAHMAN_PUTRA1 | RAHMAN_PUTRA1 | 1 |  | Advance | 2024-03-13 | WIP | [5 empty] | 2024-06-10 | [6 empty] | May |  | 23125.5538 | 21324.2305
132 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1146A | Kuala Kubu Baru Tower | Kuala Kubu Baru Tower | 1 |  | Advance | 2024-03-15 | WIP | [5 empty] | 2024-06-13 | [6 empty] | May |  | 23125.5538 | 21324.2305
133 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 |  |  | 6397A | Tmn Sri Orkid(D Harmoni) |  | 1 |  | Advance | 2024-03-14 | Site Drop | [12 empty] | May | from 2968B re-deploy to 6937A Tmn Sri Orkid(D Harmoni) | 23125.5538 | 21324.2305
134 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 |  |  | 8260A |  |  | 1 |  | Advance | 2024-03-06 | Site Drop | [5 empty] | 2024-06-27 | [6 empty] | May | FROM 2901B re-deploy to 8260A | 23125.5538 | 21324.2305
135 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 |  |  | 8379B |  |  | 1 |  | Advance | 2024-03-12 | Site Drop | [5 empty] | 2024-06-06 | [6 empty] | May | FROM 1070A re-deploy to 8379B | 23125.5538 | 21324.2305
136 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1735A | Tmn Bukit Angkasa | Tmn Bkt Angkasa | 1 |  | Advance | 2024-03-07 | WIP | [5 empty] | 2024-06-25 | [6 empty] | May |  | 23125.5538 | 21324.2305
137 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Wilayah Persekutuan Putrajaya | 3531C | TM exchange putrajaya | Tm Exchange Putrajaya | 1 |  | Advance | 2024-03-08 | Access Approval Pending | [5 empty] | 2024-06-27 | [6 empty] | May |  | 23125.5538 | 21324.2305
138 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1093A | Kian Hoe Huat | Putrajaya | 1 |  | Advance | 2024-03-15 | WIP | [5 empty] | 2024-06-20 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
139 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 |  |  | 1016A |  |  | 1 |  | Advance | 2024-03-06 | 2024-03-01 | WIP | TBC |  |  |  | 2024-06-05 | [6 empty] | Jun | FROM 1264A re-deploy to 1016A | 23125.5538 | 21324.2305
140 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1213A | Puchong Maju V5 | Puchong Maju V5 | 1 |  | Advance | 2024-02-29 | 2024-02-27 | WIP | TBC |  |  |  | 2024-06-05 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
141 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1402A | Jln Ind Puchong | Jln Ind Puchong | 1 |  | Advance | 2024-02-29 | 2024-02-26 | WIP | TBC |  |  |  | 2024-05-24 | 2024-05-24 | [5 empty] | Jun |  | 23125.5538 | 21324.2305
142 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1422A | Kundang | Kundang | 1 |  | Advance | 2024-03-13 | WIP | [5 empty] | 2024-06-11 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
143 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 2424A | PUAS Tmn Tun Perak | PUAS Tmn Tun Perak | 1 |  | Advance | 2024-03-06 | 2024-02-26 | 2024-03-13 | TBC | [10 empty] | Jun |  | 23125.5538 | 21324.2305
144 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 2448A | Asmah Tower | Asmah Tower | 1 |  | Advance | 2024-03-06 | Access Approval Pending | [5 empty] | 2024-06-26 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
145 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1233B | TTDI Jaya Shoplot | TTDI Jaya Shoplot | 1 |  | Advance | 2024-03-07 | Access Approval Pending | [12 empty] | Jun |  | 23125.5538 | 21324.2305
146 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1378B | PJS 10 | PJS 10 | 1 |  | Advance | 2024-02-27 | Access Approval Pending | [5 empty] | 2024-06-26 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
147 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1179A | Indera Subang | Indera Subang | 1 |  | Advance | 2024-02-28 | Access Approval Pending | [5 empty] | 2024-06-06 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
148 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1079A | Harpsoon | Harpsoon | 1 |  | Advance | 2024-03-11 | Access Approval Pending | [5 empty] | 2024-06-27 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
149 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 2722A | Anggerik Eria | Anggerik Eria | 1 |  | Advance | 2024-03-11 | 2024-03-06 | WIP | TBC |  |  |  | 2024-05-24 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
150 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1266B | CherasJaya Industrial | CherasJaya Industrial | 1 |  | Advance | 2024-03-08 | Access Approval Pending | [5 empty] | 2024-06-19 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
151 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1201A | Stellar | Stellar | 1 |  | Advance | 2024-02-29 | 2024-02-28 | 2024-03-13 | TBC |  |  |  | 2024-06-21 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
152 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1995B | Common MDF KLIA | Common MDF KLIA | 1 |  | Advance | 2024-03-15 | Access Approval Pending | [5 empty] | 2024-06-19 | [6 empty] | Jun |  | 23125.5538 | 21324.2305
153 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Pahang | 1015A | Awana Golf &Country | Awana Golf &Country | 1 |  | Advance | 2024-03-14 | Pending | [5 empty] | 2024-05-21 | 2024-05-21 | [5 empty] | Jun |  | 23125.5538 | 21324.2305
154 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1088A | Bkt Naga | Bkt Naga | 1 |  | Advance | 2024-02-27 | 2024-02-27 | 2024-03-13 | TBC |  |  |  | 2024-05-24 | [6 empty] | Apr |  | 23125.5538 | 21324.2305
155 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1950A | Tmn Desa Ria | Tmn Desa Ria | 1 |  | Advance | 2024-02-28 | 2024-02-28 | 2024-03-13 | TBC |  |  |  | 2024-06-14 | [6 empty] | Apr |  | 23125.5538 | 21324.2305
156 | MAC Swap | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B1 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1362B | Kelana Business Centre | Kelana Business Centre | 1 |  | Advance | 2024-03-13 | WIP | [5 empty] | 2024-06-21 | [6 empty] | Apr |  | 23125.5538 | 21324.2305
157 | MAC Swap - BR | MIP2023.269 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N106+ V2 | N/A | YR24 Q1 | Q1 | MIP2023.269 | ML229489 | 2024-02-08 | MIP2023.269 | ML217576 | 2023-12-07 | Northern | Kedah | 4966A | Kulim Hi-Tech Tower | Kulim Hi Tech | 1 | N106 | FO&T | 2024-03-04 | 2024-03-08 | 2024-03-18 |  |  |  |  | 2024-06-07 | [6 empty] | Apr |  | 28201.81 | 34000.9254
158 | MAC Swap - BR | MIP2023.269 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N106+ V2 | N/A | YR24 Q1 | Q1 | MIP2023.269 | ML229489 | 2024-02-08 | MIP2023.269 | ML217576 | 2023-12-07 | Northern | Kedah | 4683A | Bkt Tok Alang | Bkt Tok Alang | 1 | N106 | FO&T | 2024-03-04 | 2024-03-08 | 2024-03-18 |  |  |  |  | 2024-06-07 | [6 empty] | Apr |  | 28201.81 | 34000.9254
159 | MAC Swap - BR | MIP2023.271 CD Digi NIC FTK EQ BOQ- 2024Q1 600 site list accelerate ZTE- N115+ - V2 | N/A | YR24 Q1 | Q1 | NA | NA | NA | MIP2023.271 | ML217579 | 2023-12-07 | Northern | Kedah | 4770A | Toklin (Trunk ) | Toklin (Trunk ) | 1 | N115 | FO&T | TBA | TBA | TBA | TBA |  |  |  | 2024-06-05 | [6 empty] | Apr |  |  | 19093.0056
160 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1409A | Kota Damansara | Kota Damansara |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
161 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 1085A | Pekan Meru | Pekan Meru |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
162 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | Central | Selangor | 2777C | JBA Bkt Lipat (TX REL - Celcom) | JBA Bkt Lipat (TX REL - Celcom) |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
163 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 1 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
164 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 2 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
165 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 3 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
166 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 4 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
167 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 5 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
168 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 6 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
169 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 7 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
170 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 8 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
171 | Exp 100G Cards | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | YR24 B2 | Q1 | MIP2023.330 | ML230330 | 2024-02-20 | MIP2023.330 | ML221416 | 2023-12-20 | TBA | TBA | Site 9 | #N/A | TBA |  |  |  | NA |  | NA | [13 empty] | 23125.5538 | 21324.2305
172 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan | 2 |  | BBAND | 2024-03-07 | 2024-03-20 | 2024-03-22 | [11 empty] | May |  | 85115.35 | 123380.5468
173 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan | 2 |  | BBAND | 2024-03-07 | 2024-03-20 | 2024-03-22 | [11 empty] | May |  | 85115.35 | 123380.5468
174 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) | 3 |  | FO&T | 2024-03-05 | 2024-03-11 | 2024-03-18 | [11 empty] | May |  | 85115.35 | 123380.5468
175 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) | 3 |  | FO&T | 2024-03-05 | 2024-03-11 | 2024-03-18 | [11 empty] | May |  | 85115.35 | 123380.5468
176 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) | 3 |  | FO&T | 2024-03-05 | 2024-03-11 | 2024-03-18 | [11 empty] | May |  | 85115.35 | 123380.5468
177 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Southern | Johor | 6000A | MSC JB | MSC JB | 2 |  | BBAND | 2024-03-20 | 2024-02-18 | 2024-03-25 | [11 empty] | May |  | 85115.35 | 123380.5468
178 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Southern | Johor | 6000A | MSC JB | MSC JB | 2 |  | BBAND | 2024-03-20 | 2024-02-18 | 2024-03-25 | [11 empty] | May |  | 85115.35 | 123380.5468
179 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan | 2 |  | FO&T | 2024-02-26 | 2024-02-26 | 2024-03-01 | [11 empty] | May |  | 85115.35 | 123380.5468
180 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan | 2 |  | FO&T | 2024-02-26 | 2024-02-26 | 2024-03-01 | [11 empty] | May |  | 85115.35 | 123380.5468
181 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Sabah | Sabah | 7205A | MILE 15 TAWAU | MILE 15 TAWAU | 2 |  | FO&T | 2024-02-28 | wip | wip | [11 empty] | May |  | 85115.35 | 123380.5468
182 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Sabah | Sabah | 7205A | MILE 15 TAWAU | MILE 15 TAWAU | 2 |  | FO&T | 2024-02-28 | wip | wip | [11 empty] | Jun |  | 85115.35 | 123380.5468
183 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai | 4 |  | FO&T | 2024-02-26 | 2024-02-26 | 2024-03-18 | [11 empty] | Jun |  | 85115.35 | 123380.5468
184 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai | 4 |  | FO&T | 2024-02-26 | 2024-02-26 | 2024-03-18 | [11 empty] | Jun |  | 85115.35 | 123380.5468
185 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai | 4 |  | FO&T | 2024-02-26 | 2024-02-26 | 2024-03-18 | [11 empty] | Jun |  | 85115.35 | 123380.5468
186 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai | 4 |  | FO&T | 2024-02-26 | 2024-02-26 | 2024-03-18 | [11 empty] | Jun |  | 85115.35 | 123380.5468
187 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC | 1 |  | BBAND | 2024-03-05 | 2024-02-18 | 2024-03-22 | [11 empty] | Jun |  | 85115.35 | 123380.5468
188 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Eastern | Pahang | 8703A | Kg. Awah | Kg. Awah | 1 |  | BBAND | 2024-03-07 | 2024-02-20 | 2024-03-22 | [11 empty] | Jul |  | 85115.35 | 123380.5468
189 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Southern | Johor | 6407B | Mersing REL | Mersing REL | 1 |  | BBAND | 2024-02-28 | 2024-02-20 | 2024-03-22 | [11 empty] | Jul |  | 85115.35 | 123380.5468
190 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Southern | Johor | 6707A | Kg Jambi (Trunk) | Kg Jambi (Trunk) | 1 |  | BBAND | 2024-02-28 | 2024-02-21 | 2024-03-22 | [11 empty] | Jul |  | 85115.35 | 123380.5468
191 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Sabah | Sabah | 7570A | Kg. Garinono | Kg. Garinono | 2 |  | FO&T | TBA | TBA | TBA | TBA | [10 empty] | Jul | Relocate to 7570A-MAG-002 from 7124A Land Trig Hill | 85115.35 | 123380.5468
192 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Sabah | Sabah | 7570A | Kg. Garinono | Kg. Garinono | 2 |  |  | TBA | TBA | TBA | TBA | [10 empty] | Jul | Relocate to 7570A-MAG-001 from 4404A Kg Jering Tower Manjung | 85115.35 | 123380.5468
193 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Eastern | Kelantan | 8285A | Bukit Bunga | Bukit Bunga | 1 |  | BBAND | 2024-03-08 | 2024-03-11 | 2024-03-15 | 2024-03-18 |  |  |  | 2024-05-28 | [6 empty] | Jul |  | 85115.35 | 123380.5468
194 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Eastern | Terengganu | 8314A | Gong Terap | Gong Terap | 1 |  | BBAND | 2024-02-23 | 2024-02-23 | 2024-03-15 | 2024-03-20 | [10 empty] | Jul |  | 85115.35 | 123380.5468
195 | MAG Swap | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | YR24 B2 | Q1 | MIP2023.332 | ML229741 | 2024-02-20 | MIP2023.332 | ML221415 | 2023-12-20 | Southern | Johor | 6405A | Sri Bunian | Sri Bunian | 1 |  | BBAND | 2024-03-01 | 2024-03-20 | 2024-03-28 | 2024-04-03 | [10 empty] | Jul |  | 85115.35 | 123380.5468
196 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Selangor | 1006A | JBA Gombak | JBA Gombak | 1 | CAR04 | BBAND | 2024-03-01 | 2024-03-12 | 2024-03-22 | [11 empty] | Jul |  | 40207.3406 | 217405.4922
197 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1304A | MMA | MMA | 1 | CAR04 | BBAND | 2024-02-27 | 2024-03-08 | 2024-03-11 | 2024-03-15 | [10 empty] | Jun |  | 40207.3406 | 217405.4922
198 | Exp 100G Cards | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1745A | Baitumal | Baitumal |  | CAR04 | BBAND | NA |  | NA | [13 empty] | 40207.3406 | 217405.4922
199 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1458A | Endah Parade | Endah Parade | 1 | CAR04 | BBAND | 2024-02-28 | 2024-03-18 | 2024-03-26 | [11 empty] | Jun |  | 40207.3406 | 217405.4922
200 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | MSC Damansara | 2 | CAR04 | BBAND | 2024-02-28 | 2024-03-27 | [12 empty] | Jun |  | 40207.3406 | 217405.4922
201 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | MSC Damansara | 2 | CAR04 | BBAND | 2024-02-28 | 2024-03-27 | [12 empty] | Jun |  | 40207.3406 | 217405.4922
202 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan | 2 | CAR04 | BBAND | 2024-02-26 | 2024-02-26 | 2024-03-01 | [11 empty] | Jun |  | 40207.3406 | 217405.4922
203 | MAG Swap - BR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | MIP2023.334 | ML220138 | 2023-12-20 | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan | 2 | CAR04 | BBAND | 2024-02-26 | 2024-02-26 | 2024-03-01 | [11 empty] | Jun |  | 40207.3406 | 217405.4922
204 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 2011E | Westport Building | West Port Building | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Mar |  | 28201.81 | 24821.2241
205 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1149E | Westport T1 | (L3 Smallcell)West | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Mar |  | 28201.81 | 24821.2241
206 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1127E | West Port CT9 Pole | (L3 Smallcell) West Port CT9 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [5 empty] | 2024-05-27 | 2024-05-27 | [5 empty] | Mar |  | 28201.81 | 24821.2241
207 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1020E | West Port CT8-1 Pole | (L3 Smallcell) West Port CT8 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Mar |  | 28201.81 | 24821.2241
208 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1151E | Westport T3 | (L3 Smallcell)West Port T3 CT7-1 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Mar |  | 28201.81 | 24821.2241
209 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1019E | West Port CT6-1 Pole | (L3 Smallcell) West Port CT6 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Apr |  | 28201.81 | 24821.2241
210 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1018E | West Port CT4-2 Pole | (L3 Smallcell) West Port CT4 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Apr |  | 28201.81 | 24821.2241
211 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1150E | Westport T2 | (L3 Smallcell) West Port T2 CT4-1 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Apr |  | 28201.81 | 24821.2241
212 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 1017E | West Port CT3-1 Pole | (L3 Smallcell) West Port CT3 | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Apr |  | 28201.81 | 24821.2241
213 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 3864E | Westport | West Port Tower Block | 1 |  | Advance | 18/3/2024 - 20/3/2024 | Access Approval Pending | [12 empty] | Apr |  | 28201.81 | 24821.2241
214 | MAC Swap | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | YR24 B1 | Q1 | MIP2023.239 | ML229740 | 2024-02-20 | MIP2023.239 | ML217745 | 2023-12-08 | Central | Selangor | 3404A | Telok Gong (REL) | (L3 Smallcell) Teluk Gong | 1 |  | Advance | 2024-03-13 | 2024-03-05 | WIP | TBC | [10 empty] | Apr |  | 28201.81 | 24821.2241
215 | MAG Swap - BR | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | YR24 Q1 | Q1 | MIP2023.276 | ML230328 | 2024-02-20 | MIP2023.277 | ML218281 | 2023-12-08 | Central | Selangor | 2021B | DiGi TOC (Lot 43) | SHT | 1 | NAR01_i+ |  | 2024-03-05 | 2024-03-11 | 2024-03-18 | [11 empty] | Apr | Relocate to 2021B SHT from 4992A Pendang | 42958.9929 | 150190.5725
216 | MAG Swap - BR | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | YR24 Q1 | Q1 | MIP2023.276 | ML230328 | 2024-02-20 | MIP2023.277 | ML218281 | 2023-12-08 | Northern | Kedah | 4946A | Bukit Selambau | Bukit Selambau | 1 | NAR01_i+ | FO&T | 2024-02-05 | 2024-03-07 | 2024-03-18 | [11 empty] | Apr |  | 42958.9929 | 150190.5725
217 | MAG Swap - BR | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | YR24 Q1 | Q1 | MIP2023.276 | ML230328 | 2024-02-20 | MIP2023.277 | ML218281 | 2023-12-08 | Northern | Kedah | 4966A | Kulim Hi-Tech Tower | Kulim Hitech | 1 | NAR01_i+ | FO&T | 2024-03-04 | 2024-03-08 | 2024-03-18 | [11 empty] | Apr |  | 42958.9929 | 150190.5725
218 | MAG Swap - BR | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | YR24 Q1 | Q1 | MIP2023.277 | ML229738 | 2024-02-20 | MIP2023.276 | ML218282 | 2023-12-08 | Northern | Kedah | 4998A | Air Itam Kedah | Air Itam Kedah | 1 | NAR01_ii+ |  | TBA | TBA | TBA | TBA | [10 empty] | Apr | Spare to assign | 48541.935 | 183991.01
219 | MAG Swap - BR | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | YR24 Q1 | Q1 | MIP2023.277 | ML229738 | 2024-02-20 | MIP2023.276 | ML218282 | 2023-12-08 | Northern | Kedah | 4660A | KTM A.setar | KTM Alor Setar | 1 | NAR01_ii+ | FO&T | 2024-02-05 | 2024-03-08 | 2024-03-18 | [11 empty] | Apr |  | 48541.935 | 183991.01
220 | MAG Swap - BR | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | YR24 Q1 | Q1 | MIP2023.277 | ML229738 | 2024-02-20 | MIP2023.276 | ML218282 | 2023-12-08 | Northern | Kedah | 4938A | Taman Orkid | Taman Orkid | 1 | NAR01_ii+ | FO&T | 2024-02-06 | 2024-03-06 | 2024-03-18 | [11 empty] | Apr |  | 48541.935 | 183991.01
221 | IP BREAK RING | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | YR23 Q3 Q4 | Spillover | MIP2023.42 | ML177398 | 2023-05-22 | NA | NA | NA | Southern | Negeri Sembilan | 1649A | KUALA LUKUT | KUALA LUKUT |  | S102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-06-07 | 2023-06-07 | [7 empty] | 9746.684
222 | IP BREAK RING | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | YR23 Q3 Q4 | Spillover | MIP2023.42 | ML177398 | 2023-05-22 | NA | NA | NA | Southern | Negeri Sembilan | 1690A | Bukit Pelandok (DWDM) | Bukit Pelandok (DWDM) |  | S102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-06-07 | 2023-06-07 | [7 empty] | 9746.684
223 | IP BREAK RING | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | YR23 Q3 Q4 | Spillover | MIP2023.42 | ML177398 | 2023-05-22 | NA | NA | NA | Southern | Negeri Sembilan | 1640A | POLITEKNIK PORT DICKSON (KJS TW) | POLITEKNIK PORT DICKSON (KJS TW) |  | S102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-06-07 | 2023-06-07 | [7 empty] | 9746.684
224 | IP BREAK RING | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | YR23 Q3 Q4 | Spillover | MIP2023.42 | ML177398 | 2023-05-22 | NA | NA | NA | Southern | Negeri Sembilan | 1634A | LUKUT | LUKUT |  | S102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-06-07 | 2023-06-07 | [7 empty] | 9746.684
225 | IP BREAK RING | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | YR23 Q3 Q4 | Spillover | MIP2023.42 | ML177398 | 2023-05-22 | NA | NA | NA | Southern | Negeri Sembilan | 3148A | Tmn Abd Dato Samad | Tmn Abd Dato Samad |  | S102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-06-07 | 2023-06-07 | [7 empty] | 9746.684
226 | IP BREAK RING | ML178493 MIP2023.43 CD Digi BAU ES BOQ- C0904 break ring to support for network consolidation | N/A | YR23 Q3 Q4 | Spillover | MIP2023.43 | ML178493 | 2023-05-29 | NA | NA | NA | Southern | Negeri Sembilan | 1690A | Bukit Pelandok (DWDM) | Bukit Pelandok (DWDM) |  | C0904 | FO&T | NA |  | NA |  | NA |  | NA | 2023-06-13 | 2023-06-13 | [7 empty] | 6273.15
227 | IP BREAK RING | ML178493 MIP2023.43 CD Digi BAU ES BOQ- C0904 break ring to support for network consolidation | N/A | YR23 Q3 Q4 | Spillover | MIP2023.43 | ML178493 | 2023-05-29 | NA | NA | NA | Central | Selangor | 1124A | Batu 15 Banting | Batu 15 Banting |  | C0904 | FO&T | NA |  | NA |  | NA |  | NA | 2023-06-13 | 2023-06-13 | [7 empty] | 6273.15
228 | IP BREAK RING | ML178493 MIP2023.43 CD Digi BAU ES BOQ- C0904 break ring to support for network consolidation | N/A | YR23 Q3 Q4 | Spillover | MIP2023.43 | ML178493 | 2023-05-29 | NA | NA | NA | Central | Selangor | 1130A | Kanchong Darat | Kanchong Darat |  | C0904 | FO&T | NA |  | NA |  | NA |  | NA | 2023-06-13 | 2023-06-13 | [7 empty] | 6273.15
229 | IP BREAK RING | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | YR23 Q3 Q4 | Spillover | MIP2023.46 | ML180450 | 2023-06-07 | NA | NA | NA | Central | Selangor | 1304A | MMA | MMA |  | C0204P & C0407P | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-21 | 2023-08-21 | [7 empty] | 6976.7025
230 | IP BREAK RING | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | YR23 Q3 Q4 | Spillover | MIP2023.46 | ML180450 | 2023-06-07 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1745A | Baitumal | Baitumal |  | C0204P & C0407P | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-21 | 2023-08-21 | [7 empty] | 6976.7025
231 | IP BREAK RING | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | YR23 Q3 Q4 | Spillover | MIP2023.46 | ML180450 | 2023-06-07 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | Plaza Pengkalen |  | C0204P & C0407P | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-21 | 2023-08-21 | [7 empty] | 6976.7025
232 | IP BREAK RING | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | YR23 Q3 Q4 | Spillover | MIP2023.46 | ML180450 | 2023-06-07 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1851A | KL Plaza 4th floor | KL Plaza 4th floor |  | C0204P & C0407P | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-21 | 2023-08-21 | [7 empty] | 6976.7025
233 | IP BREAK RING | MIP2023.66 CD Digi BAU ES BOQ- C0501 break ring via DWDM and new ATN910C installation at 1110A | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.66 | ML181541 | 2023-06-13 | NA | NA | NA | Central | Selangor | 1110A | Berjaya Industrial Park | Berjaya Industrial Park |  | C0501P | FO&T | NA |  | NA |  | NA |  | NA | 2023-07-06 | 2023-07-06 | [7 empty] | 22260.34
234 | IP BREAK RING | MIP2023.67 CD Digi BAU ES BOQ- C0114 break ring to support for network consolidation | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.67 | ML181539 | 2023-06-13 | NA | NA | NA | Central | Selangor | 1088A | Bkt Naga | Bkt Naga |  | C0114 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-07 | 2023-07-07 | [7 empty] | 8364.2
235 | IP BREAK RING | MIP2023.67 CD Digi BAU ES BOQ- C0114 break ring to support for network consolidation | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.67 | ML181539 | 2023-06-13 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | C0114 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-07 | 2023-07-07 | [7 empty] | 8364.2
236 | IP BREAK RING | MIP2023.67 CD Digi BAU ES BOQ- C0114 break ring to support for network consolidation | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.67 | ML181539 | 2023-06-13 | NA | NA | NA | Central | Selangor | 2631A | Samarinda | Samarinda |  | C0114 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-07 | 2023-07-07 | [7 empty] | 8364.2
237 | IP BREAK RING | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2022.145 | ML184155 | 2023-06-23 | NA | NA | NA | Eastern | Terengganu | 8408A | Bandar Cheneh | Bandar Cheneh |  | E205 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-22 | 2023-08-22 | [7 empty] | 7820.495
238 | IP BREAK RING | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2022.145 | ML184155 | 2023-06-23 | NA | NA | NA | Eastern | Terengganu | 8403A | Bukit Mentok | Bukit Mentok |  | E205 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-22 | 2023-08-22 | [7 empty] | 7820.495
239 | IP BREAK RING | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2022.145 | ML184155 | 2023-06-23 | NA | NA | NA | Eastern | Terengganu | 8483A | DESA SOLEHAH | DESA SOLEHAH |  | E205 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-22 | 2023-08-22 | [7 empty] | 7820.495
240 | IP BREAK RING | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2022.145 | ML184155 | 2023-06-23 | NA | NA | NA | Eastern | Terengganu | 8330A | Bukit Kemuning | Bukit Kemuning |  | E205 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-22 | 2023-08-22 | [7 empty] | 7820.495
241 | IP BREAK RING | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.79 | ML184532 | 2023-06-27 | NA | NA | NA | Eastern | Pahang | 8046A | Bdr Indera Mahkota | Bdr Indera Mahkota |  | E407 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-10 | 2023-08-10 | [7 empty] | 7321.8225
242 | IP BREAK RING | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.79 | ML184532 | 2023-06-27 | NA | NA | NA | Eastern | Pahang | 8050A | Permatang Badak | Permatang Badak |  | E407 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-10 | 2023-08-10 | [7 empty] | 7321.8225
243 | IP BREAK RING | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.79 | ML184532 | 2023-06-27 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan |  | E407 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-10 | 2023-08-10 | [7 empty] | 7321.8225
244 | IP BREAK RING | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.79 | ML184532 | 2023-06-27 | NA | NA | NA | Eastern | Pahang | 8025A | Pejabat Risda | Pejabat Risda |  | E407 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-10 | 2023-08-10 | [7 empty] | 7321.8225
245 | IP BREAK RING | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.106 | ML184533 | 2023-06-28 | NA | NA | NA | Central | Selangor | 1099A | Hong Fatt Auto | Hong Fatt Auto |  | CT0120 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 6976.7025
246 | IP BREAK RING | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.106 | ML184533 | 2023-06-28 | NA | NA | NA | Central | Selangor | 2632A | Ecopark | Ecopark |  | CT0120 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 6976.7025
247 | IP BREAK RING | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.106 | ML184533 | 2023-06-28 | NA | NA | NA | Central | Selangor | 1409A | Kota Damansara | Kota Damansara |  | CT0120 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 6976.7025
248 | IP BREAK RING | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.106 | ML184533 | 2023-06-28 | NA | NA | NA | Central | Selangor | 1085A | Pekan Meru | Pekan Meru |  | CT0120 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 6976.7025
249 | IP BREAK RING | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.80 | ML184587 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8033A | Kg Pandan | Kg Pandan |  | E408 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-21 | 2023-07-21 | [7 empty] | 8739.125
250 | IP BREAK RING | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.80 | ML184587 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8933A | Bt 6 Jln Gambang | Bt 6 Jln Gambang |  | E408 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-21 | 2023-07-21 | [7 empty] | 8739.125
251 | IP BREAK RING | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.80 | ML184587 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8025A | Pejabat Risda | Pejabat Risda |  | E408 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-21 | 2023-07-21 | [7 empty] | 8739.125
252 | IP BREAK RING | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.80 | ML184587 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan |  | E408 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-21 | 2023-07-21 | [7 empty] | 8739.125
253 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8035A | Balok Kg Chengal | Balok Kg Chengal |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
254 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8936A | Sg Karang | Sg Karang |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
255 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8061A | PLD Bukit Pelindung | PLD Bukit Pelindung |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
256 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8434A | Felda Neram | Felda Neram |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
257 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8023B | Balok Baru | Balok Baru |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
258 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8953A | Balok Perdana SBC | Balok Perdana SBC |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
259 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8408A | Bandar Cheneh | Bandar Cheneh |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
260 | IP BREAK RING | Support Eastern E202 MAC break ring via DWDM [E202] | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.76 | ML185575 | 2023-07-03 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan |  | E202 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-26 | 2024-03-26 | [5 empty] | Mar |  | 6970.0463
261 | PE-MCR | MIP2023.137 CD Digi NIC ES BOQ- MAG CAR01_PE-MCR + Break ring, break at 2777C (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.137 | ML189724 | 2023-07-28 | NA | NA | NA | Central | Selangor | 2777C | JBA Bkt Lipat (TX REL - Celcom) | JBA Bkt Lipat (TX REL - Celcom) |  | CAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-08 | 2023-12-08 | [7 empty] | 8267.84
262 | PE-MCR | MIP2023.137 CD Digi NIC ES BOQ- MAG CAR01_PE-MCR + Break ring, break at 2777C (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.137 | ML189724 | 2023-07-28 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | CAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-08 | 2023-12-08 | [7 empty] | 8267.84
263 | IP BREAK RING | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.105 | ML189726 | 2023-07-30 | NA | NA | NA | Central | Selangor | 1087A | Rantau Panjang | Rantau Panjang |  | C0108 / CT11P | BBAND | NA |  | NA |  | NA |  | NA | 2023-12-19 | 2023-12-19 | [7 empty] | 6976.7025
264 | IP BREAK RING | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.105 | ML189726 | 2023-07-30 | NA | NA | NA | Central | Selangor | 1080A | WIT | WIT |  | C0108 / CT11P | BBAND | NA |  | NA |  | NA |  | NA | 2023-12-19 | 2023-12-19 | [7 empty] | 6976.7025
265 | IP BREAK RING | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.105 | ML189726 | 2023-07-30 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | C0108 / CT11P | BBAND | NA |  | NA |  | NA |  | NA | 2023-12-19 | 2023-12-19 | [7 empty] | 6976.7025
266 | IP BREAK RING | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.105 | ML189726 | 2023-07-30 | NA | NA | NA | Central | Selangor | 2777C | JBA Bkt Lipat (TX REL - Celcom) | JBA Bkt Lipat (TX REL - Celcom) |  | C0108 / CT11P | BBAND | NA |  | NA |  | NA |  | NA | 2023-12-19 | 2023-12-19 | [7 empty] | 6976.7025
267 | IP BREAK RING | MIP2023.138 CD Digi NIC ES BOQ- Reengineering MAG Colocated-Ring-4- 4000A-MAC, assess on access node uplinkbreak ring | N/A | YR23 Q3 Q4 | Spillover | MIP2023.138 | ML190486 | 2023-08-01 | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai |  | Colocated-Ring-4 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-15 | 2023-08-15 | [7 empty] | 37266.05
268 | IP BREAK RING | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.159 | ML190484 | 2023-08-01 | NA | NA | NA | Central | Selangor | 1701A | Kerling Trunk | Kerling Trunk |  | C0803 | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7074.6333
269 | IP BREAK RING | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.159 | ML190484 | 2023-08-01 | NA | NA | NA | Central | Selangor | 1066A | Sg.Choh (Timecell) | Sg.Choh (Timecell) |  | C0803 | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7074.6333
270 | IP BREAK RING | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.159 | ML190484 | 2023-08-01 | NA | NA | NA | Central | Selangor | 1146A | Kuala Kubu Baru Tower | Kuala Kubu Baru Tower |  | C0803 | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7074.6333
271 | IP BREAK RING | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.159 | ML190484 | 2023-08-01 | NA | NA | NA | Central | Selangor | 1145A | Batang Kali | Batang Kali |  | C0803 | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7074.6333
272 | IP BREAK RING | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.159 | ML190484 | 2023-08-01 | NA | NA | NA | Central | Selangor | 2038A | Antara Gapi (KJS) | Antara Gapi (KJS) |  | C0803 | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7074.6333
273 | IP BREAK RING | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.159 | ML190484 | 2023-08-01 | NA | NA | NA | Central | Selangor | 1070A | Wisma Low Kang | Wisma Low Kang |  | C0803 | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7074.6333
274 | IP BREAK RING | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.88 | ML190488 | 2023-08-01 | NA | NA | NA | Southern | Melaka | 1556A | MERLIMAU | MERLIMAU |  | S309 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-10 | 2023-10-10 | [7 empty] | 11129.63
275 | IP BREAK RING | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.88 | ML190488 | 2023-08-01 | NA | NA | NA | Southern | Johor | 1599A | BKT GAMBIR TOWN | BKT GAMBIR TOWN |  | S309 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-10 | 2023-10-10 | [7 empty] | 11129.63
276 | IP BREAK RING | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.88 | ML190488 | 2023-08-01 | NA | NA | NA | Southern | Melaka | 1553A | Umbai | Umbai |  | S309 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-10 | 2023-10-10 | [7 empty] | 11129.63
277 | IP BREAK RING | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.88 | ML190488 | 2023-08-01 | NA | NA | NA | Southern | Johor | 2402B | Pagoh Highway | Pagoh Highway |  | S309 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-10 | 2023-10-10 | [7 empty] | 11129.63
278 | IP BREAK RING | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.126 | ML190489 | 2023-08-01 | NA | NA | NA | Northern | Kedah | 4952B | SELAMA KEDAH | SELAMA KEDAH | 1 | N404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-21 | 2024-02-21 | [5 empty] | Feb |  | 7419.7533
279 | IP BREAK RING | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.126 | ML190489 | 2023-08-01 | NA | NA | NA | Northern | Perak | 4454B | Kubu Gajah RDD | Kubu Gajah RDD | 1 | N404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-21 | 2024-02-21 | [5 empty] | Feb |  | 7419.7533
280 | IP BREAK RING | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.126 | ML190489 | 2023-08-01 | NA | NA | NA | Northern | Perak | 4457A | Kamunting Industry | Kamunting Industry | 1 | N404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-21 | 2024-02-21 | [5 empty] | Feb |  | 7419.7533
281 | IP BREAK RING | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.126 | ML190489 | 2023-08-01 | NA | NA | NA | Northern | Perak | 4427B | Simpang Taiping | Simpang Taiping | 1 | N404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-21 | 2024-02-21 | [5 empty] | Feb |  | 7419.7533
282 | IP BREAK RING | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.126 | ML190489 | 2023-08-01 | NA | NA | NA | Northern | Perak | 4465A | Taman Long Jaafar RDD | Taman Long Jaafar RDD | 1 | N404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-21 | 2024-02-21 | [5 empty] | Feb |  | 7419.7533
283 | IP BREAK RING | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.126 | ML190489 | 2023-08-01 | NA | NA | NA | Northern | Perak | 4455A | KTM Taiping | KTM Taiping | 1 | N404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-21 | 2024-02-21 | [5 empty] | Feb |  | 7419.7533
284 | IP BREAK RING | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.75 | ML190491 | 2023-08-01 | NA | NA | NA | Eastern | Kelantan | 8217A | Padang Tembak | Padang Tembak |  | E107 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-24 | 2023-08-24 | [7 empty] | 7321.8225
285 | IP BREAK RING | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.75 | ML190491 | 2023-08-01 | NA | NA | NA | Eastern | Kelantan | 8263A | Pasir Mas Town | Pasir Mas Town |  | E107 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-24 | 2023-08-24 | [7 empty] | 7321.8225
286 | IP BREAK RING | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.75 | ML190491 | 2023-08-01 | NA | NA | NA | Eastern | Kelantan | 8211A | Wakaf Che Yeh | Wakaf Che Yeh |  | E107 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-24 | 2023-08-24 | [7 empty] | 7321.8225
287 | IP BREAK RING | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.75 | ML190491 | 2023-08-01 | NA | NA | NA | Eastern | Kelantan | 8221A | Cherang | Cherang |  | E107 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-24 | 2023-08-24 | [7 empty] | 7321.8225
288 | PE-MCR | MIP2023.137 CD Digi NIC ES BOQ- MAG CAR01_PE-MCR + Break ring, break at 2777C (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.137 | ML189724 | 2023-07-28 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | CAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-08 | 2023-12-08 | [7 empty] | 8267.84
289 | IP BREAK RING | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.160 | ML191274 | 2023-08-08 | NA | NA | NA | Northern | Kedah | 4995A | Changloon UUM | Changloon UUM |  | N113 / N119 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 7820.495
290 | IP BREAK RING | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.160 | ML191274 | 2023-08-08 | NA | NA | NA | Northern | Kedah | 4992A | Pendang | Pendang |  | N113 / N119 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 7820.495
291 | IP BREAK RING | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.160 | ML191274 | 2023-08-08 | NA | NA | NA | Northern | Kedah | 4662A | BKT. TINGGI, ALOR RAMBAI | BKT. TINGGI, ALOR RAMBAI |  | N113 / N119 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 7820.495
292 | IP BREAK RING | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.160 | ML191274 | 2023-08-08 | NA | NA | NA | Northern | Kedah | 4678A | Jalan Langgar | Jalan Langgar |  | N113 / N119 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 7820.495
293 | IP BREAK RING | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.122 | ML191275 | 2023-08-08 | NA | NA | NA | Central | Selangor | 1169A | Tg Karang Trunk Road | Tg Karang Trunk Road |  | C0702P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-21 | 2024-05-21 | [5 empty] | May |  | 7234.93
294 | IP BREAK RING | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.122 | ML191275 | 2023-08-08 | NA | NA | NA | Central | Selangor | 1153A | Permatang K Selangor | Permatang K Selangor |  | C0702P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-21 | 2024-05-21 | [5 empty] | May |  | 7234.93
295 | IP BREAK RING | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.122 | ML191275 | 2023-08-08 | NA | NA | NA | Central | Selangor | 1156A | Btg. Berjuntai | Btg. Berjuntai |  | C0702P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-21 | 2024-05-21 | [5 empty] | May |  | 7234.93
296 | IP BREAK RING | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.122 | ML191275 | 2023-08-08 | NA | NA | NA | Central | Selangor | 1154A | Sekinchan | Sekinchan |  | C0702P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-21 | 2024-05-21 | [5 empty] | May |  | 7234.93
297 | IP BREAK RING | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.122 | ML191275 | 2023-08-08 | NA | NA | NA | Central | Selangor | 1096A | Klang Perdana | Klang Perdana |  | C0702P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-21 | 2024-05-21 | [5 empty] | May |  | 7234.93
298 | IP BREAK RING | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.89 | ML192024 | 2023-08-14 | NA | NA | NA | Southern | Melaka | 1553A | Umbai | Umbai | 1 | S501_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7820.495
299 | IP BREAK RING | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.89 | ML192024 | 2023-08-14 | NA | NA | NA | Southern | Johor | 2388B | Taman Desa Muar | Taman Desa Muar | 1 | S501_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7820.495
300 | IP BREAK RING | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.89 | ML192024 | 2023-08-14 | NA | NA | NA | Southern | Johor | 2227B | TMN SRI JERAM | TMN SRI JERAM | 1 | S501_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7820.495
301 | IP BREAK RING | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.89 | ML192024 | 2023-08-14 | NA | NA | NA | Southern | Johor | 1591A | Parit Bakar Tengah | Parit Bakar Tengah | 1 | S501_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7820.495
302 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Kelantan | 8314A | Gong Terap | Gong Terap | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
303 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Terengganu | 8429B | Bkt Payung 2 | Bkt Payung 2 | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
304 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Kelantan | 8344A | Felda Belara | Felda Belara | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
305 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Terengganu | 8361A | Batu Rakit | Batu Rakit | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
306 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Terengganu | 8353A | Kg Manir | Kg Manir | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
307 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Terengganu | 8350B | KUSTEM | KUSTEM | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
308 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Terengganu | 8354A | KUSZA Gong Badak | KUSZA Gong Badak | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
309 | IP BREAK RING | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.77 | ML192027 | 2023-08-14 | NA | NA | NA | Eastern | Terengganu | 8923B | Tmn Semarak REL | Tmn Semarak REL | 1 | E212 | FO&T | NA |  | NA |  | NA |  | NA | 2024-02-22 | 2024-02-22 | [5 empty] | Feb |  | 7219.3825
310 | IP BREAK RING | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.127 | ML192028 | 2023-08-14 | NA | NA | NA | Northern | Perak | 4493A | KTM IPOH | KTM IPOH |  | N406 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 11129.63
311 | IP BREAK RING | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.127 | ML192028 | 2023-08-14 | NA | NA | NA | Northern | Perak | 4432A | KTM Sg Siput | KTM Sg Siput |  | N406 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 11129.63
312 | IP BREAK RING | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.127 | ML192028 | 2023-08-14 | NA | NA | NA | Northern | Perak | 4496A | LAP Tasek 1&2 | LAP Tasek 1&2 |  | N406 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 11129.63
313 | IP BREAK RING | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.127 | ML192028 | 2023-08-14 | NA | NA | NA | Northern | Perak | 4536A | Tasek Industrial | Tasek Industrial |  | N406 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 11129.63
314 | IP BREAK RING | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.163 | ML192029 | 2023-08-14 | NA | NA | NA | Central | Selangor | 2070B | Sri Gombak | Sri Gombak |  | C1102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-11-07 | 2023-11-07 | [7 empty] | 7419.7533
315 | IP BREAK RING | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.163 | ML192029 | 2023-08-14 | NA | NA | NA | Eastern | Pahang | 8709A | Bentong (Trunk) | Bentong (Trunk) |  | C1102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-11-07 | 2023-11-07 | [7 empty] | 7419.7533
316 | IP BREAK RING | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.163 | ML192029 | 2023-08-14 | NA | NA | NA | Central | Selangor | 1007A | Mimaland | Mimaland |  | C1102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-11-07 | 2023-11-07 | [7 empty] | 7419.7533
317 | IP BREAK RING | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.163 | ML192029 | 2023-08-14 | NA | NA | NA | Central | Selangor | 1787B | Karak HW KM 33.9 | Karak HW KM 33.9 |  | C1102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-11-07 | 2023-11-07 | [7 empty] | 7419.7533
318 | IP BREAK RING | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.163 | ML192029 | 2023-08-14 | NA | NA | NA | Eastern | Pahang | 1770B | Genting Sempah | Genting Sempah |  | C1102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-11-07 | 2023-11-07 | [7 empty] | 7419.7533
319 | IP BREAK RING | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.163 | ML192029 | 2023-08-14 | NA | NA | NA | Eastern | Pahang | 2086A | Balai Polis Bkt Tinggi | Balai Polis Bkt Tinggi |  | C1102 | BBAND | NA |  | NA |  | NA |  | NA | 2023-11-07 | 2023-11-07 | [7 empty] | 7419.7533
320 | IP BREAK RING | MIP2023.87 CD Digi NIC ES BOQ- IPRAN re-eng for S307 (6502A, 6413A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.87 | ML192036 | 2023-08-14 | NA | NA | NA | Southern | Johor | 6502A | Nusa Perintis(Watertank) | Nusa Perintis(Watertank) |  | S307 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-17 | 2023-10-17 | [7 empty] | 10427.3267
321 | IP BREAK RING | MIP2023.87 CD Digi NIC ES BOQ- IPRAN re-eng for S307 (6502A, 6413A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.87 | ML192036 | 2023-08-14 | NA | NA | NA | Southern | Johor | 6413A | Kg Pengkalan Raja | Kg Pengkalan Raja |  | S307 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-17 | 2023-10-17 | [7 empty] | 10427.3267
322 | IP BREAK RING | MIP2023.87 CD Digi NIC ES BOQ- IPRAN re-eng for S307 (6502A, 6413A) break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.87 | ML192036 | 2023-08-14 | NA | NA | NA | Southern | Johor | 6405A | Sri Bunian | Sri Bunian |  | S307 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-17 | 2023-10-17 | [7 empty] | 10427.3267
323 | IP BREAK RING | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | YR23 Q3 Q4 | Spillover | MIP2023.150 | ML195610 | 2023-08-22 | NA | NA | NA | Northern | Perak | 4000A | MSC Prai | MSC Prai |  | N301 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-23 | 2023-08-23 | [7 empty] | 7820.495
324 | IP BREAK RING | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | YR23 Q3 Q4 | Spillover | MIP2023.150 | ML195610 | 2023-08-22 | NA | NA | NA | Northern | Kedah | 4184A | Permatang Tinggi | Permatang Tinggi |  | N301 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-23 | 2023-08-23 | [7 empty] | 7820.495
325 | IP BREAK RING | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | YR23 Q3 Q4 | Spillover | MIP2023.150 | ML195610 | 2023-08-22 | NA | NA | NA | Northern | Kedah | 4215A | Alma Kg Kijang 2 | Alma Kg Kijang 2 |  | N301 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-23 | 2023-08-23 | [7 empty] | 7820.495
326 | IP BREAK RING | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | YR23 Q3 Q4 | Spillover | MIP2023.150 | ML195610 | 2023-08-22 | NA | NA | NA | Northern | Pulau Pinang | 4188A | NIBONG TEBAL2 | NIBONG TEBAL2 |  | N301 | BBAND | NA |  | NA |  | NA |  | NA | 2023-08-23 | 2023-08-23 | [7 empty] | 7820.495
327 | IP BREAK RING | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.90 | ML195607 | 2023-08-22 | NA | NA | NA | Southern | Negeri Sembilan | 1640A | POLITEKNIK PORT DICKSON (KJS TW) | POLITEKNIK PORT DICKSON (KJS TW) |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-26 | 2023-10-26 | [7 empty] | 8531.2625
328 | IP BREAK RING | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.90 | ML195607 | 2023-08-22 | NA | NA | NA | Southern | Melaka | 1552A | Tanjung Bidara | Tanjung Bidara |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-26 | 2023-10-26 | [7 empty] | 8531.2625
329 | IP BREAK RING | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.90 | ML195607 | 2023-08-22 | NA | NA | NA | Southern | Melaka | 1554A | Rumbia | Rumbia |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-26 | 2023-10-26 | [7 empty] | 8531.2625
330 | IP BREAK RING | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.90 | ML195607 | 2023-08-22 | NA | NA | NA | Southern | Negeri Sembilan | 1690A | Bukit Pelandok (DWDM) | Bukit Pelandok (DWDM) |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-26 | 2023-10-26 | [7 empty] | 8531.2625
331 | IP BREAK RING | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.174 | ML196714 | 2023-08-25 | NA | NA | NA | Northern | Perak | 4493A | KTM IPOH | KTM IPOH |  | N407 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7580.05
332 | IP BREAK RING | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.174 | ML196714 | 2023-08-25 | NA | NA | NA | Northern | Perak | 4515A | TG RAMBUTAN | TG RAMBUTAN |  | N407 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7580.05
333 | IP BREAK RING | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.174 | ML196714 | 2023-08-25 | NA | NA | NA | Northern | Perak | 4432A | KTM Sg Siput | KTM Sg Siput |  | N407 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7580.05
334 | IP BREAK RING | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.174 | ML196714 | 2023-08-25 | NA | NA | NA | Northern | Perak | 4498A | LAP Tambun 1&2 | LAP Tambun 1&2 |  | N407 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7580.05
335 | IP BREAK RING | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.174 | ML196714 | 2023-08-25 | NA | NA | NA | Northern | Perak | 4541A | Bercham Industry | Bercham Industry |  | N407 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7580.05
336 | IP BREAK RING | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.169 | ML196718 | 2023-08-25 | NA | NA | NA | Central | Selangor | 2070B | Sri Gombak | Sri Gombak |  | C1103 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7580.05
337 | IP BREAK RING | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.169 | ML196718 | 2023-08-25 | NA | NA | NA | Eastern | Pahang | 8709A | Bentong (Trunk) | Bentong (Trunk) |  | C1103 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7580.05
338 | IP BREAK RING | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.169 | ML196718 | 2023-08-25 | NA | NA | NA | Eastern | Pahang | 2833A | First World Hotel Indoor | First World Hotel Indoor |  | C1103 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7580.05
339 | IP BREAK RING | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.169 | ML196718 | 2023-08-25 | NA | NA | NA | Central | Selangor | 1016A | GENTING RIA APARTMENT | GENTING RIA APARTMENT |  | C1103 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7580.05
340 | IP BREAK RING | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.169 | ML196718 | 2023-08-25 | NA | NA | NA | Eastern | Pahang | 1015A | Awana Golf &Country | Awana Golf &Country |  | C1103 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7580.05
341 | IP BREAK RING | MIP2023.168 CD Digi NIC ES BOQ- IPRAN re-eng for C0103 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.168 | ML196719 | 2023-08-25 | NA | NA | NA | Central | Selangor | 1359A | Mutiara Subang | Mutiara Subang |  | C0103 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-24 | 2023-10-24 | [7 empty] | 8148.6467
342 | IP BREAK RING | MIP2023.168 CD Digi NIC ES BOQ- IPRAN re-eng for C0103 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.168 | ML196719 | 2023-08-25 | NA | NA | NA | Central | Selangor | 1409A | Kota Damansara | Kota Damansara |  | C0103 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-24 | 2023-10-24 | [7 empty] | 8148.6467
343 | IP BREAK RING | MIP2023.168 CD Digi NIC ES BOQ- IPRAN re-eng for C0103 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.168 | ML196719 | 2023-08-25 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | C0103 | BBAND | NA |  | NA |  | NA |  | NA | 2023-10-24 | 2023-10-24 | [7 empty] | 8148.6467
344 | IP BREAK RING | MIP2023.110 CD Digi BAU ES BOQ- Southern S401 Reengineering | OPM | YR23 Q3 Q4 | Spillover | MIP2023.110 | ML190493 | 2023-08-01 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC |  | S401 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-23 | 2024-05-23 | Fiber not through at 2376B Kg Tenai Ayer Gelugor towards 1659A Bahau Tower |  |  |  |  | Jul |  | 7556.34
345 | IP BREAK RING | MIP2023.110 CD Digi BAU ES BOQ- Southern S401 Reengineering | OPM | YR23 Q3 Q4 | Spillover | MIP2023.110 | ML190493 | 2023-08-01 | NA | NA | NA | Southern | Negeri Sembilan | 1659A | Bahau Tower | Bahau Tower |  | S401 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-23 | 2024-05-23 | Fiber not through at 2376B Kg Tenai Ayer Gelugor towards 1659A Bahau Tower |  |  |  |  | Jul |  | 7556.34
346 | IP BREAK RING | MIP2023.110 CD Digi BAU ES BOQ- Southern S401 Reengineering | OPM | YR23 Q3 Q4 | Spillover | MIP2023.110 | ML190493 | 2023-08-01 | NA | NA | NA | Southern | Negeri Sembilan | 2376B | KG.TENAI AIR GELUGOR | KG.TENAI AIR GELUGOR |  | S401 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-23 | 2024-05-23 | Fiber not through at 2376B Kg Tenai Ayer Gelugor towards 1659A Bahau Tower |  |  |  |  | Jul |  | 7556.34
347 | IP BREAK RING | MIP2023.184 CD Digi NIC ES BOQ- Break Ring MAC Ring 20 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.184 | ML201296 | 2023-09-15 | NA | NA | NA | Central | Selangor | 1093A | Kian Hoe Huat | Kian Hoe Huat |  | MR20/C26 | BBAND | NA |  | NA |  | NA |  | NA | Jun |  | Drop due to pending on finalising technical solution |  |  |  |  | Apr |  | 10632.0633
348 | IP BREAK RING | MIP2023.184 CD Digi NIC ES BOQ- Break Ring MAC Ring 20 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.184 | ML201296 | 2023-09-15 | NA | NA | NA | Central | Selangor | 1627B | Pulau Indah Highway(ZED) | Pulau Indah Highway(ZED) |  | MR20/C26 | BBAND | NA |  | NA |  | NA |  | NA | Jun |  | Drop due to pending on finalising technical solution |  |  |  |  | Apr |  | 10632.0633
349 | IP BREAK RING | MIP2023.184 CD Digi NIC ES BOQ- Break Ring MAC Ring 20 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.184 | ML201296 | 2023-09-15 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | MR20/C26 | BBAND | NA |  | NA |  | NA |  | NA | Jun |  | Drop due to pending on finalising technical solution |  |  |  |  | Apr |  | 10632.0633
350 | IP BREAK RING | MIP2023.84 CD Digi NIC ES BOQ- Southern 1533A-MAC-002 Bukit Duyong Integration | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.84 | ML203341 | 2023-09-26 | NA | NA | NA | Southern | Melaka | 1533A | Bkt Duyung | Bkt Duyung |  | S313P_2_ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 22260.34
351 | IP BREAK RING | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.78 | ML203344 | 2023-09-26 | NA | NA | NA | Eastern | Pahang | 8965A | Simpang Lepar Hilir | Simpang Lepar Hilir |  | E404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7321.8225
352 | IP BREAK RING | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.78 | ML203344 | 2023-09-26 | NA | NA | NA | Eastern | Pahang | 8191A | Sg Semuji(Shazan s Tower / ZED) | Sg Semuji(Shazan s Tower / ZED) |  | E404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7321.8225
353 | IP BREAK RING | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.78 | ML203344 | 2023-09-26 | NA | NA | NA | Eastern | Pahang | 8513A | Bkt Senggora | Bkt Senggora |  | E404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7321.8225
354 | IP BREAK RING | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.78 | ML203344 | 2023-09-26 | NA | NA | NA | Eastern | Pahang | 8025A | Pejabat Risda | Pejabat Risda |  | E404 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7321.8225
355 | IP BREAK RING | MIP2023.92 CD Digi NIC ES BOQ- Southern SAR03_iii MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.92 | ML203349 | 2023-09-26 | NA | NA | NA | Southern | Melaka | 1554A | Rumbia | Rumbia |  | SAR03_iii | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 9551.03
356 | IP BREAK RING | MIP2023.92 CD Digi NIC ES BOQ- Southern SAR03_iii MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.92 | ML203349 | 2023-09-26 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC |  | SAR03_iii | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 9551.03
357 | IP BREAK RING | MIP2023.92 CD Digi NIC ES BOQ- Southern SAR03_iii MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.92 | ML203349 | 2023-09-26 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB |  | SAR03_iii | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-24 | 2024-01-24 | [5 empty] | Jan |  | 9551.03
358 | PE-MCR | MIP2023.93 CD Digi NIC ES BOQ- Southern SAR05 MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.93 | ML203350 | 2023-09-26 | NA | NA | NA | Southern | Johor | 6083A | Soga | Soga |  | SAR05 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-13 | 2024-03-13 | [5 empty] | Mar |  | 9551.03
359 | PE-MCR | MIP2023.93 CD Digi NIC ES BOQ- Southern SAR05 MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.93 | ML203350 | 2023-09-26 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC |  | SAR05 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-13 | 2024-03-13 | [5 empty] | Mar |  | 9551.03
360 | PE-MCR | MIP2023.93 CD Digi NIC ES BOQ- Southern SAR05 MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.93 | ML203350 | 2023-09-26 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB |  | SAR05 | BBAND | NA |  | NA |  | NA |  | NA | 2024-03-13 | 2024-03-13 | [5 empty] | Mar |  | 9551.03
361 | IP BREAK RING | MIP2023.91 CD Digi NIC ES BOQ- Southern SAR03_ii MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.91 | ML203351 | 2023-09-26 | NA | NA | NA | Southern | Johor | 2402B | Pagoh Highway | Pagoh Highway |  | SAR03_ii | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-23 | 2024-01-23 | [5 empty] | Jan |  | 9551.03
362 | IP BREAK RING | MIP2023.91 CD Digi NIC ES BOQ- Southern SAR03_ii MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.91 | ML203351 | 2023-09-26 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC |  | SAR03_ii | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-23 | 2024-01-23 | [5 empty] | Jan |  | 9551.03
363 | IP BREAK RING | MIP2023.91 CD Digi NIC ES BOQ- Southern SAR03_ii MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.91 | ML203351 | 2023-09-26 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB |  | SAR03_ii | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-23 | 2024-01-23 | [5 empty] | Jan |  | 9551.03
364 | Ring Expansion (MAG-PE) | MIP2023.81 CD Digi NIC ES BOQ- Eastern EAR02_2 MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.81 | ML203352 | 2023-09-26 | NA | NA | NA | Eastern | Terengganu | 8429B | Bkt Payung 2 | Bkt Payung 2 |  | EAR02_2 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-28 | 2024-05-28 | [5 empty] | Mar |  | 9551.03
365 | Ring Expansion (MAG-PE) | MIP2023.81 CD Digi NIC ES BOQ- Eastern EAR02_2 MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.81 | ML203352 | 2023-09-26 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan |  | EAR02_2 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-28 | 2024-05-28 | [5 empty] | Mar |  | 9551.03
366 | Ring Expansion (MAG-PE) | MIP2023.81 CD Digi NIC ES BOQ- Eastern EAR02_2 MAG Break Ring | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.81 | ML203352 | 2023-09-26 | NA | NA | NA | Northern | Perak | 4000A | MSC Prai | MSC Prai |  | EAR02_2 | FO&T | NA |  | NA |  | NA |  | NA | 2024-05-28 | 2024-05-28 | [5 empty] | Mar |  | 9551.03
367 | IP BREAK RING | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.182 | ML204699 | 2023-10-04 | NA | NA | NA | Northern | Perak | 4521A | MSC Ipoh | MSC Ipoh | 1 | N601 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-05 | 2024-03-05 | [5 empty] | Mar |  | 7978.988
368 | IP BREAK RING | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.182 | ML204699 | 2023-10-04 | NA | NA | NA | Northern | Perak | 4440B | Tapah Road | Tapah Road | 1 | N601 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-05 | 2024-03-05 | [5 empty] | Mar |  | 7978.988
369 | IP BREAK RING | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.182 | ML204699 | 2023-10-04 | NA | NA | NA | Northern | Perak | 4509A | LAP Tmn Taufik | LAP Tmn Taufik | 1 | N601 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-05 | 2024-03-05 | [5 empty] | Mar |  | 7978.988
370 | IP BREAK RING | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.182 | ML204699 | 2023-10-04 | NA | NA | NA | Northern | Perak | 4516A | Simpang Pulai | Simpang Pulai | 1 | N601 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-05 | 2024-03-05 | [5 empty] | Mar |  | 7978.988
371 | IP BREAK RING | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.182 | ML204699 | 2023-10-04 | NA | NA | NA | Northern | Perak | 4368A | TAR College | TAR College | 1 | N601 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-05 | 2024-03-05 | [5 empty] | Mar |  | 7978.988
372 | IP BREAK RING | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.201 | ML205405 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6283A | LARKIN INDUSTRIAL | LARKIN INDUSTRIAL |  | New Ring_5 |  | NA |  | NA |  | NA |  | NA | 2024-06-12 | [6 empty] | May |  | 7978.988
373 | IP BREAK RING | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.201 | ML205405 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6043A | K.K.Kam | K.K.Kam |  | New Ring_5 |  | NA |  | NA |  | NA |  | NA | 2024-06-12 | [6 empty] | May |  | 7978.988
374 | IP BREAK RING | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.201 | ML205405 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6026A | Grand Continental | Grand Continental |  | New Ring_5 |  | NA |  | NA |  | NA |  | NA | 2024-06-12 | [6 empty] | May |  | 7978.988
375 | IP BREAK RING | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.201 | ML205405 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB |  | New Ring_5 |  | NA |  | NA |  | NA |  | NA | 2024-06-12 | [6 empty] | May |  | 7978.988
376 | IP BREAK RING | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.201 | ML205405 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6502A | Nusa Perintis(Watertank) | Nusa Perintis(Watertank) |  | New Ring_5 |  | NA |  | NA |  | NA |  | NA | 2024-06-12 | [6 empty] | May |  | 7978.988
377 | IP BREAK RING | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.214 | ML205259 | 2023-10-05 | MIP2023.214 | ML214068 | TBA | Northern | Kedah | 4995A | Changloon UUM | Changloon UUM |  | N113 | FO&T | 2024-01-15 |  | WIP |  |  |  |  | Jun | [6 empty] | Jul |  | 50876.8425 | 150190.5725
378 | IP BREAK RING | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.215 | ML205406 | 2023-10-05 | MIP2023.165 | ML203364 | 2023-09-25 | Northern | Kedah | 4992A | Pendang | Pendang |  | N113 | FO&T | 2023-10-10 |  | 2023-10-11 |  | Battery Bank_3_Cooling Cabinet_1_Rectifier + DCPDB_1_Subrack rectifier_1_Breaker_40Ax2,Plinth_1_Pole relocate/Decom_2 |  |  | Jun | [6 empty] | Jul |  | 50876.8425 | 124846.73
379 | IP BREAK RING | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.215 | ML205406 | 2023-10-05 | NA | NA | NA | Northern | Kedah | 4663A | Derga Jaya | Derga Jaya |  | N113 | FO&T | NA |  | NA |  | NA |  | NA | Jun | [6 empty] | Jul |  | 50876.8425
380 | IP BREAK RING | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.215 | ML205406 | 2023-10-05 | NA | NA | NA | Northern | Kedah | 4973B | Tajar | Tajar |  | N113 | FO&T | NA |  | NA |  | NA |  | NA | Jun | [6 empty] | Jul |  | 50876.8425
381 | IP BREAK RING | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.216 | ML205408 | 2023-10-05 | NA | NA | NA | Northern | Kedah | 4863B | Wisma PKNK | Wisma PKNK |  | N103 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-07 | [6 empty] | Apr |  | 8319.1675
382 | IP BREAK RING | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.216 | ML205408 | 2023-10-05 | NA | NA | NA | Northern | Kedah | 4669A | Alor Janggus (Trunk) | Alor Janggus (Trunk) |  | N103 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-07 | [6 empty] | Apr |  | 8319.1675
383 | IP BREAK RING | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.216 | ML205408 | 2023-10-05 | NA | NA | NA | Northern | Kedah | 4660A | KTM A.setar | KTM A.setar |  | N103 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-07 | [6 empty] | Apr |  | 8319.1675
384 | IP BREAK RING | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.216 | ML205408 | 2023-10-05 | NA | NA | NA | Northern | Kedah | 4998A | Air Itam Kedah | Air Itam Kedah |  | N103 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-07 | [6 empty] | Apr |  | 8319.1675
385 | IP BREAK RING | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.218 | ML205409 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan |  | C0607P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7974.0475
386 | IP BREAK RING | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.218 | ML205409 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1196A | JBA Puchong | JBA Puchong |  | C0607P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7974.0475
387 | IP BREAK RING | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.218 | ML205409 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1408A | Puchong Jaya | Puchong Jaya |  | C0607P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7974.0475
388 | IP BREAK RING | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.218 | ML205409 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1402A | Jln Ind Puchong | Jln Ind Puchong |  | C0607P | BBAND | NA |  | NA |  | NA |  | NA | 2024-05-07 | 2024-05-07 | [5 empty] | Mar |  | 7974.0475
389 | IP BREAK RING | MIP2023.204 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_S602M | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.204 | ML205410 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6955A | Putri Wangsa 2 | Putri Wangsa 2 | 1 | S602M | BBAND | NA |  | NA |  | NA |  | NA | 2024-02-23 | 2024-02-23 | [5 empty] | Feb |  | 11092.2233
390 | IP BREAK RING | MIP2023.204 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_S602M | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.204 | ML205410 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB | 1 | S602M | BBAND | NA |  | NA |  | NA |  | NA | 2024-02-23 | 2024-02-23 | [5 empty] | Feb |  | 11092.2233
391 | IP BREAK RING | MIP2023.204 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_S602M | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.204 | ML205410 | 2023-10-05 | NA | NA | NA | Southern | Johor | 6369A | Sri Saujana | Sri Saujana | 1 | S602M | BBAND | NA |  | NA |  | NA |  | NA | 2024-02-23 | 2024-02-23 | [5 empty] | Feb |  | 11092.2233
392 | PE-MCR | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.213 | ML205258 | 2023-10-05 | NA | NA | NA | Northern | Perak | 4440B | Tapah Road | Tapah Road |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 9230.2325
393 | PE-MCR | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.213 | ML205258 | 2023-10-05 | NA | NA | NA | Northern | Perak | 4521A | MSC Ipoh | MSC Ipoh |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 9230.2325
394 | PE-MCR | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.213 | ML205258 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 9230.2325
395 | PE-MCR | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.213 | ML205258 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1701A | Kerling Trunk | Kerling Trunk |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-06 | 2024-03-06 | [5 empty] | Mar |  | 9230.2325
396 | Ring Expansion | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.212 | ML205260 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7112.088
397 | Ring Expansion | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.212 | ML205260 | 2023-10-05 | NA | NA | NA | Northern | Perak | 4521A | MSC Ipoh | MSC Ipoh |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7112.088
398 | Ring Expansion | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.212 | ML205260 | 2023-10-05 | NA | NA | NA | Central | Selangor | 1701A | Kerling Trunk | Kerling Trunk |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7112.088
399 | Ring Expansion | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.212 | ML205260 | 2023-10-05 | NA | NA | NA | Central | Selangor | 4412A | KTM Sungkai | KTM Sungkai |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7112.088
400 | Ring Expansion | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.212 | ML205260 | 2023-10-05 | NA | NA | NA | Northern | Perak | 4440B | Tapah Road | Tapah Road |  | NAR06 | FO&T | NA |  | NA |  | NA |  | NA | 2024-01-30 | 2024-01-30 | [5 empty] | Jan |  | 7112.088
401 | PE-MCR | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.223 | ML206211 | 2023-10-10 | NA | NA | NA | Northern | Pulau Pinang | 4188A | NIBONG TEBAL2 | NIBONG TEBAL2 |  | NAR03 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-20 | 2024-03-20 | [5 empty] | Mar |  | 11469.7525
402 | PE-MCR | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.223 | ML206211 | 2023-10-10 | NA | NA | NA | Northern | Pulau Pinang | 4331A | Bagan Serai | Bagan Serai |  | NAR03 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-20 | 2024-03-20 | [5 empty] | Mar |  | 11469.7525
403 | PE-MCR | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.223 | ML206211 | 2023-10-10 | NA | NA | NA | Northern | Pulau Pinang | 4310A | Matang Acheh | Matang Acheh |  | NAR03 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-20 | 2024-03-20 | [5 empty] | Mar |  | 11469.7525
404 | PE-MCR | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.223 | ML206211 | 2023-10-10 | NA | NA | NA | Northern | Perak | 4521A | MSC Ipoh | MSC Ipoh |  | NAR03 | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-20 | 2024-03-20 | [5 empty] | Mar |  | 11469.7525
405 | IP BREAK RING | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.219 | ML206598 | 2023-10-12 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | MAC RING 18-C24 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7974.0475
406 | IP BREAK RING | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.219 | ML206598 | 2023-10-12 | NA | NA | NA | Central | Selangor | 1360A | Hicom Glenmarie | Hicom Glenmarie |  | MAC RING 18-C24 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7974.0475
407 | IP BREAK RING | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.219 | ML206598 | 2023-10-12 | NA | NA | NA | Central | Selangor | 1172A | Glomac | Glomac |  | MAC RING 18-C24 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7974.0475
408 | IP BREAK RING | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.219 | ML206598 | 2023-10-12 | NA | NA | NA | Central | Selangor | 1362B | Kelana Business Centre | Kelana Business Centre |  | MAC RING 18-C24 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7974.0475
409 | IP BREAK RING | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.222 | ML206998 | 2023-10-19 | NA | NA | NA | Northern | Kedah | 4946A | Bukit Selambau | Bukit Selambau |  | N106 | FO&T | NA |  | NA |  | NA |  | NA | 2023-11-16 | 2023-11-16 | [7 empty] | 9973.735
410 | IP BREAK RING | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.222 | ML206998 | 2023-10-19 | NA | NA | NA | Northern | Kedah | 4966A | Kulim Hi-Tech Tower | Kulim Hi-Tech Tower |  | N106 | FO&T | NA |  | NA |  | NA |  | NA | 2023-11-16 | 2023-11-16 | [7 empty] | 9973.735
411 | IP BREAK RING | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.222 | ML206998 | 2023-10-19 | NA | NA | NA | Northern | Kedah | 4683A | Bkt Tok Alang | Bkt Tok Alang |  | N106 | FO&T | NA |  | NA |  | NA |  | NA | 2023-11-16 | 2023-11-16 | [7 empty] | 9973.735
412 | IP BREAK RING | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.222 | ML206998 | 2023-10-19 | NA | NA | NA | Northern | Kedah | 4085D | Kulim Hitech 2 (REL) | Kulim Hitech 2 (REL) |  | N106 | FO&T | NA |  | NA |  | NA |  | NA | 2023-11-16 | 2023-11-16 | [7 empty] | 9973.735
413 | IP BREAK RING | MIP2023.221 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N302 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.221 | ML206997 | 2023-10-19 | NA | NA | NA | Northern | Kedah | 4241A | Juru Tower | Juru Tower |  | N302 | FO&T | NA |  | NA |  | NA |  | NA | 2024-04-25 | 2024-04-25 | [5 empty] | Mar |  | 11092.2233
414 | IP BREAK RING | MIP2023.221 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N302 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.221 | ML206997 | 2023-10-19 | NA | NA | NA | Northern | Perak | 4000A | MSC Prai | MSC Prai |  | N302 | FO&T | NA |  | NA |  | NA |  | NA | 2024-04-25 | 2024-04-25 | [5 empty] | Mar |  | 11092.2233
415 | IP BREAK RING | MIP2023.221 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N302 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.221 | ML206997 | 2023-10-19 | NA | NA | NA | Northern | Perak | 4188A | NIBONG TEBAL2 | NIBONG TEBAL2 |  | N302 | FO&T | NA |  | NA |  | NA |  | NA | 2024-04-25 | 2024-04-25 | [5 empty] | Mar |  | 11092.2233
416 | IP BREAK RING | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.271 | ML219845 | 2023-12-15 | NA | NA | NA | Northern | Kedah | 4770A | Toklin (Trunk ) | Toklin (Trunk ) |  | N115+ | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-07 | 2023-12-07 | [7 empty] | 12295.696
417 | IP BREAK RING | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.271 | ML219845 | 2023-12-15 | NA | NA | NA | Northern | Kedah | 4932A | BKT TOK ACHEH | BKT TOK ACHEH |  | N115+ | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-07 | 2023-12-07 | [7 empty] | 12295.696
418 | IP BREAK RING | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.271 | ML219845 | 2023-12-15 | NA | NA | NA | Northern | Kedah | 4688A | Lunas | Lunas |  | N115+ | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-07 | 2023-12-07 | [7 empty] | 12295.696
419 | IP BREAK RING | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.271 | ML219845 | 2023-12-15 | NA | NA | NA | Northern | Kedah | 4966A | Kulim Hi-Tech Tower | Kulim Hi-Tech Tower |  | N115+ | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-07 | 2023-12-07 | [7 empty] | 12295.696
420 | IP BREAK RING | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.271 | ML219845 | 2023-12-15 | NA | NA | NA | Northern | Kedah | 4946A | Bukit Selambau | Bukit Selambau |  | N115+ | FO&T | NA |  | NA |  | NA |  | NA | 2023-12-07 | 2023-12-07 | [7 empty] | 12295.696
421 | IP BREAK RING | MIP2023.07 CDB Digi BAU- ES BOQ for re-eng medium for link 8268A-8211A from DWDM to OB fiber (Ring E110) V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.07 | ML184159 | 2023-06-23 | NA | NA | NA | Eastern | Kelantan | 8268A | Bachok | Bachok |  | E110 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-06 | 2023-07-06 | [7 empty] | 7615.615
422 | IP BREAK RING | MIP2023.07 CDB Digi BAU- ES BOQ for re-eng medium for link 8268A-8211A from DWDM to OB fiber (Ring E110) V2 | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.07 | ML184159 | 2023-06-23 | NA | NA | NA | Eastern | Kelantan | 8211A | Wakaf Che Yeh | Wakaf Che Yeh |  | E110 | BBAND | NA |  | NA |  | NA |  | NA | 2023-07-06 | 2023-07-06 | [7 empty] | 7615.615
423 | IP BREAK RING | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.151 | ML189723 | 2023-07-27 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan |  | EAR04 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 7820.495
424 | IP BREAK RING | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.151 | ML189723 | 2023-07-27 | NA | NA | NA | Eastern | Pahang | 8709A | Bentong (Trunk) | Bentong (Trunk) |  | EAR04 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 7820.495
425 | IP BREAK RING | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.151 | ML189723 | 2023-07-27 | NA | NA | NA | Eastern | Pahang | 8025A | Pejabat Risda | Pejabat Risda |  | EAR04 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 7820.495
426 | IP BREAK RING | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | DWDM | YR23 Q3 Q4 | Spillover | MIP2023.151 | ML189723 | 2023-07-27 | NA | NA | NA | Eastern | Pahang | 8703A | Kg. Awah | Kg. Awah |  | EAR04 | FO&T | NA |  | NA |  | NA |  | NA | 2023-10-25 | 2023-10-25 | [7 empty] | 7820.495
427 | IP BREAK RING | MIP2023.266 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT01P+ | DWDM | YR24 Q1 | Q1 | MIP2023.266 | ML225970 | 2024-01-18 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | CT01P+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-31 | 2024-01-31 | [5 empty] | Jan |  | 10632.0633
428 | IP BREAK RING | MIP2023.266 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT01P+ | DWDM | YR24 Q1 | Q1 | MIP2023.266 | ML225970 | 2024-01-18 | NA | NA | NA | Central | Selangor | 1309A | Ivory | Ivory |  | CT01P+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-31 | 2024-01-31 | [5 empty] | Jan |  | 10632.0633
429 | IP BREAK RING | MIP2023.266 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT01P+ | DWDM | YR24 Q1 | Q1 | MIP2023.266 | ML225970 | 2024-01-18 | NA | NA | NA | Central | Selangor | 1298A | Kepong Knit | Kepong Knit |  | CT01P+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-01-31 | 2024-01-31 | [5 empty] | Jan |  | 10632.0633
430 | IP BREAK RING | MIP2023.267 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT04+ | DWDM | YR24 Q1 | Q1 | MIP2023.267 | ML230522 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1413A | KTM Rawang | KTM Rawang |  | CT04+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 9542.335
431 | IP BREAK RING | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | DWDM | YR24 Q1 | Q1 | MIP2023.273 | ML220247 | 2023-12-22 | NA | NA | NA | Northern | Kedah | 4621A | CAYMEN SHOPPING | CAYMEN SHOPPING |  | NT09P+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-19 | 2024-03-19 | [5 empty] | Mar |  | 8319.1675
432 | IP BREAK RING | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | DWDM | YR24 Q1 | Q1 | MIP2023.273 | ML220247 | 2023-12-22 | NA | NA | NA | Northern | Kedah | 4625A | KTM Sungai Petani | KTM Sungai Petani |  | NT09P+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-19 | 2024-03-19 | [5 empty] | Mar |  | 8319.1675
433 | IP BREAK RING | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | DWDM | YR24 Q1 | Q1 | MIP2023.273 | ML220247 | 2023-12-22 | NA | NA | NA | Northern | Kedah | 4640A | SP Plaza | SP Plaza |  | NT09P+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-19 | 2024-03-19 | [5 empty] | Mar |  | 8319.1675
434 | IP BREAK RING | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | DWDM | YR24 Q1 | Q1 | MIP2023.273 | ML220247 | 2023-12-22 | NA | NA | NA | Northern | Kedah | 4693A | KTM Gurun TX | KTM Gurun TX |  | NT09P+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-19 | 2024-03-19 | [5 empty] | Mar |  | 8319.1675
435 |  | MIP2023.XX CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_Area 139 | DWDM | YR24 Q1 | Q1 | MIP2023.224 | ML230499 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4946A | Bukit Selambau | Bukit Selambau |  | Area 139 | FO&T | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - IP BREAK RING | 25838.88
436 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8513A | Bkt Senggora | Bkt Senggora |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
437 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8709A | Bentong (Trunk) | Bentong (Trunk) |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
438 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8105A | South Of Raub(AsiaSpace) | South Of Raub(AsiaSpace) |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
439 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8667A | Jerangsang | Jerangsang |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
440 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8145Z | Kg. Paya Luas | Kg. Paya Luas |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
441 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8112A | Bukit Istana | Bukit Istana |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
442 | Ring Expansion (MAG-PE) | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | DWDM | YR24 Q1 | Q1 | MIP2023.249 | ML230612 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8173A | Bandar Pusat Jengka | Bandar Pusat Jengka |  | EAR06 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 11475.8357
443 | Ring Expansion | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.250 | ML230611 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1690A | Bukit Pelandok (DWDM) | Bukit Pelandok (DWDM) |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-11 | [6 empty] | May |  | 13622.9925
444 | Ring Expansion | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.250 | ML230611 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1640A | POLITEKNIK PORT DICKSON (KJS TW) | POLITEKNIK PORT DICKSON (KJS TW) |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-11 | [6 empty] | May |  | 13622.9925
445 | Ring Expansion | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.250 | ML230611 | 2024-02-20 | NA | NA | NA | Southern | Melaka | 1554A | Rumbia | Rumbia |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-11 | [6 empty] | May |  | 13622.9925
446 | Ring Expansion | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.250 | ML230611 | 2024-02-20 | NA | NA | NA | Southern | Melaka | 1552A | Tanjung Bidara | Tanjung Bidara |  | SAR01 | FO&T | NA |  | NA |  | NA |  | NA | 2024-06-11 | [6 empty] | May |  | 13622.9925
447 | IP BREAK RING | MIP2023.251 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.251 | ML230610 (PO cancel) | 2024-02-20 | NA | NA | NA | Northern | Perak | 4000A | MSC Prai | MSC Prai |  | EAR01 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May
448 | IP BREAK RING | MIP2023.251 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.251 | ML230610 (PO cancel) | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | MSC Kuantan |  | EAR01 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May
449 | IP BREAK RING | MIP2023.251 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR01 | DWDM | YR24 Q1 | Q1 | MIP2023.251 | ML230610 (PO cancel) | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8224A | Pasir Puteh | Pasir Puteh |  | EAR01 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May
450 | IP BREAK RING | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | DWDM | YR24 Q1 | Q1 | MIP2023.240 | ML230624 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8288B | Bukit Panau | Bukit Panau |  | E104 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
451 | IP BREAK RING | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | DWDM | YR24 Q1 | Q1 | MIP2023.240 | ML230624 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8263A | Pasir Mas Town | Pasir Mas Town |  | E104 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
452 | IP BREAK RING | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | DWDM | YR24 Q1 | Q1 | MIP2023.240 | ML230624 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8269B | Chetok (IQ) | Chetok (IQ) |  | E104 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
453 | IP BREAK RING | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | DWDM | YR24 Q1 | Q1 | MIP2023.240 | ML230624 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8294A | Kangkong | Kangkong |  | E104 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
454 | IP BREAK RING | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | DWDM | YR24 Q1 | Q1 | MIP2023.241 | ML230623 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8211A | Wakaf Che Yeh | Wakaf Che Yeh |  | E105 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7978.988
455 | IP BREAK RING | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | DWDM | YR24 Q1 | Q1 | MIP2023.241 | ML230623 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8139B | CBG4TUMPAT1 | CBG4TUMPAT1 |  | E105 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7978.988
456 | IP BREAK RING | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | DWDM | YR24 Q1 | Q1 | MIP2023.241 | ML230623 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8229A | Tumpat | Tumpat |  | E105 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7978.988
457 | IP BREAK RING | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | DWDM | YR24 Q1 | Q1 | MIP2023.241 | ML230623 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8212A | Wakaf Bharu | Wakaf Bharu |  | E105 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7978.988
458 | IP BREAK RING | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | DWDM | YR24 Q1 | Q1 | MIP2023.241 | ML230623 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8263A | Pasir Mas Town | Pasir Mas Town |  | E105 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7978.988
459 | IP BREAK RING | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | DWDM | YR24 Q1 | Q1 | MIP2023.242 | ML230621 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8224A | Pasir Puteh | Pasir Puteh |  | E109 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 8319.1675
460 | IP BREAK RING | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | DWDM | YR24 Q1 | Q1 | MIP2023.242 | ML230621 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8222A | Peringat | Peringat |  | E109 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 8319.1675
461 | IP BREAK RING | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | DWDM | YR24 Q1 | Q1 | MIP2023.242 | ML230621 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8242B | Jln Kuala Krai | Jln Kuala Krai |  | E109 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 8319.1675
462 | IP BREAK RING | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | DWDM | YR24 Q1 | Q1 | MIP2023.242 | ML230621 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8211A | Wakaf Che Yeh | Wakaf Che Yeh |  | E109 | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 8319.1675
463 | IP BREAK RING | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | DWDM | YR24 Q1 | Q1 | MIP2023.243 | ML230620 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8367A | Bukit Kechil | Bukit Kechil |  | E111 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9958.2917
464 | IP BREAK RING | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | DWDM | YR24 Q1 | Q1 | MIP2023.243 | ML230620 | 2024-02-20 | NA | NA | NA | Eastern | Terengganu | 8317A | Kampung Pak Wong | Kampung Pak Wong |  | E111 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9958.2917
465 | IP BREAK RING | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | DWDM | YR24 Q1 | Q1 | MIP2023.243 | ML230620 | 2024-02-20 | NA | NA | NA | Eastern | Terengganu | 8439A | Alor Lintang (Celcom) | Alor Lintang (Celcom) |  | E111 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9958.2917
466 | IP BREAK RING | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | DWDM | YR24 Q1 | Q1 | MIP2023.243 | ML230620 | 2024-02-20 | NA | NA | NA | Eastern | Terengganu | 8407A | Jerteh (Maxis) | Jerteh (Maxis) |  | E111 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9958.2917
467 | IP BREAK RING | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | DWDM | YR24 Q1 | Q1 | MIP2023.243 | ML230620 | 2024-02-20 | NA | NA | NA | Eastern | Terengganu | 8322B | Padang Luas | Padang Luas |  | E111 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9958.2917
468 | IP BREAK RING | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | DWDM | YR24 Q1 | Q1 | MIP2023.243 | ML230620 | 2024-02-20 | NA | NA | NA | Eastern | Kelantan | 8224A | Pasir Puteh | Pasir Puteh |  | E111 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9958.2917
469 | IP BREAK RING | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | DWDM | YR24 Q1 | Q1 | MIP2023.244 | ML230619 | 2024-02-20 | NA | NA | NA | Southern | Melaka | 1554A | Rumbia | Rumbia |  | S301 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
470 | IP BREAK RING | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | DWDM | YR24 Q1 | Q1 | MIP2023.244 | ML230619 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC |  | S301 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
471 | IP BREAK RING | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | DWDM | YR24 Q1 | Q1 | MIP2023.244 | ML230619 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1560A | Bkt Tiga | Bkt Tiga |  | S301 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
472 | IP BREAK RING | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | DWDM | YR24 Q1 | Q1 | MIP2023.244 | ML230619 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1563A | Bkt Iman | Bkt Iman |  | S301 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 9973.735
473 | IP BREAK RING | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | DWDM | YR24 Q1 | Q1 | MIP2023.245 | #N/A | #N/A | NA | NA | NA | Southern | Melaka | 1553A | Umbai | Umbai |  | S309+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 11628.3025
474 | IP BREAK RING | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | DWDM | YR24 Q1 | Q1 | MIP2023.245 | #N/A | #N/A | NA | NA | NA | Southern | Johor | 2402B | Pagoh Highway | Pagoh Highway |  | S309+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 11628.3025
475 | IP BREAK RING | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | DWDM | YR24 Q1 | Q1 | MIP2023.245 | #N/A | #N/A | NA | NA | NA | Southern | Melaka | 1556A | MERLIMAU | MERLIMAU |  | S309+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 11628.3025
476 | IP BREAK RING | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | DWDM | YR24 Q1 | Q1 | MIP2023.245 | #N/A | #N/A | NA | NA | NA | Southern | Johor | 1599A | BKT GAMBIR TOWN | BKT GAMBIR TOWN |  | S309+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 11628.3025
477 | IP BREAK RING | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | DWDM | YR24 Q1 | Q1 | MIP2023.246 | ML230617 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB |  | ST21P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
478 | IP BREAK RING | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | DWDM | YR24 Q1 | Q1 | MIP2023.246 | ML230617 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6369A | Sri Saujana | Sri Saujana |  | ST21P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
479 | IP BREAK RING | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | DWDM | YR24 Q1 | Q1 | MIP2023.246 | ML230617 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6400A | Jln Pasir Gudang REL | Jln Pasir Gudang REL |  | ST21P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
480 | IP BREAK RING | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | DWDM | YR24 Q1 | Q1 | MIP2023.246 | ML230617 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6312A | Jalan Cenderai | Jalan Cenderai |  | ST21P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
481 | IP BREAK RING | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | DWDM | YR24 Q1 | Q1 | MIP2023.247 | ML230616 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6382A | KTM Pasir Gudang | KTM Pasir Gudang |  | ST21P_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
482 | IP BREAK RING | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | DWDM | YR24 Q1 | Q1 | MIP2023.247 | ML230616 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6063A | KTM Plentong(PLE) | KTM Plentong(PLE) |  | ST21P_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
483 | IP BREAK RING | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | DWDM | YR24 Q1 | Q1 | MIP2023.247 | ML230616 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | MSC JB |  | ST21P_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
484 | IP BREAK RING | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | DWDM | YR24 Q1 | Q1 | MIP2023.247 | ML230616 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6369A | Sri Saujana | Sri Saujana |  | ST21P_1 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 8319.1675
485 | IP BREAK RING | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | DWDM | YR24 Q1 | Q1 | MIP2023.248 | ML230615 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1607A | KM Plaza | KM Plaza |  | ST27P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 22420.0725
486 | IP BREAK RING | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | DWDM | YR24 Q1 | Q1 | MIP2023.248 | ML230615 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | Senawang MSC |  | ST27P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 22420.0725
487 | IP BREAK RING | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | DWDM | YR24 Q1 | Q1 | MIP2023.248 | ML230615 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1608A | KTM SEREMBAN | KTM SEREMBAN |  | ST27P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 22420.0725
488 | IP BREAK RING | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | DWDM | YR24 Q1 | Q1 | MIP2023.248 | ML230615 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1610A | GUN HILL | GUN HILL |  | ST27P | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 22420.0725
489 | Ring Expansion | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | YR24 Q1 | Q1 | MIP2023.263 | ML230526 | 2024-02-20 | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | Area 141+ V2 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 10125.8575
490 | Ring Expansion | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | YR24 Q1 | Q1 | MIP2023.263 | ML230526 | 2024-02-20 | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | Area 141+ V2 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 10125.8575
491 | Ring Expansion | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | YR24 Q1 | Q1 | MIP2023.263 | ML230526 | 2024-02-20 | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | Area 141+ V2 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 10125.8575
492 | Ring Expansion | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | YR24 Q1 | Q1 | MIP2023.263 | ML230526 | 2024-02-20 | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | Area 141+ V2 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 10125.8575
493 | Ring Expansion | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | YR24 Q1 | Q1 | MIP2023.264 | ML230253 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | Colocated-Ring-2+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-04-05 | 2024-04-05 | [5 empty] | Mar |  | 6976.7025
494 | Ring Expansion | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | YR24 Q1 | Q1 | MIP2023.264 | ML230253 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | Colocated-Ring-2+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-04-05 | 2024-04-05 | [5 empty] | Mar |  | 6976.7025
495 | Ring Expansion | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | YR24 Q1 | Q1 | MIP2023.264 | ML230253 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | Colocated-Ring-2+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-04-05 | 2024-04-05 | [5 empty] | Mar |  | 6976.7025
496 | Ring Expansion | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | YR24 Q1 | Q1 | MIP2023.264 | ML230253 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | Colocated-Ring-2+ | BBAND | NA |  | NA |  | NA |  | NA | 2024-04-05 | 2024-04-05 | [5 empty] | Mar |  | 6976.7025
497 | Ring Expansion | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | YR24 Q1 | Q1 | MIP2023.265 | ML229483 | 2024-02-08 | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai |  | Colocated-Ring-4+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7321.8225
498 | Ring Expansion | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | YR24 Q1 | Q1 | MIP2023.265 | ML229483 | 2024-02-08 | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai |  | Colocated-Ring-4+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7321.8225
499 | Ring Expansion | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | YR24 Q1 | Q1 | MIP2023.265 | ML229483 | 2024-02-08 | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai |  | Colocated-Ring-4+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7321.8225
500 | Ring Expansion | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | YR24 Q1 | Q1 | MIP2023.265 | ML229483 | 2024-02-08 | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai |  | Colocated-Ring-4+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 7321.8225
501 | IP BREAK RING | MIP2023.267 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- CT04+ | DWDM | YR24 Q1 | Q1 | MIP2023.267 | ML230522 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | CT04+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 9542.335
502 | IP BREAK RING | MIP2023.267 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- CT04+ | DWDM | YR24 Q1 | Q1 | MIP2023.267 | ML230522 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1413A | KTM Rawang | KTM Rawang |  | CT04+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 9542.335
503 | IP BREAK RING | MIP2023.267 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- CT04+ | DWDM | YR24 Q1 | Q1 | MIP2023.267 | ML230522 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1412A | Bkt Tadun | Bkt Tadun |  | CT04+ | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 9542.335
504 | IP BREAK RING | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | DWDM | YR24 Q1 | Q1 | MIP2023.268 | ML230515 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | MAC RING 6,C09+ |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7974.0475
505 | IP BREAK RING | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | DWDM | YR24 Q1 | Q1 | MIP2023.268 | ML230515 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | MAC RING 6,C09+ |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7974.0475
506 | IP BREAK RING | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | DWDM | YR24 Q1 | Q1 | MIP2023.268 | ML230515 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1192A | Subng NewVillge | Subng NewVillge |  | MAC RING 6,C09+ |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7974.0475
507 | IP BREAK RING | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | DWDM | YR24 Q1 | Q1 | MIP2023.268 | ML230515 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1230A | Tmn Perindustrian Sg Buloh | Tmn Perindustrian Sg Buloh |  | MAC RING 6,C09+ |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7974.0475
508 | IP BREAK RING | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | DWDM | YR24 Q1 | Q1 | MIP2023.270 | ML229564 | 2024-02-11 | NA | NA | NA | Northern | Kedah | 4692A | Gurun | Gurun |  | N114M+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-27 | 2024-03-27 | [5 empty] | Mar |  | 7978.988
509 | IP BREAK RING | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | DWDM | YR24 Q1 | Q1 | MIP2023.270 | ML229564 | 2024-02-11 | NA | NA | NA | Northern | Kedah | 4940A | Semeling | Semeling |  | N114M+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-27 | 2024-03-27 | [5 empty] | Mar |  | 7978.988
510 | IP BREAK RING | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | DWDM | YR24 Q1 | Q1 | MIP2023.270 | ML229564 | 2024-02-11 | NA | NA | NA | Northern | Kedah | 4938A | Taman Orkid | Taman Orkid |  | N114M+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-27 | 2024-03-27 | [5 empty] | Mar |  | 7978.988
511 | IP BREAK RING | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | DWDM | YR24 Q1 | Q1 | MIP2023.270 | ML229564 | 2024-02-11 | NA | NA | NA | Northern | Kedah | 4938A | Taman Orkid | Taman Orkid |  | N114M+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-27 | 2024-03-27 | [5 empty] | Mar |  | 7978.988
512 | IP BREAK RING | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | DWDM | YR24 Q1 | Q1 | MIP2023.270 | ML229564 | 2024-02-11 | NA | NA | NA | Northern | Kedah | 4660A | KTM A.setar | KTM A.setar |  | N114M+ | FO&T | NA |  | NA |  | NA |  | NA | 2024-03-27 | 2024-03-27 | [5 empty] | Mar |  | 7978.988
513 | IP BREAK RING | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | DWDM | YR24 Q1 | Q1 | MIP2023.272 | ML229563 | 2024-02-10 | NA | NA | NA | Northern | Kedah | 4118A | Machang Bubuk 2 | Machang Bubuk 2 |  | N401+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7752.2017
514 | IP BREAK RING | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | DWDM | YR24 Q1 | Q1 | MIP2023.272 | ML229563 | 2024-02-10 | NA | NA | NA | Northern | Kedah | 4689A | Taman Desa Impian | Taman Desa Impian |  | N401+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7752.2017
515 | IP BREAK RING | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | DWDM | YR24 Q1 | Q1 | MIP2023.272 | ML229563 | 2024-02-10 | NA | NA | NA | Northern | Kedah | 4965A | Politeknik Kulim | Politeknik Kulim |  | N401+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7752.2017
516 | IP BREAK RING | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | DWDM | YR24 Q1 | Q1 | MIP2023.272 | ML229563 | 2024-02-10 | NA | NA | NA | Northern | Kedah | 4686B | Terap | Terap |  | N401+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7752.2017
517 | IP BREAK RING | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | DWDM | YR24 Q1 | Q1 | MIP2023.272 | ML229563 | 2024-02-10 | NA | NA | NA | Northern | Kedah | 4952B | SELAMA KEDAH | SELAMA KEDAH |  | N401+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7752.2017
518 | IP BREAK RING | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | DWDM | YR24 Q1 | Q1 | MIP2023.272 | ML229563 | 2024-02-10 | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | MSC Prai |  | N401+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7752.2017
519 | Ring Expansion | MIP2023.274 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 7000A-MAG(M14)-001&002+ | N/A | YR24 Q1 | Q1 | MIP2023.274 | ML230514 | 2024-02-20 | MIP2023.274 | ML217566 | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | 7000A-MAG(M14)-001&002+ |  | NA |  | NA |  | NA |  | NA | 2024-05-16 | 2024-05-16 | [5 empty] | Apr |  | 20251.715
520 | Ring Expansion | MIP2023.274 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 7000A-MAG(M14)-001&002+ | N/A | YR24 Q1 | Q1 | MIP2023.274 | ML230514 | 2024-02-20 | MIP2023.274 | ML217566 | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | 7000A-MAG(M14)-001&002+ |  | NA |  | NA |  | NA |  | NA | 2024-05-16 | 2024-05-16 | [5 empty] | Apr |  | 20251.715
521 | Ring Expansion | MIP2023.275 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 9999A-MAG(M14)-001&002+ | N/A | YR24 Q1 | Q1 | MIP2023.275 | ML230256 | 2024-02-20 | MIP2023.275 | ML217565 | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | 9999A-MAG(M14)-001&002+ |  | NA |  | NA |  | NA |  | NA | Jun | [6 empty] | Apr |  | 26235.785 | 40038.2
522 | Ring Expansion | MIP2023.275 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 9999A-MAG(M14)-001&002+ | N/A | YR24 Q1 | Q1 | MIP2023.275 | ML230256 | 2024-02-20 | MIP2023.275 | ML217565 | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | 9999A-MAG(M14)-001&002+ |  | NA |  | NA |  | NA |  | NA | Jun | [6 empty] | Apr |  | 26235.785 | 40038.2
523 | Ring Expansion (MAG-PE) | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | DWDM | YR24 Q1 | Q1 | MIP2023.276 | ML229738 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4992A | Pendang | Pendang |  | NAR01_i+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 48541.935
524 | Ring Expansion (MAG-PE) | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | DWDM | YR24 Q1 | Q1 | MIP2023.276 | ML229738 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4946A | Bukit Selambau | Bukit Selambau |  | NAR01_i+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 48541.935
525 | Ring Expansion (MAG-PE) | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | DWDM | YR24 Q1 | Q1 | MIP2023.276 | ML229738 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4966A | Kulim Hi-Tech Tower | Kulim Hi-Tech Tower |  | NAR01_i+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 48541.935
526 | Ring Expansion (MAG-PE) | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | DWDM | YR24 Q1 | Q1 | MIP2023.277 | ML230328 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4998A | Air Itam Kedah | Air Itam Kedah |  | NAR01_ii+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 42958.9929
527 | Ring Expansion (MAG-PE) | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | DWDM | YR24 Q1 | Q1 | MIP2023.277 | ML230328 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4660A | KTM A.setar | KTM A.setar |  | NAR01_ii+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 42958.9929
528 | Ring Expansion (MAG-PE) | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | DWDM | YR24 Q1 | Q1 | MIP2023.277 | ML230328 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4938A | Taman Orkid | Taman Orkid |  | NAR01_ii+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 42958.9929
529 | Ring Expansion (MAG-PE) | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | DWDM | YR24 Q1 | Q1 | MIP2023.277 | ML230328 | 2024-02-20 | NA | NA | NA | Northern | Kedah | 4606A | KTM Padang Besar | KTM Padang Besar |  | NAR01_ii+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 42958.9929
530 | Ring Expansion | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | YR24 Q1 | Q1 | MIP2023.347 | ML229484 | 2024-02-08 | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | Area 163 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9289.66
531 | Ring Expansion | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | YR24 Q1 | Q1 | MIP2023.347 | ML229484 | 2024-02-08 | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | Area 163 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9289.66
532 | Ring Expansion | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | YR24 Q1 | Q1 | MIP2023.347 | ML229484 | 2024-02-08 | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | Area 163 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9289.66
533 | Ring Expansion | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | YR24 Q1 | Q1 | MIP2023.347 | ML229484 | 2024-02-08 | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | Area 163 |  | NA |  | NA |  | NA |  | NA | [7 empty] | May |  | 9289.66
534 | IP BREAK RING | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | DWDM | YR24 Q1 | Q1 | MIP2023.349 | ML229609 | 2024-02-15 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | Plaza Pengkalen |  | C0210P | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7633.868
535 | IP BREAK RING | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | DWDM | YR24 Q1 | Q1 | MIP2023.349 | ML229609 | 2024-02-15 | NA | NA | NA | Central | Selangor | 1859A | Midvalleycas | Midvalleycas |  | C0210P | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7633.868
536 | IP BREAK RING | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | DWDM | YR24 Q1 | Q1 | MIP2023.349 | ML229609 | 2024-02-15 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | Plaza Pengkalen |  | C0210P | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7633.868
537 | IP BREAK RING | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | DWDM | YR24 Q1 | Q1 | MIP2023.349 | ML229609 | 2024-02-15 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | Plaza Pengkalen |  | C0210P | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7633.868
538 | IP BREAK RING | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | DWDM | YR24 Q1 | Q1 | MIP2023.349 | ML229609 | 2024-02-15 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 2878A | Mont Kiara | Mont Kiara |  | C0210P | ADVANCE | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7633.868
539 | PE-MCR | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.350 | ML229746 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 8 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 87973.1925
540 | PE-MCR | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.350 | ML229746 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 8 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 87973.1925
541 | PE-MCR | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.350 | ML229746 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 8 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 87973.1925
542 | PE-MCR | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.350 | ML229746 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 8 | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 87973.1925
543 | Ring Expansion | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | YR24 Q1 | Q1 | MIP2023.351 | ML229608 | 2024-02-14 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 12 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7668.855
544 | Ring Expansion | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | YR24 Q1 | Q1 | MIP2023.351 | ML229608 | 2024-02-14 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 12 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7668.855
545 | Ring Expansion | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | YR24 Q1 | Q1 | MIP2023.351 | ML229608 | 2024-02-14 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 12 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7668.855
546 | Ring Expansion | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | YR24 Q1 | Q1 | MIP2023.351 | ML229608 | 2024-02-14 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | Colo Ring 12 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7668.855
547 | Ring Expansion (MAG-PE) | MIP2023.352 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_7000A-MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.352 | ML229464 | 2024-02-08 | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | 7000A-MAG |  | NA |  | NA |  | NA |  | NA | 2024-05-16 | 2024-05-16 | [5 empty] | Apr |  | 23567.02
548 | Ring Expansion (MAG-PE) | MIP2023.352 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_7000A-MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.352 | ML229464 | 2024-02-08 | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KK MSC |  | 7000A-MAG |  | NA |  | NA |  | NA |  | NA | 2024-05-16 | 2024-05-16 | [5 empty] | Apr |  | 23567.02
549 | PE-MCR | MIP2023.353 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_9999A-MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.353 | ML229605 | 2024-02-13 | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | 9999A-MAG |  | NA |  | NA |  | NA |  | NA | 2024-05-14 | 2024-05-14 | [5 empty] | Jun |  | 23567.02
550 | PE-MCR | MIP2023.353 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_9999A-MAG (require IPCore) | N/A | YR24 Q1 | Q1 | MIP2023.353 | ML229605 | 2024-02-13 | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | 9999A-MAG |  | NA |  | NA |  | NA |  | NA | 2024-05-14 | 2024-05-14 | [5 empty] | Jun |  | 23567.02
551 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1006A | JBA Gombak | JBA Gombak |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
552 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1304A | MMA | MMA |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
553 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1745A | Baitumal | Baitumal |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
554 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1458A | Endah Parade | Endah Parade |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
555 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
556 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
557 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
558 | PE-MCR | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | DWDM | YR24 Q1 | Q1 | MIP2023.354 | ML229747 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan |  | CAR04 | BBAND | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 40207.3406
559 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4985A | BALING TOWN | 4985A-MAG-001 Baling Town |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
560 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4988A | Kupang | 4988A-MAC-001 |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
561 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4968A | Inokom Kulim | 4968A-MAC-001 |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
562 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4956B | KUALA PEGANG | 4956B-MAC-001 |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
563 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4950B | Pulai | 4950B-MAC-001 |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
564 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4986A | Binjul | 4986A-MAC-001 |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
565 | IP BREAK RING | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | DWDM | YR24 Q1 | Q1 | MIP2024.14 | ML229276 | 2024-02-08 | NA | NA | NA | Northern | Kedah | 4685B | Kg Sg Karangan | 4685B-MAC-001 |  | N201+ | FO&T | NA |  | NA |  | NA |  | NA | [7 empty] | Apr |  | 8947.2451
566 |  | MIP2023.252 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL405 | LL | YR24 Q1 | Q1 | MIP2023.252 | ML230609 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8183A | Chini Pusat (Maxis) | 8183A-MAC-001 Chini Pusat (Maxis) |  | EL405 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
567 |  | MIP2023.252 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL405 | LL | YR24 Q1 | Q1 | MIP2023.252 | ML230609 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL405 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
568 |  | MIP2023.252 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL405 | LL | YR24 Q1 | Q1 | MIP2023.252 | ML230609 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL405 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
569 |  | MIP2023.253 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL407 | LL | YR24 Q1 | Q1 | MIP2023.253 | ML230608 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8163A | Bukit Harimau | 8163A-MAC-001 Bkt Harimau |  | EL407 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
570 |  | MIP2023.253 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL407 | LL | YR24 Q1 | Q1 | MIP2023.253 | ML230608 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL407 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
571 |  | MIP2023.253 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL407 | LL | YR24 Q1 | Q1 | MIP2023.253 | ML230608 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL407 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
572 |  | MIP2023.254 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL408 | LL | YR24 Q1 | Q1 | MIP2023.254 | ML230607 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8165A | Bdr Tun Razak | 8165A-MAC-001 Bdr Tun Razak |  | EL408 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
573 |  | MIP2023.254 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL408 | LL | YR24 Q1 | Q1 | MIP2023.254 | ML230607 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL408 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
574 |  | MIP2023.254 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL408 | LL | YR24 Q1 | Q1 | MIP2023.254 | ML230607 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL408 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
575 | Ring Expansion | MIP2023.255 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL409 | LL | YR24 Q1 | Q1 | MIP2023.255 | ML230606 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8089A | Bukit Ridan | 8089A-MAC-001 Bukit Ridan |  | EL409 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7556.34
576 | Ring Expansion | MIP2023.255 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL409 | LL | YR24 Q1 | Q1 | MIP2023.255 | ML230606 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL409 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7556.34
577 | Ring Expansion | MIP2023.255 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL409 | LL | YR24 Q1 | Q1 | MIP2023.255 | ML230606 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL409 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7556.34
578 |  | MIP2023.256 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL411 | LL | YR24 Q1 | Q1 | MIP2023.256 | ML230602 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8501A | ECE KM138.9 | 8501A-MAC-001 ECE |  | EL411 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
579 |  | MIP2023.256 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL411 | LL | YR24 Q1 | Q1 | MIP2023.256 | ML230602 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL411 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
580 |  | MIP2023.256 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL411 | LL | YR24 Q1 | Q1 | MIP2023.256 | ML230602 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL411 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
581 |  | MIP2023.257 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL419 | LL | YR24 Q1 | Q1 | MIP2023.257 | ML230601 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8998A | Kerayung | 8998A-MAC-001 Kerayung |  | EL419 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
582 |  | MIP2023.257 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL419 | LL | YR24 Q1 | Q1 | MIP2023.257 | ML230601 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL419 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
583 |  | MIP2023.257 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL419 | LL | YR24 Q1 | Q1 | MIP2023.257 | ML230601 | 2024-02-20 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL419 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
584 | Ring Expansion | MIP2023.258 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL401 | LL | YR24 Q1 | Q1 | MIP2023.258 | ML230600 | 2024-02-20 | NA | NA | NA | Southern | Melaka | 1506A | Bkt Beruang | 1506A-MAC-001 JBA Bkt Beruang |  | SL401 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7556.34
585 | Ring Expansion | MIP2023.258 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL401 | LL | YR24 Q1 | Q1 | MIP2023.258 | ML230600 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-001 SNW |  | SL401 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7556.34
586 | Ring Expansion | MIP2023.258 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL401 | LL | YR24 Q1 | Q1 | MIP2023.258 | ML230600 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-002 SNW |  | SL401 |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jul |  | 7556.34
587 | Ring Expansion | MIP2023.259 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL408P | LL | YR24 Q1 | Q1 | MIP2023.259 | ML230599 | 2024-02-20 | NA | NA | NA | Southern | Melaka | 2124B | Zoo Melaka | 2124B-MAC-001 Zoo Melaka |  | L408P |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7556.34
588 | Ring Expansion | MIP2023.259 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL408P | LL | YR24 Q1 | Q1 | MIP2023.259 | ML230599 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-001 SNW |  | L408P |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7556.34
589 | Ring Expansion | MIP2023.259 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL408P | LL | YR24 Q1 | Q1 | MIP2023.259 | ML230599 | 2024-02-20 | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-002 SNW |  | L408P |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 7556.34
590 |  | MIP2023.260 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL703 | LL | YR24 Q1 | Q1 | MIP2023.260 | ML230597 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6029B | SAJ Seri Alam F | 6029B-MAC-001 SAJ Seri Alam |  | SL703 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
591 |  | MIP2023.260 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL703 | LL | YR24 Q1 | Q1 | MIP2023.260 | ML230597 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-001 JBR |  | SL703 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
592 |  | MIP2023.260 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL703 | LL | YR24 Q1 | Q1 | MIP2023.260 | ML230597 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-002 JBR |  | SL703 |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
593 |  | MIP2023.261 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL729P | LL | YR24 Q1 | Q1 | MIP2023.261 | ML230596 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6544A | Tmn Flora Height | 6544A-MAC-001 Flora Height |  | L729P |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
594 |  | MIP2023.261 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL729P | LL | YR24 Q1 | Q1 | MIP2023.261 | ML230596 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-001 JBR |  | L729P |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
595 |  | MIP2023.261 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL729P | LL | YR24 Q1 | Q1 | MIP2023.261 | ML230596 | 2024-02-20 | NA | NA | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-002 JBR |  | L729P |  | NA |  | NA |  | NA |  | NA | [8 empty] | Drop - Ring Expansion | 7556.34
596 | Ring Expansion | MIP2023.345 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1029B-LL | LL | YR24 Q1 | Q1 | MIP2023.345 | ML228929 | 2024-02-07 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1029B | Wisma Central | 1029B-MAC-001 |  | 1029B-LL |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 6273.15
597 | Ring Expansion | MIP2023.345 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1029B-LL | LL | YR24 Q1 | Q1 | MIP2023.345 | ML228929 | 2024-02-07 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MAC(CX)-003 |  | 1029B-LL |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 6273.15
598 | Ring Expansion | MIP2023.346 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1273A-LL | LL | YR24 Q1 | Q1 | MIP2023.346 | ML228928 | 2024-02-07 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MCR-001 |  | 1273A-LL |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 6273.15
599 | Ring Expansion | MIP2023.346 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1273A-LL | LL | YR24 Q1 | Q1 | MIP2023.346 | ML228928 | 2024-02-07 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MCR-002 |  | 1273A-LL |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 6273.15
600 | Ring Expansion | MIP2023.346 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1273A-LL | LL | YR24 Q1 | Q1 | MIP2023.346 | ML228928 | 2024-02-07 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1273A | Binova | 1273A-MAC-001 |  | 1273A-LL |  | NA |  | NA |  | NA |  | NA | [7 empty] | Jun |  | 6273.15
601 | Ring Expansion | MIP2024.18 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- Colocated-Ring-3 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.18 | ML242480 | 2024-04-30 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MAC(CX)-003 KTN |  | Colocated-Ring-3 | [17 empty] | 8005.655
602 | Ring Expansion | MIP2024.18 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- Colocated-Ring-3 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.18 | ML242480 | 2024-04-30 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MAC(CX)-004 KTN |  | Colocated-Ring-3 | [17 empty] | 8005.655
603 | IP BREAK RING | MIP2024.19 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E207 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.19 | ML242479 | 2024-04-30 | NA | #N/A | NA | Eastern | Terengganu | 8303A | Bkt Bauk | 8303A-MAG-001 Bauk |  | E207 | [17 empty] | 9296.12
604 | IP BREAK RING | MIP2024.19 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E207 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.19 | ML242479 | 2024-04-30 | NA | #N/A | NA | Eastern | Terengganu | 8368A | Serating | 8368A-MAG(M14)-001 Serating |  | E207 | [17 empty] | 9296.12
605 | IP BREAK RING | MIP2024.19 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E207 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.19 | ML242479 | 2024-04-30 | NA | #N/A | NA | Eastern | Terengganu | 8303A | Bkt Bauk | 8303A-MAC-001 Bkt Bauk |  | E207 | [17 empty] | 9296.12
606 | IP BREAK RING | MIP2024.20 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E209 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.20 | ML238052 | 2024-03-27 | NA | #N/A | NA | Eastern | Terengganu | 8429B | Bkt Payung 2 | 8429B-MAG(M14)-001 Bpayung 2 |  | E209 | [17 empty] | 9296.12
607 | IP BREAK RING | MIP2024.20 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E209 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.20 | ML238052 | 2024-03-27 | NA | #N/A | NA | Eastern | Terengganu | 8368A | Serating | 8368A-MAC-001 Serating |  | E209 | [17 empty] | 9296.12
608 | IP BREAK RING | MIP2024.20 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E209 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.20 | ML238052 | 2024-03-27 | NA | #N/A | NA | Eastern | Terengganu | 8368A | Serating | 8368A-MAG(M14)-001 Serating |  | E209 | [17 empty] | 9296.12
609 | IP BREAK RING | MIP2024.21 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E301 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.21 | ML238050 | 2024-03-27 | NA | #N/A | NA | Eastern | Pahang | 8088A | Sg. Beto | 8088A-MAG-001 Sg.Beto |  | E301 | [17 empty] | 9296.12
610 | IP BREAK RING | MIP2024.21 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E301 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.21 | ML238050 | 2024-03-27 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | E301 | [17 empty] | 9296.12
611 | IP BREAK RING | MIP2024.21 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E301 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.21 | ML238050 | 2024-03-27 | NA | #N/A | NA | Eastern | Pahang | 8712A | Kg Jawa Pekan (trunk) | 8712A-MAC-001 Kg.Jawa Pekan |  | E301 | [17 empty] | 9296.12
612 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE01 |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
613 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | KTNPE01 |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
614 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Terengganu | 8367A | Bukit Kechil | 8367A-MAG(M14)-001 B.Kechil |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
615 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Kelantan | 8285A | Bukit Bunga | 8285A-MAG(M14)-001 Bukit Bunga |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
616 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Kelantan | 8224A | Pasir Puteh | 8224A-MAG(M14)-001 Pasir Puteh |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
617 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Kelantan | 8288B | Bukit Panau | 8288B-MAG(M14)-001 Panau |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
618 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Kelantan | 8211A | Wakaf Che Yeh | 8211A-MAG(M8)-001 WCY |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
619 | Ring Expansion (MAG-PE) | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.22 | ML238048 | 2024-03-27 | NA | #N/A | NA | Eastern | Kelantan | 8263A | Pasir Mas Town | 8263A-MAG(M14)-001 Pasir Mas Town |  | EAR01_1 & EAR01_3 | [17 empty] | 11300.8862
620 | Ring Expansion | MIP2024.24 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EL404 | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.24 | ML242477 | 2024-04-30 | NA | #N/A | NA | Eastern | Pahang | 8020A | Tempoyang | 8020A-MAC-001 Tempoyang |  | EL404 | [17 empty] | 7886.54
621 | Ring Expansion | MIP2024.24 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EL404 | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.24 | ML242477 | 2024-04-30 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-001 KTN |  | EL404 | [17 empty] | 7886.54
622 | Ring Expansion | MIP2024.24 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EL404 | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.24 | ML242477 | 2024-04-30 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | 8000A-MCR-002 KTN |  | EL404 | [17 empty] | 7886.54
623 | Ring Expansion | MIP2024.25 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S001 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.25 | ML238028 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MAC(CX)-003 JBR |  | S001 | [17 empty] | 6948.47
624 | Ring Expansion | MIP2024.25 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S001 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.25 | ML238028 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MAC(CX)-004 JBR |  | S001 | [17 empty] | 6948.47
625 | Ring Expansion | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.26 | ML238047 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-001 SNW |  | S002 | [17 empty] | 7873.01
626 | Ring Expansion | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.26 | ML238047 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-002 SNW |  | S002 | [17 empty] | 7873.01
627 | Ring Expansion | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.26 | ML238047 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MAC(CX)-001 SNW |  | S002 | [17 empty] | 7873.01
628 | Ring Expansion | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.26 | ML238047 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MAC(CX)-002 SNW |  | S002 | [17 empty] | 7873.01
629 | IP BREAK RING | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.27 | ML238027 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6104A | Bukit Kelicap | 6104A-MAG(M8)-001 Bkt Kelicap |  | S305 | [17 empty] | 8357.06
630 | IP BREAK RING | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.27 | ML238027 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 2402B | Pagoh Highway | 2402B-MAG(M14)-001 Pagoh Highway |  | S305 | [17 empty] | 8357.06
631 | IP BREAK RING | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.27 | ML238027 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6701A | Parit Sulong (Trunk) | 6701A-MAC-001 Parit Sulong |  | S305 | [17 empty] | 8357.06
632 | IP BREAK RING | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.27 | ML238027 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6093A | SRI MEDAN | 6093A-MAC-001 Sri Medan |  | S305 | [17 empty] | 8357.06
633 | IP BREAK RING | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.27 | ML238027 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6088A | ABI | 6088A-MAC-001 ABI |  | S305 | [17 empty] | 8357.06
634 | IP BREAK RING | MIP2024.28 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S306M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.28 | ML242478 | 2024-04-30 | NA | #N/A | NA | Southern | Johor | 6405A | Sri Bunian | 6405A-MAG-001 Sri Bunian |  | S306M | [17 empty] | 9296.12
635 | IP BREAK RING | MIP2024.28 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S306M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.28 | ML242478 | 2024-04-30 | NA | #N/A | NA | Southern | Johor | 6104A | Bukit Kelicap | 6104A-MAC-001 Bkt Kelicap |  | S306M | [17 empty] | 9296.12
636 | IP BREAK RING | MIP2024.28 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S306M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.28 | ML242478 | 2024-04-30 | NA | #N/A | NA | Southern | Johor | 6104A | Bukit Kelicap | 6104A-MAG(M8)-001 Bkt Kelicap |  | S306M | [17 empty] | 9296.12
637 | IP BREAK RING | MIP2024.29 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S313P_2 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.29 | #N/A | #N/A | NA | #N/A | NA | Southern | Melaka | 1554A | Rumbia | 1554A-MAG(M14)-001 Rumbia |  | S313P_2 | [17 empty] | 9296.12
638 | IP BREAK RING | MIP2024.29 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S313P_2 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.29 | #N/A | #N/A | NA | #N/A | NA | Southern | Melaka | 1553A | Umbai | 1553A-MAG(M14)-001 Umbai |  | S313P_2 | [17 empty] | 9296.12
639 | IP BREAK RING | MIP2024.29 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S313P_2 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.29 | #N/A | #N/A | NA | #N/A | NA | Southern | Melaka | 1533A | Bkt Duyung | 1533A-MAC-001 Bukit Duyong |  | S313P_2 | [17 empty] | 9296.12
640 | IP BREAK RING | MIP2024.30 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S403 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.30 | ML242475 | 2024-04-30 | NA | #N/A | NA | Southern | Negeri Sembilan | 1659A | Bahau Tower | 1659A-MAC-001 Bahau |  | S403 | [17 empty] | 9296.12
641 | IP BREAK RING | MIP2024.30 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S403 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.30 | ML242475 | 2024-04-30 | NA | #N/A | NA | Southern | Negeri Sembilan | 1659A | Bahau Tower | 1659A-MAG-001 Bahau Tower |  | S403 | [17 empty] | 9296.12
642 | IP BREAK RING | MIP2024.30 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S403 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.30 | ML242475 | 2024-04-30 | NA | #N/A | NA | Southern | Negeri Sembilan | 6212A | KTM GEMAS | 6212A-MAG-001 KTM Gemas |  | S403 | [17 empty] | 9296.12
643 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6151A | MERSING | 6151A-MAC-001 Mersing |  | S504M | [8 empty] | 2024-06-13 | [8 empty] | 7300.2463
644 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6166A | FELDA NITAR 2 | 6166A-MAC-001 Felda Nitar |  | S504M | [8 empty] | 2024-06-13 | [8 empty] | 7300.2463
645 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6160A | Bkt Tinggi | 6160A-MAC-001 Bkt Tinggi |  | S504M | [17 empty] | 7300.2463
646 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6138A | KAHANG | 6138A-MAC-001 Kahang Maxis |  | S504M | [8 empty] | 2024-06-13 | [8 empty] | 7300.2463
647 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6134A | KLUANG INDUSTRY (PROFINA) | 6134A-MAC-001 Kluang Industry |  | S504M | [17 empty] | 7300.2463
648 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6616A | Tmn Seri Permai | 6616A-MAC-001 Sri Permai |  | S504M | [8 empty] | 2024-06-13 | [8 empty] | 7300.2463
649 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6126A | KTM KLUANG | 6126A-MAG(M8)-001 KTM Kluang |  | S504M | [17 empty] | 7300.2463
650 | IP BREAK RING | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.31 | ML238046 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6369A | Sri Saujana | 6369A-MAG-002 Sri Saujana |  | S504M | [17 empty] | 7300.2463
651 | Ring Expansion | MIP2024.32 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S607M | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.32 | ML242474 | 2024-04-30 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-001 JBR |  | S607M | [17 empty] | 7886.54
652 | Ring Expansion | MIP2024.32 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S607M | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.32 | ML242474 | 2024-04-30 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-002 JBR |  | S607M | [17 empty] | 7886.54
653 | Ring Expansion | MIP2024.32 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S607M | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.32 | ML242474 | 2024-04-30 | NA | #N/A | NA | Southern | Johor | 6380A | Desaru Resort-100Q4(D Harmoni) | 6380A-MAC-001 Desaru Resort |  | S607M | [17 empty] | 7886.54
654 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-001 SNW |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
655 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-001 JBR |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
656 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Melaka | 1554A | Rumbia | 1554A-MAG(M14)-001 Rumbia |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
657 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6502A | Nusa Perintis(Watertank) | 6502A-MAG(M14)-001 Nusa Perintis |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
658 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Melaka | 1553A | Umbai | 1553A-MAG(M14)-001 Umbai |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
659 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6405A | Sri Bunian | 6405A-MAG(M14)-001 Sri Bunian |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
660 | PE-MCR | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.33 | ML238026 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6104A | Bukit Kelicap | 6104A-MAG(M8)-001 Bkt Kelicap |  | SAR03_i & SAR03_iii | [17 empty] | 11186.96
661 | Ring Expansion (MAG-PE) | MIP2024.34 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR06 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.34 | ML238045 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | JBRPE02 |  | SAR06 | [17 empty] | 11410.4933
662 | Ring Expansion (MAG-PE) | MIP2024.34 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR06 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.34 | ML238045 | 2024-03-27 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | KTNPE02 |  | SAR06 | [17 empty] | 11410.4933
663 | Ring Expansion (MAG-PE) | MIP2024.34 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR06 | DWDM | YR24 Q2 Q3 HW | Q3 | MIP2024.34 | ML238045 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6707A | Kg Jambi (Trunk) | 6707A-MAG-001 Jambi |  | SAR06 | [17 empty] | 11410.4933
664 | Ring Expansion | MIP2024.35 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL408P | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.35 | ML238043 | 2024-03-27 | NA | #N/A | NA | Southern | Melaka | 2124B | Zoo Melaka | 2124B-MAC-001 Zoo Melaka |  | SL408P | [17 empty] | 7886.54
665 | Ring Expansion | MIP2024.35 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL408P | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.35 | ML238043 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-001 SNW |  | SL408P | [17 empty] | 7886.54
666 | Ring Expansion | MIP2024.35 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL408P | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.35 | ML238043 | 2024-03-27 | NA | #N/A | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | 1621A-MCR-002 SNW |  | SL408P | [17 empty] | 7886.54
667 | Ring Expansion | MIP2024.36 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL732P | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.36 | ML238042 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-001 JBR |  | SL732P | [17 empty] | 6948.47
668 | Ring Expansion | MIP2024.36 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL732P | LL | YR24 Q2 Q3 HW | Q3 | MIP2024.36 | ML238042 | 2024-03-27 | NA | #N/A | NA | Southern | Johor | 6000A | MSC JB | 6000A-MCR-002 JBR |  | SL732P | [17 empty] | 6948.47
669 | Ring Expansion | MIP2024.38 CD Digi NIC ES BOQ- ZTE 2024 Q2- 3571B-LL | LL | YR24 Q2 ZTE | Q2 | MIP2024.38 | ML238430 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MAC(CX)-001 SHT |  | 3571B-LL | [17 empty] | 6582.645
670 | Ring Expansion | MIP2024.38 CD Digi NIC ES BOQ- ZTE 2024 Q2- 3571B-LL | LL | YR24 Q2 ZTE | Q2 | MIP2024.38 | ML238430 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 3571B | National Stadium Bukit Jalil | 3571B-MAC-001 National Stadium |  | 3571B-LL | [17 empty] | 6582.645
671 | IP BREAK RING | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.39 | ML238428 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MCR-002 SKB |  | AREA 154 | [17 empty] | 8343.3825
672 | IP BREAK RING | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.39 | ML238428 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1855B | TPM (AsiaSpace) | 1855B-MAC-001 TPM |  | AREA 154 | [17 empty] | 8343.3825
673 | IP BREAK RING | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.39 | ML238428 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1458A | Endah Parade | 1458A-MAC-001 Endah Parade |  | AREA 154 | [17 empty] | 8343.3825
674 | IP BREAK RING | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.39 | ML238428 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1458A | Endah Parade | 1458A-MAG-001 Endah Parade |  | AREA 154 | [17 empty] | 8343.3825
675 | IP BREAK RING | MIP2024.40 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0211+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.40 | ML238426 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1851A | KL Plaza 4th floor | 1851A-MAG(M14)-001 KL Plaza |  | C0211+ | [17 empty] | 8930.2933
676 | IP BREAK RING | MIP2024.40 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0211+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.40 | ML238426 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1859A | Midvalleycas | 1859A-MAG(M14)-001 Midvalley |  | C0211+ | [17 empty] | 8930.2933
677 | IP BREAK RING | MIP2024.40 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0211+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.40 | ML238426 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 2888A | Plaza Sentral Indoor | 2888A-MAC-001 Plaza Central |  | C0211+ | [17 empty] | 8930.2933
678 | IP BREAK RING | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.41 | ML238425 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2448A | Asmah Tower | 2448A-MAC-001 Asmah Tower |  | C0515+ | [17 empty] | 7051.6783
679 | IP BREAK RING | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.41 | ML238425 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2424A | PUAS Tmn Tun Perak | 2424A-MAC-001 PUAS Tmn Tun Perak |  | C0515+ | [17 empty] | 7051.6783
680 | IP BREAK RING | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.41 | ML238425 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2024A | Bdr Mahkota Cheras | 2024A-MAC-001 Bdr Mahkota Cheras |  | C0515+ | [17 empty] | 7051.6783
681 | IP BREAK RING | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.41 | ML238425 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1902B | Bdr Sg Long 3 | 1902B-MAC-001 Bdr Sg Long |  | C0515+ | [17 empty] | 7051.6783
682 | IP BREAK RING | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.41 | ML238425 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1039A | Cheras Jaya 2202 | 1039A-MAG(M14)-001 Cheras Jaya |  | C0515+ | [17 empty] | 7051.6783
683 | IP BREAK RING | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.41 | ML238425 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MCR-001 SKB |  | C0515+ | [17 empty] | 7051.6783
684 | IP BREAK RING | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.42 | ML238423 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MCR-001 SKB |  | C0607P+ | [17 empty] | 8343.3825
685 | IP BREAK RING | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.42 | ML238423 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1196A | JBA Puchong | 1196A-MAC-001 JBA Puchong |  | C0607P+ | [17 empty] | 8343.3825
686 | IP BREAK RING | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.42 | ML238423 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1408A | Puchong Jaya | 1408A-MAC-001 Puchong Jaya |  | C0607P+ | [17 empty] | 8343.3825
687 | IP BREAK RING | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.42 | ML238423 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1402A | Jln Ind Puchong | 1402A-MAG-001 Jalan Industry Puchong |  | C0607P+ | [17 empty] | 8343.3825
688 | Ring Expansion | MIP2024.43 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-1+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.43 | ML238424 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MAC(CX)-001 |  | Colocated-Ring-1+ | [8 empty] | July | [8 empty] | 6582.645
689 | Ring Expansion | MIP2024.43 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-1+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.43 | ML238424 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MAC(CX)-002 |  | Colocated-Ring-1+ | [8 empty] | July | [8 empty] | 6582.645
690 | Ring Expansion | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.44 | ML238422 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | 4000A-MAC(CX)-001 PRI |  | Colocated-Ring-4+ | [17 empty] | 8197.7383
691 | Ring Expansion | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.44 | ML238422 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | 4000A-MAC(CX)-002 PRI |  | Colocated-Ring-4+ | [17 empty] | 8197.7383
692 | Ring Expansion | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.44 | ML238422 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | 4000A-MAC(CX)-003 PRI |  | Colocated-Ring-4+ | [17 empty] | 8197.7383
693 | Ring Expansion | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.44 | ML238422 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | 4000A-MAC(CX)-004 PRI |  | Colocated-Ring-4+ | [17 empty] | 8197.7383
694 | Ring Expansion | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.44 | ML238422 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | 4000A-MCR-001 PRI |  | Colocated-Ring-4+ | [17 empty] | 8197.7383
695 | Ring Expansion | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | YR24 Q2 ZTE | Q2 | MIP2024.44 | ML238422 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | 4000A-MCR-002 PRI |  | Colocated-Ring-4+ | [17 empty] | 8197.7383
696 | IP BREAK RING | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.45 | ML238427 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MCR-002 SHT |  | CT0241P+ | [17 empty] | 7991.234
697 | IP BREAK RING | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.45 | ML238427 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1918A | Damansara Intan | 1918A-MAG(M14)-001 Damansara Intan |  | CT0241P+ | [17 empty] | 7991.234
698 | IP BREAK RING | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.45 | ML238427 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1197A | JBAEFF | 1197A-MAC-002 JBA Effingham |  | CT0241P+ | [17 empty] | 7991.234
699 | IP BREAK RING | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.45 | ML238427 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1197A | JBAEFF | 1197A-MAC-001 JBA Effingham |  | CT0241P+ | [17 empty] | 7991.234
700 | IP BREAK RING | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.45 | ML238427 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1211A | KDU | 1211A-MAC-001 KDU |  | CT0241P+ | [17 empty] | 7991.234
701 | IP BREAK RING | MIP2024.46 CD Digi NIC ES BOQ- ZTE 2024 Q2- MAC Ring 15/ C21+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.46 | ML238421 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1458A | Endah Parade | 1458A-MAG-001 Endah Parade |  | MAC Ring 15/ C21+ | [17 empty] | 7639.83
702 | IP BREAK RING | MIP2024.46 CD Digi NIC ES BOQ- ZTE 2024 Q2- MAC Ring 15/ C21+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.46 | ML238421 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 2502A | PUAS Bdr Tun Razak | 2502A-MAC-001 Bdar Tun Razak |  | MAC Ring 15/ C21+ | [17 empty] | 7639.83
703 | IP BREAK RING | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.47 | ML238354 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4995A | Changloon UUM | 4995A-MAG-001 UUM Highway |  | N104+ | [17 empty] | 7417.505
704 | IP BREAK RING | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.47 | ML238354 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4995A | Changloon UUM | 4995A-MAC-001 UUM Highway |  | N104+ | [17 empty] | 7417.505
705 | IP BREAK RING | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.47 | ML238354 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4992A | Pendang | 4992A-MAG(M14)-001 Pendang |  | N104+ | [17 empty] | 7417.505
706 | IP BREAK RING | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.47 | ML238354 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4991A | UUM | 4991A-MAC-001 UUM |  | N104+ | [17 empty] | 7417.505
707 | IP BREAK RING | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.47 | ML238354 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4672A | CHANGLOON | 4672A-MAC-001 Changloon |  | N104+ | [17 empty] | 7417.505
708 | IP BREAK RING | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.47 | ML238354 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4665A | Jitra | 4665A-MAC-001 Jitra |  | N104+ | [17 empty] | 7417.505
709 | IP BREAK RING | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.48 | ML238348 | 2024-03-29 | NA | #N/A | NA | Northern | Perlis | 4604A | JBA KUAL PERLIS | 4604A-MAC-001 Kuala Perlis |  | N107+ | [17 empty] | 7417.505
710 | IP BREAK RING | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.48 | ML238348 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4601A | Federal Kangar | 4601A-MAC-001 Federal Kangar |  | N107+ | [17 empty] | 7417.505
711 | IP BREAK RING | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.48 | ML238348 | 2024-03-29 | NA | #N/A | NA | Northern | Perlis | 4612A | Jalan Kaki Bukit | 4612A-MAC-001 Jln Kaki Bkt |  | N107+ | [17 empty] | 7417.505
712 | IP BREAK RING | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.48 | ML238348 | 2024-03-29 | NA | #N/A | NA | Northern | Perlis | 4613A | Berseri Perlis | 4613A-MAC-001 Taman Bestari Perlis |  | N107+ | [17 empty] | 7417.505
713 | IP BREAK RING | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.48 | ML238348 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4998A | Air Itam Kedah | 4998A-MAG(M14)-001 Air Itam Kedah |  | N107+ | [17 empty] | 7417.505
714 | IP BREAK RING | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.48 | ML238348 | 2024-03-29 | NA | #N/A | NA | Northern | Perlis | 4606A | KTM Padang Besar | 4606A-MAG(M8)-001 Padang Besar |  | N107+ | [17 empty] | 7417.505
715 | IP BREAK RING | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.49 | ML238346 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4432A | KTM Sg Siput | 4432A-MAG-001 KTM Sungai Siput |  | N405+ | [17 empty] | 8357.06
716 | IP BREAK RING | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.49 | ML238346 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4379A | Bukit Mercu | 4379A-MAC-001 Bkt Mercu |  | N405+ | [17 empty] | 8357.06
717 | IP BREAK RING | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.49 | ML238346 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4378A | Jerlun Tower | 4378A-MAC-001 Jerlun Tower |  | N405+ | [17 empty] | 8357.06
718 | IP BREAK RING | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.49 | ML238346 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4374A | LAP Talang RDD | 4374A-MAC-001 LAP Talang |  | N405+ | [17 empty] | 8357.06
719 | IP BREAK RING | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.49 | ML238346 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4455A | KTM Taiping | 4455A-MAG(M14)-001 KTM Taiping |  | N405+ | [17 empty] | 8357.06
720 | IP BREAK RING | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.50 | ML238360 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4506A | Perak Taipu Assc | 4506A-MAC-001 Perak Taipu |  | N408+ | [17 empty] | 8357.06
721 | IP BREAK RING | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.50 | ML238360 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4546A | KWSP Ipoh RDD | 4546A-MAC-001 KWSP Ipoh |  | N408+ | [17 empty] | 8357.06
722 | IP BREAK RING | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.50 | ML238360 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4515A | TG RAMBUTAN | 4515A-MAC-001 Tg Rambutan |  | N408+ | [17 empty] | 8357.06
723 | IP BREAK RING | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.50 | ML238360 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4432A | KTM Sg Siput | 4432A-MAG-001 KTM Sungai Siput |  | N408+ | [17 empty] | 8357.06
724 | IP BREAK RING | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.50 | ML238360 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4493A | KTM IPOH | 4493A-MAG-001 KTM Ipoh |  | N408+ | [17 empty] | 8357.06
725 | IP BREAK RING | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.51 | ML238340 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4432A | KTM Sg Siput | 4432A-MAG-001 KTM Sungai Siput |  | N411+ | [17 empty] | 8357.06
726 | IP BREAK RING | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.51 | ML238340 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4433A | LAP Sg Siput | 4433A-MAC-001 LAP Sg Siput |  | N411+ | [17 empty] | 8357.06
727 | IP BREAK RING | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.51 | ML238340 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4377B | Karai | 4377B-MAC-001 Karai |  | N411+ | [17 empty] | 8357.06
728 | IP BREAK RING | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.51 | ML238340 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4373A | KTM K.Kangsar | 4373A-MAC-001 KTM K.Kangsar |  | N411+ | [17 empty] | 8357.06
729 | IP BREAK RING | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.51 | ML238340 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4455A | KTM Taiping | 4455A-MAG(M14)-001 KTM Taiping |  | N411+ | [17 empty] | 8357.06
730 | Ring Expansion (MAG-PE) | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | LL / DWDM | YR24 Q2 ZTE | Q2 | MIP2024.52 | ML238359 | 2024-03-29 | NA | #N/A | NA | Sabah | Sabah | 7000A | KK MSC | KKBPE02 |  | 7124A-MAG-001&002 | [17 empty] | 9745.68
731 | Ring Expansion (MAG-PE) | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | LL / DWDM | YR24 Q2 ZTE | Q2 | MIP2024.52 | ML238359 | 2024-03-29 | NA | #N/A | NA | Sabah | Sabah | 7000A | KK MSC | KKBPE01 |  | 7124A-MAG-001&002 | [17 empty] | 9745.68
732 | Ring Expansion (MAG-PE) | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | LL / DWDM | YR24 Q2 ZTE | Q2 | MIP2024.52 | ML238359 | 2024-03-29 | NA | #N/A | NA | Sabah | Sabah | 7124A | Land Trig Hill | 7124A-MAG(M14)-001 Trig Hill |  | 7124A-MAG-001&002 | [17 empty] | 9745.68
733 | Ring Expansion (MAG-PE) | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | LL / DWDM | YR24 Q2 ZTE | Q2 | MIP2024.52 | ML238359 | 2024-03-29 | NA | #N/A | NA | Sabah | Sabah | 7124A | Land Trig Hill | 7124A-MAG(M14)-002 Trig Hill |  | 7124A-MAG-001&002 | [17 empty] | 9745.68
734 | Ring Expansion (MAG-PE) | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | LL | YR24 Q2 ZTE | Q2 | MIP2024.53 | ML238358 | 2024-03-29 | NA | #N/A | NA | Sarawak | Sarawak | 9368A | Salim Road Sacofa | 9368A-MAG(M8)-001 Salim Road |  | 9368A-MAG-001&002 | [17 empty] | 12738.6725
735 | Ring Expansion (MAG-PE) | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | LL | YR24 Q2 ZTE | Q2 | MIP2024.53 | ML238358 | 2024-03-29 | NA | #N/A | NA | Sarawak | Sarawak | 9368A | Salim Road Sacofa | 9368A-MAG(M8)-002 Salim Road |  | 9368A-MAG-001&002 | [17 empty] | 12738.6725
736 | Ring Expansion (MAG-PE) | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | LL | YR24 Q2 ZTE | Q2 | MIP2024.53 | ML238358 | 2024-03-29 | NA | #N/A | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Nokia KCHPE01 |  | 9368A-MAG-001&002 | [17 empty] | 12738.6725
737 | Ring Expansion (MAG-PE) | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | LL | YR24 Q2 ZTE | Q2 | MIP2024.53 | ML238358 | 2024-03-29 | NA | #N/A | NA | Sarawak | Sarawak | 9999A | Kuching MSC | Nokia KCHPE02 |  | 9368A-MAG-001&002 | [17 empty] | 12738.6725
738 | Ring Expansion (MAG-PE) | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.54 | ML238357 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1253A | Plaza Pengkalen | 1253A-MAG(M14)-001 Plaza Pengkalan |  | CAR02-i+ | [17 empty] | 8154.1
739 | Ring Expansion (MAG-PE) | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.54 | ML238357 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1851A | KL Plaza 4th floor | 1851A-MAG(M14)-001 KL Plaza 2 |  | CAR02-i+ | [17 empty] | 8154.1
740 | Ring Expansion (MAG-PE) | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.54 | ML238357 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1859A | Midvalleycas | 1859A-MAG(M14)-001 Midvalley |  | CAR02-i+ | [17 empty] | 8154.1
741 | Ring Expansion (MAG-PE) | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.54 | ML238357 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | KPGPE02 |  | CAR02-i+ | [17 empty] | 8154.1
742 | Ring Expansion (MAG-PE) | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.54 | ML238357 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | SHTPE02 |  | CAR02-i+ | [17 empty] | 8154.1
743 | Ring Expansion (MAG-PE) | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.55 | ML238353 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1172A | Glomac | 1172A-MAG(M14)-001 Glomac |  | CAR02-ii+ | [17 empty] | 8658.408
744 | Ring Expansion (MAG-PE) | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.55 | ML238353 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1918A | Damansara Intan | 1918A-MAG(M14)-001 Damansara Intan |  | CAR02-ii+ | [17 empty] | 8658.408
745 | Ring Expansion (MAG-PE) | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.55 | ML238353 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1859A | Midvalleycas | 1859A-MAG(M14)-001 Midvalley |  | CAR02-ii+ | [17 empty] | 8658.408
746 | Ring Expansion (MAG-PE) | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.55 | ML238353 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | KPGPE02 |  | CAR02-ii+ | [17 empty] | 8658.408
747 | Ring Expansion (MAG-PE) | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.55 | ML238353 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | SHTPE02 |  | CAR02-ii+ | [17 empty] | 8658.408
748 | Ring Expansion (MAG-PE) | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.56 | ML238352 | 2024-03-29 | NA | #N/A | NA | Northern | Perlis | 4606A | KTM Padang Besar | 4606A-MAG(M8)-001 Padang Besar |  | NAR01_iii+ | [17 empty] | 8716.774
749 | Ring Expansion (MAG-PE) | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.56 | ML238352 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4995A | Changloon UUM | 4995A-MAG(M14)-001 UUM Highway |  | NAR01_iii+ | [17 empty] | 8716.774
750 | Ring Expansion (MAG-PE) | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.56 | ML238352 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4992A | Pendang | 4992A-MAG(M14)-001 Pendang |  | NAR01_iii+ | [17 empty] | 8716.774
751 | Ring Expansion (MAG-PE) | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.56 | ML238352 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE02 |  | NAR01_iii+ | [17 empty] | 8716.774
752 | Ring Expansion (MAG-PE) | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.56 | ML238352 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4521A | MSC Ipoh | IPHPE02 |  | NAR01_iii+ | [17 empty] | 8716.774
753 | Ring Expansion (MAG-PE) | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.57 | ML238351 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE01 |  | NAR02_ii+ | [17 empty] | 7652.0225
754 | Ring Expansion (MAG-PE) | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.57 | ML238351 | 2024-03-29 | NA | #N/A | NA | Eastern | Pahang | 8000A | MSC Kuantan | KTNPE01 |  | NAR02_ii+ | [17 empty] | 7652.0225
755 | Ring Expansion (MAG-PE) | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.57 | ML238351 | 2024-03-29 | NA | #N/A | NA | Northern | Kedah | 4985A | BALING TOWN | 4985A-MAG-001 Baling Town |  | NAR02_ii+ | [17 empty] | 7652.0225
756 | Ring Expansion (MAG-PE) | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.57 | ML238351 | 2024-03-29 | NA | #N/A | NA | Eastern | Kelantan | 8282B | Tasik Pergau | 8282B-MAG-003 Pergau |  | NAR02_ii+ | [17 empty] | 7652.0225
757 | Ring Expansion (MAG-PE) | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.58 | ML238350 | 2024-03-29 | NA | #N/A | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE02 |  | NAR04_ii+ | [17 empty] | 8114.044
758 | Ring Expansion (MAG-PE) | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.58 | ML238350 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4521A | MSC Ipoh | IPHPE02 |  | NAR04_ii+ | [17 empty] | 8114.044
759 | Ring Expansion (MAG-PE) | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.58 | ML238350 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4493A | KTM IPOH | 4493A-MAG(M14)-001 KTM Ipoh |  | NAR04_ii+ | [17 empty] | 8114.044
760 | Ring Expansion (MAG-PE) | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.58 | ML238350 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4432A | KTM Sg Siput | 4432A-MAG(M14)-001 KTM Sungai Siput |  | NAR04_ii+ | [17 empty] | 8114.044
761 | Ring Expansion (MAG-PE) | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.58 | ML238350 | 2024-03-29 | NA | #N/A | NA | Northern | Perak | 4455A | KTM Taiping | 4455A-MAG(M14)-001 KTM Taiping |  | NAR04_ii+ | [17 empty] | 8114.044
762 | IP BREAK RING | MIP2024.59 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0126 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.59 | ML242493 | 2024-04-30 | NA | NA | NA | Central | Selangor | 1364B | Subang Bestari | 1364B-MAC-001 Bestari |  | C0126 | [17 empty] | 11124.51
763 | IP BREAK RING | MIP2024.59 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0126 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.59 | ML242493 | 2024-04-30 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | 1049B-MCR-002 KPG |  | C0126 | [17 empty] | 11124.51
764 | IP BREAK RING | MIP2024.59 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0126 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.59 | ML242493 | 2024-04-30 | NA | NA | NA | Central | Selangor | 1409A | Kota Damansara | 1409A-MAG(M14)-001 Kota Damansara |  | C0126 | [17 empty] | 11124.51
765 | IP BREAK RING | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.60 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1851A | KL Plaza 4th floor | 1851A-MAG(M14)001 |  | 1063B-Linear+ & Area 79_2+ | [17 empty] | 8108.8633
766 | IP BREAK RING | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.60 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1461A | Shaw Parade | 1461A |  | 1063B-Linear+ & Area 79_2+ | [17 empty] | 8108.8633
767 | IP BREAK RING | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.60 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1745A | Baitumal | 1745A |  | 1063B-Linear+ & Area 79_2+ | [17 empty] | 8108.8633
768 | IP BREAK RING | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.60 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1745A | Baitumal | 1745A-MAG-001 |  | 1063B-Linear+ & Area 79_2+ | [17 empty] | 8108.8633
769 | IP BREAK RING | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.60 | #N/A | #N/A | NA | NA | NA | Central | WILAYAH PERSEKUTUAN KUALA LUMPUR | 1722E | UE3 Plaza | 1722E |  | 1063B-Linear+ & Area 79_2+ | [17 empty] | 8108.8633
770 | IP BREAK RING | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.60 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MCR-001 |  | 1063B-Linear+ & Area 79_2+ | [17 empty] | 8108.8633
771 |  | MIP2024.61 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1288A-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.61 | ML243421 | 2024-05-06 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MCR-002 SHT |  | 1288A-LL+ | [16 empty] | Drop - Ring Expansion | 8930.2933
772 |  | MIP2024.61 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1288A-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.61 | ML243421 | 2024-05-06 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | 2021B-MCR-001 SHT |  | 1288A-LL+ | [16 empty] | Drop - Ring Expansion | 8930.2933
773 |  | MIP2024.61 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1288A-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.61 | ML243421 | 2024-05-06 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1288A | JBA Wangsa.Maju | 1288A-MAC-001 JBA Wangsa Maju |  | 1288A-LL+ | [16 empty] | Drop - Ring Expansion | 8930.2933
774 | Ring Expansion | MIP2024.62 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9294A-LL+ (3x1G) | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.62 | ML242944 | 2024-05-02 | NA | NA | NA | Sarawak | Sarawak | 9294A | Marudi (SACOFA) | 9294A-MAC-001 Marudi |  | 9294A-LL+ (3x1G) | [17 empty] | 8163.51
775 | Ring Expansion | MIP2024.63 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9710A-LL+ (2 x 1G) | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.63 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9710A | TT844 | 9710A-MAC-001 |  | 9710A-LL+ (2 x 1G) | [17 empty] | 8163.51
776 | IP BREAK RING | MIP2024.64 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0319P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.64 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1271A | Risda | 1271A-MAG-001 Risda |  | C0319P+ | [17 empty] | 7639.83
777 | IP BREAK RING | MIP2024.64 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0319P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.64 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1270A | Puteri Park Plaza | 1270A-MAC-001 Puteri Park Plaza |  | C0319P+ | [17 empty] | 7639.83
778 | IP BREAK RING | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.65 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1304A | MMA | 1304A-MAG-001 MMA |  | C0407P+ | [17 empty] | 7991.234
779 | IP BREAK RING | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.65 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1745A | Baitumal | 1745A-MAG(M14)-001 Baitumal |  | C0407P+ | [17 empty] | 7991.234
780 | IP BREAK RING | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.65 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1737A | Bernama - Rack 1 | 1737A-MAC-001 Bernama |  | C0407P+ | [17 empty] | 7991.234
781 | IP BREAK RING | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.65 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1737A | Bernama - Rack 1 | 1737A-MAC-002 Bernama |  | C0407P+ | [17 empty] | 7991.234
782 | IP BREAK RING | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.65 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1266A | Sucasa | 1266A-MAC-001 Sucasa |  | C0407P+ | [17 empty] | 7991.234
783 | IP BREAK RING | MIP2024.66 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C1101+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.66 | #N/A | #N/A | NA | NA | NA | Eastern | Pahang | 8709A | Bentong (Trunk) | 8709A-MAG-003 Bentong |  | C1101+ | [17 empty] | 7886.54
784 | IP BREAK RING | MIP2024.66 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C1101+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.66 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 2070B | Sri Gombak | 2070B-MAG-001 Gombak |  | C1101+ | [17 empty] | 7886.54
785 | IP BREAK RING | MIP2024.66 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C1101+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.66 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 2070B | Sri Gombak | 2070B-MAC-001 Gombak |  | C1101+ | [17 empty] | 7886.54
786 | IP BREAK RING | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.67 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1270A | Puteri Park Plaza | 1270A-MAG-001 Puteri Park Plaza |  | CT0316P+ | [17 empty] | 8343.3825
787 | IP BREAK RING | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.67 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1271A | Risda | 1271A-MAG-001 Risda |  | CT0316P+ | [17 empty] | 8343.3825
788 | IP BREAK RING | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.67 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1747A | Jln Ampng Besar | 1747A-MAC-001 Jln. Besar Ampang |  | CT0316P+ | [17 empty] | 8343.3825
789 | IP BREAK RING | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.67 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 2805A | Ampang City Plaza | 2805A-MAC-001 Ampang City |  | CT0316P+ | [17 empty] | 8343.3825
790 | IP BREAK RING | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.68 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1465A | JBA TMN SEGAR L1 | 1465A-MAG-001 JBA Taman Segar |  | CT031P_2+ | [17 empty] | 8343.3825
791 | IP BREAK RING | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.68 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1270A | Puteri Park Plaza | 1270A-MAG-001 Puteri Park Plaza |  | CT031P_2+ | [17 empty] | 8343.3825
792 | IP BREAK RING | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.68 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1903B | Kemacahaya | 1903B-MAC-001 Tmn Kemacahaya |  | CT031P_2+ | [17 empty] | 8343.3825
793 | IP BREAK RING | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.68 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1905B | Ampang Lookout Point | 1905B-MAC-001 Ampang Lookout Point |  | CT031P_2+ | [17 empty] | 8343.3825
794 | IP BREAK RING | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.69 | #N/A | #N/A | NA | NA | NA | Northern | Perlis | 4606A | KTM Padang Besar | 4606A-MAC-001 KTM Padang Besar |  | N112PM+ | [17 empty] | 8357.06
795 | IP BREAK RING | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.69 | #N/A | #N/A | NA | NA | NA | Northern | Perlis | 4605A | KTM Arau | 4605A-MAC-001 KTM Arau |  | N112PM+ | [17 empty] | 8357.06
796 | IP BREAK RING | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.69 | #N/A | #N/A | NA | NA | NA | Northern | Perlis | 4606B | Arau Trunk | 4606B-MAC-001 Arau |  | N112PM+ | [17 empty] | 8357.06
797 | IP BREAK RING | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.69 | #N/A | #N/A | NA | NA | NA | Northern | Kedah | 4995A | Changloon UUM | 4995A-MAG(M14)-001 UUM Highway |  | N112PM+ | [17 empty] | 8357.06
798 | IP BREAK RING | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.69 | #N/A | #N/A | NA | NA | NA | Northern | Perlis | 4606A | KTM Padang Besar | 4606A-MAG(M8)-001 Padang Besar |  | N112PM+ | [17 empty] | 8357.06
799 | IP BREAK RING | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.70 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4331A | Bagan Serai | 4331A-MAG-001 Bagan Serai |  | N304+ | [17 empty] | 8357.06
800 | IP BREAK RING | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.70 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4310A | Matang Acheh | 4310A-MAG-001 Kampung Matang Acheh |  | N304+ | [17 empty] | 8357.06
801 | IP BREAK RING | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.70 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4331A | Bagan Serai | 4331A-MAC-001 Bagan Serai |  | N304+ | [17 empty] | 8357.06
802 | IP BREAK RING | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.70 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4391B | Sg Gedung (Maxis) RDD | 4391B-MAC-001 Sg Gedung |  | N304+ | [17 empty] | 8357.06
803 | IP BREAK RING | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.70 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4736A | Jebong | 4736A-MAC-001 Jebong |  | N304+ | [17 empty] | 8357.06
804 | IP BREAK RING | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | OPM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.71 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4521A | MSC Ipoh | 4521A-MCR-002 Ipoh |  | N305+ | [17 empty] | 8709.2075
805 | IP BREAK RING | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | OPM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.71 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4734A | Kg Teluk Kepayang (trunk) | 4734A-MAC-001 Kg Teluk Kepayang |  | N305+ | [17 empty] | 8709.2075
806 | IP BREAK RING | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | OPM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.71 | #N/A | #N/A | NA | NA | NA | Northern | PERAK | 4490A | Kg Merbau | 4490A-MAC-001 Kg Merbau |  | N305+ | [17 empty] | 8709.2075
807 | IP BREAK RING | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | OPM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.71 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4310A | Matang Acheh | 4310A-MAG-001 Kampung Matang Acheh |  | N305+ | [17 empty] | 8709.2075
808 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4472A | Durian Sebatang | 4472A-MAG-001 Durian Sebatang |  | N503+ | [17 empty] | 7350.5
809 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4473A | Hutan Melintang | 4473A-MAG-001 Hutan Melintang |  | N503+ | [17 empty] | 7350.5
810 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4472A | Durian Sebatang | 4472A-MAC-001 Durian Sebatang |  | N503+ | [17 empty] | 7350.5
811 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4580B | Jenderata Perak | 4580B-MAC-001 J'derata Perak |  | N503+ | [17 empty] | 7350.5
812 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4740B | Hutan Melintang Industry | 4740B-MAC-001 Hutan Melintang Industry |  | N503+ | [17 empty] | 7350.5
813 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4470B | Bagan Pasir | 4470B-MAC-001 Bagan Pasir |  | N503+ | [17 empty] | 7350.5
814 | IP BREAK RING | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.72 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4473A | Hutan Melintang | 4473A-MAC-001 Hutan Melintang |  | N503+ | [17 empty] | 7350.5
815 | IP BREAK RING | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.73 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4440B | Tapah Road | 4440B-MAG-001 Tapah Road |  | N602+ | [17 empty] | 7417.505
816 | IP BREAK RING | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.73 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4412A | KTM Sungkai | 4412A-MAG-001 KTM Sungkai |  | N602+ | [17 empty] | 7417.505
817 | IP BREAK RING | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.73 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4732A | Ladang Tapah (trunk) | 4732A-MAC-001 Ladang Tapah |  | N602+ | [17 empty] | 7417.505
818 | IP BREAK RING | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.73 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4442A | Bukit Temoh | 4442A-MAC-001 Bukit Temoh |  | N602+ | [17 empty] | 7417.505
819 | IP BREAK RING | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.73 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4311A | Dunlop Kliniktrak | 4311A-MAC-001 Dunlop Kliniktrak |  | N602+ | [17 empty] | 7417.505
820 | IP BREAK RING | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.73 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4414A | SUNGKAI LAND | 4414A-MAC-001 Sungkai Land |  | N602+ | [17 empty] | 7417.505
821 | Ring Expansion | MIP2024.74 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- New Ring_7+ | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.74 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4517A | Pengkalan Industry | 4517A-MAC-001 Pengkalan Industry |  | New Ring_7+ | [17 empty] | 6948.47
822 | Ring Expansion | MIP2024.74 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- New Ring_7+ | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.74 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4323A | LAP Bemban | 4323A-MAC-001 LAP Bemban |  | New Ring_7+ | [17 empty] | 6948.47
823 | PE-MCR | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.75 | #N/A | #N/A | NA | NA | NA | Sabah | Sabah | 7100A | Muhibah Lahad Datu | 7100A-MAG(M14)-001 MLD |  | 7100A-MAG-LL+ | [17 empty] | 10981.43
824 | PE-MCR | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.75 | #N/A | #N/A | NA | NA | NA | Sabah | Sabah | 7100A | Muhibah Lahad Datu | 7100A-MAG(M14)-002 MLD |  | 7100A-MAG-LL+ | [17 empty] | 10981.43
825 | PE-MCR | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.75 | #N/A | #N/A | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KKBPE01 |  | 7100A-MAG-LL+ | [17 empty] | 10981.43
826 | PE-MCR | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.75 | #N/A | #N/A | NA | NA | NA | Sabah | Sabah | 7000A | KK MSC | KKBPE02 |  | 7100A-MAG-LL+ | [17 empty] | 10981.43
827 | Ring Expansion (MAG-PE) | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.76 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9074A | MSC Miri | 9074A-MAG(M8)-001 CHM |  | 9074A-MAG-LL+ | [17 empty] | 10624.3
828 | Ring Expansion (MAG-PE) | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.76 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9074A | MSC Miri | 9074A-MAG(M8)-002 CHM |  | 9074A-MAG-LL+ | [17 empty] | 10624.3
829 | Ring Expansion (MAG-PE) | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.76 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | KCHPE01 |  | 9074A-MAG-LL+ | [17 empty] | 10624.3
830 | Ring Expansion (MAG-PE) | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.76 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | KCHPE02 |  | 9074A-MAG-LL+ | [17 empty] | 10624.3
831 | Ring Expansion (MAG-PE) | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.77 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9106A | Bkt Nyabau | 9106A-MAG(M14)-001 NYB |  | 9106A-MAG-LL+ | [17 empty] | 8867.0575
832 | Ring Expansion (MAG-PE) | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.77 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9106A | Bkt Nyabau | 9106A-MAG(M14)-002 NYB |  | 9106A-MAG-LL+ | [17 empty] | 8867.0575
833 | Ring Expansion (MAG-PE) | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.77 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | KCHPE01 |  | 9106A-MAG-LL+ | [17 empty] | 8867.0575
834 | Ring Expansion (MAG-PE) | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | LL | YR24 Q3 Q4 ZTE | Q4 | MIP2024.77 | #N/A | #N/A | NA | NA | NA | Sarawak | Sarawak | 9999A | Kuching MSC | KCHPE02 |  | 9106A-MAG-LL+ | [17 empty] | 8867.0575
835 | PE-MCR | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.78 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | KPGPE02 |  | CAR03 | [17 empty] | 9166.05
836 | PE-MCR | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.78 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | SKBPE02 |  | CAR03 | [17 empty] | 9166.05
837 | PE-MCR | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.78 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1002A | Sri Murni | 1002A-MAG(M14)-001 Sri Murni Selayang |  | CAR03 | [17 empty] | 9166.05
838 | PE-MCR | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.78 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1465A | JBA TMN SEGAR L1 | 1465A-MAG(M14)-001 JBA Taman Segar |  | CAR03 | [17 empty] | 9166.05
839 | PE-MCR | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.78 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1207A | Puteri Park Plaza | 1207A-MAG(M14)-001 Puteri Park Plaza |  | CAR03 | [17 empty] | 9166.05
840 | PE-MCR | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.78 | #N/A | #N/A | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1271A | Risda | 1271A-MAG(M14)-001 Risda |  | CAR03 | [17 empty] | 9166.05
841 | Ring Expansion (MAG-PE) | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.79 | ML243413 | 2024-05-06 | NA | NA | NA | Eastern | Pahang | 8709A | Bentong (Trunk) | 8709A-MAG-003 Bentong |  | CAR11+ | [17 empty] | 10732.1225
842 | Ring Expansion (MAG-PE) | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.79 | ML243413 | 2024-05-06 | NA | NA | NA | Central | Selangor | 2070B | Sri Gombak | 2070B-MAG-001 Gombak |  | CAR11+ | [17 empty] | 10732.1225
843 | Ring Expansion (MAG-PE) | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.79 | ML243413 | 2024-05-06 | NA | NA | NA | Eastern | Pahang | 8000A | MSC Kuantan | KTNPE02 |  | CAR11+ | [17 empty] | 10732.1225
844 | Ring Expansion (MAG-PE) | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | DWDM | YR24 Q3 Q4 ZTE | Q4 | MIP2024.79 | ML243413 | 2024-05-06 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | KPGPE02 |  | CAR11+ | [17 empty] | 10732.1225
845 | IP BREAK RING | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.37 | ML238431 | 2024-03-29 | NA | #N/A | NA | Central | Selangor | 1475A | BSC Sri Kembangan | 1475A-MCR-001 SKB |  | 1063B-Linear (in PFS swap plan) | [17 empty] | 7286.195
846 | IP BREAK RING | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.37 | ML238431 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1851A | KL Plaza 4th floor | 1851A-MAG(M14)-001 KL Plaza |  | 1063B-Linear (in PFS swap plan) | [17 empty] | 7286.195
847 | IP BREAK RING | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.37 | ML238431 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1246A | Complex Nagaria | Berjaya Plaza 1246A |  | 1063B-Linear (in PFS swap plan) | [17 empty] | 7286.195
848 | IP BREAK RING | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | DWDM | YR24 Q2 ZTE | Q2 | MIP2024.37 | ML238431 | 2024-03-29 | NA | #N/A | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1063B | BERJAYA TIMES SQUARE | Berjaya Time Square 1063B |  | 1063B-Linear (in PFS swap plan) | [17 empty] | 7286.195
849 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8381A | Jambu Bongkok (Celcom) | 8381A-MAC-001 | 1 | E207 | FO&T | [16 empty] | 27469.6943 | 17059.6563
850 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8303A | Bkt Bauk | 8303A-MAC-001 | 2 | E207 | FO&T | [16 empty] | 27469.6943 | 17059.6563
851 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8303A | Bkt Bauk | 8303A-MAC-002 | 2 | E207 | FO&T | [16 empty] | 27469.6943 | 17059.6563
852 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8301A | UMNO Dungun | 8301A-MAC-001 | 1 | E207 | FO&T | [16 empty] | 27469.6943 | 17059.6563
853 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8368A | Serating | 8368A-MAC-001 | 1 | E209 | FO&T | [16 empty] | 27469.6943 | 17059.6563
854 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8356A | Padang Midin | 8356A-MAC-001 | 1 | E209 | FO&T | [16 empty] | 27469.6943 | 17059.6563
855 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Terengganu | 8360A | Bkt Chendering | 8360A-MAC-001 | 1 | E209 | FO&T | [16 empty] | 27469.6943 | 17059.6563
856 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8712A | Kg Jawa Pekan (trunk) | 8712A-MAC-001 | 2 | E301 | FO&T | [16 empty] | 27469.6943 | 17059.6563
857 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8712A | Kg Jawa Pekan (trunk) | 8712A-MAC-002 | 2 | E301 | FO&T | [16 empty] | 27469.6943 | 17059.6563
858 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8087A | #N/A | 8087A-MAC-001 | 1 | E301 | FO&T | [16 empty] | 27469.6943 | 17059.6563
859 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8085A | #N/A | 8085A-MAC-001 | 1 | E301 | FO&T | [16 empty] | 27469.6943 | 17059.6563
860 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8067A | #N/A | 8067A-MAC-001 | 1 | E301 | FO&T | [16 empty] | 27469.6943 | 17059.6563
861 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8038A | #N/A | 8038A-MAC-001 | 1 | E301 | FO&T | [16 empty] | 27469.6943 | 17059.6563
862 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8120A | Lanchang | 8120A-MAC-001 | 1 | E402 | FO&T | [16 empty] | 27469.6943 | 17059.6563
863 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8072A | Bkt Mikro | 8072A-MAC-001 | 2 | E402 | FO&T | [16 empty] | 27469.6943 | 17059.6563
864 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8072A | Bkt Mikro | 8072A-MAC-002 | 2 | E402 | FO&T | [16 empty] | 27469.6943 | 17059.6563
865 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Eastern | Pahang | 8092A | Jalan Karak Mentakab | 8092A-MAC-001 | 1 | E402 | FO&T | [16 empty] | 27469.6943 | 17059.6563
866 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6701A | Parit Sulong (Trunk) | 6701A-MAC-001 | 1 | S305 | BBAND | [16 empty] | 27469.6943 | 17059.6563
867 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6104A | Bukit Kelicap | 6104A-MAC-001 | 1 | S306M | BBAND | [16 empty] | 27469.6943 | 17059.6563
868 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6409A | Air Baloi | 6409A-MAC-001 | 1 | S306M | BBAND | [7 empty] | 2024-06-27 | [8 empty] | 27469.6943 | 17059.6563
869 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Negeri Sembilan | 1659A | Bahau Tower | 1659A-MAC-001 | 1 | S403 | BBAND | [7 empty] | 2024-06-11 | [8 empty] | 27469.6943 | 17059.6563
870 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Negeri Sembilan | 2384B | PASIR BESAR | 2384B-MAC-001 | 1 | S403 | BBAND | [7 empty] | 2024-06-12 | [8 empty] | 27469.6943 | 17059.6563
871 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6151A | MERSING | 6151A-MAC-001 | 1 | S504M | BBAND | [7 empty] | 2024-06-13 | [8 empty] | 27469.6943 | 17059.6563
872 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6166A | FELDA NITAR 2 | 6166A-MAC-001 | 1 | S504M | BBAND | [7 empty] | 2024-06-14 | [8 empty] | 27469.6943 | 17059.6563
873 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6160A | #N/A | 6160A-MAC-001 | 1 | S504M | BBAND | [16 empty] | 27469.6943 | 17059.6563
874 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6138A | KAHANG | 6138A-MAC-001 | 1 | S504M | BBAND | [7 empty] | 2024-06-12 | [8 empty] | 27469.6943 | 17059.6563
875 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6616A | Tmn Seri Permai | 6616A-MAC-001 | 1 | S504M | BBAND | [7 empty] | 2024-06-11 | [8 empty] | 27469.6943 | 17059.6563
876 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6374A | Air Tawar 4 | 6374A-MAC-001 | 1 | S607M | BBAND | [7 empty] | 2024-06-26 | [8 empty] | 27469.6943 | 17059.6563
877 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6380A | Desaru Resort-100Q4(D Harmoni) | 6380A-MAC-001 | 2 | S607M | BBAND | [7 empty] | 2024-06-25 | [8 empty] | 27469.6943 | 17059.6563
878 | MAC Swap - BR | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.003 | ML238053 | 2024-03-27 | MIP2024.003 | ML236161 | 2024-03-21 | Southern | Johor | 6380A | Desaru Resort-100Q4(D Harmoni) | 6380A-MAC-002 | 2 | S607M | BBAND | [7 empty] | 2024-06-25 | [8 empty] | 27469.6943 | 17059.6563
879 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Eastern | Terengganu | 8303A | Bkt Bauk | 8303A-MAG-001 | 1 | E207 | FO&T | [16 empty] | 85184.6738 | 176079.72
880 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Eastern | Pahang | 8701A | Jambu Rias (Trunk) | 8701A-MAG-001 | 1 | E402 | FO&T | [16 empty] | 85184.6738 | 176079.72
881 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Eastern | Kelantan | 8282B | Tasik Pergau | 8282B-MAG-001 | 1 | EAR01_1 & EAR01_3 | FO&T | [16 empty] | 85184.6738 | 176079.72
882 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Eastern | Kelantan | 8288B | Bukit Panau | 8288B-MAG-001 | 1 | EAR01_1 & EAR01_3 | FO&T | [16 empty] | 85184.6738 | 176079.72
883 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Eastern | Kelantan | 8224A | Pasir Puteh | 8224A-MAG-001 | 1 | EAR01_1 & EAR01_3 | FO&T | [16 empty] | 85184.6738 | 176079.72
884 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Eastern | Terengganu | 8367A | Bukit Kechil | 8367A-MAG-001 | 1 | EAR01_1 & EAR01_3 | FO&T | [16 empty] | 85184.6738 | 176079.72
885 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Southern | Johor | 2402B | Pagoh Highway | 2402B-MAG-001 | 1 | S305 | BBAND | [16 empty] | 85184.6738 | 176079.72
886 | MAG Swap - BR | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | YR24 Q2 Q3 HW | Q3 | MIP2024.004 | ML238059 | 2024-03-27 | MIP2024.004 | ML236160 | 2024-03-21 | Southern | Johor | 6502A | Nusa Perintis(Watertank) | 6502A-MAG-001 | 1 | SAR03_i & SAR03_iii | BBAND | [16 empty] | 85184.6738 | 176079.72
887 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Central | Selangor | 1207A | #N/A | 1207A-MAC-001 | 1 | C0126 | [17 empty] | 27269.3346 | 17165.7929
888 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Central | Selangor | 1364B | Subang Bestari | 1364B-MAC-001 | 1 | C0126 | [17 empty] | 27269.3346 | 17165.7929
889 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Central | Selangor | 2070B | Sri Gombak | 2070B-MAC-001 | 1 | C1101 | [17 empty] | 27269.3346 | 17165.7929
890 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Central | Wilayah Persekutuan Kuala Lumpur | 1288A | JBA Wangsa.Maju | 1288A-MAC-002 | 2 | 1288A-LL | [17 empty] | 27269.3346 | 17165.7929
891 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Central | Wilayah Persekutuan Kuala Lumpur | 1288A | JBA Wangsa.Maju | 1288A-MAC-002 | 2 | 1288A-LL | [17 empty] | 27269.3346 | 17165.7929
892 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Sarawak | Sarawak | 9318A | Kpg Merdang Gayam (Sacofa) | 9318A-MAC-001 | 1 | 9318A-LL | [17 empty] | 27269.3346 | 17165.7929
893 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4736A | Jebong | 4736A-MAC-001 | 1 | N304 | [17 empty] | 27269.3346 | 17165.7929
894 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4331A | Bagan Serai | 4331A-MAC-001 | 2 | N304 | [17 empty] | 27269.3346 | 17165.7929
895 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4331A | Bagan Serai | 4331A-MAC-001 | 2 | N304 | [17 empty] | 27269.3346 | 17165.7929
896 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4734A | Kg Teluk Kepayang (trunk) | 4734A-MAC-001 | 2 | N305 | [17 empty] | 27269.3346 | 17165.7929
897 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4734A | Kg Teluk Kepayang (trunk) | 4734A-MAC-001 | 2 | N305 | [17 empty] | 27269.3346 | 17165.7929
898 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | PERAK | 4490A | Kg Merbau | 4490A-MAC-001 | 1 | N305 | [17 empty] | 27269.3346 | 17165.7929
899 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4489A | Changkat Kruing RDD | 4489A-MAC-001 | 1 | N305 | [17 empty] | 27269.3346 | 17165.7929
900 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4323A | LAP Bemban | 4323A-MAC-001 | 2 | N305 | [17 empty] | 27269.3346 | 17165.7929
901 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4323A | LAP Bemban | 4323A-MAC-001 | 2 | N305 | [17 empty] | 27269.3346 | 17165.7929
902 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4470B | Bagan Pasir | 4470B-MAC-001 | 1 | N503 | [17 empty] | 27269.3346 | 17165.7929
903 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4473A | Hutan Melintang | 4473A-MAC-001 | 1 | N503 | [17 empty] | 27269.3346 | 17165.7929
904 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4472A | Durian Sebatang | 4472A-MAC-001 | 1 | N503 | [17 empty] | 27269.3346 | 17165.7929
905 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4580B | Jenderata Perak | 4580B-MAC-001 | 1 | N503 | [17 empty] | 27269.3346 | 17165.7929
906 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4311A | #N/A | 4311A-MAC-001 | 1 | N602 | [17 empty] | 27269.3346 | 17165.7929
907 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4442A | #N/A | 4442A-MAC-001 | 1 | N602 | [17 empty] | 27269.3346 | 17165.7929
908 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4732A | Ladang Tapah (trunk) | 4732A-MAC-001 | 1 | N602 | [17 empty] | 27269.3346 | 17165.7929
909 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4414A | SUNGKAI LAND | 4414A-MAC-001 | 1 | N602 | [17 empty] | 27269.3346 | 17165.7929
910 | MAC Swap - BR | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.017 | #N/A | #N/A | MIP2024.017 | Pending PO | TBA | Northern | Perak | 4517A | Pengkalan Industry | 4517A-MAC-001 | 1 | New Ring_7 | [17 empty] | 27269.3346 | 17165.7929
911 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Sabah | Sabah | 7100A | Muhibah Lahad Datu | 7100A-MAG-001 | 1 | 7100-MAG-LL | [17 empty] | 85184.6736 | 115749.8986
912 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Central | Wilayah Persekutuan Kuala Lumpur | 1304A | MMA | 1304A-MAG-001 | 1 | C0407P | [17 empty] | 85184.6736 | 115749.8986
913 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Eastern | Pahang | 8709A | Bentong (Trunk) | 8709A-MAG-003 | 1 | C1101 | [17 empty] | 85184.6736 | 115749.8986
914 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Central | Selangor | 2070B | Sri Gombak | 2070B-MAG-001 | 1 | C1101 | [17 empty] | 85184.6736 | 115749.8986
915 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Northern | Perak | 4310A | Matang Acheh | 4310A-MAG-001 | 1 | N304 | [17 empty] | 85184.6736 | 115749.8986
916 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Northern | Perak | 4331A | Bagan Serai | 4331A-MAG-001 | 1 | N304 | [17 empty] | 85184.6736 | 115749.8986
917 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Northern | Perak | 4473A | Hutan Melintang | 4473A-MAG-001 | 1 | N503 | [17 empty] | 85184.6736 | 115749.8986
918 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Northern | Perak | 4472A | Durian Sebatang | 4472A-MAG-001 | 1 | N503 | [17 empty] | 85184.6736 | 115749.8986
919 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Northern | Perak | 4412A | KTM Sungkai | 4412A-MAG-001 | 1 | N602 | [17 empty] | 85184.6736 | 115749.8986
920 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Northern | Perak | 4440B | Tapah Road | 4440B-MAG-001 | 1 | N602 | [17 empty] | 85184.6736 | 115749.8986
921 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Central | Wilayah Persekutuan Kuala Lumpur | 1271A | Risda | 1271A-MAG-001 | 1 | CAR03 | [17 empty] | 85184.6736 | 115749.8986
922 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Central | Selangor | 1270A | Puteri Park Plaza | 1270A-MAG-001 | 1 | CAR03 | [17 empty] | 85184.6736 | 115749.8986
923 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Central | Wilayah Persekutuan Kuala Lumpur | 1465A | JBA TMN SEGAR L1 | 1465A-MAG-001 | 1 | CAR03 | [17 empty] | 85184.6736 | 115749.8986
924 | MAG Swap - BR | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | YR24 Q3 Q4 ZTE | Q4 | MIP2024.016 | #N/A | #N/A | MIP2024.016 | Pending PO | TBA | Central | Selangor | 1002A | Sri Murni | 1002A-MAG-001 | 1 | CAR03 | [17 empty] | 85184.6736 | 115749.8986
925 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2024 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Central | Selangor | 2024A | #N/A | 2024A-MAC-001 | 1 | C0515+ | BBAND | [7 empty] | 2024-06-05 | [8 empty] | 27698.6762 | 17105.66
926 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2025 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Central | Wilayah Persekutuan Kuala Lumpur | 2502A | PUAS Bdr Tun Razak | 2502A-MAC-001 | 2 | MAC Ring 15/ C21+ | BBAND | [7 empty] | 2024-06-06 | [8 empty] | 27698.6762 | 17105.66
927 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2026 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Central | Wilayah Persekutuan Kuala Lumpur | 2502A | PUAS Bdr Tun Razak | 2502A-MAC-002 | 2 | MAC Ring 15/ C21+ | BBAND | [7 empty] | 2024-06-06 | [8 empty] | 27698.6762 | 17105.66
928 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2027 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Kedah | 4995A | Changloon UUM | 4995A-MAC-001 | 1 | N104 | FO&T | [16 empty] | 27698.6762 | 17105.66
929 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2028 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Kedah | 4991A | UUM | 4991A-MAC-001 | 1 | N104 | FO&T | [16 empty] | 27698.6762 | 17105.66
930 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2029 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Kedah | 4672A | CHANGLOON | 4672A-MAC-001 | 1 | N104 | FO&T | [16 empty] | 27698.6762 | 17105.66
931 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2030 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Kedah | 4665A | Jitra | 4665A-MAC-001 | 1 | N104 | FO&T | [16 empty] | 27698.6762 | 17105.66
932 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2031 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perlis | 4604A | JBA KUAL PERLIS | 4604A-MAC-001 | 1 | N107 | FO&T | [16 empty] | 27698.6762 | 17105.66
933 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2032 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Pulau Pinang | 4601A | #N/A | 4601A-MAC-001 | 1 | N107 | FO&T | [16 empty] | 27698.6762 | 17105.66
934 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2033 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perlis | 4612A | Jalan Kaki Bukit | 4612A-MAC-001 | 1 | N107 | FO&T | [16 empty] | 27698.6762 | 17105.66
935 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2034 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perlis | 4613A | Berseri Perlis | 4613A-MAC-001 | 1 | N107 | FO&T | [16 empty] | 27698.6762 | 17105.66
936 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2035 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4379A | Bukit Mercu | 4379A-MAC-001 | 1 | N405+ | FO&T | [16 empty] | 27698.6762 | 17105.66
937 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2036 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4378A | Jerlun Tower | 4378A-MAC-001 | 1 | N405+ | FO&T | [16 empty] | 27698.6762 | 17105.66
938 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2037 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4374A | LAP Talang RDD | 4374A-MAC-001 | 1 | N405+ | FO&T | [16 empty] | 27698.6762 | 17105.66
939 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2038 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4506A | Perak Taipu Assc | 4506A-MAC-001 | 1 | N408+ | FO&T | [16 empty] | 27698.6762 | 17105.66
940 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2039 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4546A | KWSP Ipoh RDD | 4546A-MAC-001 | 2 | N408+ | FO&T | [16 empty] | 27698.6762 | 17105.66
941 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2040 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4546A | KWSP Ipoh RDD | 4546A-MAC-002 | 2 | N408+ | FO&T | [16 empty] | 27698.6762 | 17105.66
942 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2041 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4515A | TG RAMBUTAN | 4515A-MAC-001 | 1 | N408+ | FO&T | [16 empty] | 27698.6762 | 17105.66
943 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2042 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4433A | LAP Sg Siput | 4433A-MAC-001 | 1 | N411+ | FO&T | [16 empty] | 27698.6762 | 17105.66
944 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2041 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4377B | Karai | 4377B-MAC-001 | 1 | N411+ | FO&T | [16 empty] | 27698.6762 | 17105.66
945 | MAC Swap - BR | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2042 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.005 | ML238434 | 2024-03-29 | MIP2024.005 | ML236898 | 2024-03-23 | Northern | Perak | 4373A | KTM K.Kangsar | 4373A-MAC-001 | 1 | N411+ | FO&T | [16 empty] | 27698.6762 | 17105.66
946 | MAG Swap - BR | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.006 | ML238433 | 2024-03-29 | MIP2024.006 | #N/A | TBA | Sabah | Sabah | 7124A | Land Trig Hill | 7124A-MAG-001 | 1 | 7124A-MAG-001&002 | FO&T | [16 empty] | 85184.6725 | 268765.58
947 | MAG Swap - BR | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.006 | ML238433 | 2024-03-29 | MIP2024.006 | #N/A | TBA | Northern | Kedah | 4995A | Changloon UUM | 4995A-MAG-001 | 1 | NAR01_iii | FO&T | [16 empty] | 85184.6725 | 268765.58
948 | MAG Swap - BR | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.006 | ML238433 | 2024-03-29 | MIP2024.006 | #N/A | TBA | Northern | Perak | 4493A | KTM IPOH | 4493A-MAG-001 | 1 | NAR04_ii+ | FO&T | [16 empty] | 85184.6725 | 268765.58
949 | MAG Swap - BR | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | YR24 Q2 ZTE | Q2 | MIP2024.006 | ML238433 | 2024-03-29 | MIP2024.006 | #N/A | TBA | Northern | Perak | 4432A | KTM Sg Siput | 4432A-MAG-001 | 1 | NAR04_ii+ | FO&T | [16 empty] | 85184.6725 | 268765.58
950 | Ring Expansion (MAG-PE) | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | DWDM | YR24 Q1 | Q1 | MIP2024.07 | ML230536 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1409A | Kota Damansara | 1409A-MAG(M14)-001 Kota Damansara |  | CAR01_01 | BBAND | [7 empty] | 2024-06-11 | [6 empty] | May |  | 9460.092
951 | Ring Expansion (MAG-PE) | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | DWDM | YR24 Q1 | Q1 | MIP2024.07 | ML230536 | 2024-02-20 | NA | NA | NA | Central | Selangor | 1085A | Pekan Meru | 1085A-MAG-001 Pekan Meru |  | CAR01_01 | BBAND | [7 empty] | 2024-06-11 | [6 empty] | May |  | 9460.092
952 | Ring Expansion (MAG-PE) | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | DWDM | YR24 Q1 | Q1 | MIP2024.07 | ML230536 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2777C | JBA Bkt Lipat (TX REL - Celcom) | 2777C-MAG(M8)-001 JBA Bukit Lipat |  | CAR01_01 | BBAND | [7 empty] | 2024-06-11 | [6 empty] | May |  | 9460.092
953 | Ring Expansion (MAG-PE) | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | DWDM | YR24 Q1 | Q1 | MIP2024.07 | ML230536 | 2024-02-20 | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | SHTPE |  | CAR01_01 | BBAND | [7 empty] | 2024-06-11 | [6 empty] | May |  | 9460.092
954 | Ring Expansion (MAG-PE) | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | DWDM | YR24 Q1 | Q1 | MIP2024.07 | ML230536 | 2024-02-20 | NA | NA | NA | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | KPGPE |  | CAR01_01 | BBAND | [7 empty] | 2024-06-11 | [6 empty] | May |  | 9460.092
955 | PE-MCR | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | DWDM | YR23 | Spillover | MIP2023.134 | ML192034 | 2023-08-14 |  |  |  | Central | Selangor | 1049B | MSC Damansara | MSC Damansara |  | CAR02 | [8 empty] | Jun | [6 empty] | Mar
956 | PE-MCR | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | DWDM | YR23 | Spillover | MIP2023.134 | ML192034 | 2023-08-14 |  |  |  | Central | Selangor | 1172A | Glomac | Glomac |  | CAR02 | [8 empty] | Jun | [6 empty] | Mar
957 | PE-MCR | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | DWDM | YR23 | Spillover | MIP2023.134 | ML192034 | 2023-08-14 |  |  |  | Central | Selangor | 1253A | Plaza Pengkalen | Plaza Pengkalen |  | CAR02 | [8 empty] | Jun | [6 empty] | Mar
958 | PE-MCR | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | DWDM | YR23 | Spillover | MIP2023.134 | ML192034 | 2023-08-14 |  |  |  | Central | Selangor | 1859A | Midvalleycas | Midvalleycas |  | CAR02 | [8 empty] | Jun | [6 empty] | Mar
959 | PE-MCR | MIP2021.33 ES BOQ for IBEAM relocation of Trig Hill 7124A MAC to 7570A Kg. Garinono | LL | YR23 | Spillover | MIP2021.33 | ML40399 | 2021-03-05 |  |  |  | Sabah | Sabah | 7124A | Land Trig Hill | Land Trig Hill |  | 7124A | [15 empty] | Jul
960 | PE-MCR | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2021.120 | ML64464 | 2021-08-26 |  |  |  | Central | Selangor | 2021B | DiGi TOC (Lot 43) | DiGi TOC (Lot 43) |  | CAR05 | [8 empty] | 2024-05-24 | 2024-05-24 | [5 empty] | Jul
961 | PE-MCR | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2021.120 | ML64464 | 2021-08-26 |  |  |  | Central | Selangor | 1475A | BSC Sri Kembangan | BSC Sri Kembangan |  | CAR05 | [8 empty] | 2024-05-24 | 2024-05-24 | [5 empty] | Jul
962 | PE-MCR | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2021.120 | ML64464 | 2021-08-26 |  |  |  | Central | Selangor | 1110A | Berjaya Industrial Park | Berjaya Industrial Park |  | CAR05 | [8 empty] | 2024-05-24 | 2024-05-24 | [5 empty] | Jul
963 | PE-MCR | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2021.120 | ML64464 | 2021-08-26 |  |  |  | Central | Selangor | 1128A | Kg Ola Lempik | Kg Ola Lempik |  | CAR05 | [8 empty] | 2024-05-24 | 2024-05-24 | [5 empty] | Jul
964 | PE-MCR | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2021.120 | ML64464 | 2021-08-26 |  |  |  | Central | Selangor | 1037A | JBA Bangi | JBA Bangi |  | CAR05 | [8 empty] | 2024-05-24 | 2024-05-24 | [5 empty] | Jul
965 | PE-MCR | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2021.120 | ML64464 | 2021-08-26 |  |  |  | Central | Selangor | 1039A | Cheras Jaya 2202 | Cheras Jaya 2202 |  | CAR05 | [8 empty] | 2024-05-24 | 2024-05-24 | [5 empty] | Jul
966 | PE-MCR | MIP2024.94 CD Digi NIC ES BOQ- CAR08 PE-MCR Migration | DWDM | YR24 Q4 HW | Q4 | MIP2024.94 | #N/A |  |  |  |  | Central | Selangor | CAR02 | #N/A | CAR02 |  | CAR08
967 | PE-MCR | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.91 | #N/A |  |  |  |  | Eastern | Pahang | 8173A | Bandar Pusat Jengka | Bandar Pusat Jengka |  | EAR05 | [17 empty] | 17662.395
968 | PE-MCR | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.91 | #N/A |  |  |  |  | Eastern | Pahang | 8112A | Bukit Istana | Bukit Istana |  | EAR05 | [17 empty] | 17662.395
969 | PE-MCR | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.91 | #N/A |  |  |  |  | Eastern | Pahang | 8527A | Jengka 8 | Jengka 8 |  | EAR05 | [17 empty] | 17662.395
970 | PE-MCR | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.91 | #N/A |  |  |  |  | Eastern | Pahang | 8528A | #N/A | #N/A |  | EAR05 | [17 empty] | 17662.395
971 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Central | Wilayah Persekutuan Kuala Lumpur | 1049B | MSC Damansara | KPGPE01 |  | EAR07 | [17 empty] | 7902.2887
972 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Northern | Pulau Pinang | EAR07 | #N/A | PRIPE01 |  | EAR07 | [17 empty] | 7902.2887
973 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Eastern | Kelantan | 8215B | Dabong | Dabong |  | EAR07 | [17 empty] | 7902.2887
974 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Eastern | Kelantan | 8240A | Gua Musang Town (Celcom) | Gua Musang Town (Celcom) |  | EAR07 | [17 empty] | 7902.2887
975 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Eastern | Kelantan | 8038Z | Sg.Berok | Sg.Berok |  | EAR07 | [17 empty] | 7902.2887
976 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Eastern | Pahang | 8110Z | Pos Mensun | Pos Mensun |  | EAR07 | [17 empty] | 7902.2887
977 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Eastern | Pahang | 8002Z | Pos Betau | Pos Betau |  | EAR07 | [17 empty] | 7902.2887
978 | PE-MCR | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | DWDM | YR24 Q4 HW | Q4 | MIP2024.92 | #N/A |  |  |  |  | Eastern | Pahang | 8120Z | Kg.Bt Talam | Kg.Bt Talam |  | EAR07 | [17 empty] | 7902.2887
979 | IP BREAK RING | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | DWDM | YR24 Q4 HW | Q4 | MIP20324.9 | #N/A |  |  |  |  | Eastern | Pahang | 8173A | Bandar Pusat Jengka | 8173A-MAG-001 |  | E604 | [17 empty] | 8839.2225
980 | IP BREAK RING | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | DWDM | YR24 Q4 HW | Q4 | MIP20324.9 | #N/A |  |  |  |  | Eastern | Pahang | 8112A | Bukit Istana | 8112A-MAG-001 |  | E604 | [17 empty] | 8839.2225
981 | IP BREAK RING | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | DWDM | YR24 Q4 HW | Q4 | MIP20324.9 | #N/A |  |  |  |  | Eastern | Pahang | 8527A | Jengka 8 | 8527A-MAC-001 |  | E604 | [17 empty] | 8839.2225
982 | IP BREAK RING | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | DWDM | YR24 Q4 HW | Q4 | MIP20324.9 | #N/A |  |  |  |  | Eastern | Pahang | 8528A | #N/A | 8528A-MAC-001 |  | E604 | [17 empty] | 8839.2225
983 | PE-MCR | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2023.138 | ML190486 | 2023-08-01 |  |  |  | Southern | Johor | 1621A | Senawang MSC | Senawang MSC |  | SAR04 | [8 empty] | 2024-06-19 | [6 empty] | May
984 | PE-MCR | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2023.138 | ML190486 | 2023-08-01 |  |  |  | Southern | Johor | 1659A | Bahau Tower | Bahau Tower |  | SAR04 | [8 empty] | 2024-06-19 | [6 empty] | May
985 | PE-MCR | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2023.138 | ML190486 | 2023-08-01 |  |  |  | Southern | Johor | 6911C | KTM LABIS REL | KTM LABIS REL |  | SAR04 | [8 empty] | 2024-06-19 | [6 empty] | May
986 | PE-MCR | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | DWDM | YR23 | Spillover | MIP2023.138 | ML190486 | 2023-08-01 |  |  |  | Southern | Johor | 6442A | Airport Senai | Airport Senai |  | SAR04 | [8 empty] | 2024-06-19 | [6 empty] | May
987 | PE-MCR | MIP2023.146 CD Digi NIC ES BOQ- SACOFA trunk upgrade and PE-MCR migration for 9106A Bukit Nyabau (SACOFA) | LL | YR23 | Spillover | MIP2023.146 | ML194765 | 2023-08-18 |  |  |  | Sarawak | Sarawak | 9106A | Bkt Nyabau | Bkt Nyabau |  | 9106A-MAG-LL | [8 empty] | 2024-05-17 | 2024-05-17 | [5 empty] | Apr
988 | PE-MCR | MIP2023.147 CD Digi NIC ES BOQ- SACOFA trunk upgrade and PE-MCR migration for 9368A Salim Road Sacofa | LL | YR23 | Spillover | MIP2023.147 | ML195608 | 2023-08-22 |  |  |  | Sarawak | Sarawak | 9368A | Salim Road Sacofa | Salim Road Sacofa |  | 9368A-MAG-LL | [8 empty] | 2024-06-04 | [6 empty] | Apr
989 | PE-MCR | MIP2023.144 CD Digi NIC ES BOQ- CAR11 MAG ring upgrade via DWDM and PE-MCR migration | DWDM | YR23 | Spillover | MIP2023.144 | ML199038 | 2023-09-06 |  |  |  | Central | Selangor | 2070B | Sri Gombak | Sri Gombak |  | CAR11 | [8 empty] | 2024-06-21 | [6 empty] | May
990 | PE-MCR | MIP2023.144 CD Digi NIC ES BOQ- CAR11 MAG ring upgrade via DWDM and PE-MCR migration | DWDM | YR23 | Spillover | MIP2023.144 | ML199038 | 2023-09-06 |  |  |  | Eastern | Pahang | 8709A | Bentong (Trunk) | Bentong (Trunk) |  | CAR11 | [8 empty] | 2024-06-21 | [6 empty] | May
991 | Ring Expansion | MIP2023.225 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_9151B-LL (Upgrade LL) | LL | YR23 | Spillover | MIP2023.225 | ML213374 | 2023-11-16 |  |  |  | Sarawak | Sarawak | 9999A | Kuching MSC | Kuching MSC |  | 9151B-LL | [15 empty] | Jun
992 | Ring Expansion | MIP2023.225 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_9151B-LL (Upgrade LL) | LL | YR23 | Spillover | MIP2023.225 | ML213374 | 2023-11-16 |  |  |  | Sarawak | SARAWAK | 9151B | TM Demak Laut (REL) | TM Demak Laut (REL) |  | 9151B-LL | [15 empty] | Jun
993 | PE-MCR | MIP2023.148 CD Digi NIC ES BOQ- SACOFA trunk upgrade and PE-MCR migration for 9074A MSC Miri | LL | YR23 | Spillover | MIP2023.148 | ML191273 | 2023-08-08 |  |  |  | Sarawak | Sarawak | 9074A | MSC Miri | MSC Miri |  | 9074A-MAG-LL | [8 empty] | 2024-05-23 | 2024-05-23 | [5 empty] | Apr
994 | PE-MCR | MIP2022.49 ES BOQ for CTS trunk upgrade and PE-MCR migration for 7205A Mile 15 Tawau and 7124A Trig Hill Sandakan | LL | YR23 | Spillover | MIP2022.49 | ML111608 | 2022-06-30 |  |  |  | Sabah | Sabah | 7205A | MILE 15 TAWAU | MILE 15 TAWAU |  | 7205A-MAG-LL | [8 empty] | 2024-06-11 | [6 empty] | Apr
995 | PE-MCR | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 |  | YR24 Q4 HW | Q4 | MIP2024.106 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | SHTPE01 |  | CAR09
996 | PE-MCR | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 |  | YR24 Q4 HW | Q4 | MIP2024.106 | #N/A | #N/A | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | SNWPE01 |  | CAR09
997 | PE-MCR | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 |  | YR24 Q4 HW | Q4 | MIP2024.106 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1124A | Batu 15 Banting | 1124A-MAG-001 |  | CAR09
998 | PE-MCR | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 |  | YR24 Q4 HW | Q4 | MIP2024.106 | #N/A | #N/A | NA | NA | NA | Southern | Negeri Sembilan | 1690A | Bukit Pelandok (DWDM) | 1690A-MAG-001 |  | CAR09
999 | PE-MCR | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 |  | YR24 Q4 HW | Q4 | MIP2024.107 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | SKBPE02 |  | SAR02
1000 | PE-MCR | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 |  | YR24 Q4 HW | Q4 | MIP2024.107 | #N/A | #N/A | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | SNWPE02 |  | SAR02
1001 | PE-MCR | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 |  | YR24 Q4 HW | Q4 | MIP2024.107 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1851B | Rinching Tengah (KJS) | 1851B-MAG-002 |  | SAR02
1002 | PE-MCR | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 |  | YR24 Q4 HW | Q4 | MIP2024.107 | #N/A | #N/A | NA | NA | NA | Southern | Negeri Sembilan | 1607A | KM Plaza | 1607A-MAG-001 |  | SAR02
1003 | PE-MCR | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 |  | YR24 Q4 HW | Q4 | MIP2024.108 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4521A | MSC Ipoh | IPHPE01 |  | NAR05
1004 | PE-MCR | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 |  | YR24 Q4 HW | Q4 | MIP2024.108 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 2021B | DiGi TOC (Lot 43) | SHTPE01 |  | NAR05
1005 | PE-MCR | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 |  | YR24 Q4 HW | Q4 | MIP2024.108 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4404A | Kg Jering Tower Manjung | 4404A-MAG-001 |  | NAR05
1006 | PE-MCR | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 |  | YR24 Q4 HW | Q4 | MIP2024.108 | #N/A | #N/A | NA | NA | NA | Northern | Perak | 4473A | Hutan Melintang | 4473A-MAG-001 |  | NAR05
1007 | PE-MCR | MIP2024.109 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR10 |  | YR24 Q4 HW | Q4 | MIP2024.109 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1475A | BSC Sri Kembangan | SKBPE02 |  | CAR10
1008 | PE-MCR | MIP2024.109 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR10 |  | YR24 Q4 HW | Q4 | MIP2024.109 | #N/A | #N/A | NA | NA | NA | Southern | Negeri Sembilan | 1621A | Senawang MSC | SNWPE02 |  | CAR10
1009 | PE-MCR | MIP2024.109 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR10 |  | YR24 Q4 HW | Q4 | MIP2024.109 | #N/A | #N/A | NA | NA | NA | Central | Selangor | 1851B | Rinching Tengah (KJS) | 1851B-MAG-001 |  | CAR10
1010 | PE-MCR | MIP2024.110 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL432P |  | YR24 Q4 HW | Q4 | MIP2024.110 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE01 |  | NL432P
1011 | PE-MCR | MIP2024.110 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL432P |  | YR24 Q4 HW | Q4 | MIP2024.110 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE02 |  | NL432P
1012 | PE-MCR | MIP2024.110 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL432P |  | YR24 Q4 HW | Q4 | MIP2024.110 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4012A | Prime Plaza | 4012A-MAG-001 |  | NL432P
1013 | PE-MCR | MIP2024.111 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL433P |  | YR24 Q4 HW | Q4 | MIP2024.111 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE01 |  | NL433P
1014 | PE-MCR | MIP2024.111 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL433P |  | YR24 Q4 HW | Q4 | MIP2024.111 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE02 |  | NL433P
1015 | PE-MCR | MIP2024.111 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL433P |  | YR24 Q4 HW | Q4 | MIP2024.111 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4015A | Axis Complex V4 | 4015A-MAG-001 |  | NL433P
1016 | PE-MCR | MIP2024.112 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL435P |  | YR24 Q4 HW | Q4 | MIP2024.112 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE01 |  | NL435P
1017 | PE-MCR | MIP2024.112 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL435P |  | YR24 Q4 HW | Q4 | MIP2024.112 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE02 |  | NL435P
1018 | PE-MCR | MIP2024.112 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL435P |  | YR24 Q4 HW | Q4 | MIP2024.112 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4056A | Vistana Hotel | 4056A-MAG-001 |  | NL435P
1019 | PE-MCR | MIP2024.113 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL424 |  | YR24 Q4 HW | Q4 | MIP2024.113 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE01 |  | NL424
1020 | PE-MCR | MIP2024.113 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL424 |  | YR24 Q4 HW | Q4 | MIP2024.113 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4000A | MSC Prai | PRIPE02 |  | NL424
1021 | PE-MCR | MIP2024.113 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL424 |  | YR24 Q4 HW | Q4 | MIP2024.113 | #N/A | #N/A | NA | NA | NA | Northern | Pulau Pinang | 4090A | Shoplot Permatang Damar | 4090A-MAG-001 |  | NL424