## Sheet1
Ring ID | DUID / Activity Name | Batch | Priority | Site ID | Site Name | Subcon | CME Type | CME Status | Plan Survey | Actual Survey | Plan MOS | Actual MOS | Plan Power Up | Actual Power Up | Plan Integration | Actual Integration | Integrated Date (30days + install) | Break Ring Status | Region | State | Survey Plan | Survey Completed | Plan Migration | Actual Migration | PO ES Date | PO EQ Date
N401 | MAC | Pending Po | N/A | 4686B | N/A | Fo&T | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | MAC | Pending Po | N/A | 4965A | N/A | Fo&T | BATTERY BANK = 1 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | MAC001 Machang Bubuk 2 | Pending Po | N/A | 4118A | Machang Bubuk 2 | Fo&T | DCPDB = 1 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | MAC001 Tmn Desa Impian | Pending Po | N/A | 4689A | Tmn Desa Impian | Fo&T | BATTERY BANK = 1 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | MAG001 Selama | Pending Po | N/A | 4952B | Selama | Fo&T | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | MCR002 PRI | Pending Po | N/A | 4000A | MSC Prai | Fo&T | DC BREAKER: 63A X 12 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR18/C24 | xD_DWDM-BRKRing_MCR18/C24_1362B Kelana Business_0004582306610C_00045823162822 | 2023 | P2 | 1362B | 1362B Kelana Business | BBand | DCPDB = 1 | Completed | N/A | N/A | 2023-11-22 | 2023-11-22 | N/A | N/A | 2024-02-12 | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0204 | xD_DWDM_BRKRing_C0204_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 2024 Q1 | P2 | 1253A | 1253A Plaza Pengkalan | Advance | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | PRPO | N/A | 2024-01-27 | 2024-07-30 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0204 | xD_DWDM_BRKRing_C0204_1261A KWSP_0004582309050Y_00045824006623 | 2024 Q1 | P2 | 1261A | 1261A KWSP | Advance | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0204 | xD_DWDM_BRKRing_C0204_18451A KL Plaza2_0004582309050Y_00045824006623 | 2024 Q1 | P2 | 1851A | 1851A-MAG(M14)-001 KL Plaza 2 | Advance | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | N/A | N/A | 2024-07-30 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0204 | xD_DWDM_BRKRing_C0204_1869A Daya Bumi_0004582309050Y_00045824006623 | 2024 Q1 | P2 | 1869A | 1869A Dayabumi | Advance | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0702P | xD_DWDM-BRKRing_C0702P_1096A MAG KlangPerdana_0004582304330Y_00045823098821 | 2023 | P1 | 1096A | 1096A MAG KlangPerdana | BBand | No CME | N/A | N/A | N/A | 2023-11-22 | 2023-11-23 | N/A | N/A | 2024-02-15 | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR18/C24 | xD_DWDM-BRKRing_MCR18/C24_1378B PJS 10_0004582304330Y_00045823098821 | 2023 | P2 | 1378B | 1378B PJS 10 | BBand | DC BREAKER: 63A X 2 | Completed | N/A | N/A | 2023-11-22 | 2023-11-23 | N/A | N/A | 2024-02-12 | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT0120 | xD-DWDM-BRKRing_CT0120_1099A HongFatt_0004582304160F_0004582308742 | 2023 | P1_IP_BR-Q1 | 1099A | 1099A HongFatt | Advance | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | 2023-12-06 | 2023-12-06 | N/A | N/A | 2024-04-23 | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0407P | xD_DWDM_BRKRing_C0407P_1266A Sucasa_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1266A | 1266A Sucasa | BBand | 1.Add module = 1 | PRPO | N/A | 2023-12-01 | 2024-05-30 | N/A | 2024-06-04 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT0120 | xD-DWDM-BRKRing_CT0120_1409A Damansara_0004582304160F_0004582308742 | 2023 | P1_IP_BR-Q1 | 1409A | 1409A Damansara | Advance | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | 2023-12-07 | 2023-12-07 | 2024-06-07 | N/A | 2024-04-24 | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0407P | xD_DWDM_BRKRing_C0407P_1304A MMA_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1304A | 1304A MMA | BBand | No CME | N/A | N/A | 2023-12-07 | 2024-03-26 | 2024-03-26 | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0407P | xD_DWDM_BRKRing_C0407P_1745A Baitumal_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1745A | 1745A Baitamal | BBand | swap emerson rectifier c/w 6 bank battery | N/A | N/A | 2023-11-30 | 2024-07-30 | N/A | 2024-06-21 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0417P | xD_DWDM_BRKRing_C0417P_1006A JBA Gombak_0004582309050Y_00045824006623 | 2024 Q1 | P2 | 1006A | 1006A JBA Gombak | Advance | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | 2024-05-20 | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0417P | xD_DWDM_BRKRing_C0417P_1203A JBA Sri Damansara_0004582309050Y_00045824006623 | 2024 Q1 | P2 | 1203A | 1203A JBA Sri Damansara | Advance | 1. Add Battery Bank = 4 | PRPO | N/A | 2024-01-27 | 2024-05-21 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM_BRKRing_CAR04_1006A JBA Gombak_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1006A | 1006A JBA Gombak | BBand | RECTIFIER + DCPDB = 1 | Completed | N/A | 2023-12-07 | 2024-04-25 | 2024-04-25 | N/A | N/A | N/A | Y | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM_BRKRing_CAR04_1304A MMA_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1304A | 1304A MMA | BBand | N/A | N/A | N/A | 2024-12-07 | 2024-03-26 | 2024-03-26 | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0210P | xD_DWDM_BRKRing_C0210P_1253A Plaza Pengkalan_0004582309010S_00045824006622 | 2024 Q1 | P1_IP_BR-Q1 | 1253A | 1253A Plaza Pengkalan | Advance | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | PRPO | N/A | 2024-01-27 | 2024-04-23 | 2024-04-23 | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM_BRKRing_CAR04_1458A Endah Parade_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1458A | 1458A Endah Parade | BBand | BATTERY BANK = 1 | Completed | N/A | 2024-12-07 | 2024-04-23 | 2024-04-23 | N/A | N/A | N/A | Y | 2024-05-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM_BRKRing_CAR04_1475A SKB_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1475A | 1475A SKB | BBand | 1.ODF Rack (Glass Door) | PRPO | N/A | 2024-02-13 | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM_BRKRing_CAR04_1745A Baitumal_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1745A | 1745A Baitumal | BBand | N/A | N/A | N/A | 2023-11-30 | 2024-06-30 | N/A | 2024-06-21 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E104 | xD_DWDM_BRKRing_E104_8263AMAG(M14)- 001 Pmas_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8263A | 8263AMAG(M14)- 001 Pmas | Advance | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4 DC breaker) | PRPO | N/A | 2024-01-30 | 2024-04-23 | 2024-04-23 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E104 | xD_DWDM_BRKRing_E104_8288B-MAG001 Panau_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8288B | 8288B-MAG001 Panau | Advance | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | N/A | 2024-01-30 | 2024-04-22 | 2024-04-23 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD_DWDM_BRKRing_S309_2402B-MAG001 Pagoh Highway_0004582309010R_00045824006624 | 2024 Q1 | P3 | 2402B | 2402B-MAG001 Pagoh Highway | BBand | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | PRPO | N/A | 2024-01-23 | 2024-04-23 | 2024-04-23 | 2024-06-04 | N/A | N/A | N/A | 2024-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0210P | xD_DWDM_BRKRing_C0210P_1859A Midvalleycas_0004582309010S_00045824006622 | 2024 Q1 | P1_IP_BR-Q1 | 1859A | 1859A Midvalleycas | Advance | 1.Add modules = 2 | PRPO | N/A | 2024-01-26 | 2024-04-24 | 2024-04-24 | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E104 | xD_DWDM_BRKRing_E104_8269B-MAC001 Chetok_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8269B | 8269B-MAC001 Chetok | Advance | N/A | N/A | N/A | 2024-01-30 | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0407P | xD_DWDM_BRKRing_C0407P_1737A Bernama_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1737A | 1737A Bernama | BBand | 1. Replace CSU controller = 1 (Action FF) 2. Add Modules = 2 3. Add Battery Bank = 1 | PRPO | N/A | 2023-12-07 | 2024-04-24 | 2024-04-24 | 2024-06-04 | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E104 | xD_DWDM_BRKRing_E104_8294A-MAC001 Kangkong_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8294A | 8294A-MAC001 Kangkong | Advance | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) | PRPO | N/A | 2024-01-30 | 2024-06-05 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E105 | xD_DWDM_BRKRing_E105_8139B-MAC001 CBC_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8139B | 8139B-MAC001 CBC | FO&T | 1.swap rectifier (Outdoor) = 1 (Require 63A x 4 DC breaker) | PRPO | N/A | 2023-12-21 | 2024-06-25 | N/A | 2024-06-14 | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E105 | xD_DWDM_BRKRing_E105_8211A-MAG(M8)- 001 WCY_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8211A | 8211A-MAG(M8)- 001 WCY | FO&T | N/A | N/A | N/A | 2023-12-19 | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E105 | xD_DWDM_BRKRing_E105_8229A-MAC001 Tumpat_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8229A | 8229A-MAC001 Tumpat | FO&T | 1. Add Battery Bank = 3 | PRPO | N/A | 2023-12-21 | 2024-04-24 | 2024-04-24 | 2024-06-14 | N/A | N/A | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E109 | xD_DWDM_BRKRing_E109_8222A-MAC001 Peringat_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8222A | 8222A-MAC001 Peringat | Advance | 1. Add Battery Bank = 4 | PRPO | N/A | 2024-01-30 | 2024-04-24 | 2024-04-24 | 2024-06-14 | N/A | N/A | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8145Z-MAG 001 T3E 0160 Kg Paya Luas_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8145Z | 8145Z-MAG 001 T3E 0160 Kg Paya Luas | Fo&T | N/A | N/A | N/A | 2024-02-06 | 2024-04-25 | 2024-04-24 | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E109 | xD_DWDM_BRKRing_E109_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8224A | 8224A-MAG-001 Pasir Puteh | Advance | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | PRPO | N/A | N/A | 2024-06-06 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0210P | xD_DWDM_BRKRing_C0210P_2878A Mont Kiara_0004582309050Y_00045824006623 | 2024 Q1 | P1_IP_BR-Q1 | 2878A | 2878A Mont Kiara | Advance | 1. Swap Rectifier (Indoor) = 1 (Require 63A x 8 DC breaker) | PRPO | N/A | 2024-01-26 | 2024-04-25 | 2024-04-25 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E111 | xD_DWDM_BRKRing_E111_8317A-MAC-001 Kampung Pak Wong_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8317A | 8317A-MAC-001 Kampung Pak Wong | FO&T | N/A | N/A | N/A | 2023-12-21 | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E105 | xD_DWDM_BRKRing_E105_8212A-MAC001 Wbharu_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8212A | 8212A-MAC001 Wbharu | FO&T | N/A | N/A | N/A | 2023-12-21 | 2024-04-24 | 2024-04-25 | N/A | N/A | N/A | N/A | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E109 | xD_DWDM_BRKRing_E109_8242B-MAC001 JKKrai_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8242B | 8242B-MAC001 JKKrai | Advance | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | PRPO | N/A | 2024-01-30 | 2024-04-25 | 2024-04-25 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E111 | xD_DWDM_BRKRing_E111_8407A-MAC001 Jerteh_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8407A | 8407A-MAC001 Jerteh | FO&T | N/A | N/A | N/A | 2023-12-21 | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E111 | xD_DWDM_BRKRing_E111_8322B-MAC001 Padang Luas_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8322B | 8322B-MAC001 Padang Luas | FO&T | 1.Swap Breaker = 2 (Require 100A x 2 DC breaker) 2.Add modules = 2 3.Add battery bank = 2 4.Extend beam and shelter = 1 5.Padlock and lock bar = 1 6.Trunking = 1 | PRPO | N/A | 2023-12-21 | 2024-04-25 | 2024-04-25 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01 | xD_DWDM_BRKRing_EAR01_4000A-MCR-001 PRI_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 4000A | 4000A-MCR-001 PRI | Fo&T | No CME | Completed | N/A | N/A | 2024-03-18 | 2024-03-19 | N/A | N/A | N/A | Y | 2024-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01 | xD_DWDM_BRKRing_EAR01_8000A-MCR001 KTN_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8000A | 8000A-MCR001 KTN | Fo&T | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8112A-MAG 001 Bukit Istana_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8112A | 8112A-MAG 001 Bukit Istana | Fo&T | N/A | N/A | N/A | 2024-02-06 | 2024-04-24 | 2024-04-25 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_1475A-MSC MSK_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 1475A | 1475A-MSC MSK | Fo&T | No CME | PRPO | N/A | N/A | 2024-03-18 | 2024-03-19 | N/A | N/A | N/A | Y | 2024-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8173A-MAG 001 Bandar Pusat Jengka_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8173A | 8173A-MAG 001 Bandar Pusat Jengka | Fo&T | N/A | N/A | N/A | 2024-02-06 | 2024-04-25 | 2024-04-25 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8105A-MAG 001 South Of Raub_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8105A | 8105A-MAG 001 South Of Raub | Fo&T | N/A | N/A | N/A | 2024-03-13 | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST21P | xD_DWDM_BRKRing_ST21P_6369A-MAG001 Sri Saujana_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 6369A | 6369A-MAG001 Sri Saujana | BBand | 1. Add Battery Bank = 6 | PRPO | N/A | 2023-12-30 | 2024-04-26 | 2024-04-26 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_2021B SBHT_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 2021B | 2021B Subang Hitech | BBand | No CME | PRPO | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1110A Berjaya Indst Park_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1110A | 1110A Berjaya industrial Park | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1037A_JBA Bangi_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1037A | 1037A JBA Bangi | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1039A JBA Cheras Jaya_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1039A | 1039A JBA Cheras Jaya | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8709A-MAG002 Bentong_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8709A | 8709A-MAG002 Bentong | Fo&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC RING 9/C13 | xD_DWDM_BRKRing_MR9/C13_1295A Com Bkt Maluri_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1295A | 1295A-MAC-001 | Advance | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106+ | xD_DWDM_BRKRing_N106+_4683A Bkt Tok Alang_0004582309010S_00045824006622 | 2024 Q1 | P1 | 4683A | 4683A Bkt Tok Alang | FO&T | 1. Add Battery Bank = 3 | PRPO | Week 12 March | 2024-03-20 | 2024-05-07 | 2024-05-07 | 2024-06-07 | N/A | N/A | Y | 2024-05-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1120A Kota Kemuning_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1120A | 1120A Kota Kemuning | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N113(ii) | xD_DWDM_BRKRing_N113_4663A Derga Jaya_0004582306610C_00045823162822 | 2023 | P1 | 4663A | 4663A Derga Jaya | Fo&T | DC BREAKER : 100A X 2 | Completed | N/A | N/A | 2024-02-22 | 2024-02-23 | N/A | N/A | 2024-03-13 | Y | 2024-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N113(ii) | xD_DWDM_BRKRing_N113_4973B Tajar_0004582306610C_00045823162822 | 2023 | P1 | 4973B | 4973B Tajar | Fo&T | MGB = 1 | Completed | N/A | N/A | 2024-02-22 | 2024-02-22 | N/A | N/A | Plan | Y | 2024-04-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N115 | xD_DWDM_BRKRing_N115_4770A Tok Lin_0004582309010S_00045824006622 | 2023_2024 | N/A | 4770A | 4770A Tok Lin | N/A | RECTTIFIER MODULE = 2 | Completed | N/A | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NT09P | xD_DWDM_BRKRing_NT09P_4640A Sp Plaza_0004582309010S_00045824006622 | 2023_2024 | P1 | 4640A | 4640A Sp Plaza | N/A | DCPDB = 1 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S301 | xD_DWDM_BRKRing_S301_1554AMAG(M14)-001 Rumbia_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1554A | 1554AMAG(M14)-001 Rumbia | BBand | 1.Add battery bank = 3 | PRPO | N/A | 2024-01-24 | 2024-05-29 | 2024-05-29 | 2024-06-07 | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S301 | xD_DWDM_BRKRing_S301_1560A-MAC001 Bkt Tiga_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1560A | 1560A-MAC001 Bkt Tiga | BBand | 1.Add module = 1 | PRPO | N/A | 2024-02-02 | 2024-05-27 | 2024-05-27 | 2024-06-04 | N/A | N/A | N/A | 2024-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S301 | xD_DWDM_BRKRing_S301_1563A-MAC001 Bkt Iman_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1563A | 1563A-MAC001 Bkt Iman | BBand | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | PRPO | N/A | 2024-02-02 | 2024-05-28 | 2024-05-28 | 2024-06-04 | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S301 | xD_DWDM_BRKRing_S301_1621A-MCR001 SNW_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1621A | 1621A-MCR001 SNW | BBand | N/A | N/A | N/A | 2024-01-23 | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD_DWDM_BRKRing_S309_1553AMAG(M14)-001 Umbai_0004582309010R_00045824006624 | 2024 Q1 | P3 | 1553A | 1553AMAG(M14)-001 Umbai | BBand | 1.New plinth | PRPO | N/A | 2024-02-05 | 2024-06-30 | N/A | 2024-07-05 | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD_DWDM_BRKRing_S309_1556A-MAC001 Merlimau_0004582309010R_00045824006624 | 2024 Q1 | P3 | 1556A | 1556A-MAC001 Merlimau | BBand | BATTERY BANK = 3 | PRPO | N/A | 2024-03-05 | 2024-06-12 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD_DWDM_BRKRing_S309_1599A-MAC001 Bkt Gambir Town_0004582309010R_00045824006624 | 2024 Q1 | P3 | 1599A | 1599A-MAC001 Bkt Gambir Town | BBand | BATTERY BANK = 3 | Completed | N/A | 2024-02-01 | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1122A Jenjarum_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1122A | 1122A Jenjarum | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD_DWDM_BRKRing_SAR01_1552A-MAG(M8)-001 Tanjung Bidara_0004582309010R_00045824006624 | 2024 Q1 | P0 | 1552A | 1552A-MAG(M8)-001 Tanjung Bidara | Bband | No CME | N/A | N/A | N/A | 2024-03-21 | 2024-04-05 | N/A | N/A | N/A | Y | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD_DWDM_BRKRing_SAR01_1621A-MCR Senawang_0004582309010R_00045824006624 | 2024 Q1 | P0 | 1621A | 1621A-MCR Senawang | Bband | No CME | N/A | N/A | N/A | 2024-03-22 | 2024-04-05 | N/A | N/A | N/A | Y | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD_DWDM_BRKRing_SAR01_1640A-MAG(M8)-001 Politeknik Port Dickson_0004582309010R_00045824006624 | 2024 Q1 | P0 | 1640A | 1640A-MAG(M8)-001 Politeknik Port Dickson | Bband | No CME | N/A | N/A | N/A | 2024-03-22 | 2024-04-05 | N/A | N/A | N/A | Y | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD_DWDM_BRKRing_SAR01_2021B-Subang Hi-Tech_0004582309010R_00045824006624 | 2024 Q1 | P0 | 2021B | 2021B-Subang Hi-Tech | Bband | No CME | PRPO | N/A | N/A | 2024-03-21 | 2023-12-21 | N/A | N/A | N/A | Y | 2023-12-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Spare | xD_DWDM_BRKRing_Spare_2021B SBHT_0004582307400B_0004582307400C_00045823174223 | 2023 | N/A | 2021B | 2021B SBHT | BBand | No CME | PRPO | N/A | N/A | 2023-12-12 | 2023-12-12 | N/A | N/A | N/A | Y | 2023-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST21P_1 | xD_DWDM_BRKRing_ST21P_1_6063A-MAC-001 KTM Plentong_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 6063A | 6063A-MAC-001 KTM Plentong | BBand | N/A | N/A | N/A | 2023-12-27 | 2024-04-25 | 2024-04-25 | N/A | N/A | N/A | Y | 2024-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST21P_1 | xD_DWDM_BRKRing_ST21P_1_6382A-MAC-001 KTM Pasir Gudang_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 6382A | 6382A-MAC-001 KTM Pasir Gudang | BBand | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | PRPO | N/A | 2023-12-28 | 2024-06-04 | N/A | 2024-06-14 | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST21P | xD_DWDM_BRKRing_ST21P_6000A-MCR002 JBR_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 6000A | 6000A-MCR002 JBR | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | 2024-01-23 | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST21P | xD_DWDM_BRKRing_ST21P_6312A-MAC-001 Jln Cenderai_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 6312A | 6312A-MAC-001 Jln Cenderai | BBand | N/A | N/A | N/A | 2023-12-30 | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_2048B Sg Merab_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 2048B | 2048B Sg Merab | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-06 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST21P | xD_DWDM_BRKRing_ST21P_6400A-MAC-001 Jln Perak_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 6400A | 6400A-MAC-001 Jln Perak | BBand | N/A | N/A | N/A | 2023-12-30 | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST27P | xD_DWDM_BRKRing_ST27P_1607A-MAG001 KM Plaza_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1607A | 1607A-MAG001 KM Plaza | Bband | 1. Decomm Cabinet | PRPO | N/A | 2023-12-21 | 2024-05-27 | 2024-05-27 | 2024-06-07 | N/A | N/A | N/A | 2024-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST27P | xD_DWDM_BRKRing_ST27P_1608A KTM Seremban_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1608A | 1608A KTM Seremban | Bband | N/A | N/A | N/A | 2023-12-21 | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ST27P | xD_DWDM_BRKRing_ST27P_1610A Gun Hill_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 1610A | 1610A Gun Hill | Bband | 1.Add 2nd rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | PRPO | N/A | 2023-12-21 | 2024-05-29 | 2024-05-29 | 2024-06-07 | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Area139 | xD_DWDM-BRKRing_Area139_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | 2023 | P0 | 4000A | 4000A MSC Prai | FO&T | No CME | Completed | N/A | N/A | 2024-03-22 | 2024-03-22 | N/A | N/A | N/A | N/A | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Area139 | xD_DWDM-BRKRing_Area139_4946A Bukit Selambau_0004582306610A_0004582306610D_00045823162822 | 2023 | P0 | 4946A | 4946A Bukit Selambau | FO&T | No CME | Drop | N/A | N/A | 2023-11-22 | 2023-11-22 | N/A | N/A | N/A | N/A | 2024-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 (C0126) | xD_DWDM-BRKRing_C0103_1049B MCR KPG_0004582400320X_00045824009023 | 2024 Q1 | P2 | 1049B | 1049B-MCR001 KPG | Advance | No CME | PRPO | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-05-23 | N/A | N/A | N/A | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8513A-MAG002 Senggora_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8513A | 8513A-MAG002 Senggora | Fo&T | 1.Add battery bank = 2 | PRPO | N/A | 2024-02-02 | 2024-05-08 | 2024-05-07 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E111 | xD_DWDM_BRKRing_E111_8439A-MAC001 A.Lintang_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8439A | 8439A-MAC001 A.Lintang | FO&T | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | N/A | 2024-02-07 | 2024-05-08 | 2024-05-08 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 (C0126) | xD_DWDM-BRKRing_C0103_1364B Bestari(Maxis)_0004582400320X_00045824009023 | 2024 Q1 | P2 | 1364B | 1364B-MAC-001 Bestari (Maxis) | Advance | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0607P | xD_DWDM-BRKRing_C0607P_1196A JBA Puchong_0004582306610C_00045823162822 | 2023 | P1_Z_Oct | 1196A | 1196A JBA Puchong | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | 2023-11-22 | 2023-11-22 | Completed | Y | N/A | Y | 2023-11-23 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0607P | xD_DWDM-BRKRing_C0607P_1402A Jalan Industry Puchong_0004582306610C_00045823162822 | 2023 | P1_Z_Oct | 1402A | 1402A Jalan Industry Puchong | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | 2023-11-22 | 2023-11-22 | Completed | Y | N/A | Y | 2023-11-23 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0607P | xD_DWDM-BRKRing_C0607P_1408A Puchong Jaya_0004582306610C_00045823162822 | 2023 | P1_Z_Oct | 1408A | 1408A Puchong Jaya | BBand | DCPDB = 1 | Completed | N/A | N/A | 2023-11-22 | 2023-11-22 | N/A | N/A | Replan | Y | 2024-02-22 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8000A-MSC Kuantan_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8000A | 8000A-MSC Kuantan | Fo&T | N/A | N/A | N/A | 2024-02-02 | 2024-05-08 | 2024-05-08 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0702P | xD_DWDM-BRKRing_C0702P_1153A MAC PermatangKSelangor_0004582304330Y_00045823098821 | 2023 | P1 | 1153A | 1153A MAC PermatangKSelangor | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | 2023-11-24 | 2023-11-24 | Completed | Y | N/A | Y | 2023-11-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0702P | xD_DWDM-BRKRing_C0702P_1154A MAGSekinchan_0004582304330Y_00045823098821 | 2023 | P1 | 1154A | 1154A MAGSekinchan | BBand | ODF CABINET = 1 | Drop | N/A | N/A | 2023-11-23 | 2023-11-23 | Completed | Y | N/A | Y | 2023-11-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0702P | xD_DWDM-BRKRing_C0702P_1156A MAC BtgBerjuntai_0004582304330Y_00045823098821 | 2023 | P1 | 1156A | 1156A MAC BtgBerjuntai | BBand | ODF CABINET = 1 | Drop | N/A | N/A | 2023-11-24 | 2023-11-24 | Completed | Y | N/A | Y | 2023-11-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0702P | xD_DWDM-BRKRing_C0702P_1169A MAC TgKrngTrunkRd_0004582304330Y_00045823098821 | 2023 | P1 | 1169A | 1169A MAC TgKrngTrunkRd | BBand | DCPDB = 1 | Completed | N/A | N/A | 2023-11-24 | 2023-11-24 | Completed | Y | 2024-01-22 | Y | 2024-01-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0704P | xD_DWDM-BRKRing_C0704P_1073A KTM PadangJawa_0004582306610C_00045823162822 | 2023 | N/A | 1073A | 1073A KTM PadangJawa | Bband | NOT REQUIRED | Drop | N/A | N/A | 2023-11-23 | 2023-11-23 | N/A | N/A | 2024-01-26 | Y | 2024-01-29 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0704P | xD_DWDM-BRKRing_C0704P_1096A Klang Perdana_0004582306610C_00045823162822 | 2023 | N/A | 1096A | 1096A Klang Perdana | BBand | N/A | N/A | N/A | N/A | 2023-11-23 | 2023-11-23 | N/A | N/A | 2024-02-15 | N/A | 2024-07-11 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0704P | xD_DWDM-BRKRing_C0704P_1342A MBSA_0004582306610C_00045823162822 | 2023 | N/A | 1342A | 1342A MBSA | Bband | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | N/A | N/A | N/A | Y | 2024-02-20 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0704P | xD_DWDM-BRKRing_C0704P_1367A Worldwide Biz_0004582306610C_00045823162822 | 2023 | N/A | 1367A | 1367A Worldwide Biz | Bband | NOT REQUIRED | Drop | N/A | N/A | 2023-11-24 | 2023-11-24 | N/A | N/A | 2024-01-05 | Y | 2024-01-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0704P | xD_DWDM-BRKRing_C0704P_2021B SBHT_0004582306610C_00045823162822 | 2023 | N/A | 2021B | 2021B SBHT | BBand | 1.ODF Rack (Glass Door) | PRPO | N/A | N/A | 2023-12-04 | 2023-12-04 | N/A | N/A | 2024-01-09 | Y | 2023-12-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0713P | xD_DWDM-BRKRing_C0713P_1071A_Chi Liung Plaza_0004582304330V_00045823098821 | 2023 | P0 | 1071A | Chi Liung Plaza | BBand | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Completed | Y | 4//1/2024 | Y | 2024-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0713P | xD_DWDM-BRKRing_C0713P_1096A_KlangPerdana_0004582304330V_00045823098821 | 2023 | P0 | 1096A | KlangPerdana | BBand | No CME | N/A | N/A | N/A | 2023-11-23 | 2023-11-23 | Completed | Y | N/A | Y | 2023-11-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0713P | xD_DWDM-BRKRing_C0713P_1342A_MBSA_00045823098821 | 2023 | P0 | 1342A | MBSA | BBand | No CME | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0713P | xD_DWDM-BRKRing_C0713P_2021B_SBHT_0004582304330V_00045823098821 | 2023 | P0 | 2021B | SBHT | BBand | No CME | PRPO | N/A | N/A | 2023-12-12 | 2023-12-12 | Completed | Y | N/A | Y | 2023-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1049B MCR KPG_0004582400460T_00045824009529 | 2024 Q1 | P0 | 1049B | 1049B MCR KPG | BBand | No CME | PRPO | N/A | N/A | 2024-03-22 | 2024-03-22 | N/A | N/A | N/A | Y | 2024-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1049B_KPG_0004582304330V_00045823098821 | 2023 | P0 | 1049B | KPG | BBand | No CME | PRPO | N/A | N/A | 2023-11-06 | 2023-11-06 | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1058A_Pekan Meru_00045823098821 | 2023 | P0 | 1058A | Pekan Meru | BBand | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1071A_Chi Liung Plaza_00045823098821 | 2023 | P0 | 1071A | Chi Liung Plaza | BBand | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 | 2024 Q1 | P0 | 1085A | 1085A Pekan Meru | BBand | No CME | N/A | N/A | N/A | 2024-03-22 | 2024-03-22 | N/A | N/A | N/A | Y | 2024-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1096A_KlangPerdana_00045823098821 | 2023 | P0 | 1096A | KlangPerdana | BBand | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1359A_Mutiara Subang_00045823098821 | 2023 | P0 | 1359A | Mutiara Subang | BBand | No CME | PRPO | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1409A Kota Damansara_0004582400460T_00045824009529 | 2024 Q1 | P0 | 1409A | 1409A Kota Damansara | BBand | No CME | Completed | N/A | N/A | 2024-03-20 | 2024-03-21 | N/A | N/A | N/A | Y | 2024-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1409A_Kota Damansara_00045823098821 | 2023 | P0 | 1409A | Kota Damansara | BBand | No CME | Completed | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_2021B SBHT_0004582400460T_00045824009529 | 2024 Q1 | P0 | 2021B | 2021B SBHT | BBand | No CME | PRPO | N/A | N/A | 2024-03-20 | 2024-03-22 | N/A | N/A | N/A | Y | 2024-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_2021B_SBHT_0004582304330V_00045823098821 | 2023 | P0 | 2021B | SBHT | BBand | No CME | PRPO | N/A | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_2631A_Samarinda_00045823098821 | 2023 | P0 | 2631A | Samarinda | BBand | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_2777C JBA Bukit Lipat_0004582400460T_00045824009529 | 2024 Q1 | P0 | 2777C | 2777C JBA Bukit Lipat | BBand | No CME | N/A | N/A | N/A | 2024-03-21 | 2024-03-25 | N/A | N/A | N/A | Y | 2024-03-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_2777C_JBABkitLipat_0004582304330V_00045823098821 | 2023 | P0 | 2777C | JBABkitLipat | BBand | No CME | N/A | N/A | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | 2023-12-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1253A Plaza Pengkalan_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1253A | Plaza Pengkalan 1253A | BBand | No CME | PRPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1261A KWSP_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1261A | KWSP 1261A | BBand | No CME | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1266A Sucasa_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1266A | Sucasa 1266A | BBand | No CME | PRPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1271A Risda_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1271A | Risda 1271A | BBand | No CME | PRPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1461A Shaw Parade_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1461A | Shaw parade 1461A | BBand | No CME | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1737A Bernama_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1737A | Bernama 1737A | BBand | No CME | PRPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1851A KL Plaza_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1851A | KL Plaze 1851A | BBand | No CME | PRPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM-BRKRing_CAR04_1855B TPM_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1855B | TPM 1855B | BBand | No CME | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Y | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR11 | xD_DWDM-BRKRing_CAR11_1049B MCR Kepong_0004582400700P_00045824009527 | 2024 Q1 | P0 | 1049B | 1049B-MCR-002 KPG | BBand | No CME | PRPO | N/A | N/A | 2024-04-22 | 2024-04-22 | N/A | N/A | N/A | Y | 2024-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR11 | xD_DWDM-BRKRing_CAR11_2070B Gombak_0004582400700P_00045824009527 | 2024 Q1 | P0 | 2070B | 2070B-MAG-001 Gombak Tx | BBand | No CME | Completed | N/A | N/A | 2024-04-22 | 2024-04-22 | N/A | N/A | N/A | Y | 2024-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR11 | xD_DWDM-BRKRing_CAR11_8709A Bentong_0004582400700P_00045824009527 | 2024 Q1 | P0 | 8709A | 8709A-MAG-003 Bentong | BBand | No CME | Completed | N/A | N/A | 2024-04-18 | 2024-04-18 | N/A | N/A | N/A | Y | 2024-04-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT0120 | xD_DWDM-BRKRing_CT0120_2632A Ecopark_0004582304160F_0004582308742 | 2023 | P1_IP_BR-Q1 | 2632A | 2632A Ecopark | Advance | AC BREAKER : 32 X 3 | Completed | N/A | N/A | 2024-05-21 | 2024-03-27 | N/A | N/A | 2024-04-23 | Y | 2024-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD_DWDM-BRKRing_E212_8923B Tmn Semarak_0004582304160F_00045823087420 | 2023 | N/A | 8923B | 8923B Tmn Semarak | FO&T | ADD 100A X 2 BREAKER | Drop | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR04 | xD_DWDM-BRKRing_EAR04_1049B_KPG_00045823098821 | 2023 | N/A | 1049B | KPG | FO&T | No CME | PRPO | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-10-25 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR04 | xD_DWDM-BRKRing_EAR04_1475A_MSC MSK_00045823098821 | 2023 | N/A | 1475A | MSC MSK | FO&T | No CME | PRPO | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-10-25 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR04 | xD_DWDM-BRKRing_EAR04_2021B_SBHT_00045823098821 | 2023 | N/A | 2021B | SBHT | FO&T | No CME | PRPO | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-10-25 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR04 | xD_DWDM-BRKRing_EAR04_8000A_MSC KTN_00045823098821 | 2023 | N/A | 8000A | MSC KTN | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-10-25 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR04 | xD_DWDM-BRKRing_EAR04_8703A_KG Awah_00045823098821 | 2023 | N/A | 8703A | KG Awah | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-10-25 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR144 | xD_DWDM-BRKRing_MCR144_1007A MAC Mimaland_0004582304330Y_00045823098821 | 2023 | N/A | 1007A | 1007A MAC Mimaland | BBand | DCPDB = 1 UNIT | Completed | N/A | N/A | N/A | 2023-10-10 | Completed | Y | N/A | Y | 2023-10-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR144 | xD_DWDM-BRKRing_MCR144_1770B MAC GentingSempah_0004582304330Y_00045823098821 | 2023 | N/A | 1770B | 1770B MAC GentingSempah | Bband | AC BREAKER : 32 X 3 | Completed | N/A | N/A | N/A | 2023-10-17 | Completed | Y | N/A | Y | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR144 | xD_DWDM-BRKRing_MCR144_1787B MAC KarakHW_0004582304330Y_00045823098821 | 2023 | N/A | 1787B | 1787B MAC KarakHW | Bband | DC BREAKER: 63A X 2 | Completed | N/A | N/A | N/A | 2023-10-17 | Completed | Y | N/A | Y | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR144 | xD_DWDM-BRKRing_MCR144_2070B MAC Gombak_0004582304330Y_00045823098821 | 2023 | N/A | 2070B | 2070B MAC Gombak | Bband | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-19 | Completed | Y | N/A | Y | 2023-10-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR144 | xD_DWDM-BRKRing_MCR144_2086A Balai Polis Bkt Tinggi_0004582304330Y_00045823098821 | 2023 | N/A | 2086A | 2086A Balai Polis Bkt Tinggi | Bband | DC BREAKER: 63A X 2 | Completed | N/A | N/A | N/A | 2023-10-18 | Completed | Y | N/A | Y | 2023-10-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR144 | xD_DWDM-BRKRing_MCR144_8709A MAG Bentong_0004582304330Y_00045823098821 | 2023 | N/A | 8709A | 8709A MAG Bentong | BBand | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-16 | Completed | Y | N/A | Y | 2023-10-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR18/C24 | xD_DWDM-BRKRing_MCR18/C24_1172A Glomac_0004582306610C_00045823162822 | 2023 | P2 | 1172A | 1172A Glomac | BBand | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E111 | xD_DWDM_BRKRing_E111_8367A-MAG001 B.Kechil_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8367A | 8367A-MAG001 B.Kechil | FO&T | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) 2.Add battery bank = 9 3.Battery rack | PRPO | N/A | 2024-02-07 | 2024-05-08 | 2024-05-09 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01 | xD_DWDM_BRKRing_EAR01_8224A-MAG-001 Pasir Puteh_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_BR-Q1 | 8224A | 8224A-MAG-001 Pasir Puteh | Fo&T | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | PRPO | N/A | 2023-12-21 | 2024-05-09 | 2024-05-09 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR06 | xD_DWDM_BRKRing_EAR06_8667A-MAG 001 Kg Jerangsang_0004582309010R_00045824006624 | 2024 Q1 | P1_IP_R_EXP-Q1 | 8667A | 8667A-MAG 001 Kg Jerangsang | Fo&T | 1.Add modules = 2 | PRPO | N/A | 2024-02-07 | 2024-05-09 | 2024-05-09 | 2024-06-07 | N/A | N/A | N/A | 2024-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR18/C24 | xD_DWDM-BRKRing_MCR18/C24_2021B SBHT_0004582306610C_00045823162822 | 2023 | P2 | 2021B | 2021B SBHT | Bband | 1.ODF Rack (Glass Door) | PRPO | N/A | N/A | N/A | 2023-11-07 | Completed | Y | 2024-01-09 | Y | 2023-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N103 | xD_DWDM-BRKRing_N103_4660A KTM Alorstar_0004582306610C_00045823162822 | 2023 | P1 | 4660A | 4660A KTM Alorstar | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-24 | N/A | N/A | 2024-01-12 | Y | 2024-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N103 | xD_DWDM-BRKRing_N103_4669A Alor Janggus_0004582306610C_00045823162822 | 2023 | P1 | 4669A | 4669A Alor Janggus | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-03-15 | Y | 2024-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N103 | xD_DWDM-BRKRing_N103_4863B Wisma PKNK_0004582306610C_00045823162822 | 2023 | P1 | 4863B | 4863B Wisma PKNK | FO&T | 1. Add Battery Bank = 1 | PRPO | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-05-25 | N/A | Replan | Y | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N103 | xD_DWDM-BRKRing_N103_4998A Air Itam Kedah_0004582306610C_00045823162822 | 2023 | P1 | 4998A | 4998A Air Itam Kedah | FO&T | 1. Add Battery Bank = 1 | PRPO | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-01-12 | Y | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106 | xD_DWDM-BRKRing_N106_4085D Kulim Hitech2_0004582306610C_00045823162822 | 2023 | N/A | 4085D | 4085D Kulim Hitech2 | FO&T | RECTTIFIER MODULE = 2 | Completed | N/A | N/A | N/A | 2023-11-08 | Completed | Y | N/A | Y | 2023-11-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106 | xD_DWDM-BRKRing_N106_4683A Bkt Tok Alang_0004582306610C_00045823162822 | 2023 | N/A | 4683A | 4683A Bkt Tok Alang | FO&T | 1. Add Battery Bank = 3 | PRPO | N/A | N/A | N/A | 2023-11-09 | Completed | Y | N/A | Y | 2023-11-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106 | xD_DWDM-BRKRing_N106_4946A Bukit Selambau_0004582306610C_00045823162822 | 2023 | N/A | 4946A | 4946A Bukit Selambau | FO&T | DROP | Drop | N/A | N/A | N/A | 2023-11-09 | Completed | Y | N/A | Y | 2023-11-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106 | xD_DWDM-BRKRing_N106_4966A Kulim Hi Tech_0004582306610C_00045823162822 | 2023 | N/A | 4966A | 4966A Kulim Hi Tech | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | Completed | Y | N/A | Y | 2023-11-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N113 | xD_DWDM-BRKRing_N113_4662A MAC BktTinggiJitra_0004582304330Y_00045823098821 | 2023 | N/A | 4662A | 4662A MAC BktTinggiJitra | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-25 | Completed | Y | 04/01/2024-5/1/2024 | Y | 2024-01-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N113 | xD_DWDM-BRKRing_N113_4678A MAC JlnLanggar_0004582304330Y_00045823098821 | 2023 | N/A | 4678A | 4678A MAC JlnLanggar | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-23 | Completed | Y | 04/01/2024-5/1/2024 | Y | 2024-01-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N113 | xD_DWDM-BRKRing_N113_4992A MAG Pendang_0004582304330Y_00045823098821 | 2023 | N/A | 4992A | 4992A MAG Pendang | FO&T | 1.Swap breaker = 4 (4x100A DC) | Completed | N/A | N/A | N/A | 2023-10-25 | Completed | Y | 04/01/2024-5/1/2024 | Y | 2024-01-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N113 | xD_DWDM-BRKRing_N113_4995A MAG UUMHW_0004582304330Y_00045823098821 | 2023 | N/A | 4995A | 4995A MAG UUMHW | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | Completed | Y | 04/01/2024-5/1/2024 | Y | 2024-01-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N114M | xD_DWDM-BRKRing_N114M_4660A Ktm Astar_000458237400E_00045823174223 | 2023 | N/A | 4660A | 4660A Ktm Astar | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-24 | Completed | Y | 2024-01-18 | Y | 2024-01-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N114M | xD_DWDM-BRKRing_N114M_4692A Gurun_0004582306610C_00045823162822 | 2023 | N/A | 4692A | 4692A Gurun | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | N/A | N/A | 2024-01-29 | Y | 2024-01-29 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N114M | xD_DWDM-BRKRing_N114M_4938A Tmn Orkid_000458237400E_00045823174223 | 2023 | N/A | 4938A | 4938A Tmn Orkid | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-23 | N/A | N/A | 2024-03-07 | Y | 2024-03-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N114M | xD_DWDM-BRKRing_N114M_4938A Tmn Orkid2_000458237400E_00045823174223 | 2023 | N/A | 4938A | 4938A Tmn Orkid2 | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-23 | N/A | N/A | 2024-03-07 | Y | 2024-03-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N114M | xD_DWDM-BRKRing_N114M_4940A Semeling_0004582306610C_00045823162822 | 2023 | N/A | 4940A | 4940A Semeling | FO&T | BATTERY BANK = 2 | Completed | N/A | N/A | N/A | 2023-11-22 | N/A | N/A | 2024-01-30 | Y | 2024-01-30 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N115 | xD_DWDM-BRKRing_N115_4770A Toklin_0004582304160F_00045823087420 | 2023 | N/A | 4770A | 4770A Toklin | FO&T | RECTTIFIER MODULE = 2 | Completed | N/A | N/A | N/A | 2023-11-22 | Completed | Y | N/A | Y | 2023-11-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4000A MSC Prai_000458237400E_00045823174223 | 2023 | P?? | 4000A | 4000A MSC Prai | FO&T | DC BREAKER: 63A X 12 | Completed | N/A | N/A | N/A | 2023-11-20 | Completed | Y | 2024-01-31 | Y | 2023-11-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4685B Kg Sungai Karangan_000458237400E_00045823174223 | 2023 | P?? | 4685B | 4685B Kg Sungai Karangan | FO&T | DCPDB = 1 UNIT | Completed | N/A | N/A | N/A | 2023-11-30 | Completed | Y | 2024-02-01 | Y | 2024-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4950B Pulai_000458237400E_00045823174223 | 2023 | P?? | 4950B | 4950B Pulai | FO&T | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-11-23 | N/A | N/A | 2024-02-06 | Y | 2024-02-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4956B Kuala Pegang_000458237400E_00045823174223 | 2023 | P?? | 4956B | 4956B Kuala Pegang | FO&T | DCPDB = 1 UNIT | Completed | N/A | N/A | N/A | 2023-11-23 | N/A | N/A | 2024-02-05 | Y | 2024-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4968A Inokom Kulim_000458237400E_00045823174223 | 2023 | P?? | 4968A | 4968A Inokom Kulim | FO&T | AC BREAKER : 32 X 3 | Completed | N/A | N/A | N/A | 2023-11-24 | Completed | Y | 2024-01-30 | Y | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4985A Baling Town_000458237400E_00045823174223 | 2023 | P?? | 4985A | 4985A Baling Town | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-02-07 | Y | 2024-02-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4986A Binjul_000458237400E_00045823174223 | 2023 | P?? | 4986A | 4986A Binjul | FO&T | DCPDB = 1 UNIT | Completed | N/A | N/A | N/A | 2023-11-24 | N/A | N/A | 2024-02-02 | Y | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N201 | xD_DWDM-BRKRing_N201_4988A Kupang_000458237400E_00045823174223 | 2023 | P?? | 4988A | 4988A Kupang | FO&T | BATTERY BANK = 2 | Completed | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-02-05 | Y | 2024-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N302 | xD_DWDM-BRKRing_N302_4000A MSC Prai_0004582306610C_00045823162822 | 2023 | N/A | 4000A | 4000A MSC Prai | FO&T | DC BREAKER: 63A X 12 | Completed | N/A | N/A | N/A | 2023-11-20 | N/A | N/A | 2024-01-31 | Y | 2024-01-31 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N302 | xD_DWDM-BRKRing_N302_4188A Nibong tebal2_0004582306610C_00045823162822 | 2023 | N/A | 4188A | 4188A Nibong tebal2 | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-01-16 | Y | 2024-01-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N302 | xD_DWDM-BRKRing_N302_4241A Juru Tower_0004582306610C_00045823162822 | 2023 | N/A | 4241A | 4241A Juru Tower | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | Completed | Y | 2024-01-16 | Y | 2024-01-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N404 | xD_DWDM-BRKRing_N404_4427B MAC SimpangTaiping_0004582304330Y_00045823098821 | 2023 | N/A | 4427B | 4427B MAC SimpangTaiping | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-19 | Completed | Y | 9/1/2024-11/1/2024 | Y | 2024-01-15 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N404 | xD_DWDM-BRKRing_N404_4454B MAC KubuGajah_0004582304330Y_0004582307060Z_00045823098821 | 2023 | N/A | 4454B | 4454B MAC KubuGajah | FO&T | DC BREAKER : 100A X 2 | Completed | N/A | N/A | N/A | 2023-11-10 | Completed | Y | 9/1/2024-11/1/2024 | Y | 2024-01-15 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N404 | xD_DWDM-BRKRing_N404_4455A MAG KTMTaiping_0004582304330Y_00045823098821 | 2023 | N/A | 4455A | 4455A MAG KTMTaiping | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | Completed | Y | 9/1/2024-11/1/2024 | Y | 2024-01-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N404 | xD_DWDM-BRKRing_N404_4457A MAC KamuntingIndst_0004582304330Y_00045823098821 | 2023 | N/A | 4457A | 4457A MAC KamuntingIndst | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | Completed | Y | 9/1/2024-11/1/2024 | Y | 2024-01-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N404 | xD_DWDM-BRKRing_N404_4465A MAC TmnLongJaafar_0004582304330Y_00045823098821 | 2023 | N/A | 4465A | 4465A MAC TmnLongJaafar | FO&T | BATTERY BANK = 7 | Completed | N/A | N/A | N/A | 2023-10-18 | Completed | Y | 9/1/2024-11/1/2024 | Y | 2024-01-15 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N404 | xD_DWDM-BRKRing_N404_4952B MAG Selama_0004582304330Y_00045823098821 | 2023 | N/A | 4952B | 4952B MAG Selama | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | Completed | Y | 9/1/2024-11/1/2024 | Y | 2024-01-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N406 | xD_DWDM-BRKRing_N406_4432A MAG KTMSgSiput_0004582304330Y_0004582304330X_00045823098821 | 2023 | N/A | 4432A | 4432A MAG KTMSgSiput | FO&T | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-22 | N/A | N/A | 2024-03-14 | Y | 2024-03-22 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N406 | xD_DWDM-BRKRing_N406_4493A MAG KTMIpoh_0004582304330Y_0004582304330X_00045823098821 | 2023 | N/A | 4493A | 4493A MAG KTMIpoh | FO&T | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | 2024-03-14 | N/A | 2024-07-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N406 | xD_DWDM-BRKRing_N406_4496A MAC LapTasek1N2_0004582304330Y_0004582304330X_00045823098821 | 2023 | N/A | 4496A | 4496A MAC LapTasek1N2 | FO&T | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | N/A | N/A | 2024-03-14 | Y | 2024-03-13 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N406 | xD_DWDM-BRKRing_N406_4536A MAC TasekIndst_0004582304330Y_0004582304330X_00045823098821 | 2023 | N/A | 4536A | 4536A MAC TasekIndst | FO&T | N/A | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | 2024-03-14 | N/A | 2024-07-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N601 | xD_DWDM-BRKRing_N601_4368A Tar College_0004582306900G_00045823168029 | 2023 | N/A | 4368A | 4368A Tar College | FO&T | DC BREAKER : 63A X 4 | Completed | N/A | N/A | N/A | 2023-11-21 | Completed | Y | 2024-01-29 | Y | 2024-01-29 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N601 | xD_DWDM-BRKRing_N601_4440B Tapah Road_0004582306900G_00045823168029 | 2023 | N/A | 4440B | 4440B Tapah Road | FO&T | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-11-22 | Completed | Y | 2024-01-17 | Y | 2024-01-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N601 | xD_DWDM-BRKRing_N601_4509A Tamn Taufik_0004582306900G_00045823168029 | 2023 | N/A | 4509A | 4509A Tamn Taufik | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-22 | N/A | N/A | 2024-02-06 | Y | 2024-02-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N601 | xD_DWDM-BRKRing_N601_4516A Simpang Pulai_0004582306900G_00045823168029 | 2023 | N/A | 4516A | 4516A Simpang Pulai | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-22 | N/A | N/A | 2024-02-07 | Y | 2024-02-06 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N601 | xD_DWDM-BRKRing_N601_4521A MSC Ipoh_0004582306900G_00045823168029 | 2023 | N/A | 4521A | 4521A MSC Ipoh | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | N/A | 2024-01-29 | Y | 2024-01-30 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01i | xD_DWDM-BRKRing_Nar01i_4000A Msc Prai | Pending PO | N/A | 4000A | 4000A Msc Prai | FO&T | No CME | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01i | xD_DWDM-BRKRing_Nar01i_4521A Msc Ipoh | Pending PO | N/A | 4521A | 4521A Msc Ipoh | FO&T | No CME | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01i | xD_DWDM-BRKRing_Nar01i_4946A Bkt Selambau | Pending PO | N/A | 4946A | 4946A Bkt Selambau | FO&T | No CME | Drop | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01i | xD_DWDM-BRKRing_Nar01i_4966A Kulim Hitech | Pending Po | N/A | 4966A | 4966A Kulim Hitech | FO&T | No CME | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01i | xD_DWDM-BRKRing_Nar01i_4992A Pendang | Pending PO | N/A | 4992A | 4992A Pendang | FO&T | No CME | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01ii | xD_DWDM-BRKRing_Nar01ii_4606A Padang Besar | Pending PO | N/A | 4606A | 4606A Padang Besar | FO&T | No CME | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01ii | xD_DWDM-BRKRing_Nar01ii_4638A Tmn Orkid | Pending PO | N/A | 4938A | 4638A Tmn Orkid | FO&T | No CME | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01ii | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | Pending PO | N/A | 4660A | 4660A Ktm Astar | FO&T | No CME | N/A | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Nar01ii | xD_DWDM-BRKRing_Nar01ii_4660A Ktm Astar | Pending PO | N/A | 4998A | 4660A Ktm Astar | FO&T | No CME | PRPO | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR03 | xD_DWDM-BRKRing_NAR03_4000A MSC Prai_0004582306610A_0004582306610D_00045823162822 | 2023 | P0 | 4000A | 4000A MSC Prai | FO&T | No CME | Completed | N/A | N/A | N/A | 2023-11-20 | N/A | N/A | 2024-01-08 | Y | 2024-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR03 | xD_DWDM-BRKRing_NAR03_4331A Bagan Serai_0004582306610A_0004582306610D_00045823162822 | 2023 | P0 | 4331A | 4331A Bagan Serai | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-11-22 | N/A | N/A | 2024-01-08 | Y | 2024-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR06 | xD_DWDM-BRKRing_NAR06_1049B Kpg_0004582306610A_0004582306610D_00045823162822 | 2023 | N/A | 1049B | 1049B Kpg | FO&T | No CME | PRPO | N/A | N/A | N/A | 2023-12-15 | N/A | N/A | 2024-01-08 | N/A | 2024-01-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR06 | xD_DWDM-BRKRing_NAR06_1801A Kerling Trnk_0004582306610A_0004582306610D_00045823162822 | 2023 | N/A | 1701A | 1801A Kerling Trnk | FO&T | No CME | Completed | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR06 | xD_DWDM-BRKRing_NAR06_4412A KTM Sungkai_0004582306610A_0004582306610D_00045823162822 | 2023 | N/A | 4412A | 4412A KTM Sungkai | FO&T | No CME | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR06 | xD_DWDM-BRKRing_NAR06_4440B Tapah Road_0004582306610A_0004582306610D_00045823162822 | 2023 | N/A | 4440B | 4440B Tapah Road | FO&T | No CME | Completed | N/A | N/A | N/A | 2024-01-23 | N/A | N/A | 2024-01-08 | Y | 2024-01-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR06 | xD_DWDM-BRKRing_NAR06_4521A MSC IPOH_0004582306610A_0004582306610D_00045823162822 | 2023 | N/A | 4521A | 4521A MSC IPOH | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | N/A | 2024-01-08 | Y | 2024-01-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR06 | xD_DWDM-BRKRing_NAR06_4521A MSC IPOH_0004582306610A_0004582306610D_00045823162822 | 2023 | N/A | 4521A | 4521A MSC IPOH | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | N/A | 2024-01-08 | Y | 2024-01-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6000A MSC JB_0004582306610B_00045823162821 | 2023 | P1 | 6000A | 6000A MSC JB | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-12-05 | N/A | N/A | 2024-02-15 | Y | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6026A Grand Cont Hotel_0004582306610B_00045823162821 | 2023 | P1 | 6026A | 6026A Grand Cont Hotel | BBand | DC BREAKER: 63A X 3 | Completed | N/A | N/A | N/A | 2023-12-07 | N/A | N/A | 2024-02-15 | Y | 2024-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6043A KK Kam_0004582306610B_00045823162821 | 2023 | P1 | 6043A | 6043A KK Kam | Bband | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | Completed | Y | 2024-01-10 | Y | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6283A Larkin Indst_0004582306610B_00045823162821 | 2023 | P1 | 6283A | 6283A Larkin Indst | BBand | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-12-08 | N/A | N/A | 2024-03-12 | Y | 2024-05-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6502A Nusa Perintis_0004582306610B_00045823162821 | 2023 | P1 | 6502A | 6502A Nusa Perintis | BBand | BATTERY BANK = 1 | Completed | N/A | N/A | N/A | 2023-12-08 | Completed | Y | N/A | Y | 2024-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
New Ring5/S406 | xD_DWDM-BRKRing_New Ring_5/S406_6836A Menara Ansar_0004582306610B_0004582316282 | 2023 | P1 | 6836A | 6836A Menara Ansar | BBand | 1.Swap Breaker = 4 (Require 63A x 4 DC breaker) | Completed | N/A | N/A | 2024-04-24 | 2024-04-24 | N/A | N/A | N/A | Y | 2024-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NT09P | xD_DWDM-BRKRing_NT09P_4000A MSC Prai_000458237400E_00045823174223 | 2023 | P1 | 4000A | 4000A MSC Prai | FO&T | DC BREAKER: 63A X 12 | Completed | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2024-01-31 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NT09P | xD_DWDM-BRKRing_NT09P_4621A Cayman Shop Comp_000458237400E_00045823174223 | 2023 | P1 | 4621A | 4621A Cayman Shop Comp | FO&T | BATTERY BANK = 3 | Completed | N/A | N/A | N/A | 2023-11-24 | Completed | Y | 2024-01-30 | Y | 2024-01-30 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NT09P | xD_DWDM-BRKRing_NT09P_4625A KTM Sg Petani_000458237400E_00045823174223 | 2023 | P1 | 4625A | 4625A KTM Sg Petani | FO&T | BATTERY BANK = 3 | Completed | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-01-31 | Y | 2024-01-31 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NT09P | xD_DWDM-BRKRing_NT09P_4640A SP Plaza_0004582304160F_00045823087420 | 2023 | P1 | 4640A | 4640A SP Plaza | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-12-07 | N/A | N/A | 2024-02-01 | Y | 2024-02-01 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NT09P | xD_DWDM-BRKRing_NT09P_4693A Ktm Gurun_000458237400E_00045823174223 | 2023 | P1 | 4693A | 4693A Ktm Gurun | FO&T | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-11-22 | Completed | Y | 2024-01-29 | Y | 2024-01-29 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PFSRING101/C0607P | xD_DWDM-BRKRing_PFSRING101/C0607P_1246A Kompleks Nagaria_0004582306610C_00045823162822 | 2023 | P1 | 1246A | 1246A Kompleks Nagaria | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-12-08 | N/A | N/A | 2024-02-16 | Y | 2024-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PFSRING101/C0607P | xD_DWDM-BRKRing_PFSRING101/C0607P_1475A Sri Kembangan_0004582306610C_00045823162822 | 2023 | P1 | 1475A | 1475A Sri Kembangan | BBand | 1.ODF Rack (Glass Door) | PRPO | N/A | N/A | N/A | 2023-12-04 | Completed | Y | 2024-01-22 | Y | 2024-01-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PFSRING101/C0607P | xD_DWDM-BRKRing_PFSRING101/C0607P_1851A KL Plaza2_0004582306610C_00045823162822 | 2023 | P1 | 1851A | 1851A KL Plaza2 | BBand | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | N/A | N/A | N/A | 2023-11-24 | N/A | N/A | 2024-02-16 | Y | 2024-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106+ | xD_DWDM_BRKRing_N106+_4966A Kulim Hitech_0004582309010S_00045824006622 | 2024 Q1 | P1 | 4966A | 4966A Kulim Hitech | FO&T | N/A | N/A | Week 12 March | 2024-03-20 | 2024-05-07 | 2024-05-09 | N/A | N/A | June Plan | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PFSRING101/C0607P | xD_DWDM-BRKRing_PFSRING101/C0607P_1899A Berjaya Times Square CAS_0004582306610C_00045823162822 | 2023 | P1 | 1899A | 1899A Berjaya Times Square | BBand | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | N/A | 2024-03-07 | 2024-05-09 | 2024-05-09 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_1016A Genting Ria_0004582307100Y_00045823168326 | 2023 | P1_Z_Aug | 1016A | 1016A Genting Ria | BBand | N/A | N/A | 2024-04-26 | N/A | 2024-06-05 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_1770B Genting Sempah_0004582307100Y_00045823168326 | 2023 | P1_Z_Aug | 1770B | 1770B Genting Sempah | BBand | AC BREAKER : 32 X 3 | Completed | N/A | N/A | N/A | 2023-12-15 | N/A | N/A | 2024-01-16 | Y | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_2070B Gombak_0004582307100Y_00045823168326 | 2023 | P1_Z_Aug | 2070B | 2070B Gombak | BBand | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-25 | Completed | Y | N/A | Y | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_2833A First World Hotel_0004582307100Y_00045823168326 | 2023 | P1_Z_Aug | 2833A | 2833A First World Hotel | BBand | AC BREAKER : 32 X 1 | Completed | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_8709A Bentong_0004582307100Y_00045823168326 | 2023 | P1_Z_Aug | 8709A | 8709A Bentong | BBand | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-25 | Completed | Y | 2024-02-16 | Y | 2024-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2_2 | xD_DWDM-BRKRing_S313P_2_2_1525A Graha Maju_0004582304160F_00045823087420 | 2023 | P3 | 1525A | 1525A Graha Maju | BBand | DC BREAKER: 16A X 2 | Completed | N/A | N/A | N/A | 2023-11-24 | Completed | Y | 2024-03-11 | Y | 2024-02-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S406 | xD_DWDM-BRKRing_S406_6442A Senai Airport_0004582306610B_00045823162821 | 2023 | P0 | 6442A | 6442A Senai Airport | BBand | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-12-06 | N/A | N/A | 2024-02-23 | Y | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S406 | xD_DWDM-BRKRing_S406_6576A Jln Seelong_0004582306610B_00045823162821 | 2023 | P0 | 6576A | 6576A Jln Seelong | BBand | DC BREAKER: 63A X 2 | Completed | N/A | N/A | N/A | 2024-02-16 | N/A | N/A | 2024-02-24 | Y | 2024-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S602M | xD_DWDM-BRKRing_S602M_6000A MSC JB_0004582306610B_00045823162821 | 2023 | N/A | 6000A | 6000A MSC JB | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-12-14 | N/A | 2024-02-14 | 2024-02-15 | Y | 2024-02-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S602M | xD_DWDM-BRKRing_S602M_6369A Sri Saujana_0004582306610B_00045823162821 | 2023 | N/A | 6369A | 6369A Sri Saujana | BBand | 1. Add Battery Bank = 6 | PRPO | N/A | N/A | 2024-06-30 | N/A | N/A | N/A | 2024-01-09 | Y | 2024-02-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S602M | xD_DWDM-BRKRing_S602M_6955A Putri Wangsa2_0004582306610B_00045823162821 | 2023 | N/A | 6955A | 6955A Putri Wangsa2 | BBand | DCPDB = 1 UNIT | Completed | N/A | N/A | N/A | 2023-12-06 | Completed | Y | 2024-01-10 | Y | 2024-01-08 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD_DWDM-BRKRing_SAR01_1690A BktPelandok_0004582304070Q_0004582304070T_00045823086825 | 2023 | P0 | 1690A | 1690A BktPelandok | BBand | No CME | N/A | N/A | N/A | 2024-03-12 | 2024-03-22 | N/A | N/A | N/A | N/A | 2023-10-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR04 | xD_DWDM-BRKRing_SAR04_1659A Bahau Tower_0004582400710C_00045824009526 | 2024 Q1 | P0 | 1659A | 1659A-MAG-001 Bahau Tower | BBand | No CME | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | N/A | N/A | N/A | Y | 2024-04-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR04 | xD_DWDM-BRKRing_SAR04_6442A Senai Airport_0004582400710C_00045824009526 | 2024 Q1 | P0 | 6442A | 6442A-MAG-001 Senai Airport | BBand | No CME | Completed | N/A | N/A | 2024-04-23 | 2024-04-23 | N/A | N/A | N/A | Y | 2024-04-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR04 | xD_DWDM-BRKRing_SAR04_6911C KTM Labis_0004582400710C_00045824009526 | 2024 Q1 | P0 | 6911C | 6911C-MAG-001 KTM Labis | BBand | No CME | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | N/A | N/A | N/A | Y | 2024-04-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0114 | xD-DWDM_BRKRingC0114_2021B SUBANG HITECH_00045823086827 | 2023 | N/A | 2021B | 2021B SUBANG HITECH | BBand | No CME | PRPO | N/A | N/A | N/A | Completed | Completed | Y | N/A | N/A | 2023-07-09 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0114 | xD-DWDM_BRKRingC0114_2631A SAMARINDA_00045823086827 | 2023 | N/A | 2631A | 2631A SAMARINDA | BBand | No CME | N/A | N/A | N/A | N/A | Completed | Completed | Y | N/A | N/A | 2023-07-09 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0501P | xD-DWDM_BRKRingC0501P_1110A BERJAYA INDUSTRIAL PARK_0045823085921 | 2023 | N/A | 1110A | 1110A BERJAYA INDUSTRIAL PARK | BBand | No CME | N/A | N/A | N/A | 2024-03-12 | Completed | Completed | Y | N/A | Y | 2023-07-06 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0501P | xD-DWDM_BRKRingC0501P_2021B SUBANG HITECH_0045823085921 | 2023 | N/A | 2021B | 2021B SUBANG HITECH | BBand | No CME | PRPO | N/A | N/A | 2024-03-12 | Completed | Completed | Y | N/A | Y | 2023-07-06 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT04 | xD-DWDM-BRKRing_1049B-002 MSC KEPONG_00045823053925 | 2023 | P1 | 1049B | 1049B-002 MSC KEPONG | BBand | 1.Swap breaker = 16 (16x63A DC) | PRPO | N/A | N/A | N/A | 2023-09-26 | Completed | Y | 2024-01-22 | Y | 2024-01-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT04 | xD-DWDM-BRKRing_1412A BKT TADUN_00045823053925 | 2023 | P1 | 1412A | 1412A BKT TADUN | BBand | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | Completed | Y | 2024-01-12 | Y | 2024-01-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT04 | xD-DWDM-BRKRing_1413A KTM RAWANG_00045823053925 | 2023 | P1 | 1413A | 1413A KTM RAWANG | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 | xD-DWDM-BRKRing_C0103_1049B Kepong_0004582304150Y_00045823087420 | 2023 | P2 | 1049B | 1049B Kepong | Advance | No CME | PRPO | N/A | N/A | N/A | 2023-10-17 | Completed | Y | N/A | Y | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 | xD-DWDM-BRKRing_C0103_1359A MutiaraSubang_0004582304150Y_00045823087420 | 2023 | P2 | 1359A | 1359A MutiaraSubang | Advance | 1. Swap breaker DC BREAKER: 63A X 2 | PRPO | N/A | N/A | N/A | 2023-10-17 | Completed | Y | N/A | Y | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 | xD-DWDM-BRKRing_C0103_1409A Damansara_0004582304150Y_00045823087420 | 2023 | P2 | 1409A | 1409A Damansara | Advance | No CME | Completed | N/A | N/A | N/A | 2023-10-17 | Completed | Y | N/A | Y | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0803 | xD-DWDM-BRKRing_C0803_1066A Sungai Choh_0004582304160F_0004582308742 | 2023 | N/A | 1066A | 1066A Sungai Choh | BBand | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | Completed | Y | 4//1/2024 | Y | 2024-01-16 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0803 | xD-DWDM-BRKRing_C0803_1070A Wsma LowKang_0004582304160F_0004582308742 | 2023 | N/A | 1070A | 1070A Wsma LowKang | BBand | BATTERY BANK = 1 | Drop | N/A | N/A | N/A | 2023-12-07 | N/A | N/A | 4//1/2024 | Y | 2024-01-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0803 | xD-DWDM-BRKRing_C0803_1145A BatangKali_0004582304160F_0004582308742 | 2023 | N/A | 1145A | 1145A BatangKali | BBand | DC BREAKER : 63A X 4 | Completed | N/A | N/A | N/A | 2023-10-11 | Completed | Y | 4//1/2024 | Y | 2024-01-04 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0803 | xD-DWDM-BRKRing_C0803_1146A KubuBaru_0004582304160F_0004582308742 | 2023 | N/A | 1146A | 1146A KubuBaru | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-10-12 | Completed | Y | 2024-01-05 | Y | 2024-01-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0803 | xD-DWDM-BRKRing_C0803_1701A Kerling Trnk_0004582304160F_0004582308742 | 2023 | N/A | 1701A | 1701A Kerling Trnk | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-10-13 | N/A | N/A | 2024-01-05 | Y | 2024-01-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0803 | xD-DWDM-BRKRing_C0803_2038A AntraGapi_0004582304160F_0004582308742 | 2023 | N/A | 2038A | 2038A AntraGapi | BBand | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | Completed | Y | 2024-01-09 | Y | 2024-01-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ring58/C1103 | xD_DWDM-BRKRing_Ring58/C1103_1015A Awana Golf_0004582307100Y_00045823168326 | 2023 | P1_Z_Aug | 1015A | 1015A Awana Golf | BBand | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1128A Kg Ola Lempik_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1128A | 1128A Kg Ola Lempik | BBand | No CME | N/A | N/A | N/A | 2024-05-08 | 2024-05-10 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT01P | xD-DWDM-BRKRing_CT01P_1049B Kpg_000458237400E_00045823174223 | 2023 | N/A | 1049B | 1049B Kpg | Bband | 1.Swap breaker = 16 (16x63A DC) | PRPO | N/A | N/A | N/A | 2023-12-06 | Completed | Y | 2024-01-26 | Y | 2024-01-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT01P | xD-DWDM-BRKRing_CT01P_1298A Kpg Knit_000458237400E_00045823174223 | 2023 | N/A | 1298A | 1298A Kpg Knit | Bband | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-12-07 | Completed | Y | 2024-01-05 | Y | 2024-01-05 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT01P | xD-DWDM-BRKRing_CT01P_1309A Ivory_000458237400E_00045823174223 | 2023 | N/A | 1309A | 1309A Ivory | Bband | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | Completed | Y | 2024-01-17 | Y | 2024-01-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT11P | xD-DWDM-BRKRing_CT11P_1050B MAH_00045823086823 | 2023 | N/A | 1050B | 1050B MAH | BBand | N/A | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-11-14 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT11P | xD-DWDM-BRKRing_CT11P_1080A WIT KLANG_00045823086823 | 2023 | N/A | 1080A | 1080A WIT KLANG | BBand | No CME | Completed | N/A | N/A | N/A | 2023-10-19 | Completed | Y | N/A | Y | 2023-11-14 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT11P | xD-DWDM-BRKRing_CT11P_1087A RANTAU PANJANG_00045823086823 | 2023 | N/A | 1087A | 1087A RANTAU PANJANG | BBand | No CME | Completed | N/A | N/A | N/A | 2023-10-11 | Completed | Y | N/A | Y | 2023-11-14 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT11P | xD-DWDM-BRKRing_CT11P_8000A MSC KUANTAN_00045823086823 | 2023 | N/A | 8000A | 8000A MSC KUANTAN | BBand | N/A | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-11-14 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E107 | xD-DWDM-BRKRing_E107_8211A WCY_0004582304150Y_00045823087420 | 2023 | N/A | 8211A | 8211A WCY | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-12-07 | Completed | Y | N/A | Y | 2023-08-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E107 | xD-DWDM-BRKRing_E107_8217A PASIR MAS_0004582304150Y_00045823087420 | 2023 | N/A | 8263A | 8217A PASIR MAS | FO&T | No CME | PRPO | N/A | N/A | N/A | 2023-12-07 | Completed | Y | N/A | Y | 2023-08-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E107 | xD-DWDM-BRKRing_E107_8217A PG TEMBAK_0004582304150Y_00045823087420 | 2023 | N/A | 8217A | 8217A PG TEMBAK | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-12-07 | Completed | Y | N/A | Y | 2023-08-24 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E110 | xD-DWDM-BRKRing_E110_8211A WCY_0004582304160F_0004582308742 | 2023 | N/A | 8211A | 8211A WCY | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | N/A | N/A | 2024-01-08 | Y | 2024-01-15 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E110 | xD-DWDM-BRKRing_E110_8224A Pasir Puteh_0004582304160F_0004582308742 | 2023 | N/A | 8224A | 8224A Pasir Puteh | FO&T | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | PRPO | N/A | N/A | N/A | 2023-10-04 | Completed | Y | 2024-01-08 | Y | 2024-01-15 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E110 | xD-DWDM-BRKRing_E110_8268A Bachok_0004582304160F_0004582308742 | 2023 | N/A | 8268A | 8268A Bachok | FO&T | MGB = 1 | Completed | N/A | N/A | N/A | 2023-10-05 | Completed | Y | 2024-01-08 | Y | 2024-01-15 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8000A MSC Kuantan_0004582304160F_0004582308742 | 2023 | N/A | 8000A | 8000A MSC Kuantan | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | Completed | Y | 2024-01-22 | Y | 2024-01-22 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8023B Balok Baru_0004582304160F_0004582308742 | 2023 | N/A | 8023B | 8023B Balok Baru | FO&T | NOT REQUIRED | Drop | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-02-01 | Y | 2024-02-01 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8035A Balok Kg Chengal_0004582304160F_0004582308742 | 2023 | N/A | 8035A | 8035A Balok Kg Chengal | FO&T | RECTIFIER MODULE = 2 | Completed | N/A | N/A | N/A | 2023-10-12 | Completed | Y | 2024-02-02 | Y | 2024-02-02 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8061A Bkt Pelindung_0004582304160F_0004582308742 | 2023 | N/A | 8061A | 8061A Bkt Pelindung | FO&T | DC BREAKER = 63A X 4 | Completed | N/A | N/A | N/A | 2023-10-13 | N/A | N/A | 2024-02-06 | Y | 2024-02-06 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8408A Cheneh_0004582304160F_0004582308742 | 2023 | N/A | 8408A | 8408A Cheneh | FO&T | BATTERY BANK = 2 | Completed | N/A | N/A | N/A | 2023-10-24 | Completed | Y | 2024-01-31 | Y | 2024-01-31 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8434A Felda Neram_0004582304160F_0004582308742 | 2023 | N/A | 8434A | 8434A Felda Neram | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-12 | N/A | N/A | 2024-02-07 | Y | 2024-02-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8936A Sg Karang_0004582304160F_0004582308742 | 2023 | N/A | 8936A | 8936A Sg Karang | FO&T | DC BREAKER : 100A X 2 | Completed | N/A | N/A | N/A | 2023-11-24 | Completed | Y | 2024-02-15 | Y | 2024-02-02 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202 | xD-DWDM-BRKRing_E202_8953A Balok Perdana_0004582304160F_0004582308742 | 2023 | N/A | 8953A | 8953A Balok Perdana | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-23 | Completed | Y | 2024-02-15 | Y | 2024-02-01 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E205 | xD-DWDM-BRKRing_E205_8321A Tabung Hji Kemaman_0004582304160F_0004582308742 | 2023 | N/A | 8321A | 8321A Tabung Hji Kemaman | FO&T | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | Y | 2024-04-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E205 | xD-DWDM-BRKRing_E205_8330A Kemuning_0004582304160F_0004582308742 | 2023 | N/A | 8330A | 8330A Kemuning | FO&T | BATTERY BANK = 1 | Completed | N/A | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | Y | 2024-04-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E205 | xD-DWDM-BRKRing_E205_8403A Bkt Mentok_0004582304160F_0004582308742 | 2023 | N/A | 8403A | 8403A Bkt Mentok | FO&T | Extend platform = 1 | PRPO | N/A | N/A | 2024-06-30 | N/A | 2024-06-14 | N/A | N/A | Y | 2024-04-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E205 | xD-DWDM-BRKRing_E205_8473A FeldaSeberangTayur_0004582304160F_0004582308742 | 2023 | N/A | 8473A | 8473A FeldaSeberangTayur | FO&T | DC BREAKER: 100A X 2 | Completed | N/A | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | Y | 2024-04-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E205 | xD-DWDM-BRKRing_E205_8483 Desa Solehah_0004582304160F_0004582308742 | 2023 | N/A | 8483A | 8483 Desa Solehah | FO&T | MGB = 1 | Completed | N/A | N/A | 2024-03-21 | 2024-03-22 | N/A | N/A | N/A | Y | 2024-04-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8314A Gong Terap_0004582304160F_0004582308742 | 2023 | N/A | 8314A | 8314A Gong Terap | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | Completed | Y | 2024-01-15 | Y | 2024-01-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8344A Felda Belara_0004582304160F_0004582308742 | 2023 | N/A | 8344A | 8344A Felda Belara | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | Completed | Y | 2024-01-29 | Y | 2024-01-29 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8350B Kustem_0004582304160F_0004582308742 | 2023 | N/A | 8350B | 8350B Kustem | FO&T | NOT REQUIRED | Drop | N/A | N/A | N/A | 2023-12-15 | Completed | Y | 2024-01-30 | Y | 2024-01-30 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8353A Kg Manir_0004582304160F_0004582308742 | 2023 | N/A | 8353A | 8353A Kg Manir | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-10 | Completed | Y | 2024-02-01 | Y | 2024-01-29 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8354A Kusza_0004582304160F_0004582308742 | 2023 | N/A | 8354A | 8354A Kusza | FO&T | RECTIFIER MODULE = 2 | Completed | N/A | N/A | N/A | 2023-10-10 | Completed | Y | 2024-01-31 | Y | 2024-01-31 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8361A Batu Rakit_0004582304160F_0004582308742 | 2023 | N/A | 8361A | 8361A Batu Rakit | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | Completed | Y | 2024-01-15 | Y | 2024-01-18 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E212 | xD-DWDM-BRKRing_E212_8429B B Payung2_0004582304160F_0004582308742 | 2023 | N/A | 8429B | 8429B B Payung2 | FO&T | NOT REQUIRED | Drop | N/A | N/A | N/A | 2023-11-10 | Completed | Y | 2024-01-15 | Y | 2024-01-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E404 | xD-DWDM-BRKRing_E404_8025A Risda_0004582304160F_0004582308742 | 2023 | N/A | 8025A | 8025A Risda | FO&T | MGB = 1 | Completed | N/A | N/A | N/A | 2023-10-12 | N/A | N/A | 2024-02-07 | Y | 2024-02-14 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E404 | xD-DWDM-BRKRing_E404_8059A Bkt Sulai_0004582304160F_0004582308742 | 2023 | N/A | 8059A | 8059A Bkt Sulai | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | Completed | Y | 2024-01-23 | Y | 2024-01-23 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E404 | xD-DWDM-BRKRing_E404_8128A Kg Luit_0004582304160F_0004582308742 | 2023 | N/A | 8128A | 8128A Kg Luit | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-11 | N/A | N/A | 2024-03-12 | Y | 2024-02-12 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E404 | xD-DWDM-BRKRing_E404_8191A Sg Semuji_0004582304160F_0004582307060Z_0004582308742 | 2023 | N/A | 8191A | 8191A Sg Semuji | FO&T | RECTTIFIER MODULE = 3 | Completed | N/A | N/A | N/A | 2023-11-24 | Completed | Y | 2024-02-01 | Y | 2024-02-01 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E404 | xD-DWDM-BRKRing_E404_8513A Senggora_0004582304160F_0004582308742 | 2023 | N/A | 8513A | 8513A Senggora | FO&T | 1.Add battery bank = 2 | PRPO | N/A | N/A | N/A | 2023-10-24 | Completed | Y | 2024-02-07 | Y | 2024-02-01 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E404 | xD-DWDM-BRKRing_E404_8965A Spg Lepar Hilir_0004582304160F_0004582308742 | 2023 | N/A | 8965A | 8965A Spg Lepar Hilir | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-10-11 | N/A | N/A | 2024-03-12 | Y | 2024-02-13 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_1475A MSC SRI KEMBANGAN_00045823086828 | 2023 | N/A | 1475A | 1475A MSC SRI KEMBANGAN | FO&T | No CME | PRPO | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8000A MSC KUANTAN_00045823086828 | 2023 | N/A | 8000A | 8000A MSC KUANTAN | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8025A RISDA_00045823086828 | 2023 | N/A | 8025A | 8025A RISDA | FO&T | No CME | Completed | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8046A BANDAR INDERA MAHKOTA_00045823086828 | 2023 | N/A | 8046A | 8046A BANDAR INDERA MAHKOTA | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8050A PERMATANG BADAK_00045823086828 | 2023 | N/A | 8050A | 8050A PERMATANG BADAK | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8059A BUKIT SULAI_00045823086828 | 2023 | N/A | 8059A | 8059A BUKIT SULAI | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8314A GONG TERAP_00045823086828 | 2023 | N/A | 8314A | 8314A GONG TERAP | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E407 | xD-DWDM-BRKRing_E407_8344A FELDA BELARA_00045823086828 | 2023 | N/A | 8344A | 8344A FELDA BELARA | FO&T | No CME | N/A | N/A | N/A | N/A | Completed | N/A | N/A | N/A | N/A | 2023-08-10 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E408 | xD-DWDM-BRKRing_E408_8033A Kg Pandan_0004582304150Y_00045823087420 | 2023 | N/A | 8033A | 8033A Kg Pandan | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-12-07 | N/A | N/A | N/A | N/A | 2023-07-21 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E408 | xD-DWDM-BRKRing_E408_8933A Bt6 Jln Gambang_0004582304150Y_00045823087420 | 2023 | N/A | 8933A | 8933A Bt6 Jln Gambang | FO&T | No CME | N/A | N/A | N/A | N/A | 2023-12-07 | N/A | N/A | N/A | N/A | 2023-07-21 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR02 | xD-DWDM-BRKRing_EAR02_2_4000A Prai_0004582304160E_00045823087420 | 2023 | P0 | 4000A | 4000A Prai | FO&T | DC BREAKER: 63A X 12 | Completed | N/A | N/A | N/A | N/A | N/A | Y | 2024-01-09 | Y | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR02 | xD-DWDM-BRKRing_EAR02_2_8000A Kuantan_0004582304160E_00045823087420 | 2023 | P0 | 8000A | 8000A Kuantan | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | Completed | Y | N/A | Y | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR02 | xD-DWDM-BRKRing_EAR02_2_8429B BktPayung_0004582304160E_00045823087420 | 2023 | P0 | 8429B | 8429B BktPayung | FO&T | NOT REQUIRED | Drop | N/A | N/A | N/A | N/A | N/A | Y | 2024-01-09 | Y | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MR20/C26 | xD-DWDM-BRKRing_MR20/C26_1081A BktLipat_0004582304160F_0004582308742 | 2023 | P1 | 1081A | 1081A BktLipat | BBand | BATTERY BANK = 2 | Completed | N/A | N/A | N/A | 2023-11-24 | N/A | N/A | 2024-01-22 | Y | 2024-01-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MR20/C26 | xD-DWDM-BRKRing_MR20/C26_1085A PekanMeru_0004582304160F_0004582308742 | 2023 | P1 | 1085A | 1085A PekanMeru | BBand | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | Completed | Y | N/A | Y | 2023-12-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MR20/C26 | xD-DWDM-BRKRing_MR20/C26_1093A KianHoeHuat_0004582304160F_0004582308742 | 2023 | P1 | 1093A | 1093A KianHoeHuat | BBand | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-24 | N/A | N/A | 2024-02-23 | Y | 2024-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MR20/C26 | xD-DWDM-BRKRing_MR20/C26_1104A SurauAlAmin_0004582304160F_0004582308742 | 2023 | P1 | 1104A | 1104A SurauAlAmin | Bband | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | Completed | Y | 2024-01-09 | Y | 2024-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MR20/C26 | xD-DWDM-BRKRing_MR20/C26_1627B IndahHighway_0004582304160F_0004582308742 | 2023 | P1 | 1627B | 1627B IndahHighway | BBand | DCPDB = 1 UNIT | Completed | N/A | N/A | N/A | 2023-10-10 | N/A | N/A | 2024-01-08 | Y | 2024-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106(ii) | xD-DWDM-BRKRing_N106_4085D Kulim Hitech 2 | 2023 | P1 | 4085D | 4085D Kulim Hitech2 | FO&T | No CME | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106(ii) | xD-DWDM-BRKRing_N106_4683A Bkt Tok Alang | 2023 | P1 | 4683A | 4683A Bkt Tok Alang | FO&T | 1. Add Battery Bank = 3 | PRPO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106 | xD-DWDM-BRKRing_N106_4946A Bkt Selambau_000458237400E_00045823174223 | 2023 | N/A | 4946A | 4946A Bkt Selambau | FO&T | DROP | Drop | N/A | N/A | N/A | N/A | N/A | Y | N/A | Y | 2023-11-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N106 | xD-DWDM-BRKRing_N106_4966A Kulim Hitech_000458237400E_00045823174223 | 2023 | N/A | 4966A | 4966A Kulim Hitech | FO&T | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | Completed | Y | N/A | Y | 2023-11-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N115 | xD-DWDM-BRKRing_N115_4668A Lunas_0004582306610C_00045823162822 | 2023 | N/A | 4688A | 4668A Lunas | FO&T | DCPDB = 1 | Completed | N/A | N/A | N/A | 2023-11-24 | N/A | N/A | 2024-02-07 | Y | 2024-02-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N115 | xD-DWDM-BRKRing_N115_4932A Bkt Tok Acheh_0004582306610C_00045823162822 | 2023 | N/A | 4932A | 4932A Bkt Tok Acheh | FO&T | BATTERY BANK = 2 | Completed | N/A | N/A | N/A | 2023-11-22 | Completed | Y | N/A | Y | 2023-11-19 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S201 | xD-DWDM-BRKRing_S201_1621A Senawang_0004582304070S_00045823086826 | 2023 | P0 | 1621A | 1621A Senawang | BBand | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | Completed | Y | 2024-01-12 | Y | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S201 | xD-DWDM-BRKRing_S201_1760A Mambau1_0004582304070S_00045823086826 | 2023 | P0 | 1760A | 1760A Mambau1 | BBand | CABINET DISMANTLE = 1 | Completed | N/A | N/A | N/A | 2023-11-15 | Completed | Y | N/A | Y | 2023-11-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S201 | xD-DWDM-BRKRing_S201_1760A Mambau2_0004582304070S_00045823086826 | 2023 | P0 | 1760A | 1760A Mambau2 | BBand | CABINET DISMANTLE = 1 | Completed | N/A | N/A | N/A | 2023-11-15 | Completed | Y | N/A | Y | 2023-11-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S201 | xD-DWDM-BRKRing_S201_3433C Bkt Pelandok_0004582304070S_00045823086826 | 2023 | P0 | 3433C | 3433C Bkt Pelandok | BBand | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | Completed | Y | N/A | Y | 2023-11-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S307 | xD-DWDM-BRKRing_S307_6405A Sri Bunian_0004582304160E_00045823087420 | 2023 | N/A | 6405A | 6405A Sri Bunian | BBand | No CME | N/A | N/A | N/A | N/A | 2023-10-17 | N/A | N/A | N/A | N/A | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S307 | xD-DWDM-BRKRing_S307_6502A Nusa Perintis_0004582304160E_00045823087420 | 2023 | N/A | 6502A | 6502A Nusa Perintis | BBand | No CME | Completed | N/A | N/A | 2024-03-12 | 2024-03-12 | N/A | N/A | N/A | N/A | 2023-10-17 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD-DWDM-BRKRing_S309_1553A Umbai_0004582304160F_0004582308742 | 2023 | P3 | 1553A | 1553A Umbai | BBand | 1.New plinth | PRPO | N/A | N/A | 2024-06-30 | N/A | 2024-07-05 | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD-DWDM-BRKRing_S309_1556A Merlimau_0004582304160F_0004582308742 | 2023 | P3 | 1556A | 1556A Merlimau | BBand | BATTERY BANK = 3 | PRPO | N/A | N/A | N/A | 2023-10-11 | N/A | N/A | N/A | Y | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD-DWDM-BRKRing_S309_1599A Gambir Town_0004582304160F_0004582308742 | 2023 | P3 | 1599A | 1599A Gambir Town | BBand | BATTERY BANK = 3 | Completed | N/A | N/A | N/A | 2023-10-11 | Completed | Y | N/A | Y | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S309 | xD-DWDM-BRKRing_S309_2402B Pagoh highway_0004582304160F_0004582308742 | 2023 | P3 | 2402B | 2402B Pagoh highway | BBand | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | PRPO | N/A | N/A | N/A | 2023-10-13 | Completed | Y | N/A | Y | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | xD-DWDM-BRKRing_S313P_2_1512A BKTRAMBAI_00045823087420 | 2023 | P1_IP_BR-Q3 | 1512A | 1512A BKTRAMBAI | BBand | No CME | N/A | N/A | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | xD-DWDM-BRKRing_S313P_2_1553A UMBAI_00045823087420 | 2023 | P1_IP_BR-Q3 | 1553A | 1553A UMBAI | BBand | No CME | PRPO | N/A | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | xD-DWDM-BRKRing_S313P_2_1554A RUMBIA_00045823087420 | 2023 | P1_IP_BR-Q3 | 1554A | 1554A RUMBIA | BBand | No CME | PRPO | N/A | N/A | N/A | 2023-11-06 | N/A | N/A | N/A | N/A | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | xD-DWDM-BRKRing_S313P_2_1621A MSC Senawang_00045823087420 | 2023 | P1_IP_BR-Q3 | 1621A | 1621A MSC Senawang | BBand | No CME | N/A | N/A | N/A | N/A | 2023-11-07 | N/A | N/A | N/A | N/A | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2_2 | xD-DWDM-BRKRing_S313P_2_2_DUYONG_0004582304160F_00045823087420 | 2023 | P3 | 1533A | DUYONG | BBand | BATTERY RACK = 1 | Completed | N/A | N/A | N/A | 2023-10-10 | N/A | N/A | 2024-02-07 | Y | 2024-02-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2_2 | xD-DWDM-BRKRing_S313P_2_2_RUMBIA_0004582304160F_00045823087420 | 2023 | P3 | 1554A | RUMBIA | BBand | 1.Add battery bank = 3 | PRPO | N/A | N/A | N/A | 2023-10-10 | Completed | Y | 8/1/2024-9/1/2024 | Y | 2024-01-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2_2 | xD-DWDM-BRKRing_S313P_2_2_UMBAI_0004582304160F_00045823087420 | 2023 | P3 | 1553A | UMBAI | BBand | 1.New plinth | PRPO | N/A | N/A | 2024-06-30 | N/A | 2024-07-05 | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | xD-DWDM-BRKRing_S313P_2_2021B SBHT_00045823087420 | 2023 | P1_IP_BR-Q3 | 2021B | 2021B SBHT | BBand | No CME | PRPO | N/A | N/A | N/A | 2023-11-07 | N/A | N/A | N/A | N/A | 2023-11-07 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S501 | xD-DWDM-BRKRing_S501_1_1591A Parit Bakar_0004582304160F_0004582308742 | 2023 | P0 | 1591A | 1591A Parit Bakar | BBand | BATTERY BANK = 3 | Completed | N/A | N/A | N/A | 2023-11-22 | Completed | Y | 2024-01-24 | Y | 2023-11-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S501 | xD-DWDM-BRKRing_S501_1_1591A Sri Jeram_0004582304160F_0004582308742 | 2023 | P0 | 2227B | 1591A Sri Jeram | BBand | BATTERY BANK = 3 | Completed | N/A | N/A | N/A | 2023-10-12 | N/A | N/A | 2024-02-01 | Y | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S501 | xD-DWDM-BRKRing_S501_1_2388B Desa Muar_0004582304160F_0004582308742 | 2023 | P0 | 2388B | 2388B Desa Muar | BBand | BATTERY BANK = 3 | Completed | N/A | N/A | N/A | 2023-10-12 | N/A | N/A | 2024-02-14 | Y | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD-DWDM-BRKRing_SAR01_1552A TanjungBidara_0004582304070Q_0004582304070T_00045823086825 | 2023 | P0 | 1552A | 1552A TanjungBidara | BBand | No CME | N/A | N/A | N/A | 2024-03-12 | 2024-03-21 | N/A | N/A | N/A | N/A | 2023-10-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD-DWDM-BRKRing_SAR01_1554A Rumbia_0004582304070Q_0004582304070T_00045823086825 | 2023 | P0 | 1554A | 1554A Rumbia | BBand | No CME | PRPO | N/A | N/A | N/A | 2023-10-19 | N/A | N/A | N/A | N/A | 2023-10-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD-DWDM-BRKRing_SAR01_1621A Senawang_0004582304070Q_0004582304070T_00045823086825 | 2023 | P0 | 1621A | 1621A Senawang | BBand | No CME | N/A | N/A | N/A | N/A | 2023-10-19 | N/A | N/A | N/A | N/A | 2023-10-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD-DWDM-BRKRing_SAR01_1640A Politenik PD_0004582304070Q_0004582304070T_00045823086825 | 2023 | P0 | 1640A | 1640A Politenik PD | BBand | No CME | N/A | N/A | N/A | 2024-03-12 | 2024-03-22 | N/A | N/A | N/A | N/A | 2023-10-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR01 | xD-DWDM-BRKRing_SAR01_2021B SBHT_0004582304070Q_0004582304070T_00045823086825 | 2023 | P0 | 2021B | 2021B SBHT | BBand | No CME | PRPO | N/A | N/A | N/A | 2023-10-19 | N/A | N/A | N/A | N/A | 2023-10-26 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03ii | xD-DWDM-BRKRing_SAR03ii_2402B PagohHighway_0004582304160E_00045823087420 | 2023 | N/A | 2402B | 2402B PagohHighway | BBand | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | PRPO | N/A | N/A | N/A | 2023-11-23 | Completed | Y | N/A | Y | 2023-12-08 | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03iii | xD-DWDM-BRKRing_SAR03iii_1554A Rumbia_0004582304160E_00045823087420 | 2023 | N/A | 1554A | 1554A Rumbia | BBand | 1.Add battery bank = 3 | PRPO | N/A | N/A | N/A | N/A | N/A | Y | N/A | Y | 2023-12-08 | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR05 | xD-DWDM-BRKRing_SAR05_1621A Senawang_0004582304160E_00045823087420 | 2023 | N/A | 1621A | 1621A Senawang | Bband | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | Completed | Y | N/A | Y | 2024-01-22 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR05 | xD-DWDM-BRKRing_SAR05_6000A JB_0004582304160E_00045823087420 | 2023 | N/A | 6000A | 6000A JB | BBand | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | N/A | 2023-11-16 | Completed | Y | N/A | Y | 2024-01-23 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR05 | xD-DWDM-BRKRing_SAR05_6083A Soga_0004582304160E_00045823087420 | 2023 | N/A | 6083A | 6083A Soga | BBand | RECTIFIER + DCPDB = 1 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | Y | 2024-02-01 | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N/A | N/A | N/A | N/A | 1195A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR01 | xD_DWDM-BRKRing_CAR01_1085A Pekan Meru_0004582400460T_00045824009529 | 2024 Q1 | P0 | 1085 | 1085A Pekan Meru | BBand | No CME | N/A | N/A | N/A | 2024-03-20 | 2024-03-22 | N/A | N/A | N/A | Y | 2024-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PFSRING101/C0607P | xD_DWDM_BRKRing_PFSRING101/C0607_1063B_Berjya Times Square Rooftop_0004582306610C_00045823162822 | 2023 | P1 | 1063B | 1063B Berjaya Times Square Rooftop | BBand | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | N/A | N/A | 2024-05-24 | 2024-05-24 | N/A | N/A | N/A | N/A | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 | xD_DWDM_BRKRing_C0103_1049B-MCR 001 KPG_0004582400930A_00045824009023 | 2024 Q2 | P2 | 1049B | 1049B-MCR 001 KPG | Advance | No CME | PRPO | N/A | N/A | 2024-05-24 | 2024-05-24 | N/A | N/A | N/A | N/A | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCR18/C24 | xD_DWDM-BRKRing_MCR18/C24_1360B Hicom Glenmarie_0004582306610C_00045823162822 | 2023 | P2 | 1360A | 1360B Hicom Glenmarie | BBand | 1. Swap Cabine | Completed | N/A | N/A | N/A | 2024-05-11 | 2024-05-30 | N/A | Replan | N/A | 2024-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR05 | xD_DWDM_BRKRing_CAR05_1475A MSC MSK_0004582401290A_00045824026525 | 2024 Q2 | P1_Z_Oct | 1475A | 1475A MSC MSK | BBand | No CME | PRPO | N/A | N/A | 2024-05-08 | 2024-05-13 | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-i+/CAR02-ii+ | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1049B KPG_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 1049B | 1049B Kepong | BBand | No CME | PRPO | N/A | N/A | 2024-05-09 | 2024-05-14 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0105P | xD_DWDM_BRKRing_C0105P_1049B MCR KPG_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1049B | 1049B-MCR-002-KPG | Advance | 1.Swap breaker = 16 (16x63A DC) | PRPO | N/A | 2024-01-30 | 2024-05-15 | 2024-05-15 | 2024-05-23 | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR04 | xD_DWDM_BRKRing_CAR04_1049B KPG_0004582309050Y_00045824006623 | 2024 Q1 | P1_Z_June | 1049B | 1049B MCR KPG | BBand | 1.Swap breaker = 16 (16x63A DC) | PRPO | N/A | 2024-02-13 | 2024-05-15 | 2024-05-15 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT0241P | xD_DWDM_BRKRing_CT0241P_1197A JBA Effingham_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1197A | 1197A JBA Effingham | Advance | 1. Add Battery Bank = 2 | PRPO | N/A | 2024-01-27 | 2024-05-15 | 2024-05-15 | 2024-05-28 | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E209 | xD_DWDM_BRKRing_E209_8429B BPayung2_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 8429B | 8429B-MAG(M14)-001 Bpayung 2 | FO&T | No CME | Drop | N/A | N/A | 2024-05-15 | 2024-05-15 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-i+/CAR02-ii+ | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_2021B SBHT_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 2021B | 2021B Subang Hi-Tech | BBand | No CME | PRPO | N/A | N/A | 2024-05-09 | 2024-05-15 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 (C0126) | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | 2024 Q1 | P2 | 1359A | 1359A-MAC-001 Mutiara Subang | Advance | 1. Swap breaker DC BREAKER: 63A X 2 | PRPO | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-05-22 | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0147P | xD_DWDM_BRKRing_C0147P_2021B_SBHT_0004582401280Z_45824026526 | 2024 Q2 | N/A | 2021B | 2021B SBHT | BBand | 1.ODF Rack (Glass Door) | PRPO | 2024-04-04 | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0147P | xD_DWDM_BRKRing_C0147P_1918A Damansara Intan_0004582401280Z_45824026526 | 2024 Q2 | N/A | 1918A | 1918A Damansara Intan | BBand | 1. Add Battery Bank = 2 | PRPO | 2024-04-15 | N/A | 2024-05-29 | 2024-05-29 | N/A | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0147P | xD_DWDM_BRKRing_C0147P_1336A Balai Islam TTDI_0004582401280Z_45824026526 | 2024 Q2 | N/A | 1336A | 1336A Balai Islam TTDI | BBand | N/A | N/A | 2024-04-15 | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0147P | xD_DWDM_BRKRing_C0147P_2831A One Utama Ph2_0004582401280Z_45824026526 | 2024 Q2 | N/A | 2831A | 2831A One Utama Phase 2 | BBand | N/A | N/A | 2024-04-15 | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0147P | xD_DWDM_BRKRing_C0147P_1197A JBA Effingham_0004582401280Z_45824026526 | 2024 Q2 | N/A | 1197A | 1197A JBA Effingham | BBand | 1. Add Battery Bank = 2 | PRPO | 2024-04-15 | N/A | 2024-05-30 | 2024-05-30 | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0147P | xD_DWDM_BRKRing_C0147P_1211A KDU_0004582401280Z_45824026526 | 2024 Q2 | N/A | 1211A | 1211A KDU | BBand | N/A | N/A | 2024-04-15 | N/A | 2024-05-30 | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_i | xD_DWDM_BRKRing_NAR01_i_4966A_Kulim Hitech_0004582401260T_45824026527 | 2024 Q2 | N/A | 4966A | 4966A-MAG001 Kulim Hitech | FO&T | N/A | N/A | 2024-04-04 | N/A | 2024-06-05 | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_i | xD_DWDM_BRKRing_NAR01_i_4946A_Bukit Selambau_0004582401260T_45824026527 | 2024 Q2 | N/A | 4946A | 4946A-MAG-001 Bukit Selambau | FO&T | DROP | Drop | 2024-04-04 | N/A | 2024-05-12 | N/A | N/A | N/A | N/A | N/A | 2024-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_i | xD_DWDM_BRKRing_NAR01_i_4992A_Pendang_0004582401260T_45824026527 | 2024 Q2 | N/A | 4992A | 4992A-MAG-001 Pendang | FO&T | 1.Swap breaker = 4 (4x100A DC) | Completed | 2024-04-04 | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_i | xD_DWDM_BRKRing_NAR01_i_4000A_Prai_0004582401260T_45824026527 | 2024 Q2 | N/A | 4000A | 4000A-MSCPrai | FO&T | No CME | Completed | N/A | N/A | 2024-05-14 | 2024-05-14 | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_i | xD_DWDM_BRKRing_NAR01_i_4521A_Msc Ipoh_0004582401260T_45824026527 | 2024 Q2 | N/A | 4521A | 4521A-MSC Menglembu | FO&T | No CME | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E209 | xD_DWDM_BRKRing_E209_8368A Serating_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 8368A | 8368A-MAC-001 Serating | FO&T | No CME | N/A | N/A | N/A | 2024-05-15 | 2024-05-16 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 (C0126) | xD_DWDM-BRKRing_C0103_1359A Mutiara Subang_0004582400320X_00045824009023 | 2024 Q2 | N/A | 1359A | 1359A-MAC-001 Mutiara Subang | Advance | No CME | PRPO | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-05-22 | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E301 | xD_DWDM_BRKRing_E301_8712A Kg Jawa Pekan_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 8712A | 8712A-MAC-001 Kg. Jawa Pekan | FO&T | BATTERY BANK = 2 | Completed | 2024-04-05 | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E301 | xD_DWDM_BRKRing_E301_8088A Sg Beto_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 8088A | 8088A-MAG-001 Sg. Beto | FO&T | No CME | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | N/A | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E301 | xD_DWDM_BRKRing_E301_8000A KTNE1_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 8000A | 8000A-MCR-002 KTN E1 | FO&T | No CME | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_4000A Msc Prai_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 4000A | 4000A MSC Prai | FO&T | DC BREAKER: 63A X 12 | Completed | 2024-04-05 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8000A MSC KTN_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8000A | 8000A MSC Kuantan | FO&T | No CME | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8282B Pergau_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8282B | 8282B-MAG(M14)-001 Pergau | FO&T | N/A | N/A | 2024-04-05 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8285A Bukit Bunga_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8285A | 8285A-MAG(M14)-001 Bukit Bunga | FO&T | N/A | N/A | 2024-04-05 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8288B Panau_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8288B | 8288B-MAG(M14)-001 Panau | FO&T | 1.DCPDB = 1 (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | 2024-04-06 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8263A Pasir Mas Town_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8263A | 8263A-MAG(M14)-001 Pasir Mas Town | FO&T | No CME | PRPO | N/A | N/A | 2024-06-05 | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8211A WCY_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8211A | 8211A-MAG(M8)-001 WCY | FO&T | No CME | N/A | N/A | N/A | 2024-06-05 | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8224A Pasir Puteh_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8224A | 8224A-MAG(M14)-001 Pasir Puteh | FO&T | 1.Add rectifier (Indoor) = 1 (Require 63A x 4 DC breaker) | PRPO | 2024-04-06 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAR01_1 & EAR01_3 | xD_DWDM_BRKRing_EAR01_1 N EAR01_3_8367A B.Kechil_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8367A | 8367A-MAG(M14)-001 B. Kechil | FO&T | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | 2024-04-06 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1621A SNW_0004582401310P_00045824026721 | 2024 Q2 | N/A | 1621A | MIP2013 1621A-MCR-001 SNW | BBand | N/A | N/A | 2024-04-16 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6000A MSC JBR_0004582401310P_00045824026721 | 2024 Q2 | N/A | 6000A | MIP2013 6000A-MCR-001 JBR | BBand | DC BREAKER: 63 A X 4 | Completed | 2024-04-22 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1554A Rumbia_0004582401310P_00045824026721 | 2024 Q2 | N/A | 1554A | 1554A-MAG(M14)-001 Rumbia | BBand | 1.Add battery bank = 3 | PRPO | 2024-04-04 | N/A | 2024-05-29 | 2024-05-29 | N/A | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_1553A Umbai_0004582401310P_00045824026721 | 2024 Q2 | N/A | 1553A | 1553A-MAG(M14)-001 Umbai | BBand | 1.New plinth | PRPO | 2024-04-01 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6104A Bkt Kelicap_0004582401310P_00045824026721 | 2024 Q2 | N/A | 6104A | 6104A-MAG(M8)-001 Bkt Kelicap | BBand | N/A | N/A | 2024-04-22 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6405A Sri Bunian_0004582401310P_00045824026721 | 2024 Q2 | N/A | 6405A | MIP2016 6405A-MAG-001 Sri Bunian | BBand | N/A | N/A | 2024-04-22 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR03_i&SAR03iii | xD_DWDM_BRKRing_SAR03_i N SAR03iii_6502A Nusa Perintis_0004582401310P_00045824026721 | 2024 Q2 | N/A | 6502A | 6502A-MAG-001 Nusa Perintis | BBand | BATTERY BANK = 1 | Completed | 2024-04-22 | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR06 | xD_DWDM_BRKRing_SAR06_6000A MSC JB_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 6000A | 6000A-MCR-001 JBR | BBand | No CME | Completed | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR06 | xD_DWDM_BRKRing_SAR06_8000A KTN_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 8000A | 8000A-MCR-001 KTN | BBand | No CME | N/A | N/A | N/A | 2024-06-05 | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR06 | xD_DWDM_BRKRing_SAR06_6707A Jambi_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_R_EXP-Q3 | 6707A | 6707A_MAG_001 Jambi | BBand | No CME | N/A | N/A | N/A | 2024-06-05 | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR04 | xD_DWDM_BRKRing_SAR04_1621A MSC SNW_0004582401310P_00045824026721 | 2024 Q2 | P0 | 1621A | MIP2013 1621A-MCR-001 SNW | BBand | N/A | N/A | 2024-04-16 | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAR04 | xD_DWDM_BRKRing_SAR04_6000A MSC JB_0004582401310P_00045824026721 | 2024 Q2 | P0 | 6000A | MIP2013 6000A-MCR-001 JBR | BBand | No CME | Completed | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR11 | xD_DWDM_BRKRing_CAR11_8000A MSC KTN_0004582401310P_00045824026721 | 2024 Q2 | P0 | 8000A | MIP2013 8000A-MCR-002 KTN | BBand | No CME | N/A | N/A | N/A | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S305 | xD_DWDM_BRKRing_S305_6701A Parit Subang_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6701A | 6701A-MAC-001 Parit Sulong | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S305 | xD_DWDM_BRKRing_S305_6093A Sri Medan_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6093A | 6093A-MAC-001 Sri Medan | BBand | 1. Add Battery Bank = 1 | PRPO | 2024-04-25 | N/A | 2024-06-30 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S305 | xD_DWDM_BRKRing_S305_6088A ABI_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6088A | 6088A-MAC-001 ABI | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S305 | xD_DWDM_BRKRing_S305_2402B Pagoh Highway_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 2402B | 2402B-MAG(M14)-001 Pagoh Highway | BBand | 1. Add Rectifier (Indoor) + 3 module = 1 (Require 63A x 4) | PRPO | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S305 | xD_DWDM_BRKRing_S305_6104A Bkt Kelicap_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6104A | 6104A-MAG(M8)-001 Bkt Kelicap | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6151A Mersing_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6151A | 6151A-MAC-001 Mersing | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6166A Felda Nitar2_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6166A | 6166A-MAC-001 Felda Nitar2 | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6160A Bkt Tinggi Maxis_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6160A | 6160A-MAC-001 Bkt Tinggi(Maxis) | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6138A Kahang Maxis_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6138A | 6138A-MAC-001 Kahang Maxis | BBand | DISMANTLE CABINET = 1 | Completed | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6134A Kluang Indst(Profina)_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6134A | 6134A-MAC-001 Kluang Industry (Profina) | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6616A Sri Permai_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6616A | 6616A-MAC-001 Sri Permai | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6369A Sri Saujana_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6369A | 6369A-MAG-002 Sri Saujana | BBand | 1. Add Battery Bank = 6 | PRPO | 2024-04-25 | N/A | 2024-06-30 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S504M | xD_DWDM_BRKRing_S504M_6126A KTM Kluang_0004582401310P_00045824026721 | 2024 Q2 | P1_IP_BR-Q3 | 6126A | 6126A-MAG(M8)-001 KTM Kluang | BBand | N/A | N/A | 2024-04-25 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_ii | xD_DWDM_BRKRing_NAR01_ii_4938A_Tmn Orkid_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4938A | 4938A-MAG001 Taman Orkid | FO&T | No CME | Completed | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_ii | xD_DWDM_BRKRing_NAR01_ii_4660A KTM Alor Star_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4660A | 4660A-MAG-001 KTM Alor Setar | FO&T | No CME | N/A | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_ii | xD_DWDM_BRKRing_NAR01_ii_4998A Air Itam Kedah_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4998A | 4998A-MAG-001 Air Itam Kedah | FO&T | No CME | PRPO | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_ii | xD_DWDM_BRKRing_NAR01_ii_4606A Padang Besar_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4606A | 4606A-MAG(M8)- 001 Padang Besar | FO&T | No CME | N/A | N/A | N/A | 2024-06-06 | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT04 | xD_DWDM_BRKRing_CT04_1049B KPG_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 1049B | 1049B-MCR 001 KPG | BBand | 1.Swap breaker = 16 (16x63A DC) | PRPO | 2024-04-17 | N/A | 2024-06-30 | N/A | 2024-05-23 | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT04 | xD_DWDM_BRKRing_CT04_1413A KTM Rawang_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 1413A | 1413A-MAC-001 KTM Rawang | BBand | DC BREAKER: 63 A X 4 | Completed | 2024-04-03 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT04 | xD_DWDM_BRKRing_CT04_1412 Bkt Tadun_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 1412A | 1412A-MAC-001 Bkt Tadun | BBand | N/A | N/A | 2024-04-03 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC RING 6/C09+ | xD_DWDM_BRKRing_MAC RING 6/C09+_2021B SBHT_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 2021B | 2021B-MCR 001 SHT | BBand | 1.ODF Rack (Glass Door) | PRPO | 2024-04-04 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC RING 6/C09+ | xD_DWDM_BRKRing_MAC RING 6/C09+_1192A Subang New Village_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 1192A | 1192A-MAC 001 Subang New Village | BBand | N/A | N/A | 2024-04-03 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC RING 6/C09+ | xD_DWDM_BRKRing_MAC RING 6/C09+_1230A P Indus Sg Buloh_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 1230A | 1230A-MAC 001 P indus Sg Buloh | BBand | 1. Add Battery Bank = 2 | PRPO | 2024-04-03 | N/A | 2024-06-30 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | xD_DWDM_BRKRing_N401_4952B Selama_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4952B | 4952B-MAG 001 Selama | FO&T | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | xD_DWDM_BRKRing_N401_4000A MSC Prai_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4000A | 4000A-MCR 002 PRI | FO&T | DC BREAKER: 63A X 12 | Completed | 2024-04-17 | N/A | 2024-05-12 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | xD_DWDM_BRKRing_N401_4684B Terap_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4686B | 4686B-MAC-001 Terap | FO&T | DC BREAKER: 63 A X 4 | Completed | N/A | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | 2024-06-11 | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | xD_DWDM_BRKRing_N401_4965A Politeknik Kulim_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4965A | 4965A-MAC-001 Politeknik Kulim | FO&T | BATTERY BANK = 1 | Completed | N/A | N/A | 2024-05-29 | 2024-05-29 | N/A | N/A | 2024-06-12 | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | xD_DWDM_BRKRing_N401_4689A Tmn Desa Impian_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4689A | 4689A-MAC 001 Tmn Desa Impian | FO&T | BATTERY BANK = 1 | Completed | N/A | N/A | 2024-05-29 | 2024-05-29 | N/A | N/A | 2024-06-12 | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N401 | xD_DWDM_BRKRing_N401_4118A Machang Bubuk2_0004582401280Y_00045824026722 | 2024 Q2 | N/A | 4118A | 4118A-MAC 001 Machang Bubuk 2 | FO&T | DCPDB = 1 | Completed | N/A | N/A | 2024-05-30 | 2024-05-30 | N/A | N/A | 2024-06-13 | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT0241P | xD_DWDM_BRKRing_CT0241P_1211A KDU_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1211A | 1211A KDU | Advance | No CME | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N407 | xD_DWDM-BRKRing_N407_4493A KTM Ipoh_0004582401300R_00045824026922 | 2024 Q2 | P1_IP_BR-Q1 | 4493A | 4493A KTM Ipoh | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N407 | xD_DWDM-BRKRing_N407_4432A KTM Sg Siput_0004582401300R_00045824026922 | 2024 Q2 | P1_IP_BR-Q1 | 4432A | 4432A KTM SG SIPUT | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-05-31 | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N407 | xD_DWDM-BRKRing_N407_4515A Tg Rambutan_0004582401300R_00045824026922 | 2024 Q2 | P1_IP_BR-Q1 | 4515A | 4515A TG RAMBUTAN | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N407 | xD_DWDM-BRKRing_N407_4498A Lap Tambun1 N 2_0004582401300R_00045824026922 | 2024 Q2 | P1_IP_BR-Q1 | 4498A | 4498A LAP Tambun 1&2 | FO&T | N/A | N/A | 2024-04-19 | N/A | 2024-05-12 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N407 | xD_DWDM-BRKRing_N407_4541A Bercham Industry_0004582401300R_00045824026922 | 2024 Q2 | P1_IP_BR-Q1 | 4541A | 4541A Bercham Industry | FO&T | N/A | N/A | 2024-04-19 | N/A | 2024-05-12 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 | xD_DWDM-BRKRing_C0103_1049B KPG_0004582401300R_00045824026922 | 2024 Q2_2 | P2 | 1049B | 1049B-MCR 001 KPG | Advance | 1.Swap breaker = 16 (16x63A DC) | PRPO | 2024-04-15 | N/A | 2024-05-24 | 2024-05-24 | 2024-05-23 | N/A | N/A | N/A | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR02_ii+ | xD_DWDM-BRKRing_NAR02_ii+_4000A MSC Prai_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4000A | 4000A MSC Prai | FO&T | No CME | Completed | N/A | N/A | 2024-05-14 | 2024-05-14 | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR02_ii+ | xD_DWDM-BRKRing_NAR02_ii+_8000A MSC KTN_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 8000A | 8000A MSC Kuantan | FO&T | No CME | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR02_ii+ | xD_DWDM-BRKRing_NAR02_ii+_4985A Baling Town_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4985A | 4985A-MAG-001 Baling Town | FO&T | No CME | Completed | N/A | N/A | 2024-05-28 | 2024-05-28 | N/A | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR02_ii+ | xD_DWDM-BRKRing_NAR02_ii+_8282B Pergau_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 8282B | 8282B-MAG(M14)-001 Pergau | FO&T | No CME | N/A | N/A | N/A | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0103 (C0126) | xD_DWDM-BRKRing_C0103_1207A Sg Buloh New Village_0004582400320X_00045824009023 | 2024 Q1 | P2 | 1207A | 1207A-MAC-001 Sg Buloh New Village | Advance | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | N/A | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CT0241P | xD_DWDM_BRKRing_CT0241P_1918A Damansara Intan_0004582309050Y_00045824006623 | 2024 Q1 | P1 | 1918A | 1918A - Damansara Intan | Advance | 1. Add Battery Bank = 2 | PRPO | N/A | 2024-01-27 | 2024-05-23 | 2024-05-23 | 2024-05-28 | N/A | N/A | N/A | 2024-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-i+/CAR02-ii+ | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1253A Plaza Pengkalan_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 1253A | 1253A-MAG(M14)-001 Plaza Pengkalan | BBand | 1. Add Rectifier (Indoor)= 1 (Require 63A x 8 DC Breaker) | PRPO | 2024-04-16 | N/A | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-i+/CAR02-ii+ | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1851A KL Plaza2_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 1851A | 1851A-MAG(M14)-001 KL Plaza 2 | BBand | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | 2024-04-16 | N/A | 2024-06-05 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-i+/CAR02-ii+ | xD_DWDM-BRKRing_CAR02-i+/CAR02-ii+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 1859A | 1859A-MAG(M14)-001 Midvalleycas | BBand | 1.Add modules = 2 | PRPO | 2024-04-16 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-ii+ | xD_DWDM-BRKRing_CAR02-ii+_1918A Damansara Intan_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 1918A | 1918A-MAG(M14)-001 Damansara Intan | BBand | 1. Add Battery Bank = 2 | PRPO | 2024-04-16 | N/A | 2024-06-06 | N/A | 2024-05-28 | N/A | N/A | N/A | 2024-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR02-ii+ | xD_DWDM-BRKRing_CAR02-ii+_1172A Glomac_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 1172A | 1172A-MAG(M14)-001 Glomac | BBand | DC BREAKER : 63A X 4 | Completed | 2024-04-16 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_iii+ | xD_DWDM-BRKRing_NAR01_iii+_4000A MSC Prai_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4000A | 4000A MSC Prai | FO&T | DC BREAKER: 63A X 12 | Completed | 2024-04-17 | N/A | 2024-05-12 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_iii+ | xD_DWDM-BRKRing_NAR01_iii+_4493A KTM Ipoh_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4493A | 4493A KTM IPOH | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_iii+ | xD_DWDM-BRKRing_NAR01_iii+_4606A Padang Besar_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4606A | 4606A-MAG(M8)-001 Padang Besar | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_iii+ | xD_DWDM-BRKRing_NAR01_iii+_4995A UUM HW_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4995A | 4995A-MAG(M14)-001 UUM Highway | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR01_iii+ | xD_DWDM-BRKRing_NAR01_iii+_4992A Pendang_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4992A | 4992A-MAG(M14)-001 Pendang | FO&T | 1.Swap breaker = 4 (4x100A DC) | Completed | 2024-04-16 | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR04_ii+ | xD_DWDM-BRKRing_NAR04_ii+_4521A Ipoh_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4521A | 4521A - IPOH | FO&T | No CME | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | N/A | N/A | N/A | N/A | 00:00:00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR04_ii+ | xD_DWDM-BRKRing_NAR04_ii+_4455A KTM Taiping_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4455A | 4455A-MAG(M14)-001 KTM Taiping | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAR04_ii+ | xD_DWDM-BRKRing_NAR04_ii+_4432A KTM Sungai Siput_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_R_EXP-Q2 | 4432A | 4432A-MAG(M14)-001 KTM Sungai Siput | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0211+ | xD_DWDM-BRKRing_C0211+_2888A Plaza Central_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 2888A | 2888A-MAC-001 Plaza Central | BBand | N/A | N/A | 2024-04-17 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1063B/AREA 154/C0211+/C0515+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1475A SKB_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Jul | 1475A | 1475A SKB | BBand | 1.ODF Rack (Glass Door) | PRPO | 2024-04-17 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1063B/AREA 154/C0211+/C0515+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1851A KL Plaza2_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Jul | 1851A | 1851A-MAG(M14)-001 KL Plaza 2 | BBand | 1.DCPDB = (C/W :63A DC x 8; 32A DC x 2 and 10A DC x 2 DC Breaker) | PRPO | 2024-04-16 | N/A | 2024-06-30 | N/A | 2024-06-07 | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1063B/AREA 154/C0211+/C0515+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1246A Berjaya Plaza_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Jul | 1246A | BERJAYA PLAZA 1246A | BBand | No CME | Completed | N/A | N/A | 2024-05-29 | 2024-05-29 | N/A | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1063B/AREA 154/C0211+/C0515+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1063B Berjaya Times Square_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Jul | 1063B | Berjaya Time Square (Tx) 1063B | BBand | No CME | PRPO | N/A | N/A | 2024-05-24 | 2024-05-24 | N/A | N/A | N/A | N/A | 2024-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AREA 154/MAC Ring 15/ C21+ | xD_DWDM-BRKRing_AREA 154/MAC Ring 15/ C21+_1458A Endah Parade_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Jul | 1458A | 1458A-MAG-001 Endah Parade | BBand | BATTERY BANK = 1 | Completed | 2024-04-17 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AREA 154/MAC Ring 15/ C21+ | xD_DWDM-BRKRing_1063B/AREA 154/C0211+/C0515+_1855B TPM_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Jul | 1855B | 1855B-MAC-001 TPM (AS) | BBand | DCPDB = 1 | Completed | 2024-04-17 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0211+ | xD_DWDM-BRKRing_C0211+_1859A MidvalleyCAS_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 1859A | 1859A-MAG(M14)-001 Midvalleycas | BBand | 1.Add modules = 2 | PRPO | 2024-04-16 | N/A | 2024-05-30 | 2024-05-30 | 2024-06-07 | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0515+ | xD_DWDM-BRKRing_C0515+_1039A Cheras Jaya_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 1039A | 1039A-MAG(M14)-001 Cheras Jaya | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0515+ | xD_DWDM-BRKRing_C0515+_2448A Asmah Tower_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 2448A | 2448A-MAC-001 Asmah Tower | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0515+ | xD_DWDM-BRKRing_C0515+_2424A PUAS Tmn Tun Perak_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 2424A | 2424A-MAC-001 PUAS Tmn Tun Perak | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0515+ | xD_DWDM-BRKRing_C0515+_2024A Bdr Makhota Cheras_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 2024A | 2024A-MAC-001 Bdr Mahkota Cheras | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C0515+ | xD_DWDM-BRKRing_C0515+_1902B Bdr Sg Long3_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 1902B | 1902B-MAC-001 Bdr Sg Long 3 | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-06-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC Ring 15/C21+ | xD_DWDM-BRKRing_MAC Ring 15/C21+_1745A Baitumal_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 1745A | 1745A-MAG(M14)-001 Baitumal | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-06-30 | N/A | 2024-06-21 | N/A | N/A | N/A | 2024-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC Ring 15/C21+ | xD_DWDM-BRKRing_MAC Ring 15/C21+_2502A Bdar Tun Razak_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 2502A | 2502A-MAC-001 B'dar Tun Razak | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC Ring 15/C21+ | xD_DWDM-BRKRing_MAC Ring 15/C21+_1974A Jln Sg Besi_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 1974A | MIP2013 1974A-MAC-001 Jln Sg Besi | BBand | N/A | N/A | 2024-04-18 | N/A | 2024-07-30 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N104+ | xD_DWDM-BRKRing_N104+_4995A UUMHW_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4995A | 4995A-MAG-001 UUM Highway | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N104+ | xD_DWDM-BRKRing_N104+_4992A Pendang_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4992A | 4992A-MAG(M14)-001 Pendang | FO&T | 1.Swap breaker = 4 (4x100A DC) | Completed | 2024-04-16 | N/A | 2024-05-30 | 2024-05-30 | N/A | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N104+ | xD_DWDM-BRKRing_N104+_4991A UUM_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4991A | 4991A-MAC-001 UUM | FO&T | 1. Add Battery Bank = 2 | PRPO | 2024-04-17 | N/A | 2024-05-29 | 2024-05-29 | 2024-06-04 | N/A | 2024-06-12 | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N104+ | xD_DWDM-BRKRing_N104+_4672A Changloon_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4672A | 4672A-MAC-001 Changloon | FO&T | 1. New DCDPB =1 (Require 63A x 4 DC breaker) | PRPO | 2024-04-17 | N/A | 2024-05-29 | 2024-05-29 | 2024-06-04 | N/A | N/A | N/A | 2024-06-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N104+ | xD_DWDM-BRKRing_N104+_4665A Jitra_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4665A | 4665A-MAC-001 Jitra | FO&T | 1. Add Battery Bank = 2 | PRPO | 2024-04-17 | N/A | 2024-05-30 | 2024-05-30 | 2024-06-04 | N/A | N/A | N/A | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N107+ | xD_DWDM-BRKRing_N107+_4998A Air Itam Kedah_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Oct | 4998A | 4998A-MAG(M14)-001 Air Itam Kedah | FO&T | 1. Add Battery Bank = 1 | PRPO | 2024-04-17 | N/A | 2024-05-28 | 2024-05-28 | 2024-06-07 | N/A | N/A | N/A | 2024-06-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N107+ | xD_DWDM-BRKRing_N107+_4606A Padang Besar_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Oct | 4606A | 4606A-MAG(M8)-001 Padang Besar | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N107+ | xD_DWDM-BRKRing_N107+_4604A Kuala Perlis_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Oct | 4604A | 4604A-MAC-001 Kuala Perlis(Trunk) | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N107+ | xD_DWDM-BRKRing_N107+_4601A Federal Kangsar_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Oct | 4601A | 4601A-MAC-001 Federal Kangar | FO&T | N/A | N/A | 2024-04-17 | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N107+ | xD_DWDM-BRKRing_N107+_4612A Jln Kaki Bkt_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Oct | 4612A | 4612A-MAC-001 Jln Kaki Bkt | FO&T | N/A | N/A | 2024-04-17 | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N107+ | xD_DWDM-BRKRing_N107+_4613A Taman Bestari Perlis_0004582401310N_00045824027823 | 2024 Q2_2 | P1_Z_Oct | 4613A | 4613A-MAC-001 Taman Bestari Perlis | FO&T | N/A | N/A | 2024-04-17 | N/A | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N405+/N408+/N411+ | xD_DWDM-BRKRing_N405+/N408+/N411+_4432A KTM Sg Siput_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 4432A | 4432A-MAG-001 KTM Singai Siput | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-05-31 | N/A | Duplicate line 283 | N/A | N/A | N/A | 2024-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N405+/N408+/N411+ | xD_DWDM-BRKRing_N405+/N408+/N411+_4455A KTM Taiping_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 4455A | 4455A-MAG(M14)-001 KTM Taiping | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N405+/N408+/N411+ | xD_DWDM-BRKRing_N405+/N408+/N411+_4374A LAP Talang_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 4374A | 4374A-MAC-001 LAP Talang | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N405+/N408+/N411+ | xD_DWDM-BRKRing_N405+/N408+/N411+_4378A Jerlun Tower_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 4378A | MIP2018 4378A-MAC-001 Jerlun Tower | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N405+/N408+/N411+ | xD_DWDM-BRKRing_N405+/N408+/N411+_4379A Bkt Mercu_0004582401310N_00045824027823 | 2024 Q2_2 | N/A | 4379A | 4379A-MAC-001 Bkt Mercu | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N408+ | xD_DWDM-BRKRing_N408+_4493A KTM Ipoh_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4493A | 4493A-MAG-001 KTM Ipoh | FO&T | N/A | N/A | 2024-04-16 | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N408+ | xD_DWDM-BRKRing_N408+_4506A Perak Taipu_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4506A | 4506A-MAC-001 Perak Taipu | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-27 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N408+ | xD_DWDM-BRKRing_N408+_4546A KWSP Ipoh_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4546A | 4546A-MAC-001 KWSP Ipoh | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N408+ | xD_DWDM-BRKRing_N408+_4515A Tg Rambutan_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4515A | 4515A-MAC-001 Tg Rambutan | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-28 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N411+ | xD_DWDM-BRKRing_N411+_4373A KTM K Kangsar_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4373A | 4373A-MAC-001 KTM K. Kangsar | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N411+ | xD_DWDM-BRKRing_N411+_4377B Karai_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4377B | 4377B-MAC-001 Karai | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-25 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N411+ | xD_DWDM-BRKRing_N411+_4433A LAP Sg Siput_0004582401310N_00045824027823 | 2024 Q2_2 | P1_IP_BR-Q2 | 4433A | 4433A-MAC-001 LAP Sg Siput | FO&T | N/A | N/A | 2024-04-18 | N/A | 2024-06-26 | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1071A | CHI LIUNG PLAZA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-08-30 | N/A | 2024-03-06 | 2024-03-06 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1071A | CHI LIUNG PLAZA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-08-30 | N/A | 2024-03-06 | 2024-03-06 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1071A | CHI LIUNG PLAZA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-08-30 | N/A | 2024-03-06 | 2024-03-06 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1073A | KTM Padang Jawa | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-03 | N/A | 2024-03-14 | 2024-03-14 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1073A | KTM Padang Jawa | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-03 | N/A | 2024-03-14 | 2024-03-14 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1342A | MBSA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-11-16 | N/A | 2024-02-22 | 2024-02-23 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1342A | MBSA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-11-16 | N/A | 2024-02-22 | 2024-02-23 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1367A | WorldWideBusiness | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-08-30 | N/A | 2024-01-17 | 2024-01-17 | 2023-09-15 | 2023-07-25
CAR07, Area70 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 2536A | Centro IB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-03 | N/A | 2024-03-06 | 2024-03-06 | 2023-09-15 | 2023-07-25
CAR07, Area76 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1096A | Klang Perdana | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-08-30 | N/A | 2024-05-28 | 2024-05-28 | 2023-09-15 | 2023-07-25
CAR07, Area76 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1362A | Electroscon | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-08-30 | N/A | 2024-05-28 | 2024-05-28 | 2023-09-15 | 2023-07-25
CAR07, Area76 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1702A | Bkt. Tagar (Trunk) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-18 | N/A | 2024-01-17 | 2024-01-17 | 2023-09-15 | 2023-07-25
Central LL2, Area 77 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1236A | Labu Lanjut | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-03 | N/A | 2023-11-21 | 2023-11-21 | 2023-09-15 | 2023-07-25
Central LL2, Area 77 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1236A | Labu Lanjut | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-03 | N/A | 2023-11-21 | 2023-11-21 | 2023-09-15 | 2023-07-25
SAR02, Area98 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1610A | GUN HILL | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | 2023-10-03 | N/A | 2024-04-18 | 2024-04-18 | 2023-09-15 | 2023-07-25
SAR02, Area98 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1610A | GUN HILL | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | 2023-10-03 | N/A | 2024-04-18 | 2024-04-18 | 2023-09-15 | 2023-07-25
SAR03, Area90 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1525A | Bang. Graha Maju | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | 2023-10-06 | N/A | 2024-03-06 | 2024-03-06 | 2023-09-15 | 2023-07-25
SAR03, Area97 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 6040A | BUKIT RESAM | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2023-10-10 | N/A | 2024-04-24 | 2024-04-24 | 2023-09-15 | 2023-07-25
SAR03, Area97 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 6040A | BUKIT RESAM | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2023-10-10 | N/A | 2024-04-24 | 2024-04-24 | 2023-09-15 | 2023-07-25
SAR03, Area97 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 6295A | Jln Permatang Kempas | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2023-10-31 | N/A | 2024-04-24 | 2024-04-24 | 2023-09-15 | 2023-07-25
SAR04, Area91 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 6336A | UTM 2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2023-10-31 | N/A | 2024-06-05 | N/A | 2023-09-15 | 2023-07-25
SAR04, Area91 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 6336A | UTM 2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2023-10-31 | N/A | 2024-06-05 | N/A | 2023-09-15 | 2023-07-25
CAR03, Area 151 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1002A | Sri Murni | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-11 | N/A | 2023-11-16 | 2023-11-16 | 2023-09-15 | 2023-07-25
CAR03, Area 151 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1002A | Sri Murni | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-11 | N/A | 2023-11-16 | 2023-11-16 | 2023-09-15 | 2023-07-25
CAR04, Area 154 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1006A | JBA Gombak | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-11-29 | N/A | 2024-05-10 | 2024-05-10 | 2023-09-15 | 2023-07-25
CAR04, Area 154 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 1006A | JBA Gombak | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-11-29 | N/A | 2024-05-10 | 2024-05-10 | 2023-09-15 | 2023-07-25
NAR03, Area134 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4310A | Matang Acheh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | 2023-09-11 | N/A | 2024-05-16 | 2024-05-16 | 2023-09-15 | 2023-07-25
NAR03, Area134 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4401B | Kg Temerloh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | 2023-09-11 | N/A | 2024-05-16 | 2024-05-16 | 2023-09-15 | 2023-07-25
Northern LL2, Area124 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4001A | Crown Prince Hotel V6 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2023-12-21 | 2023-12-21 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4012A | Prime Plaza | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2023-11-16 | 2023-11-16 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4012A | Prime Plaza | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | N/A | N/A | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4015A | Axis Complex V4 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2023-11-21 | 2023-11-21 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4015A | Axis Complex V4 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | N/A | N/A | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4031A | GeorgeTownHotel (Trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2024-04-19 | 2024-04-19 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4034A | Bukit Relau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2023-01-04 | 2023-01-04 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4054A | Sunway Hotel | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2023-11-16 | 2023-11-16 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4056A | Vistana Hotel | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2023-11-21 | 2023-11-21 | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4056A | Vistana Hotel | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | N/A | N/A | 2023-09-15 | 2023-07-25
Northern-PRI PFS, Area125 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 4063A | Komplek Tabung Haji | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2023-09-25 | N/A | 2024-04-19 | 2024-04-19 | 2023-09-15 | 2023-07-25
Sabah, Area147 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 7042A | LTP Telipok Maxis | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2023-09-15 | N/A | 2023-12-05 | 2023-12-05 | 2023-09-15 | 2023-07-25
Sabah, Area147 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 7063A | Guang Ji Temple | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2023-09-15 | N/A | 2023-12-12 | 2023-12-12 | 2023-09-15 | 2023-07-25
Sabah, Area147 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 7155A | Maxi Propose Tuaran | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2023-09-15 | N/A | 2023-12-08 | 2023-12-08 | 2023-09-15 | 2023-07-25
Sabah, Area147 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 7169A | UMW INANAM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2023-09-15 | N/A | 2023-12-07 | 2023-12-07 | 2023-09-15 | 2023-07-25
Sabah, Area147 | PR/PO Issuance request - ES (HW) Support PFS swap to Ibeam for NIC activity | N/A | N/A | 7256A | Tmn Kingfisher | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2023-09-15 | N/A | 2023-12-06 | 2023-12-06 | 2023-09-15 | 2023-07-25
N/A | PFS Swap YR22 | N/A | N/A | 1336A | Balai Islam TTDI | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-18 | 2024-01-18 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 1211A | KDU | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-18 | 2024-01-18 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 2831A | One Utama Phase 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-18 | 2024-01-18 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 1197A | JBAEFF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-18 | 2024-01-18 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 1197A | JBAEFF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-18 | 2024-01-18 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 2977B | DiGi HQ (Lot 10) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-09 | 2024-01-09 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 1611A | Mukim Labu | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-09 | 2024-01-09 | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 1407A | Menara Luxor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-23 | N/A | N/A | N/A
N/A | PFS Swap YR22 | N/A | N/A | 1186A | Tropicana2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-23 | N/A | N/A | N/A
N/A | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | N/A | 1037A | JBA Bangi | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-20 | N/A | 2023-12-15 | 2023-12-15 | 2023-07-31 | 2023-07-26
N/A | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | N/A | 1085A | Pekan Meru | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-12 | N/A | 2024-03-19 | 2024-03-20 | 2023-07-31 | 2023-07-26
N/A | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | N/A | 1110A | Berjaya Industrial Park | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-20 | N/A | 2024-05-15 | 2024-05-15 | 2023-07-31 | 2023-07-26
N/A | MIP2023.114 CD Digi BAU ES BOQ- Swap from existing CX600 to NE8000 M14 (1037A, 1085A, 1110A, 1128A) V2 | N/A | N/A | 1128A | Kg Ola Lempik | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-10-03 | N/A | 2023-11-09 | 2023-11-09 | 2023-07-31 | 2023-07-26
N/A | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | N/A | 1039A | Cheras Jaya 2202 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-25 | N/A | 2023-12-06 | 2023-12-06 | 2023-09-15 | 2023-09-25
N/A | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | N/A | 1096A | Klang Perdana | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2023-09-11 | N/A | 2024-04-05 | 2024-04-05 | 2023-09-15 | 2023-09-25
N/A | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | N/A | 4998A | Air Itam Kedah | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2023-09-25 | N/A | 2023-12-22 | 2023-12-22 | 2023-09-15 | 2023-09-25
N/A | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | N/A | 4455A | KTM Taiping | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | 2023-09-25 | N/A | 2023-12-08 | 2023-12-08 | 2023-09-15 | 2023-09-25
N/A | MIP2023.165 CD Digi NIC ES FTK BOQ- Swap from existing CX600 to NE8000 (1039A-MAG-001, 1096A-MAG-001,4998A-MAG-001, 4455A-MAG-001, 4992A-MAG-001) | N/A | N/A | 4992A | Pendang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2023-10-03 | N/A | 2024-06-06 | N/A | 2023-09-15 | 2023-09-25
N/A | MIP2023.236 CD Digi NIC ES BOQ- Swap from existing CX600 to NE8000 M14 (1554A-MAG-002) | N/A | N/A | 1554A | Rumbia | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | 2023-11-08 | N/A | 2024-02-06 | 2024-02-06 | 2023-10-17 | 2023-07-26
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7032A | RAC Radian Court | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-03-04 | 2024-03-04 | 2024-05-21 | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7038A | Lokkawi | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-03-04 | 2024-03-06 | 2024-05-20 | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7702A | BONGAWAN TRUNK_RTN02 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-03-04 | 2024-03-06 | Jun | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7703A | Beaufort Trunk | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-03-04 | 2024-03-06 | N/A | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7704A | Menumbok | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-03-04 | 2024-03-06 | N/A | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7013A | Jln Airport | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-07 | Jun | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7035A | Wisma Shing Yin | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-06 | 2024-05-23 | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7084A | IOFC | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-05 | N/A | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7705A | Kg Bebuluh Laut | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Labuan | 2024-02-28 | 2024-03-05 | 2024-05-24 | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7037A | Wisma Muis | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-04 | Jun | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7039A | Donggongon | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-04 | Jun | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7267A | Tmn Penampang PH2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-04 | Jun | N/A | 2024-02-20 | 2023-12-20
Sabah, Area147 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 7701A | PAPAR TRUNK-RTN01 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | 2024-03-09 | Jun | N/A | 2024-02-20 | 2023-12-20
Area154, | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1304A | MMA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-27 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-20
Area69, | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1822B | Mardi(ZED) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-01 | 2024-03-29 | 2024-05-23 | N/A | 2024-02-20 | 2023-12-20
Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1184A | Indah Villa | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | pending access | N/A | N/A | 2024-02-20 | 2023-12-20
Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1184A | Indah Villa | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | pending access | N/A | N/A | 2024-02-20 | 2023-12-20
C0105P, Area74 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1409A | Kota Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-28 | 2024-03-11 | N/A | N/A | 2024-02-20 | 2023-12-20
C0105P, Area74 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1409A | Kota Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-28 | 2024-03-11 | N/A | N/A | 2024-02-20 | 2023-12-20
C0207, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1253A | Plaza Pengkalen | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-08 | pending access | N/A | N/A | 2024-02-20 | 2023-12-20
C0207, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1253A | Plaza Pengkalen | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-08 | pending access | N/A | N/A | 2024-02-20 | 2023-12-20
C0210P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 2878A | Mont Kiara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-05 | pending access | N/A | N/A | 2024-02-20 | 2023-12-20
C0314P, Area151 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1271A | Risda | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-07 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-20
C0314P, Area151 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1271A | Risda | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-07 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0212P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1437A | Deliq | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-08 | pending access | 2024-05-21 | N/A | 2024-02-20 | 2023-12-20
CT0212P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1259A | Miharja | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-06 | 2024-03-06 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0212P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1745A | Baitumal | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-28 | 2024-03-04 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0239P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1918A | Damansara Intan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-08 | 2024-03-08 | Jun | N/A | 2024-02-20 | 2023-12-20
CT0239P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1918A | Damansara Intan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-08 | 2024-03-08 | Jun | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1899A | Berjaya Time Square Indoor -CAS | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-06 | 2024-03-07 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1896A | Berjaya Times Square CAS 2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-06 | 2024-03-07 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1899A | Berjaya Time Square Indoor -CAS | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-06 | 2024-03-07 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1461A | Shaw Parade | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-01 | Pending access | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1246A | Complex Nagaria | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-28 | 2024-03-08 | Jun | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1063B | BERJAYA TIMES SQUARE | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-06 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1063B | BERJAYA TIMES SQUARE | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-06 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1722E | UE3 Plaza | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | Pending access | N/A | N/A | 2024-02-20 | 2023-12-20
CT0242P, Area79 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1722E | UE3 Plaza | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | Pending access | N/A | N/A | 2024-02-20 | 2023-12-20
Area92, | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 6126A | KTM KLUANG | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-03-01 | 2024-03-18 | N/A | N/A | 2024-02-20 | 2023-12-20
Area92, | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 6106A | Parit Raja Industry | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-03-01 | 2024-03-18 | N/A | N/A | 2024-02-20 | 2023-12-20
Area98, ST27P | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 1608A | KTM SEREMBAN | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | 2024-03-01 | 2024-03-15 | 2024-04-18 | 2024-04-18 | 2024-02-20 | 2023-12-20
Area81, SL732P | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 6708A | Kg Penyabong (trunk) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-02-28 | 2024-03-15 | 2024-06-04 | N/A | 2024-02-20 | 2023-12-20
Area90, SAR03 | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 2337B | Kg Padang Ayer Molek | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | 2024-03-04 | 2024-03-15 | N/A | N/A | 2024-02-20 | 2023-12-20
Aea97, S311PM | MIP2023.331 CD Digi NIC FTK ES BOQ - ATN910C-M for PFS Q1 2024 | N/A | N/A | 6405A | Sri Bunian | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-03-01 | 2024-03-20 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 8223A | Jalan Pengkalan Chepa | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | 2024-02-21 | 2024-02-21 | 2024-06-26 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1360A | Hicom Glenmarie | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-26 | 2024-03-12 | 2024-06-25 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 2632A | Ecopark | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-21 | 2024-02-21 | 2024-05-28 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1775A | Kuvithiru Printers | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-26 | 2024-03-06 | 2024-06-20 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 8020A | N/A | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | Site Drop | 2024-06-26 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1157A | Sg. Nibong | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-27 | 2024-02-28 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1777A | Sek 4 Bdr Baru Bangi | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | 2024-02-29 | 2024-05-16 | 2024-05-16 | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 3440A | Jln Mega Mendung | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Putrajaya | 2024-03-07 | Celcom Ptw | 2024-06-26 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1627B | Pulau Indah Highway(ZED) | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-11 | 2024-03-05 | 2024-05-15 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1698A | JBA Seremban 2 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | 2024-03-08 | Site Drop | 2024-06-13 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1195A | Jln 19 Shoplot | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | 2024-01-04 | 2024-06-21 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1880B | KG LIMAU MANIS (CELCOM) | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Putrajaya | 2024-03-05 | 2024-03-06 | 2024-05-23 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1723A | Tmn Sri Petaling | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-01 | WIP | 2024-06-12 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1040A | 13Cheras | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | 2024-03-01 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1090A | Hin Hua | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-06 | Access Approval Pending | 2024-06-27 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 3411B | REKO SENTRAL | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | Owner Issue | 2024-06-25 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 2278A | Psiaran Sg Long 7A | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-07 | WIP | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1902B | Bdr Sg Long 3 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-07 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1967A | KAP Sport | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-08 | 2024-02-28 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1007A | Mimaland | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-28 | 2024-03-01 | 2024-06-24 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1121A | Bkt Changgang | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-07 | WIP | 2024-06-20 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1661A | PAJAM | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Negeri Sembilan | 2024-03-15 | 2024-03-06 | 2024-05-23 | 2024-05-23 | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1223A | Kg Tunku | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-14 | Pending | 2024-06-10 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 3412A | RAHMAN_PUTRA1 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-13 | WIP | 2024-06-10 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1146A | Kuala Kubu Baru Tower | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-15 | WIP | 2024-06-13 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 6397A | Tmn Sri Orkid(D Harmoni) | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | Site Drop | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 8260A | N/A | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | Site Drop | 2024-06-27 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 8379B | N/A | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | Site Drop | 2024-06-06 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1735A | Tmn Bukit Angkasa | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-03-07 | WIP | 2024-06-25 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 3531C | TM exchange putrajaya | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Putrajaya | 2024-03-08 | Access Approval Pending | 2024-06-27 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1093A | Kian Hoe Huat | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-15 | WIP | 2024-06-20 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1016A | N/A | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-01 | 2024-06-05 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1213A | Puchong Maju V5 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | 2024-02-27 | 2024-06-05 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1402A | Jln Ind Puchong | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | 2024-02-26 | 2024-05-24 | 2024-05-24 | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1422A | Kundang | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-13 | WIP | 2024-06-11 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 2424A | PUAS Tmn Tun Perak | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-06 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 2448A | Asmah Tower | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-06 | Access Approval Pending | 2024-06-26 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1233B | TTDI Jaya Shoplot | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-07 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1378B | PJS 10 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-27 | Access Approval Pending | 2024-06-26 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1179A | Indera Subang | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-28 | Access Approval Pending | 2024-06-06 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1079A | Harpsoon | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-11 | Access Approval Pending | 2024-06-27 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 2722A | Anggerik Eria | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-11 | 2024-03-06 | 2024-05-24 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1266B | CherasJaya Industrial | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-08 | Access Approval Pending | 2024-06-19 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1201A | Stellar | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-29 | 2024-02-28 | 2024-06-21 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1995B | Common MDF KLIA | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-15 | Access Approval Pending | 2024-06-19 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1015A | Awana Golf &Country | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Pahang | 2024-03-14 | Pending | 2024-05-21 | 2024-05-21 | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1088A | Bkt Naga | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-27 | 2024-02-27 | 2024-05-24 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1950A | Tmn Desa Ria | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-28 | 2024-02-28 | 2024-06-14 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1362B | Kelana Business Centre | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-13 | WIP | 2024-06-21 | N/A | 2024-02-20 | 2023-12-20
N106 | MIP2023.269 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N106+ V2 | N/A | N/A | 4966A | Kulim Hi-Tech Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-03-04 | 2024-03-08 | 2024-06-07 | N/A | 2024-02-08 | 2023-12-07
N106 | MIP2023.269 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N106+ V2 | N/A | N/A | 4683A | Bkt Tok Alang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-03-04 | 2024-03-08 | 2024-06-07 | N/A | 2024-02-08 | 2023-12-07
N115 | MIP2023.271 CD Digi NIC FTK EQ BOQ- 2024Q1 600 site list accelerate ZTE- N115+ - V2 | N/A | N/A | 4770A | Toklin (Trunk ) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | TBA | TBA | 2024-06-05 | N/A | N/A | 2023-12-07
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1409A | Kota Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 1085A | Pekan Meru | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | 2777C | JBA Bkt Lipat (TX REL - Celcom) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.330 CD Digi NIC ES BOQ - ATN910C-M for MAC and NE8000 100G MAG Q1 2024 v2 | N/A | N/A | Site 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | TBA | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 8000A | MSC Kuantan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | 2024-03-07 | 2024-03-20 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 8000A | MSC Kuantan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | 2024-03-07 | 2024-03-20 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | 2024-03-11 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | 2024-03-11 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | 2024-03-11 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-03-20 | 2024-02-18 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-03-20 | 2024-02-18 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 1475A | BSC Sri Kembangan | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 1475A | BSC Sri Kembangan | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 7205A | MILE 15 TAWAU | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | wip | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 7205A | MILE 15 TAWAU | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | 2024-02-28 | wip | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 1621A | Senawang MSC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | 2024-03-05 | 2024-02-18 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 8703A | Kg. Awah | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | 2024-03-07 | 2024-02-20 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 6407B | Mersing REL | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-02-28 | 2024-02-20 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 6707A | Kg Jambi (Trunk) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-02-28 | 2024-02-21 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 7570A | Kg. Garinono | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | TBA | TBA | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 7570A | Kg. Garinono | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | TBA | TBA | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 8285A | Bukit Bunga | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | 2024-03-08 | 2024-03-11 | 2024-05-28 | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 8314A | Gong Terap | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | 2024-02-23 | 2024-02-23 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.332 CD Digi NIC ES BOQ - NE8000 M14 for MAG Q1 2024 | N/A | N/A | 6405A | Sri Bunian | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | 2024-03-01 | 2024-03-20 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1006A | JBA Gombak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-01 | 2024-03-12 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1304A | MMA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-27 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1745A | Baitumal | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1458A | Endah Parade | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-28 | 2024-03-18 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-28 | 2024-03-27 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | 2024-02-28 | 2024-03-27 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1475A | BSC Sri Kembangan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1475A | BSC Sri Kembangan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-02-26 | 2024-02-26 | N/A | N/A | 2024-02-20 | 2023-12-20
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 2011E | Westport Building | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1149E | Westport T1 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1127E | West Port CT9 Pole | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | 2024-05-27 | 2024-05-27 | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1020E | West Port CT8-1 Pole | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1151E | Westport T3 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1019E | West Port CT6-1 Pole | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1018E | West Port CT4-2 Pole | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1150E | Westport T2 | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 1017E | West Port CT3-1 Pole | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 3864E | Westport | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 18/3/2024 - 20/3/2024 | Access Approval Pending | N/A | N/A | 2024-02-20 | 2023-12-08
N/A | MIP2023.239 CD Digi EB FTK ES BOQ- Westport EB modernization plan (Swap ATN) | N/A | N/A | 3404A | Telok Gong (REL) | Advance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-13 | 2024-03-05 | N/A | N/A | 2024-02-20 | 2023-12-08
NAR01_i+ | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | 2024-03-05 | 2024-03-11 | N/A | N/A | 2024-02-20 | 2023-12-08
NAR01_i+ | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | N/A | 4946A | Bukit Selambau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-02-05 | 2024-03-07 | N/A | N/A | 2024-02-20 | 2023-12-08
NAR01_i+ | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | N/A | 4966A | Kulim Hi-Tech Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-03-04 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-08
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4998A | Air Itam Kedah | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | TBA | TBA | N/A | N/A | 2024-02-20 | 2023-12-08
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4660A | KTM A.setar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-02-05 | 2024-03-08 | N/A | N/A | 2024-02-20 | 2023-12-08
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4938A | Taman Orkid | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-02-06 | 2024-03-06 | N/A | N/A | 2024-02-20 | 2023-12-08
S102 | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | N/A | 1649A | KUALA LUKUT | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-05-22 | N/A
S102 | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | N/A | 1690A | Bukit Pelandok (DWDM) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-05-22 | N/A
S102 | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | N/A | 1640A | POLITEKNIK PORT DICKSON (KJS TW) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-05-22 | N/A
S102 | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | N/A | 1634A | LUKUT | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-05-22 | N/A
S102 | ML177398 MIP2023.42 CDB BAU ES BOQ- 1649A Kuala Lukut-100Q4 new ibeam integration and S102 break ring V2 | N/A | N/A | 3148A | Tmn Abd Dato Samad | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-05-22 | N/A
C0904 | ML178493 MIP2023.43 CD Digi BAU ES BOQ- C0904 break ring to support for network consolidation | N/A | N/A | 1690A | Bukit Pelandok (DWDM) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-05-29 | N/A
C0904 | ML178493 MIP2023.43 CD Digi BAU ES BOQ- C0904 break ring to support for network consolidation | N/A | N/A | 1124A | Batu 15 Banting | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-05-29 | N/A
C0904 | ML178493 MIP2023.43 CD Digi BAU ES BOQ- C0904 break ring to support for network consolidation | N/A | N/A | 1130A | Kanchong Darat | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-05-29 | N/A
C0204P & C0407P | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | N/A | 1304A | MMA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-06-07 | N/A
C0204P & C0407P | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | N/A | 1745A | Baitumal | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-06-07 | N/A
C0204P & C0407P | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | N/A | 1253A | Plaza Pengkalen | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-06-07 | N/A
C0204P & C0407P | MIP2023.46 CD Digi BAU ES BOQ- Break ring for 1737A, 1261A, 1266A (Ring … | N/A | N/A | 1851A | KL Plaza 4th floor | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-06-07 | N/A
C0501P | MIP2023.66 CD Digi BAU ES BOQ- C0501 break ring via DWDM and new ATN910C installation at 1110A | N/A | N/A | 1110A | Berjaya Industrial Park | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-06-13 | N/A
C0114 | MIP2023.67 CD Digi BAU ES BOQ- C0114 break ring to support for network consolidation | N/A | N/A | 1088A | Bkt Naga | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-07-07 | 2023-07-07 | 2023-06-13 | N/A
C0114 | MIP2023.67 CD Digi BAU ES BOQ- C0114 break ring to support for network consolidation | N/A | N/A | 2021B | DiGi TOC (Lot 43) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-07-07 | 2023-07-07 | 2023-06-13 | N/A
C0114 | MIP2023.67 CD Digi BAU ES BOQ- C0114 break ring to support for network consolidation | N/A | N/A | 2631A | Samarinda | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-07-07 | 2023-07-07 | 2023-06-13 | N/A
E205 | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | N/A | N/A | 8408A | Bandar Cheneh | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2023-08-22 | 2023-08-22 | 2023-06-23 | N/A
E205 | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | N/A | N/A | 8403A | Bukit Mentok | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2023-08-22 | 2023-08-22 | 2023-06-23 | N/A
E205 | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | N/A | N/A | 8483A | DESA SOLEHAH | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2023-08-22 | 2023-08-22 | 2023-06-23 | N/A
E205 | MIP2022.145 CDB ES BOQ to Support Break Ring for Ring E205 via OB fiber V2 | N/A | N/A | 8330A | Bukit Kemuning | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2023-08-22 | 2023-08-22 | 2023-06-23 | N/A
E407 | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | N/A | N/A | 8046A | Bdr Indera Mahkota | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-06-27 | N/A
E407 | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | N/A | N/A | 8050A | Permatang Badak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-06-27 | N/A
E407 | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | N/A | N/A | 8000A | MSC Kuantan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-06-27 | N/A
E407 | MIP2023.79 CD Digi NIC ES BOQ- Eastern E407 MAC Break Ring | N/A | N/A | 8025A | Pejabat Risda | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-08-10 | 2023-08-10 | 2023-06-27 | N/A
CT0120 | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | N/A | N/A | 1099A | Hong Fatt Auto | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-06-28 | N/A
CT0120 | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | N/A | N/A | 2632A | Ecopark | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-06-28 | N/A
CT0120 | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | N/A | N/A | 1409A | Kota Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-06-28 | N/A
CT0120 | MIP2023.106 CD Digi NIC ES BOQ- CT0120 break ring via DWDM | N/A | N/A | 1085A | Pekan Meru | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-06-28 | N/A
E408 | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | N/A | N/A | 8033A | Kg Pandan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-07-21 | 2023-07-21 | 2023-07-03 | N/A
E408 | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | N/A | N/A | 8933A | Bt 6 Jln Gambang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-07-21 | 2023-07-21 | 2023-07-03 | N/A
E408 | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | N/A | N/A | 8025A | Pejabat Risda | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-07-21 | 2023-07-21 | 2023-07-03 | N/A
E408 | MIP2023.80 CD Digi NIC ES BOQ- Eastern E408 MAC Break Ring V2 | N/A | N/A | 8000A | MSC Kuantan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-07-21 | 2023-07-21 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8035A | Balok Kg Chengal | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8936A | Sg Karang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8061A | PLD Bukit Pelindung | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8434A | Felda Neram | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8023B | Balok Baru | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8953A | Balok Perdana SBC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8408A | Bandar Cheneh | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
E202 | Support Eastern E202 MAC break ring via DWDM [E202] | N/A | N/A | 8000A | MSC Kuantan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-03-26 | 2024-03-26 | 2023-07-03 | N/A
CAR01 | MIP2023.137 CD Digi NIC ES BOQ- MAG CAR01_PE-MCR + Break ring, break at 2777C (DWDM) | N/A | N/A | 2777C | JBA Bkt Lipat (TX REL - Celcom) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-08 | 2023-12-08 | 2023-07-28 | N/A
CAR01 | MIP2023.137 CD Digi NIC ES BOQ- MAG CAR01_PE-MCR + Break ring, break at 2777C (DWDM) | N/A | N/A | 1049B | MSC Damansara | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-08 | 2023-12-08 | 2023-07-28 | N/A
C0108 / CT11P | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | N/A | N/A | 1087A | Rantau Panjang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-19 | 2023-12-19 | 2023-07-30 | N/A
C0108 / CT11P | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | N/A | N/A | 1080A | WIT | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-19 | 2023-12-19 | 2023-07-30 | N/A
C0108 / CT11P | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | N/A | N/A | 2021B | DiGi TOC (Lot 43) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-19 | 2023-12-19 | 2023-07-30 | N/A
C0108 / CT11P | MIP2023.105 CD Digi NIC ES BOQ- C0108 break ring via DWDM | N/A | N/A | 2777C | JBA Bkt Lipat (TX REL - Celcom) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-19 | 2023-12-19 | 2023-07-30 | N/A
Colocated-Ring-4 | MIP2023.138 CD Digi NIC ES BOQ- Reengineering MAG Colocated-Ring-4- 4000A-MAC, assess on access node uplinkbreak ring | N/A | N/A | 4000A | MSC Prai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-08-01 | N/A
C0803 | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | N/A | N/A | 1701A | Kerling Trunk | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-08-01 | N/A
C0803 | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | N/A | N/A | 1066A | Sg.Choh (Timecell) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-08-01 | N/A
C0803 | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | N/A | N/A | 1146A | Kuala Kubu Baru Tower | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-08-01 | N/A
C0803 | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | N/A | N/A | 1145A | Batang Kali | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-08-01 | N/A
C0803 | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | N/A | N/A | 2038A | Antara Gapi (KJS) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-08-01 | N/A
C0803 | MIP2023.159 CD Digi NIC ES BOQ- IPRAN re-eng for C0803 break ring via DWDM | N/A | N/A | 1070A | Wisma Low Kang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-08-01 | N/A
S309 | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | N/A | N/A | 1556A | MERLIMAU | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-08-01 | N/A
S309 | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | N/A | N/A | 1599A | BKT GAMBIR TOWN | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-08-01 | N/A
S309 | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | N/A | N/A | 1553A | Umbai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-08-01 | N/A
S309 | MIP2023.88 CD Digi NIC ES BOQ- Southern S309 MAC Break Ring | N/A | N/A | 2402B | Pagoh Highway | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-08-01 | N/A
N404 | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | N/A | N/A | 4952B | SELAMA KEDAH | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-02-21 | 2024-02-21 | 2023-08-01 | N/A
N404 | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | N/A | N/A | 4454B | Kubu Gajah RDD | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-02-21 | 2024-02-21 | 2023-08-01 | N/A
N404 | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | N/A | N/A | 4457A | Kamunting Industry | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-02-21 | 2024-02-21 | 2023-08-01 | N/A
N404 | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | N/A | N/A | 4427B | Simpang Taiping | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-02-21 | 2024-02-21 | 2023-08-01 | N/A
N404 | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | N/A | N/A | 4465A | Taman Long Jaafar RDD | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-02-21 | 2024-02-21 | 2023-08-01 | N/A
N404 | MIP2023.126 CD Digi NIC ES BOQ- Reengineering MAC N404- Break 2 ring, 2 node per ring (DWDM | N/A | N/A | 4455A | KTM Taiping | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-02-21 | 2024-02-21 | 2023-08-01 | N/A
E107 | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | N/A | N/A | 8217A | Padang Tembak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-08-01 | N/A
E107 | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | N/A | N/A | 8263A | Pasir Mas Town | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-08-01 | N/A
E107 | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | N/A | N/A | 8211A | Wakaf Che Yeh | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-08-01 | N/A
E107 | MIP2023.75 CD Digi NIC ES BOQ- Eastern E107 MAC Break Ring | N/A | N/A | 8221A | Cherang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-08-01 | N/A
CAR01 | MIP2023.137 CD Digi NIC ES BOQ- MAG CAR01_PE-MCR + Break ring, break at 2777C (DWDM) | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-12-08 | 2023-12-08 | 2023-07-28 | N/A
N113 / N119 | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | N/A | N/A | 4995A | Changloon UUM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-08-08 | N/A
N113 / N119 | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | N/A | N/A | 4992A | Pendang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-08-08 | N/A
N113 / N119 | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | N/A | N/A | 4662A | BKT. TINGGI, ALOR RAMBAI | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-08-08 | N/A
N113 / N119 | MIP2023.160 CD Digi NIC ES BOQ- IPRAN re-eng for N119 break ring via DWDM | N/A | N/A | 4678A | Jalan Langgar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-08-08 | N/A
C0702P | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | N/A | N/A | 1169A | Tg Karang Trunk Road | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-21 | 2024-05-21 | 2023-08-08 | N/A
C0702P | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | N/A | N/A | 1153A | Permatang K Selangor | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-21 | 2024-05-21 | 2023-08-08 | N/A
C0702P | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | N/A | N/A | 1156A | Btg. Berjuntai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-21 | 2024-05-21 | 2023-08-08 | N/A
C0702P | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | N/A | N/A | 1154A | Sekinchan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-21 | 2024-05-21 | 2023-08-08 | N/A
C0702P | MIP2023.122 CD Digi NIC ES BOQ- Reengineering MAC C0702P- Break into 3 ring, existing 3 node, 1 node per ring (DWDM) | N/A | N/A | 1096A | Klang Perdana | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-21 | 2024-05-21 | 2023-08-08 | N/A
S501_1 | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | N/A | N/A | 1553A | Umbai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2023-08-14 | N/A
S501_1 | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | N/A | N/A | 2388B | Taman Desa Muar | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2023-08-14 | N/A
S501_1 | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | N/A | N/A | 2227B | TMN SRI JERAM | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2023-08-14 | N/A
S501_1 | MIP2023.89 CD Digi NIC ES BOQ- IPRAN Re-eng for S501_1 (2388B, 2227B) Break Ring via DWDM | N/A | N/A | 1591A | Parit Bakar Tengah | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8314A | Gong Terap | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8429B | Bkt Payung 2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8344A | Felda Belara | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8361A | Batu Rakit | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8353A | Kg Manir | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8350B | KUSTEM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8354A | KUSZA Gong Badak | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
E212 | MIP2023.77 CD Digi NIC ES BOQ- IPRAN re-eng for E212 break ring via DWDM | N/A | N/A | 8923B | Tmn Semarak REL | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-02-22 | 2024-02-22 | 2023-08-14 | N/A
N406 | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | N/A | N/A | 4493A | KTM IPOH | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-08-14 | N/A
N406 | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | N/A | N/A | 4432A | KTM Sg Siput | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-08-14 | N/A
N406 | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | N/A | N/A | 4496A | LAP Tasek 1&2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-08-14 | N/A
N406 | MIP2023.127 CD Digi NIC ES BOQ- Reengineering MAC N406 (4493A,4432A,4496A,4536A) Break Ring via DWDM | N/A | N/A | 4536A | Tasek Industrial | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-08-14 | N/A
C1102 | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | N/A | N/A | 2070B | Sri Gombak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-08-14 | N/A
C1102 | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | N/A | N/A | 8709A | Bentong (Trunk) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-08-14 | N/A
C1102 | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | N/A | N/A | 1007A | Mimaland | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-08-14 | N/A
C1102 | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | N/A | N/A | 1787B | Karak HW KM 33.9 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-08-14 | N/A
C1102 | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | N/A | N/A | 1770B | Genting Sempah | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-08-14 | N/A
C1102 | MIP2023.163 CD Digi NIC ES BOQ- IPRAN re-eng for C1102 (1770B, 1787B, 1007A, 2086A) break ring via DWDM | N/A | N/A | 2086A | Balai Polis Bkt Tinggi | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-08-14 | N/A
S307 | MIP2023.87 CD Digi NIC ES BOQ- IPRAN re-eng for S307 (6502A, 6413A) break ring via DWDM | N/A | N/A | 6502A | Nusa Perintis(Watertank) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2023-10-17 | 2023-10-17 | 2023-08-14 | N/A
S307 | MIP2023.87 CD Digi NIC ES BOQ- IPRAN re-eng for S307 (6502A, 6413A) break ring via DWDM | N/A | N/A | 6413A | Kg Pengkalan Raja | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2023-10-17 | 2023-10-17 | 2023-08-14 | N/A
S307 | MIP2023.87 CD Digi NIC ES BOQ- IPRAN re-eng for S307 (6502A, 6413A) break ring via DWDM | N/A | N/A | 6405A | Sri Bunian | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2023-10-17 | 2023-10-17 | 2023-08-14 | N/A
N301 | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | N/A | 4000A | MSC Prai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-08-22 | N/A
N301 | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | N/A | 4184A | Permatang Tinggi | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-08-22 | N/A
N301 | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | N/A | 4215A | Alma Kg Kijang 2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-08-22 | N/A
N301 | MIP2023.150 CD Digi NIC ES BOQ- N301 break ring via OB fiber | N/A | N/A | 4188A | NIBONG TEBAL2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-08-22 | N/A
SAR01 | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | N/A | N/A | 1640A | POLITEKNIK PORT DICKSON (KJS TW) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-10-26 | 2023-10-26 | 2023-08-22 | N/A
SAR01 | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | N/A | N/A | 1552A | Tanjung Bidara | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2023-10-26 | 2023-10-26 | 2023-08-22 | N/A
SAR01 | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | N/A | N/A | 1554A | Rumbia | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2023-10-26 | 2023-10-26 | 2023-08-22 | N/A
SAR01 | MIP2023.90 CD Digi NIC ES BOQ- SAR01 MAG ring upgrade from 20G to 40G via DWDM | N/A | N/A | 1690A | Bukit Pelandok (DWDM) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2023-10-26 | 2023-10-26 | 2023-08-22 | N/A
N407 | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | N/A | N/A | 4493A | KTM IPOH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
N407 | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | N/A | N/A | 4515A | TG RAMBUTAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
N407 | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | N/A | N/A | 4432A | KTM Sg Siput | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
N407 | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | N/A | N/A | 4498A | LAP Tambun 1&2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
N407 | MIP2023.174 CD Digi NIC ES BOQ- IPRAN re-eng for N407 break ring via DWDM | N/A | N/A | 4541A | Bercham Industry | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
C1103 | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | N/A | N/A | 2070B | Sri Gombak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
C1103 | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | N/A | N/A | 8709A | Bentong (Trunk) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
C1103 | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | N/A | N/A | 2833A | First World Hotel Indoor | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
C1103 | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | N/A | N/A | 1016A | GENTING RIA APARTMENT | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
C1103 | MIP2023.169 CD Digi NIC ES BOQ- Ring 58_C1103 break ring (1016A, 1015A, 2833A) via DWDM | N/A | N/A | 1015A | Awana Golf &Country | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2023-08-25 | N/A
C0103 | MIP2023.168 CD Digi NIC ES BOQ- IPRAN re-eng for C0103 break ring via DWDM | N/A | N/A | 1359A | Mutiara Subang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-10-24 | 2023-10-24 | 2023-08-25 | N/A
C0103 | MIP2023.168 CD Digi NIC ES BOQ- IPRAN re-eng for C0103 break ring via DWDM | N/A | N/A | 1409A | Kota Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-10-24 | 2023-10-24 | 2023-08-25 | N/A
C0103 | MIP2023.168 CD Digi NIC ES BOQ- IPRAN re-eng for C0103 break ring via DWDM | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2023-10-24 | 2023-10-24 | 2023-08-25 | N/A
S401 | MIP2023.110 CD Digi BAU ES BOQ- Southern S401 Reengineering | N/A | N/A | 1621A | Senawang MSC | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-05-23 | 2024-05-23 | 2023-08-01 | N/A
S401 | MIP2023.110 CD Digi BAU ES BOQ- Southern S401 Reengineering | N/A | N/A | 1659A | Bahau Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-05-23 | 2024-05-23 | 2023-08-01 | N/A
S401 | MIP2023.110 CD Digi BAU ES BOQ- Southern S401 Reengineering | N/A | N/A | 2376B | KG.TENAI AIR GELUGOR | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-05-23 | 2024-05-23 | 2023-08-01 | N/A
MR20/C26 | MIP2023.184 CD Digi NIC ES BOQ- Break Ring MAC Ring 20 | N/A | N/A | 1093A | Kian Hoe Huat | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-09-15 | N/A
MR20/C26 | MIP2023.184 CD Digi NIC ES BOQ- Break Ring MAC Ring 20 | N/A | N/A | 1627B | Pulau Indah Highway(ZED) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-09-15 | N/A
MR20/C26 | MIP2023.184 CD Digi NIC ES BOQ- Break Ring MAC Ring 20 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-09-15 | N/A
S313P_2_ | MIP2023.84 CD Digi NIC ES BOQ- Southern 1533A-MAC-002 Bukit Duyong Integration | N/A | N/A | 1533A | Bkt Duyung | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2023-09-26 | N/A
E404 | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | N/A | N/A | 8965A | Simpang Lepar Hilir | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-09-26 | N/A
E404 | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | N/A | N/A | 8191A | Sg Semuji(Shazan s Tower / ZED) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-09-26 | N/A
E404 | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | N/A | N/A | 8513A | Bkt Senggora | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-09-26 | N/A
E404 | MIP2023.78 CD Digi NIC ES BOQ- Eastern E404 MAC Break Ring | N/A | N/A | 8025A | Pejabat Risda | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-09-26 | N/A
SAR03_iii | MIP2023.92 CD Digi NIC ES BOQ- Southern SAR03_iii MAG Break Ring | N/A | N/A | 1554A | Rumbia | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-09-26 | N/A
SAR03_iii | MIP2023.92 CD Digi NIC ES BOQ- Southern SAR03_iii MAG Break Ring | N/A | N/A | 1621A | Senawang MSC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-09-26 | N/A
SAR03_iii | MIP2023.92 CD Digi NIC ES BOQ- Southern SAR03_iii MAG Break Ring | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-01-24 | 2024-01-24 | 2023-09-26 | N/A
SAR05 | MIP2023.93 CD Digi NIC ES BOQ- Southern SAR05 MAG Break Ring | N/A | N/A | 6083A | Soga | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-03-13 | 2024-03-13 | 2023-09-26 | N/A
SAR05 | MIP2023.93 CD Digi NIC ES BOQ- Southern SAR05 MAG Break Ring | N/A | N/A | 1621A | Senawang MSC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-03-13 | 2024-03-13 | 2023-09-26 | N/A
SAR05 | MIP2023.93 CD Digi NIC ES BOQ- Southern SAR05 MAG Break Ring | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-03-13 | 2024-03-13 | 2023-09-26 | N/A
SAR03_ii | MIP2023.91 CD Digi NIC ES BOQ- Southern SAR03_ii MAG Break Ring | N/A | N/A | 2402B | Pagoh Highway | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-01-23 | 2024-01-23 | 2023-09-26 | N/A
SAR03_ii | MIP2023.91 CD Digi NIC ES BOQ- Southern SAR03_ii MAG Break Ring | N/A | N/A | 1621A | Senawang MSC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-01-23 | 2024-01-23 | 2023-09-26 | N/A
SAR03_ii | MIP2023.91 CD Digi NIC ES BOQ- Southern SAR03_ii MAG Break Ring | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-01-23 | 2024-01-23 | 2023-09-26 | N/A
EAR02_2 | MIP2023.81 CD Digi NIC ES BOQ- Eastern EAR02_2 MAG Break Ring | N/A | N/A | 8429B | Bkt Payung 2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | 2024-05-28 | 2024-05-28 | 2023-09-26 | N/A
EAR02_2 | MIP2023.81 CD Digi NIC ES BOQ- Eastern EAR02_2 MAG Break Ring | N/A | N/A | 8000A | MSC Kuantan | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-05-28 | 2024-05-28 | 2023-09-26 | N/A
EAR02_2 | MIP2023.81 CD Digi NIC ES BOQ- Eastern EAR02_2 MAG Break Ring | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-05-28 | 2024-05-28 | 2023-09-26 | N/A
N601 | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | N/A | N/A | 4521A | MSC Ipoh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-05 | 2024-03-05 | 2023-10-04 | N/A
N601 | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | N/A | N/A | 4440B | Tapah Road | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-05 | 2024-03-05 | 2023-10-04 | N/A
N601 | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | N/A | N/A | 4509A | LAP Tmn Taufik | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-05 | 2024-03-05 | 2023-10-04 | N/A
N601 | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | N/A | N/A | 4516A | Simpang Pulai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-05 | 2024-03-05 | 2023-10-04 | N/A
N601 | MIP2023.182 CD Digi NIC ES BOQ- IPRAN re-eng for N601 break ring via DWDM | N/A | N/A | 4368A | TAR College | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-05 | 2024-03-05 | 2023-10-04 | N/A
New Ring_5 | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | N/A | N/A | 6283A | LARKIN INDUSTRIAL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-12 | N/A | 2023-10-05 | N/A
New Ring_5 | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | N/A | N/A | 6043A | K.K.Kam | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-12 | N/A | 2023-10-05 | N/A
New Ring_5 | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | N/A | N/A | 6026A | Grand Continental | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-12 | N/A | 2023-10-05 | N/A
New Ring_5 | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-12 | N/A | 2023-10-05 | N/A
New Ring_5 | MIP2023.201 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_ New Ring_5 | N/A | N/A | 6502A | Nusa Perintis(Watertank) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-12 | N/A | 2023-10-05 | N/A
N113 | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | N/A | N/A | 4995A | Changloon UUM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2024-01-15 | N/A | Jun | N/A | 2023-10-05 | TBA
N113 | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | N/A | N/A | 4992A | Pendang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | 2023-10-10 | N/A | Jun | N/A | 2023-10-05 | 2023-09-25
N113 | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | N/A | N/A | 4663A | Derga Jaya | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | Jun | N/A | 2023-10-05 | N/A
N113 | MIP2023.215 CD Digi NIC FTK ES BOQ- Accelerated Sites Break Ring ZTE_N113 (NE 8000) | N/A | N/A | 4973B | Tajar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | Jun | N/A | 2023-10-05 | N/A
N103 | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | N/A | N/A | 4863B | Wisma PKNK | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-06-07 | N/A | 2023-10-05 | N/A
N103 | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | N/A | N/A | 4669A | Alor Janggus (Trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-06-07 | N/A | 2023-10-05 | N/A
N103 | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | N/A | N/A | 4660A | KTM A.setar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-06-07 | N/A | 2023-10-05 | N/A
N103 | MIP2023.216 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N103 | N/A | N/A | 4998A | Air Itam Kedah | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-06-07 | N/A | 2023-10-05 | N/A
C0607P | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | N/A | N/A | 1475A | BSC Sri Kembangan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-10-05 | N/A
C0607P | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | N/A | N/A | 1196A | JBA Puchong | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-10-05 | N/A
C0607P | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | N/A | N/A | 1408A | Puchong Jaya | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-10-05 | N/A
C0607P | MIP2023.218 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_C0607P | N/A | N/A | 1402A | Jln Ind Puchong | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-07 | 2024-05-07 | 2023-10-05 | N/A
S602M | MIP2023.204 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_S602M | N/A | N/A | 6955A | Putri Wangsa 2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-02-23 | 2024-02-23 | 2023-10-05 | N/A
S602M | MIP2023.204 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_S602M | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-02-23 | 2024-02-23 | 2023-10-05 | N/A
S602M | MIP2023.204 CD Digi NIC ES BOQ- Accelerated Sites Break Ring Huawei_S602M | N/A | N/A | 6369A | Sri Saujana | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-02-23 | 2024-02-23 | 2023-10-05 | N/A
NAR06 | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | N/A | N/A | 4440B | Tapah Road | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-06 | 2024-03-06 | 2023-10-05 | N/A
NAR06 | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | N/A | N/A | 4521A | MSC Ipoh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-06 | 2024-03-06 | 2023-10-05 | N/A
NAR06 | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | N/A | N/A | 1049B | MSC Damansara | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-03-06 | 2024-03-06 | 2023-10-05 | N/A
NAR06 | MIP2023.213 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (PE MCR migration) | N/A | N/A | 1701A | Kerling Trunk | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-03-06 | 2024-03-06 | 2023-10-05 | N/A
NAR06 | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | N/A | N/A | 1049B | MSC Damansara | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-10-05 | N/A
NAR06 | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | N/A | N/A | 4521A | MSC Ipoh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-10-05 | N/A
NAR06 | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | N/A | N/A | 1701A | Kerling Trunk | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-10-05 | N/A
NAR06 | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | N/A | N/A | 4412A | KTM Sungkai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-10-05 | N/A
NAR06 | MIP2023.212 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR06 (Expansion) | N/A | N/A | 4440B | Tapah Road | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-01-30 | 2024-01-30 | 2023-10-05 | N/A
NAR03 | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | N/A | N/A | 4188A | NIBONG TEBAL2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | 2024-03-20 | 2024-03-20 | 2023-10-10 | N/A
NAR03 | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | N/A | N/A | 4331A | Bagan Serai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | 2024-03-20 | 2024-03-20 | 2023-10-10 | N/A
NAR03 | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | N/A | N/A | 4310A | Matang Acheh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | 2024-03-20 | 2024-03-20 | 2023-10-10 | N/A
NAR03 | MIP2023.223 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_NAR03 | N/A | N/A | 4521A | MSC Ipoh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-03-20 | 2024-03-20 | 2023-10-10 | N/A
MAC RING 18-C24 | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-10-12 | N/A
MAC RING 18-C24 | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | N/A | N/A | 1360A | Hicom Glenmarie | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-10-12 | N/A
MAC RING 18-C24 | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | N/A | N/A | 1172A | Glomac | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-10-12 | N/A
MAC RING 18-C24 | MIP2023.219 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_MAC RING 18-C24 | N/A | N/A | 1362B | Kelana Business Centre | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2023-10-12 | N/A
N106 | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | N/A | N/A | 4946A | Bukit Selambau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-10-19 | N/A
N106 | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | N/A | N/A | 4966A | Kulim Hi-Tech Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-10-19 | N/A
N106 | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | N/A | N/A | 4683A | Bkt Tok Alang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-10-19 | N/A
N106 | MIP2023.222 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N106 | N/A | N/A | 4085D | Kulim Hitech 2 (REL) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-10-19 | N/A
N302 | MIP2023.221 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N302 | N/A | N/A | 4241A | Juru Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-04-25 | 2024-04-25 | 2023-10-19 | N/A
N302 | MIP2023.221 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N302 | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-04-25 | 2024-04-25 | 2023-10-19 | N/A
N302 | MIP2023.221 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_N302 | N/A | N/A | 4188A | NIBONG TEBAL2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | 2024-04-25 | 2024-04-25 | 2023-10-19 | N/A
N115+ | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | N/A | N/A | 4770A | Toklin (Trunk ) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-15 | N/A
N115+ | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | N/A | N/A | 4932A | BKT TOK ACHEH | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-15 | N/A
N115+ | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | N/A | N/A | 4688A | Lunas | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-15 | N/A
N115+ | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | N/A | N/A | 4966A | Kulim Hi-Tech Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-15 | N/A
N115+ | MIP2023.271 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE 2nd acceleration (754 sites)- N115+ V2 | N/A | N/A | 4946A | Bukit Selambau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-15 | N/A
E110 | MIP2023.07 CDB Digi BAU- ES BOQ for re-eng medium for link 8268A-8211A from DWDM to OB fiber (Ring E110) V2 | N/A | N/A | 8268A | Bachok | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-06-23 | N/A
E110 | MIP2023.07 CDB Digi BAU- ES BOQ for re-eng medium for link 8268A-8211A from DWDM to OB fiber (Ring E110) V2 | N/A | N/A | 8211A | Wakaf Che Yeh | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-06-23 | N/A
EAR04 | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | N/A | N/A | 8000A | MSC Kuantan | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-07-27 | N/A
EAR04 | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | N/A | N/A | 8709A | Bentong (Trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-07-27 | N/A
EAR04 | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | N/A | N/A | 8025A | Pejabat Risda | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-07-27 | N/A
EAR04 | MIP2023.151 CD Digi NIC ES BOQ- EAR04 MAG ring upgrade and PE-MCR migration | N/A | N/A | 8703A | Kg. Awah | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2023-10-25 | 2023-10-25 | 2023-07-27 | N/A
CT01P+ | MIP2023.266 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT01P+ | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-01-18 | N/A
CT01P+ | MIP2023.266 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT01P+ | N/A | N/A | 1309A | Ivory | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-01-18 | N/A
CT01P+ | MIP2023.266 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT01P+ | N/A | N/A | 1298A | Kepong Knit | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-01-18 | N/A
CT04+ | MIP2023.267 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- CT04+ | N/A | N/A | 1413A | KTM Rawang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NT09P+ | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | N/A | N/A | 4621A | CAYMEN SHOPPING | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-19 | 2024-03-19 | 2023-12-22 | N/A
NT09P+ | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | N/A | N/A | 4625A | KTM Sungai Petani | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-19 | 2024-03-19 | 2023-12-22 | N/A
NT09P+ | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | N/A | N/A | 4640A | SP Plaza | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-19 | 2024-03-19 | 2023-12-22 | N/A
NT09P+ | MIP2023.273 CD Digi NIC ES BOQ- 2024Q1 600 site list accelerate ZTE- NT09P+ | N/A | N/A | 4693A | KTM Gurun TX | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-19 | 2024-03-19 | 2023-12-22 | N/A
Area 139 | MIP2023.XX CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_Area 139 | N/A | N/A | 4946A | Bukit Selambau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8513A | Bkt Senggora | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8709A | Bentong (Trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8105A | South Of Raub(AsiaSpace) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8667A | Jerangsang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8145Z | Kg. Paya Luas | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8112A | Bukit Istana | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR06 | MIP2023.249 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR06 (Link Expansion) | N/A | N/A | 8173A | Bandar Pusat Jengka | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SAR01 | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | N/A | N/A | 1690A | Bukit Pelandok (DWDM) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
SAR01 | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | N/A | N/A | 1640A | POLITEKNIK PORT DICKSON (KJS TW) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
SAR01 | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | N/A | N/A | 1554A | Rumbia | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
SAR01 | MIP2023.250 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_SAR01 | N/A | N/A | 1552A | Tanjung Bidara | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
EAR01 | MIP2023.251 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR01 | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR01 | MIP2023.251 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR01 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EAR01 | MIP2023.251 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_EAR01 | N/A | N/A | 8224A | Pasir Puteh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E104 | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | N/A | N/A | 8288B | Bukit Panau | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E104 | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | N/A | N/A | 8263A | Pasir Mas Town | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E104 | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | N/A | N/A | 8269B | Chetok (IQ) | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E104 | MIP2023.240 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E104 | N/A | N/A | 8294A | Kangkong | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E105 | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | N/A | N/A | 8211A | Wakaf Che Yeh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E105 | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | N/A | N/A | 8139B | CBG4TUMPAT1 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E105 | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | N/A | N/A | 8229A | Tumpat | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E105 | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | N/A | N/A | 8212A | Wakaf Bharu | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E105 | MIP2023.241 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E105 | N/A | N/A | 8263A | Pasir Mas Town | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E109 | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | N/A | N/A | 8224A | Pasir Puteh | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E109 | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | N/A | N/A | 8222A | Peringat | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E109 | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | N/A | N/A | 8242B | Jln Kuala Krai | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E109 | MIP2023.242 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E109 | N/A | N/A | 8211A | Wakaf Che Yeh | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E111 | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | N/A | N/A | 8367A | Bukit Kechil | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E111 | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | N/A | N/A | 8317A | Kampung Pak Wong | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E111 | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | N/A | N/A | 8439A | Alor Lintang (Celcom) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E111 | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | N/A | N/A | 8407A | Jerteh (Maxis) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E111 | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | N/A | N/A | 8322B | Padang Luas | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
E111 | MIP2023.243 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_E111 | N/A | N/A | 8224A | Pasir Puteh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
S301 | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | N/A | N/A | 1554A | Rumbia | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
S301 | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | N/A | N/A | 1621A | Senawang MSC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
S301 | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | N/A | N/A | 1560A | Bkt Tiga | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
S301 | MIP2023.244 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S301 | N/A | N/A | 1563A | Bkt Iman | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
S309+ | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | N/A | N/A | 1553A | Umbai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | N/A | N/A
S309+ | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | N/A | N/A | 2402B | Pagoh Highway | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | N/A | N/A
S309+ | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | N/A | N/A | 1556A | MERLIMAU | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | N/A | N/A
S309+ | MIP2023.245 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_S309 | N/A | N/A | 1599A | BKT GAMBIR TOWN | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | N/A | N/A
ST21P | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | N/A | N/A | 6369A | Sri Saujana | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | N/A | N/A | 6400A | Jln Pasir Gudang REL | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P | MIP2023.246 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P | N/A | N/A | 6312A | Jalan Cenderai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P_1 | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | N/A | N/A | 6382A | KTM Pasir Gudang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P_1 | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | N/A | N/A | 6063A | KTM Plentong(PLE) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P_1 | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | N/A | N/A | 6000A | MSC JB | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST21P_1 | MIP2023.247 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST21P_1 | N/A | N/A | 6369A | Sri Saujana | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST27P | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | N/A | N/A | 1607A | KM Plaza | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST27P | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | N/A | N/A | 1621A | Senawang MSC | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST27P | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | N/A | N/A | 1608A | KTM SEREMBAN | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
ST27P | MIP2023.248 CD Digi NIC FTK ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_ST27P (PFS Swap) | N/A | N/A | 1610A | GUN HILL | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Area 141+ V2 | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Area 141+ V2 | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Area 141+ V2 | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Area 141+ V2 | MIP2023.263 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Area 141+ V2 | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Colocated-Ring-2+ | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-02-20 | N/A
Colocated-Ring-2+ | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-02-20 | N/A
Colocated-Ring-2+ | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-02-20 | N/A
Colocated-Ring-2+ | MIP2023.264 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-2+ | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-02-20 | N/A
Colocated-Ring-4+ | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
Colocated-Ring-4+ | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
Colocated-Ring-4+ | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
Colocated-Ring-4+ | MIP2023.265 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
CT04+ | MIP2023.267 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- CT04+ | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CT04+ | MIP2023.267 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- CT04+ | N/A | N/A | 1413A | KTM Rawang | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CT04+ | MIP2023.267 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- CT04+ | N/A | N/A | 1412A | Bkt Tadun | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
MAC RING 6,C09+ | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
MAC RING 6,C09+ | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
MAC RING 6,C09+ | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | N/A | N/A | 1192A | Subng NewVillge | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
MAC RING 6,C09+ | MIP2023.268 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- MAC RING 6,C09+ | N/A | N/A | 1230A | Tmn Perindustrian Sg Buloh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
N114M+ | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | N/A | N/A | 4692A | Gurun | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-02-11 | N/A
N114M+ | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | N/A | N/A | 4940A | Semeling | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-02-11 | N/A
N114M+ | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | N/A | N/A | 4938A | Taman Orkid | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-02-11 | N/A
N114M+ | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | N/A | N/A | 4938A | Taman Orkid | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-02-11 | N/A
N114M+ | MIP2023.270 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N114M+ | N/A | N/A | 4660A | KTM A.setar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-02-11 | N/A
N401+ | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | N/A | N/A | 4118A | Machang Bubuk 2 | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-10 | N/A
N401+ | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | N/A | N/A | 4689A | Taman Desa Impian | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-10 | N/A
N401+ | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | N/A | N/A | 4965A | Politeknik Kulim | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-10 | N/A
N401+ | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | N/A | N/A | 4686B | Terap | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-10 | N/A
N401+ | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | N/A | N/A | 4952B | SELAMA KEDAH | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-10 | N/A
N401+ | MIP2023.272 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N401+ | N/A | N/A | 4000A | MSC Prai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-02-10 | N/A
7000A-MAG(M14)-001&002+ | MIP2023.274 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 7000A-MAG(M14)-001&002+ | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-02-20 | N/A
7000A-MAG(M14)-001&002+ | MIP2023.274 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 7000A-MAG(M14)-001&002+ | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-02-20 | N/A
9999A-MAG(M14)-001&002+ | MIP2023.275 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 9999A-MAG(M14)-001&002+ | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | Jun | N/A | 2024-02-20 | N/A
9999A-MAG(M14)-001&002+ | MIP2023.275 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- 9999A-MAG(M14)-001&002+ | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | Jun | N/A | 2024-02-20 | N/A
NAR01_i+ | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | N/A | 4992A | Pendang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NAR01_i+ | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | N/A | 4946A | Bukit Selambau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NAR01_i+ | MIP2023.276 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_i+ | N/A | N/A | 4966A | Kulim Hi-Tech Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4998A | Air Itam Kedah | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4660A | KTM A.setar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4938A | Taman Orkid | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
NAR01_ii+ | MIP2023.277 CD Digi NIC FTK ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- NAR01_ii+ | N/A | N/A | 4606A | KTM Padang Besar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Area 163 | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
Area 163 | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
Area 163 | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
Area 163 | MIP2023.347 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Area 163_Redeploy 2x10G card to MAC from buffer | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
C0210P | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | N/A | N/A | 1253A | Plaza Pengkalen | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-15 | N/A
C0210P | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | N/A | N/A | 1859A | Midvalleycas | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-15 | N/A
C0210P | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | N/A | N/A | 1253A | Plaza Pengkalen | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-15 | N/A
C0210P | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | N/A | N/A | 1253A | Plaza Pengkalen | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-15 | N/A
C0210P | MIP2023.349 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_C0210P Breakring | N/A | N/A | 2878A | Mont Kiara | ADVANCE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-15 | N/A
Colo Ring 8 | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Colo Ring 8 | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Colo Ring 8 | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Colo Ring 8 | MIP2023.350 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 8_Swap MAC and MAG (require IPCore) | N/A | N/A | 2021B | DiGi TOC (Lot 43) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
Colo Ring 12 | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-14 | N/A
Colo Ring 12 | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-14 | N/A
Colo Ring 12 | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-14 | N/A
Colo Ring 12 | MIP2023.351 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_Colo Ring 12 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-14 | N/A
7000A-MAG | MIP2023.352 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_7000A-MAG (require IPCore) | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-02-08 | N/A
7000A-MAG | MIP2023.352 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_7000A-MAG (require IPCore) | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-02-08 | N/A
9999A-MAG | MIP2023.353 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_9999A-MAG (require IPCore) | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-02-13 | N/A
9999A-MAG | MIP2023.353 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_9999A-MAG (require IPCore) | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-02-13 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1006A | JBA Gombak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1304A | MMA | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1745A | Baitumal | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1458A | Endah Parade | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1475A | BSC Sri Kembangan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
CAR04 | MIP2023.354 CD Digi NIC FTK ES BOQ- 2024Q1 ZTE(754 sites)_CAR04_PE-MCR Swap MAG and purchase 100G board (IPCore) | N/A | N/A | 1475A | BSC Sri Kembangan | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4985A | BALING TOWN | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4988A | Kupang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4968A | Inokom Kulim | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4956B | KUALA PEGANG | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4950B | Pulai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4986A | Binjul | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
N201+ | MIP2024.14 CD Digi NIC ES BOQ- 2023Q4 ZTE 2nd acceleration (600 sites)- N201+ Break Ring | N/A | N/A | 4685B | Kg Sg Karangan | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-02-08 | N/A
EL405 | MIP2023.252 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL405 | N/A | N/A | 8183A | Chini Pusat (Maxis) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL405 | MIP2023.252 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL405 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL405 | MIP2023.252 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL405 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL407 | MIP2023.253 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL407 | N/A | N/A | 8163A | Bukit Harimau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL407 | MIP2023.253 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL407 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL407 | MIP2023.253 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL407 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL408 | MIP2023.254 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL408 | N/A | N/A | 8165A | Bdr Tun Razak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL408 | MIP2023.254 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL408 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL408 | MIP2023.254 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL408 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL409 | MIP2023.255 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL409 | N/A | N/A | 8089A | Bukit Ridan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL409 | MIP2023.255 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL409 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL409 | MIP2023.255 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL409 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL411 | MIP2023.256 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL411 | N/A | N/A | 8501A | ECE KM138.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL411 | MIP2023.256 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL411 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL411 | MIP2023.256 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL411 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL419 | MIP2023.257 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL419 | N/A | N/A | 8998A | Kerayung | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL419 | MIP2023.257 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL419 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
EL419 | MIP2023.257 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_EL419 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SL401 | MIP2023.258 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL401 | N/A | N/A | 1506A | Bkt Beruang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SL401 | MIP2023.258 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL401 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SL401 | MIP2023.258 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL401 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
L408P | MIP2023.259 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL408P | N/A | N/A | 2124B | Zoo Melaka | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
L408P | MIP2023.259 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL408P | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
L408P | MIP2023.259 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL408P | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SL703 | MIP2023.260 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL703 | N/A | N/A | 6029B | SAJ Seri Alam F | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SL703 | MIP2023.260 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL703 | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
SL703 | MIP2023.260 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL703 | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
L729P | MIP2023.261 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL729P | N/A | N/A | 6544A | Tmn Flora Height | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
L729P | MIP2023.261 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL729P | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
L729P | MIP2023.261 CD Digi NIC ES BOQ- 2024Q1 HW_1068 accelerated sites IPRAN break ring_MAC-LL_SL729P | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-02-20 | N/A
1029B-LL | MIP2023.345 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1029B-LL | N/A | N/A | 1029B | Wisma Central | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-07 | N/A
1029B-LL | MIP2023.345 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1029B-LL | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-07 | N/A
1273A-LL | MIP2023.346 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1273A-LL | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-07 | N/A
1273A-LL | MIP2023.346 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1273A-LL | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-02-07 | N/A
1273A-LL | MIP2023.346 CD Digi NIC ES BOQ- 2024Q1 ZTE(754 sites)_1273A-LL | N/A | N/A | 1273A | Binova | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-02-07 | N/A
Colocated-Ring-3 | MIP2024.18 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- Colocated-Ring-3 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
Colocated-Ring-3 | MIP2024.18 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- Colocated-Ring-3 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
E207 | MIP2024.19 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E207 | N/A | N/A | 8303A | Bkt Bauk | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
E207 | MIP2024.19 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E207 | N/A | N/A | 8368A | Serating | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
E207 | MIP2024.19 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E207 | N/A | N/A | 8303A | Bkt Bauk | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
E209 | MIP2024.20 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E209 | N/A | N/A | 8429B | Bkt Payung 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
E209 | MIP2024.20 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E209 | N/A | N/A | 8368A | Serating | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
E209 | MIP2024.20 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E209 | N/A | N/A | 8368A | Serating | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
E301 | MIP2024.21 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E301 | N/A | N/A | 8088A | Sg. Beto | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
E301 | MIP2024.21 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E301 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
E301 | MIP2024.21 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- E301 | N/A | N/A | 8712A | Kg Jawa Pekan (trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8367A | Bukit Kechil | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8285A | Bukit Bunga | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8224A | Pasir Puteh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8288B | Bukit Panau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8211A | Wakaf Che Yeh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EAR01_1 & EAR01_3 | MIP2024.22 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EAR01_1 & EAR01_3 | N/A | N/A | 8263A | Pasir Mas Town | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
EL404 | MIP2024.24 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EL404 | N/A | N/A | 8020A | Tempoyang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
EL404 | MIP2024.24 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EL404 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
EL404 | MIP2024.24 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- EL404 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S001 | MIP2024.25 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S001 | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S001 | MIP2024.25 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S001 | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S002 | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S002 | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S002 | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S002 | MIP2024.26 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S002 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S305 | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | N/A | N/A | 6104A | Bukit Kelicap | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S305 | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | N/A | N/A | 2402B | Pagoh Highway | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S305 | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | N/A | N/A | 6701A | Parit Sulong (Trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S305 | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | N/A | N/A | 6093A | SRI MEDAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S305 | MIP2024.27 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S305 | N/A | N/A | 6088A | ABI | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S306M | MIP2024.28 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S306M | N/A | N/A | 6405A | Sri Bunian | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S306M | MIP2024.28 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S306M | N/A | N/A | 6104A | Bukit Kelicap | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S306M | MIP2024.28 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S306M | N/A | N/A | 6104A | Bukit Kelicap | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S313P_2 | MIP2024.29 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S313P_2 | N/A | N/A | 1554A | Rumbia | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | MIP2024.29 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S313P_2 | N/A | N/A | 1553A | Umbai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | N/A | N/A
S313P_2 | MIP2024.29 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S313P_2 | N/A | N/A | 1533A | Bkt Duyung | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | N/A | N/A
S403 | MIP2024.30 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S403 | N/A | N/A | 1659A | Bahau Tower | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S403 | MIP2024.30 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S403 | N/A | N/A | 1659A | Bahau Tower | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S403 | MIP2024.30 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S403 | N/A | N/A | 6212A | KTM GEMAS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6151A | MERSING | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-13 | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6166A | FELDA NITAR 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-13 | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6160A | Bkt Tinggi | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6138A | KAHANG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-13 | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6134A | KLUANG INDUSTRY (PROFINA) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6616A | Tmn Seri Permai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-13 | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6126A | KTM KLUANG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S504M | MIP2024.31 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S504M | N/A | N/A | 6369A | Sri Saujana | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
S607M | MIP2024.32 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S607M | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S607M | MIP2024.32 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S607M | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
S607M | MIP2024.32 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- S607M | N/A | N/A | 6380A | Desaru Resort-100Q4(D Harmoni) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 1554A | Rumbia | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 6502A | Nusa Perintis(Watertank) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 1553A | Umbai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 6405A | Sri Bunian | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR03_i & SAR03_iii | MIP2024.33 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR03_i & SAR03_iii | N/A | N/A | 6104A | Bukit Kelicap | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR06 | MIP2024.34 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR06 | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR06 | MIP2024.34 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR06 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SAR06 | MIP2024.34 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SAR06 | N/A | N/A | 6707A | Kg Jambi (Trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SL408P | MIP2024.35 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL408P | N/A | N/A | 2124B | Zoo Melaka | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Melaka | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SL408P | MIP2024.35 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL408P | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SL408P | MIP2024.35 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL408P | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SL732P | MIP2024.36 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL732P | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
SL732P | MIP2024.36 CD Digi NIC ES BOQ- Huawei 2024 Q2-Q3- SL732P | N/A | N/A | 6000A | MSC JB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | N/A
3571B-LL | MIP2024.38 CD Digi NIC ES BOQ- ZTE 2024 Q2- 3571B-LL | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
3571B-LL | MIP2024.38 CD Digi NIC ES BOQ- ZTE 2024 Q2- 3571B-LL | N/A | N/A | 3571B | National Stadium Bukit Jalil | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
AREA 154 | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
AREA 154 | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | N/A | N/A | 1855B | TPM (AsiaSpace) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
AREA 154 | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | N/A | N/A | 1458A | Endah Parade | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
AREA 154 | MIP2024.39 CD Digi NIC ES BOQ- ZTE 2024 Q2- AREA 154 | N/A | N/A | 1458A | Endah Parade | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0211+ | MIP2024.40 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0211+ | N/A | N/A | 1851A | KL Plaza 4th floor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0211+ | MIP2024.40 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0211+ | N/A | N/A | 1859A | Midvalleycas | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0211+ | MIP2024.40 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0211+ | N/A | N/A | 2888A | Plaza Sentral Indoor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0515+ | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | N/A | N/A | 2448A | Asmah Tower | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0515+ | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | N/A | N/A | 2424A | PUAS Tmn Tun Perak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0515+ | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | N/A | N/A | 2024A | Bdr Mahkota Cheras | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0515+ | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | N/A | N/A | 1902B | Bdr Sg Long 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0515+ | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | N/A | N/A | 1039A | Cheras Jaya 2202 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0515+ | MIP2024.41 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0515+ | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0607P+ | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0607P+ | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | N/A | N/A | 1196A | JBA Puchong | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0607P+ | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | N/A | N/A | 1408A | Puchong Jaya | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0607P+ | MIP2024.42 CD Digi NIC ES BOQ- ZTE 2024 Q2- C0607P+ | N/A | N/A | 1402A | Jln Ind Puchong | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
Colocated-Ring-1+ | MIP2024.43 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-1+ | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | July | N/A | 2024-03-29 | N/A
Colocated-Ring-1+ | MIP2024.43 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-1+ | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | July | N/A | 2024-03-29 | N/A
Colocated-Ring-4+ | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
Colocated-Ring-4+ | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
Colocated-Ring-4+ | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
Colocated-Ring-4+ | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
Colocated-Ring-4+ | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
Colocated-Ring-4+ | MIP2024.44 CD Digi NIC ES BOQ- ZTE 2024 Q2- Colocated-Ring-4+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CT0241P+ | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CT0241P+ | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | N/A | N/A | 1918A | Damansara Intan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CT0241P+ | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | N/A | N/A | 1197A | JBAEFF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CT0241P+ | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | N/A | N/A | 1197A | JBAEFF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CT0241P+ | MIP2024.45 CD Digi NIC ES BOQ- ZTE 2024 Q2- CT0241P+ | N/A | N/A | 1211A | KDU | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
MAC Ring 15/ C21+ | MIP2024.46 CD Digi NIC ES BOQ- ZTE 2024 Q2- MAC Ring 15/ C21+ | N/A | N/A | 1458A | Endah Parade | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
MAC Ring 15/ C21+ | MIP2024.46 CD Digi NIC ES BOQ- ZTE 2024 Q2- MAC Ring 15/ C21+ | N/A | N/A | 2502A | PUAS Bdr Tun Razak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N104+ | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | N/A | N/A | 4995A | Changloon UUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N104+ | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | N/A | N/A | 4995A | Changloon UUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N104+ | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | N/A | N/A | 4992A | Pendang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N104+ | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | N/A | N/A | 4991A | UUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N104+ | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | N/A | N/A | 4672A | CHANGLOON | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N104+ | MIP2024.47 CD Digi NIC ES BOQ- ZTE 2024 Q2- N104+ | N/A | N/A | 4665A | Jitra | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N107+ | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | N/A | N/A | 4604A | JBA KUAL PERLIS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N107+ | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | N/A | N/A | 4601A | Federal Kangar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N107+ | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | N/A | N/A | 4612A | Jalan Kaki Bukit | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N107+ | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | N/A | N/A | 4613A | Berseri Perlis | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N107+ | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | N/A | N/A | 4998A | Air Itam Kedah | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N107+ | MIP2024.48 CD Digi NIC ES BOQ- ZTE 2024 Q2- N107+ | N/A | N/A | 4606A | KTM Padang Besar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N405+ | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | N/A | N/A | 4432A | KTM Sg Siput | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N405+ | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | N/A | N/A | 4379A | Bukit Mercu | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N405+ | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | N/A | N/A | 4378A | Jerlun Tower | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N405+ | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | N/A | N/A | 4374A | LAP Talang RDD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N405+ | MIP2024.49 CD Digi NIC ES BOQ- ZTE 2024 Q2- N405+ | N/A | N/A | 4455A | KTM Taiping | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N408+ | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | N/A | N/A | 4506A | Perak Taipu Assc | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N408+ | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | N/A | N/A | 4546A | KWSP Ipoh RDD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N408+ | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | N/A | N/A | 4515A | TG RAMBUTAN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N408+ | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | N/A | N/A | 4432A | KTM Sg Siput | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N408+ | MIP2024.50 CD Digi NIC ES BOQ- ZTE 2024 Q2- N408+ | N/A | N/A | 4493A | KTM IPOH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N411+ | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | N/A | N/A | 4432A | KTM Sg Siput | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N411+ | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | N/A | N/A | 4433A | LAP Sg Siput | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N411+ | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | N/A | N/A | 4377B | Karai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N411+ | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | N/A | N/A | 4373A | KTM K.Kangsar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
N411+ | MIP2024.51 CD Digi NIC ES BOQ- ZTE 2024 Q2- N411+ | N/A | N/A | 4455A | KTM Taiping | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
7124A-MAG-001&002 | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
7124A-MAG-001&002 | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
7124A-MAG-001&002 | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | N/A | N/A | 7124A | Land Trig Hill | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
7124A-MAG-001&002 | MIP2024.52 CD Digi NIC ES BOQ- ZTE 2024 Q2- 7124A-MAG-001&002 | N/A | N/A | 7124A | Land Trig Hill | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
9368A-MAG-001&002 | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | N/A | N/A | 9368A | Salim Road Sacofa | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
9368A-MAG-001&002 | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | N/A | N/A | 9368A | Salim Road Sacofa | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
9368A-MAG-001&002 | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
9368A-MAG-001&002 | MIP2024.53 CD Digi NIC ES BOQ- ZTE 2024 Q2- 9368A-MAG-001&002 | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-i+ | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | N/A | N/A | 1253A | Plaza Pengkalen | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-i+ | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | N/A | N/A | 1851A | KL Plaza 4th floor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-i+ | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | N/A | N/A | 1859A | Midvalleycas | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-i+ | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-i+ | MIP2024.54 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-i+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-ii+ | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | N/A | N/A | 1172A | Glomac | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-ii+ | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | N/A | N/A | 1918A | Damansara Intan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-ii+ | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | N/A | N/A | 1859A | Midvalleycas | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-ii+ | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
CAR02-ii+ | MIP2024.55 CD Digi NIC ES BOQ- ZTE 2024 Q2- CAR02-ii+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR01_iii+ | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | N/A | N/A | 4606A | KTM Padang Besar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR01_iii+ | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | N/A | N/A | 4995A | Changloon UUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR01_iii+ | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | N/A | N/A | 4992A | Pendang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR01_iii+ | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR01_iii+ | MIP2024.56 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR01_iii+ | N/A | N/A | 4521A | MSC Ipoh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR02_ii+ | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR02_ii+ | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR02_ii+ | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | N/A | N/A | 4985A | BALING TOWN | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR02_ii+ | MIP2024.57 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR02_ii+ | N/A | N/A | 8282B | Tasik Pergau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR04_ii+ | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR04_ii+ | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | N/A | N/A | 4521A | MSC Ipoh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR04_ii+ | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | N/A | N/A | 4493A | KTM IPOH | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR04_ii+ | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | N/A | N/A | 4432A | KTM Sg Siput | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
NAR04_ii+ | MIP2024.58 CD Digi NIC ES BOQ- ZTE 2024 Q2- NAR04_ii+ | N/A | N/A | 4455A | KTM Taiping | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
C0126 | MIP2024.59 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0126 | N/A | N/A | 1364B | Subang Bestari | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
C0126 | MIP2024.59 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0126 | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
C0126 | MIP2024.59 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0126 | N/A | N/A | 1409A | Kota Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-04-30 | N/A
1063B-Linear+ & Area 79_2+ | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | N/A | N/A | 1851A | KL Plaza 4th floor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
1063B-Linear+ & Area 79_2+ | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | N/A | N/A | 1461A | Shaw Parade | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
1063B-Linear+ & Area 79_2+ | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | N/A | N/A | 1745A | Baitumal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
1063B-Linear+ & Area 79_2+ | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | N/A | N/A | 1745A | Baitumal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
1063B-Linear+ & Area 79_2+ | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | N/A | N/A | 1722E | UE3 Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | WILAYAH PERSEKUTUAN KUALA LUMPUR | N/A | N/A | N/A | N/A | N/A | N/A
1063B-Linear+ & Area 79_2+ | MIP2024.60 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1063B-Linear+ & Area 79_2+ | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
1288A-LL+ | MIP2024.61 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1288A-LL+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
1288A-LL+ | MIP2024.61 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1288A-LL+ | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
1288A-LL+ | MIP2024.61 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 1288A-LL+ | N/A | N/A | 1288A | JBA Wangsa.Maju | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
9294A-LL+ (3x1G) | MIP2024.62 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9294A-LL+ (3x1G) | N/A | N/A | 9294A | Marudi (SACOFA) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2024-05-02 | N/A
9710A-LL+ (2 x 1G) | MIP2024.63 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9710A-LL+ (2 x 1G) | N/A | N/A | 9710A | TT844 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
C0319P+ | MIP2024.64 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0319P+ | N/A | N/A | 1271A | Risda | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
C0319P+ | MIP2024.64 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0319P+ | N/A | N/A | 1270A | Puteri Park Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
C0407P+ | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | N/A | N/A | 1304A | MMA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
C0407P+ | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | N/A | N/A | 1745A | Baitumal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
C0407P+ | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | N/A | N/A | 1737A | Bernama - Rack 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
C0407P+ | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | N/A | N/A | 1737A | Bernama - Rack 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
C0407P+ | MIP2024.65 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C0407P+ | N/A | N/A | 1266A | Sucasa | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
C1101+ | MIP2024.66 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C1101+ | N/A | N/A | 8709A | Bentong (Trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
C1101+ | MIP2024.66 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C1101+ | N/A | N/A | 2070B | Sri Gombak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
C1101+ | MIP2024.66 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- C1101+ | N/A | N/A | 2070B | Sri Gombak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CT0316P+ | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | N/A | N/A | 1270A | Puteri Park Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CT0316P+ | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | N/A | N/A | 1271A | Risda | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CT0316P+ | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | N/A | N/A | 1747A | Jln Ampng Besar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CT0316P+ | MIP2024.67 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT0316P+ | N/A | N/A | 2805A | Ampang City Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CT031P_2+ | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | N/A | N/A | 1465A | JBA TMN SEGAR L1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CT031P_2+ | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | N/A | N/A | 1270A | Puteri Park Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CT031P_2+ | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | N/A | N/A | 1903B | Kemacahaya | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CT031P_2+ | MIP2024.68 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CT031P_2+ | N/A | N/A | 1905B | Ampang Lookout Point | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
N112PM+ | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | N/A | N/A | 4606A | KTM Padang Besar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | N/A | N/A
N112PM+ | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | N/A | N/A | 4605A | KTM Arau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | N/A | N/A
N112PM+ | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | N/A | N/A | 4606B | Arau Trunk | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | N/A | N/A
N112PM+ | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | N/A | N/A | 4995A | Changloon UUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | N/A | N/A
N112PM+ | MIP2024.69 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N112PM+ | N/A | N/A | 4606A | KTM Padang Besar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | N/A | N/A
N304+ | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | N/A | N/A | 4331A | Bagan Serai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N304+ | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | N/A | N/A | 4310A | Matang Acheh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N304+ | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | N/A | N/A | 4331A | Bagan Serai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N304+ | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | N/A | N/A | 4391B | Sg Gedung (Maxis) RDD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N304+ | MIP2024.70 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N304+ | N/A | N/A | 4736A | Jebong | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N305+ | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | N/A | N/A | 4521A | MSC Ipoh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N305+ | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | N/A | N/A | 4734A | Kg Teluk Kepayang (trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N305+ | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | N/A | N/A | 4490A | Kg Merbau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | PERAK | N/A | N/A | N/A | N/A | N/A | N/A
N305+ | MIP2024.71 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N305+ | N/A | N/A | 4310A | Matang Acheh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4472A | Durian Sebatang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4473A | Hutan Melintang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4472A | Durian Sebatang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4580B | Jenderata Perak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4740B | Hutan Melintang Industry | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4470B | Bagan Pasir | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N503+ | MIP2024.72 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N503+ | N/A | N/A | 4473A | Hutan Melintang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N602+ | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | N/A | N/A | 4440B | Tapah Road | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N602+ | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | N/A | N/A | 4412A | KTM Sungkai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N602+ | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | N/A | N/A | 4732A | Ladang Tapah (trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N602+ | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | N/A | N/A | 4442A | Bukit Temoh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N602+ | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | N/A | N/A | 4311A | Dunlop Kliniktrak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
N602+ | MIP2024.73 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- N602+ | N/A | N/A | 4414A | SUNGKAI LAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
New Ring_7+ | MIP2024.74 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- New Ring_7+ | N/A | N/A | 4517A | Pengkalan Industry | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
New Ring_7+ | MIP2024.74 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- New Ring_7+ | N/A | N/A | 4323A | LAP Bemban | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
7100A-MAG-LL+ | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | N/A | N/A | 7100A | Muhibah Lahad Datu | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | N/A | N/A
7100A-MAG-LL+ | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | N/A | N/A | 7100A | Muhibah Lahad Datu | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | N/A | N/A
7100A-MAG-LL+ | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | N/A | N/A
7100A-MAG-LL+ | MIP2024.75 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 7100A-MAG-LL+ | N/A | N/A | 7000A | KK MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | N/A | N/A
9074A-MAG-LL+ | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | N/A | N/A | 9074A | MSC Miri | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9074A-MAG-LL+ | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | N/A | N/A | 9074A | MSC Miri | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9074A-MAG-LL+ | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9074A-MAG-LL+ | MIP2024.76 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9074A-MAG-LL+ | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9106A-MAG-LL+ | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | N/A | N/A | 9106A | Bkt Nyabau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9106A-MAG-LL+ | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | N/A | N/A | 9106A | Bkt Nyabau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9106A-MAG-LL+ | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
9106A-MAG-LL+ | MIP2024.77 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- 9106A-MAG-LL+ | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | N/A
CAR03 | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CAR03 | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CAR03 | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | N/A | N/A | 1002A | Sri Murni | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CAR03 | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | N/A | N/A | 1465A | JBA TMN SEGAR L1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CAR03 | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | N/A | N/A | 1207A | Puteri Park Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CAR03 | MIP2024.78 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR03 | N/A | N/A | 1271A | Risda | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
CAR11+ | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | N/A | N/A | 8709A | Bentong (Trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
CAR11+ | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | N/A | N/A | 2070B | Sri Gombak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
CAR11+ | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | N/A | N/A | 8000A | MSC Kuantan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
CAR11+ | MIP2024.79 CD Digi NIC ES BOQ- NIC ZTE 2024 Q3-Q4- CAR11 | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-05-06 | N/A
1063B-Linear (in PFS swap plan) | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
1063B-Linear (in PFS swap plan) | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | N/A | N/A | 1851A | KL Plaza 4th floor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
1063B-Linear (in PFS swap plan) | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | N/A | N/A | 1246A | Complex Nagaria | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
1063B-Linear (in PFS swap plan) | MIP2024.37 CD Digi NIC ES BOQ- ZTE 2024 Q2- 1063B-Linear (in PFS swap plan) | N/A | N/A | 1063B | BERJAYA TIMES SQUARE | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | 2024-03-29 | N/A
E207 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8381A | Jambu Bongkok (Celcom) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E207 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8303A | Bkt Bauk | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E207 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8303A | Bkt Bauk | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E207 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8301A | UMNO Dungun | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E209 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8368A | Serating | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E209 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8356A | Padang Midin | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E209 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8360A | Bkt Chendering | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E301 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8712A | Kg Jawa Pekan (trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E301 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8712A | Kg Jawa Pekan (trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E301 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8087A | N/A | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E301 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8085A | N/A | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E301 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8067A | N/A | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E301 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8038A | N/A | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E402 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8120A | Lanchang | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E402 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8072A | Bkt Mikro | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E402 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8072A | Bkt Mikro | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E402 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 8092A | Jalan Karak Mentakab | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
S305 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6701A | Parit Sulong (Trunk) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
S306M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6104A | Bukit Kelicap | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
S306M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6409A | Air Baloi | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-27 | N/A | 2024-03-27 | 2024-03-21
S403 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 1659A | Bahau Tower | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-06-11 | N/A | 2024-03-27 | 2024-03-21
S403 | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 2384B | PASIR BESAR | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | 2024-06-12 | N/A | 2024-03-27 | 2024-03-21
S504M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6151A | MERSING | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-13 | N/A | 2024-03-27 | 2024-03-21
S504M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6166A | FELDA NITAR 2 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-14 | N/A | 2024-03-27 | 2024-03-21
S504M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6160A | N/A | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
S504M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6138A | KAHANG | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-12 | N/A | 2024-03-27 | 2024-03-21
S504M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6616A | Tmn Seri Permai | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-11 | N/A | 2024-03-27 | 2024-03-21
S607M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6374A | Air Tawar 4 | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-26 | N/A | 2024-03-27 | 2024-03-21
S607M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6380A | Desaru Resort-100Q4(D Harmoni) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-25 | N/A | 2024-03-27 | 2024-03-21
S607M | MIP2024.003 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC Huawei Q2Q3 2024 | N/A | N/A | 6380A | Desaru Resort-100Q4(D Harmoni) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-25 | N/A | 2024-03-27 | 2024-03-21
E207 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 8303A | Bkt Bauk | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
E402 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 8701A | Jambu Rias (Trunk) | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
EAR01_1 & EAR01_3 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 8282B | Tasik Pergau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
EAR01_1 & EAR01_3 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 8288B | Bukit Panau | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
EAR01_1 & EAR01_3 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 8224A | Pasir Puteh | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
EAR01_1 & EAR01_3 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 8367A | Bukit Kechil | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Terengganu | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
S305 | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 2402B | Pagoh Highway | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
SAR03_i & SAR03_iii | MIP2024.004 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG Huawei Q2Q3 2024 | N/A | N/A | 6502A | Nusa Perintis(Watertank) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-21
C0126 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 1207A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | TBA
C0126 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 1364B | Subang Bestari | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | TBA
C1101 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 2070B | Sri Gombak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | TBA
1288A-LL | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 1288A | JBA Wangsa.Maju | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | TBA
1288A-LL | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 1288A | JBA Wangsa.Maju | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | TBA
9318A-LL | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 9318A | Kpg Merdang Gayam (Sacofa) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | N/A | TBA
N304 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4736A | Jebong | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N304 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4331A | Bagan Serai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N304 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4331A | Bagan Serai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N305 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4734A | Kg Teluk Kepayang (trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N305 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4734A | Kg Teluk Kepayang (trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N305 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4490A | Kg Merbau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | PERAK | N/A | N/A | N/A | N/A | N/A | TBA
N305 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4489A | Changkat Kruing RDD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N305 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4323A | LAP Bemban | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N305 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4323A | LAP Bemban | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N503 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4470B | Bagan Pasir | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N503 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4473A | Hutan Melintang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N503 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4472A | Durian Sebatang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N503 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4580B | Jenderata Perak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N602 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4311A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N602 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4442A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N602 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4732A | Ladang Tapah (trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N602 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4414A | SUNGKAI LAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
New Ring_7 | MIP2024.017 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q3Q4 2024 | N/A | N/A | 4517A | Pengkalan Industry | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
7100-MAG-LL | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 7100A | Muhibah Lahad Datu | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | N/A | TBA
C0407P | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 1304A | MMA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | TBA
C1101 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 8709A | Bentong (Trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | TBA
C1101 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 2070B | Sri Gombak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | TBA
N304 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 4310A | Matang Acheh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N304 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 4331A | Bagan Serai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N503 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 4473A | Hutan Melintang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N503 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 4472A | Durian Sebatang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N602 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 4412A | KTM Sungkai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
N602 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 4440B | Tapah Road | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | TBA
CAR03 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 1271A | Risda | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | TBA
CAR03 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 1270A | Puteri Park Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | TBA
CAR03 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 1465A | JBA TMN SEGAR L1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | TBA
CAR03 | MIP2024.016 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q3Q4 2024 | N/A | N/A | 1002A | Sri Murni | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | TBA
C0515+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2024 | N/A | N/A | 2024A | N/A | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-06-05 | N/A | 2024-03-29 | 2024-03-23
MAC Ring 15/ C21+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2025 | N/A | N/A | 2502A | PUAS Bdr Tun Razak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | 2024-06-06 | N/A | 2024-03-29 | 2024-03-23
MAC Ring 15/ C21+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2026 | N/A | N/A | 2502A | PUAS Bdr Tun Razak | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | 2024-06-06 | N/A | 2024-03-29 | 2024-03-23
N104 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2027 | N/A | N/A | 4995A | Changloon UUM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N104 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2028 | N/A | N/A | 4991A | UUM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N104 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2029 | N/A | N/A | 4672A | CHANGLOON | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N104 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2030 | N/A | N/A | 4665A | Jitra | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N107 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2031 | N/A | N/A | 4604A | JBA KUAL PERLIS | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N107 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2032 | N/A | N/A | 4601A | N/A | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N107 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2033 | N/A | N/A | 4612A | Jalan Kaki Bukit | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N107 | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2034 | N/A | N/A | 4613A | Berseri Perlis | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perlis | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N405+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2035 | N/A | N/A | 4379A | Bukit Mercu | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N405+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2036 | N/A | N/A | 4378A | Jerlun Tower | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N405+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2037 | N/A | N/A | 4374A | LAP Talang RDD | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N408+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2038 | N/A | N/A | 4506A | Perak Taipu Assc | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N408+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2039 | N/A | N/A | 4546A | KWSP Ipoh RDD | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N408+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2040 | N/A | N/A | 4546A | KWSP Ipoh RDD | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N408+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2041 | N/A | N/A | 4515A | TG RAMBUTAN | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N411+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2042 | N/A | N/A | 4433A | LAP Sg Siput | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N411+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2041 | N/A | N/A | 4377B | Karai | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
N411+ | MIP2024.005 CD Digi FTK NIC ES BOQ - ATN910C-M for MAC ZTE 1255 site Q2 2042 | N/A | N/A | 4373A | KTM K.Kangsar | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-23
7124A-MAG-001&002 | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | N/A | 7124A | Land Trig Hill | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2024-03-29 | TBA
NAR01_iii | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | N/A | 4995A | Changloon UUM | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Kedah | N/A | N/A | N/A | N/A | 2024-03-29 | TBA
NAR04_ii+ | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | N/A | 4493A | KTM IPOH | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | TBA
NAR04_ii+ | MIP2024.006 CD Digi FTK NIC ES BOQ - NE8000(M14) for MAG ZTE Q2 2024 | N/A | N/A | 4432A | KTM Sg Siput | FO&T | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | 2024-03-29 | TBA
CAR01_01 | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | N/A | N/A | 1409A | Kota Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
CAR01_01 | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | N/A | N/A | 1085A | Pekan Meru | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
CAR01_01 | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | N/A | N/A | 2777C | JBA Bkt Lipat (TX REL - Celcom) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
CAR01_01 | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | N/A | N/A | 2021B | DiGi TOC (Lot 43) | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
CAR01_01 | MIP2024.07 CD Digi NIC ES BOQ- MAG Ring CAR01 ring from 40G to 100G | N/A | N/A | 1049B | MSC Damansara | BBAND | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | 2024-06-11 | N/A | 2024-02-20 | N/A
CAR02 | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-08-14 | N/A
CAR02 | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | N/A | N/A | 1172A | Glomac | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-08-14 | N/A
CAR02 | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | N/A | N/A | 1253A | Plaza Pengkalen | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-08-14 | N/A
CAR02 | ML142230 MIP2022.134_ES_BOQ_to_support_CAR02_break_ring_and_PE-MCR_re-eng | N/A | N/A | 1859A | Midvalleycas | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | Jun | N/A | 2023-08-14 | N/A
7124A | MIP2021.33 ES BOQ for IBEAM relocation of Trig Hill 7124A MAC to 7570A Kg. Garinono | N/A | N/A | 7124A | Land Trig Hill | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | N/A | N/A | 2021-03-05 | N/A
CAR05 | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-24 | 2024-05-24 | 2021-08-26 | N/A
CAR05 | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-24 | 2024-05-24 | 2021-08-26 | N/A
CAR05 | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1110A | Berjaya Industrial Park | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-24 | 2024-05-24 | 2021-08-26 | N/A
CAR05 | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1128A | Kg Ola Lempik | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-24 | 2024-05-24 | 2021-08-26 | N/A
CAR05 | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1037A | JBA Bangi | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-24 | 2024-05-24 | 2021-08-26 | N/A
CAR05 | 64464 MIP2021.120_ES_BOQ_to_support_for_CAR05_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1039A | Cheras Jaya 2202 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-05-24 | 2024-05-24 | 2021-08-26 | N/A
CAR08 | MIP2024.94 CD Digi NIC ES BOQ- CAR08 PE-MCR Migration | N/A | N/A | CAR02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
EAR05 | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | N/A | N/A | 8173A | Bandar Pusat Jengka | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
EAR05 | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | N/A | N/A | 8112A | Bukit Istana | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
EAR05 | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | N/A | N/A | 8527A | Jengka 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
EAR05 | MIP2024.91 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR05 (20G expansion + PE-MCR) | N/A | N/A | 8528A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 1049B | MSC Damansara | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Wilayah Persekutuan Kuala Lumpur | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | EAR07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 8215B | Dabong | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 8240A | Gua Musang Town (Celcom) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 8038Z | Sg.Berok | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Kelantan | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 8110Z | Pos Mensun | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 8002Z | Pos Betau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
EAR07 | MIP2024.92 CD Digi NIC ES BOQ- Huawei 2024 Q4- EAR07 (40G expansion + PE-MCR) | N/A | N/A | 8120Z | Kg.Bt Talam | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
E604 | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | N/A | N/A | 8173A | Bandar Pusat Jengka | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
E604 | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | N/A | N/A | 8112A | Bukit Istana | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
E604 | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | N/A | N/A | 8527A | Jengka 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
E604 | MIP2024.93 CD Digi NIC ES BOQ- Huawei 2024 Q4- E604 (BreakRing) | N/A | N/A | 8528A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | N/A | N/A | N/A | N/A
SAR04 | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-19 | N/A | 2023-08-01 | N/A
SAR04 | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | N/A | N/A | 1659A | Bahau Tower | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-19 | N/A | 2023-08-01 | N/A
SAR04 | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | N/A | N/A | 6911C | KTM LABIS REL | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-19 | N/A | 2023-08-01 | N/A
SAR04 | 69549 MIP2021.138_ES_BOQ_to_support_for_SAR04_Dual_Uplink_migration_PE-MCR | N/A | N/A | 6442A | Airport Senai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Johor | N/A | N/A | 2024-06-19 | N/A | 2023-08-01 | N/A
9106A-MAG-LL | MIP2023.146 CD Digi NIC ES BOQ- SACOFA trunk upgrade and PE-MCR migration for 9106A Bukit Nyabau (SACOFA) | N/A | N/A | 9106A | Bkt Nyabau | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | 2024-05-17 | 2024-05-17 | 2023-08-18 | N/A
9368A-MAG-LL | MIP2023.147 CD Digi NIC ES BOQ- SACOFA trunk upgrade and PE-MCR migration for 9368A Salim Road Sacofa | N/A | N/A | 9368A | Salim Road Sacofa | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | 2024-06-04 | N/A | 2023-08-22 | N/A
CAR11 | MIP2023.144 CD Digi NIC ES BOQ- CAR11 MAG ring upgrade via DWDM and PE-MCR migration | N/A | N/A | 2070B | Sri Gombak | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | 2024-06-21 | N/A | 2023-09-06 | N/A
CAR11 | MIP2023.144 CD Digi NIC ES BOQ- CAR11 MAG ring upgrade via DWDM and PE-MCR migration | N/A | N/A | 8709A | Bentong (Trunk) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Eastern | Pahang | N/A | N/A | 2024-06-21 | N/A | 2023-09-06 | N/A
9151B-LL | MIP2023.225 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_9151B-LL (Upgrade LL) | N/A | N/A | 9999A | Kuching MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | N/A | N/A | 2023-11-16 | N/A
9151B-LL | MIP2023.225 CD Digi NIC ES BOQ- Accelerated Sites Break Ring ZTE_9151B-LL (Upgrade LL) | N/A | N/A | 9151B | TM Demak Laut (REL) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | SARAWAK | N/A | N/A | N/A | N/A | 2023-11-16 | N/A
9074A-MAG-LL | MIP2023.148 CD Digi NIC ES BOQ- SACOFA trunk upgrade and PE-MCR migration for 9074A MSC Miri | N/A | N/A | 9074A | MSC Miri | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sarawak | Sarawak | N/A | N/A | 2024-05-23 | 2024-05-23 | 2023-08-08 | N/A
7205A-MAG-LL | MIP2022.49 ES BOQ for CTS trunk upgrade and PE-MCR migration for 7205A Mile 15 Tawau and 7124A Trig Hill Sandakan | N/A | N/A | 7205A | MILE 15 TAWAU | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sabah | Sabah | N/A | N/A | 2024-06-11 | N/A | 2022-06-30 | N/A
CAR09 | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CAR09 | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | N/A | N/A
CAR09 | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 | N/A | N/A | 1124A | Batu 15 Banting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CAR09 | MIP2024.106 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR09 | N/A | N/A | 1690A | Bukit Pelandok (DWDM) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | N/A | N/A
SAR02 | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
SAR02 | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | N/A | N/A
SAR02 | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 | N/A | N/A | 1851B | Rinching Tengah (KJS) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
SAR02 | MIP2024.107 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- SAR02 | N/A | N/A | 1607A | KM Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | N/A | N/A
NAR05 | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 | N/A | N/A | 4521A | MSC Ipoh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
NAR05 | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 | N/A | N/A | 2021B | DiGi TOC (Lot 43) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
NAR05 | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 | N/A | N/A | 4404A | Kg Jering Tower Manjung | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
NAR05 | MIP2024.108 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NAR05 | N/A | N/A | 4473A | Hutan Melintang | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Perak | N/A | N/A | N/A | N/A | N/A | N/A
CAR10 | MIP2024.109 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR10 | N/A | N/A | 1475A | BSC Sri Kembangan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
CAR10 | MIP2024.109 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR10 | N/A | N/A | 1621A | Senawang MSC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Southern | Negeri Sembilan | N/A | N/A | N/A | N/A | N/A | N/A
CAR10 | MIP2024.109 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- CAR10 | N/A | N/A | 1851B | Rinching Tengah (KJS) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Central | Selangor | N/A | N/A | N/A | N/A | N/A | N/A
NL432P | MIP2024.110 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL432P | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL432P | MIP2024.110 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL432P | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL432P | MIP2024.110 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL432P | N/A | N/A | 4012A | Prime Plaza | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL433P | MIP2024.111 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL433P | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL433P | MIP2024.111 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL433P | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL433P | MIP2024.111 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL433P | N/A | N/A | 4015A | Axis Complex V4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL435P | MIP2024.112 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL435P | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL435P | MIP2024.112 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL435P | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL435P | MIP2024.112 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL435P | N/A | N/A | 4056A | Vistana Hotel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL424 | MIP2024.113 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL424 | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL424 | MIP2024.113 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL424 | N/A | N/A | 4000A | MSC Prai | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A
NL424 | MIP2024.113 CD Digi NIC ES BOQ- 2024 Q3 PE-MCR Migration- NL424 | N/A | N/A | 4090A | Shoplot Permatang Damar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Northern | Pulau Pinang | N/A | N/A | N/A | N/A | N/A | N/A